## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 4 - Pavements | itp |  |  |  |  | F2LSIP - ITP 4 - Pavements
section | 4.0 - Pavements
checkpoint | Pavements
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by CR
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 4.1 - Source Properties as per NZS 4407
checkpoint-no-status | Source Properties as per NZS 4407
label | Acceptance Criteria - Subbase AP65
checkpoint | 4.1.1 - Crushing Resistance Test 3.10
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - Under a load of 100 kN less than 10% fines passing 2.36mm sieve size shall be produced
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.1.2 - Weathering Quality Index Test Test 3.11
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - AA, AB, AC, BA, BB, CA or CB
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.1.3 - Soaked CBR Test Test 3.15
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - CBR ≥ 80%
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.2 - Production Properties as per NZS 4407
checkpoint-no-status | Production Properties as per NZS 4407
label | Acceptance Criteria - Subbase AP65
checkpoint | 4.2.1 - Quality of Fines - SE 3.6 - CI 3.5 - PI 3.4
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - SE ≥ 25, CI ≤ 3, PI ≤ 6
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.2.2 - Broken Face Content Test 3.14
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 60% by weight shall have two or more broken faces.
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.2.3 - Particle Size Distribution Test 3.8.1
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - As per table 302.2.3
label | Verifying Document - IANZ Lab Report
label | Frequency - Once Per Source/Supplier
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 4.3 - Source Properties as per NZTA M-4
checkpoint-no-status | Source Properties as per NZTA M-4
label | Acceptance Criteria - Basecourse AP40
checkpoint | 4.3.1 - Crushing Resistance Test 3.1
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - Under 130kN load < 10% fines passing 2.36mm sieve.
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per 10,000m3
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.3.2 - Weathering Quality Index Test 3.11
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - AA,AB,BA,BB,CA
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per 10,000m3
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.3.3 - California Bearing Ratio Test 3.15
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - Not less than 80%
label | Verifying Document - IANZ Lab Report
label | Frequency - Once per 10,000m3
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 4.4 - Production Properties as per NZTA M-4
checkpoint-no-status | Production Properties as per NZTA M-4
label | Acceptance Criteria - Basecourse AP40
checkpoint | 4.4.1 - Quality of Fines - SE 3.6 - CI 3.5 - PI 3.4
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - SE ≥ 40, CI ≤ 3, PI ≤ 5
label | Verifying Document - IANZ Lab Report
label | Frequency - Lot Size =
label | ○ < 400m2 = 2 Samples
label | ○ 400 to 1500m2 = 3 Samples
label | ○ 1500 to 4000m3 = 4 Samples
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.4.2 - Broken Face Content Test 3.14
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - 19mm - 37.5mm - NOT LESS THAN 70%
label | ○ 9.5mm - 19.0mm - NOT LESS THAN 70%
label | ○ 4.75mm - 9.5mm - NOT LESS THAN 70%
label | Verifying Document - IANZ Lab Report
label | Frequency - Lot Size =
label | ○ < 400m2 = 2 Samples
label | ○ 400 to 1500m2 = 3 Samples
label | ○ 1500 to 4000m3 = 4 Samples
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
checkpoint | 4.4.3 - Particle Size Distribution Test 3.8.1
label | Inspection Point: Quality Control Activity - Samples to be sent to lab for testing or provided by quarry
label | Acceptance Criteria - As per NZTA M/4 AP40 PSD Requirements
label | Verifying Document - IANZ Lab Report
label | Frequency - Lot Size =
label | ○ < 400m2 = 2 Samples
label | ○ 400 to 1500m2 = 3 Samples
label | ○ 1500 to 4000m3 = 4 Samples
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - ER
section | 4.5 - Pavement Construction
checkpoint | 4.5.1 - Visual inspection of final trimmed subgrade surface
label | Inspection Point: Quality Control Activity - Pre pavement construction visual inspection
label | Acceptance Criteria - Entire surface to be firm, uniform and smooth.
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - PM & ER
checkpoint | 4.5.2 - Survey Setout
label | Inspection Point: Quality Control Activity - Height Check
label | Acceptance Criteria - Check to ensure pegs are still sitting at correct height from initial set out.
label | Verifying Document - Visual
label | Frequency - Prior to subbase construction
label | Inspection Type - Check
label | Inspection: Key - C
label | Inspection: By - SV
checkpoint | 4.5.3 - Subbase Compaction
label | Inspection Point: Quality Control Activity - NDM - Dry Density
label | Acceptance Criteria - Mean DD ≥ 95% of MDD, Minimum DD ≥ 92% of MDD
label | Verifying Document - IANZ Lab & Report, NDM Report
label | Frequency - MDD to be determind per 5000m2 of material laid.
label | ○ Compacted layer to be tested in 1000m2 lots, at randomly generated locations.
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.4 - Subbase Deflection
label | Inspection Point: Quality Control Activity - Benklemen Beam Test
label | Acceptance Criteria - Maximum Deflections of not more than (see surfacing notes)
label | Verifying Document - IANZ Report and Truck Weightbridge Docket (where applicable)
label | Frequency - 10m Intervals - alternating wheel paths
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.5 - Level Compliance
label | Inspection Point: Quality Control Activity - Survey As-built
label | Acceptance Criteria - Subbase level to be within +5mm / - 25mm of design
label | Verifying Document - 20m Survey Cross Sections
label | Frequency - 20m Cross Sections
label | Inspection Type - Witness Point
label | Inspection: Key - W
label | Inspection: By - PM & ER
checkpoint | 4.5.6 - Basecourse Compaction
label | Inspection Point: Quality Control Activity - NDM - Dry Density
label | Acceptance Criteria - Mean DD ≥ 98% of MDD, Minimum DD ≥ 95% of MDD
label | Verifying Document - IANZ Lab & Report, NDM Report
label | Frequency - MDD to be determind per 5000m2 of material laid.
label | ○ Compacted layer to be tested in 1000m2 lots, at randomly generated locations.
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.7 - Basecourse Deflections
label | Inspection Point: Quality Control Activity - Benklemen Beam Test
label | Acceptance Criteria - Only Required if subbase BB not completed - Engineer to advise target
label | Verifying Document - IANZ Report and Truck Weightbridge Docket (where applicable)
label | Frequency - 10m Intervals - alternating wheel paths
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.8 - Final Surface Shape & Levels
label | Inspection Point: Quality Control Activity - Straight Edge, Survey As-built
label | Acceptance Criteria - Pavement shall not deviate greater than 10mm under a 3m straight edge.
label | ○ No area of pavement shall pond water where grade is greater than 1%.
label | ○ Pavement to be within +15mm / -5mm of design levels (or +/- 5mm against the lip of a channel)
label | Verifying Document - Straight Edge Sheet, Site Inspection Form, 20m Survey Cross Sections
label | Frequency - Once per construction area, 20m Cross Sections
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5.9 - Final Surface Visual Inspection
label | Inspection Point: Quality Control Activity - Onsite Surface Inspection
label | Acceptance Criteria - Shall present a swpet, tightly consolidated surface in which:
label | ○ Large aggregate is exposed to the surface & held in place with a matrix of smaller agregates.
label | ○ Smaller aggregate is held in place by fines material
label | ○ Matrix does not displace under normal trafficing or sweeping.
label | Verifying Document - Site Inspection Form
label | Frequency - Once per construction area
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM & ER
holdpoint | AUTHORITY HOLDPOINT