## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | F2LSIP - ITP 7 - Sealing | itp |  |  |  |  | F2LSIP - ITP 7 - Sealing
section | 7.0 - Sealing
checkpoint | Sealing
label | Inspection Point: Quality Control Activity - Final Sign Off
label | Acceptance Criteria - All below requirements are met and approved by ER
label | Verifying Document - Referenced Item numbers as below
label | Frequency - Once post construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.1 - Bitumen Approval
checkpoint | 7.1.1 - NZTA M1: 2022: Bitumen Material Approval
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Bitumen/binder compliant with NZTA M/1 - Table 5.1
label | Verifying Document - Manufacturers Certificate
label | Frequency - Minimum 5 working days prior to construction
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.2 - Source Properties
checkpoint | 7.2.1 - NZTA M6: 2022: 4.2 Crushing Resistance
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Maximum of 10% fines shall be produced under a load of 230kN.
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2.2 - NZTA M6: 2022: 4.3 Weathering Resistance
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - The aggregate shall have a quality index of AA or BA
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2.3 - NZTA M6: 2022: 4.4 Weak Particles Test
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Note - only required if source properties are disputed.
label | ○ The aggregate shall have a maximum of 1% of unsound materials
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2.4 - NZTA M6: 2022: 4.6 Polished Stone Value
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Polished Stone Value (PSV) - compliant with NZTA M6: 2022: 4.6 & project requirements
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially from stockpile then repeat for every 10,000m3 of source material used or once per annum, whichever is lesser
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.3 - Production Properties
checkpoint-no-status | Production Properties
label | Acceptance Criteria - Grade 2, 3 & 4 Chip
checkpoint | 7.3.1 - NZTA M6: 2022: 5.1 Cleanness
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Cleaness of aggregate samples compliant with NZTA M6: 2022 5.2 Cleanness
label | – – – – – – – – – – – – – – – – – – – – –
label | Chip Grade ¦¦ Minimum Cleaness Value
label | – – – – – – – – – – – – – – – – – – – – –
label | 2 ¦¦ 89
label | 3 ¦¦ 87
label | 4 ¦¦ 85
label | 5 ¦¦ Report only
label | 6 ¦¦ Report only
label | – – – – – – – – – – – – – – – – – – – – –
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | ○ 1 test per < 100m3;
label | ○ 2 tests per 100-500m3; or
label | ○ 3 tests per > 500m3
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3.2 - NZTA M6: 2022: 5.2 Size and Shape
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Size and Shape of Aggregate Particles compliant with NZTA M6: 2022: 5.2 Size and Shape
label | – – – – – – – – – – – – – – – – – – – – –
label | Grade of Chip ¦¦ ALD (mm) ¦¦ % of Least Dimensions Within 2.5mm of ALD ¦¦ AGD/ALD Ratio ¦¦ % Passing 4.75mm Sieve ¦¦ % With at Least Two Broken Faces
label | – – – – – – – – – – – – – – – – – – – – –
label | 2 ¦¦ 9.5 - 12.0 ¦¦ 65 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | 3 ¦¦ 7.5 - 10.0 ¦¦ 70 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | 4 ¦¦ 5.5 - 8.0 ¦¦ 75 min. ¦¦ 2.25 max. ¦¦ 1.1 max. ¦¦ 98 min.
label | 5 ¦¦ Report ¦¦ Report ¦¦ Report ¦¦ Report ¦¦ Report
label | – – – – – – – – – – – – – – – – – – – – –
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | ○ 1 test per < 100m3;
label | ○ 2 tests per 100-500m3; or
label | ○ 3 tests per > 500m3
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.4 - Production Properties
checkpoint-no-status | Production Properties
label | Acceptance Criteria - Grade 5 & 6 Chip
checkpoint | 7.4.1 - NZTA M6: 2022 5.3 PSD
label | Inspection Point: Quality Control Activity - Test Report Review
label | Acceptance Criteria - Particle Size Distribution compliant with NZTA M6: 2022 5.1 Table 4
label | – – – – – – – – – – – – – – – – – – – – –
label | Siege Size (mm) ¦¦ Percentage Passing Sieve (Grade 5 :: Grade 6)
label | – – – – – – – – – – – – – – – – – – – – –
label | 13.2 ¦¦ 100 :: -
label | 9.5 ¦¦ 95 - 100 :: 100
label | 6.7 ¦¦ - :: 95 - 100
label | 4.75 ¦¦ 0 - 8 :: -
label | 2.36 ¦¦ 0 - 2 :: 0 - 15
label | 0.300 ¦¦ 0 :: 0 - 8
label | – – – – – – – – – – – – – – – – – – – – –
label | Verifying Document - IANZ Lab Report
label | Frequency - Three initially per grade of chip from stockpile, then repeat as follows:
label | ○ 1 test per < 100m3;
label | ○ 2 tests per 100-500m3; or
label | ○ 3 tests per > 500m3
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.5 - Pre-Construction
checkpoint | 7.5.1 - Chipseal Design Submission
label | Inspection Point: Quality Control Activity - Design Review
label | Acceptance Criteria - Designer to approve sealing design
label | Verifying Document - NTC confirming acceptance
label | Frequency - Once per seal design
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.5.2 - Pre-seal Inspection
label | Inspection Point: Quality Control Activity - Visual Site Inspection
label | Acceptance Criteria - Basecourse (prime seal) - To be prepped to a tight, uniform surface, swept to remove any dust and other foreign objects.
label | ○ Prime or previouis seal - Full surface swept with a power broom to remove excess chip and any other foreign material
label | Verifying Document - Site Inspection Form
label | Frequency - Prior to construction of sealing coat
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.5.3 - Pre-seal testing
label | Inspection Point: Quality Control Activity - Degree of Saturation test TNZB/02 Clause 12
label | Acceptance Criteria - Compliant as per TNZ B/02 Clause 12 DOS at each of minimim 5 points < 80%
label | Verifying Document - Testing results
label | Frequency - Minimum 5 tests per 1000m2
label | Inspection Type - Hold Point
label | Inspection: Key - H
label | Inspection: By - PM/ER
holdpoint | AUTHORITY HOLDPOINT
section | 7.6 - Construction
checkpoint | 7.6.1 - Working Temperature Prior to Spraying
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying shall be carried out when the air temperature measured within the confines of the sealing course is below 10 degrees C in the shade
label | Verifying Document - Sealing Checklist
label | Frequency - Prior to Spraying
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER
checkpoint | 7.6.2 - Application rate for Bituminous Seal
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - Sprayed Rate measured compliant with the Approved Seal Design
label | Verifying Document - Sealing Checklist
label | Frequency - Per spray run
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER
checkpoint | 7.6.3 - Chip Spread Rate
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - Sealing Records showing compliant spread rate of the chips based on C0213.5;TNZ P/3: 1995-21 Cl. 28
label | Verifying Document - Sealing Checklist
label | Frequency - 1 test per chip grade per 2,000m2 seal constructed
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER
checkpoint | 7.6.4 - Rolling Requirements
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - Sealing Records showing compliant rolling requirements based on C0213.5;TNZ P/3: 1995-22 ROLLING
label | Verifying Document - Sealing Checklist
label | Frequency - Per Shift
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER
checkpoint | 7.6.5 - On Site Checks - Post PTR and Brooming
label | Inspection Point: Quality Control Activity - Onsite check & Document
label | Acceptance Criteria - Surface Compliant and Surplus chip removed
label | Verifying Document - Sealing Checklist
label | Frequency - Prior to construction of next layer/ Prior removal of the temporary speed restriction signs
label | Inspection Type - Review
label | Inspection: Key - R
label | Inspection: By - PM/ER