## ITP-CIV-RSS Walls
ConQA Team Notes:
Document Title: |  | ITP-102-STR-CPD-RSS Wall Main
ITP Description: |  | CPD-RSS Wall Main
Discipline (e.g. CIV/STR/RAIL) |  | STR
Revision Number: |  | 0
Revision Date: |  | 09/11/2023
ITP created by: |  | Matthew Dib/Jason Quan
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP to be available for Calder Park Drive Project Only
Inspection & Test Plan - RSS Wall Main
[9 empty] | Revision: | 0
[9 empty] | Date: | 09/11/2023
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 682 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | VicRoads Section 204 December 2015 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | IFC drawings | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries-Materials
2.1 | Concrete-Leveling Pad | IFC drawings | Concrete compressive strength grade must not be less than N25 for levelling course and backing blocks; [Free text]: Reference: Teambinder MA number: | Document Review | Each element | HP* | PE/Nominated Authority | Material approval
2.2 | Select fill | IFC Drawings VR 682 | Select fill shall comply with the requirements of the RSS designer: UNIT WEIGHT (Max): ≤ 16 kN/m³ COHESION (Min): ≥ 0 kPa INTERNAL FRICTION ANGLE (Min): ≥ 36° Gradation: 150mm : 100% PASSING 37.5mm : 60 TO 100% PASSING 9.5mm : 25 TO 100% PASSING 2.36mm : 15 TO 100% PASSING 0.6mm : 10 TO 100% PASSING 0.075mm : 0 TO 15% PASSING Electrochemical Properties: pH: 5 - 10 RESISTIVITY >1000 Ω-cm CHLORIDES <200 mg/kg SULPHATES <200 mg/kg ORGANIC CONTENT 0% Structural Properties: COEFFICIENT OF UNIFORMITY ≥ 5 LIQUID LIMIT ≤ 30% PLASTICITY INDEX ≤ 12 The select backfill must meet the minimum requirements of Vicroads Type A filling Reference: Material approval in Teambinder | Document Review | Each material specification | HP | Nominated Authority | Material approval
2.3 | General fill | IFC Drawings VR 204 | Backfill behind the reinforced block shall be Vicroads Type B or better in accordance with Vicroads standard specification 204: Select General fill shall comply with the requirements of the RSS designer (RW05-RW06): UNIT WEIGHT: ≤ 19 kN/m³ COHESION (MIN): ≤ 2 kPa INTERNAL FRICTION ANGLE (Min): ≥ 30° Reference: Material approval in Teambinder | Document Review | Each material specification | HP | Nominated Authority | Material approval
2.4 | Perforated Pipe-material | IFC Drawings | Perforated plastic pipe perforations shall be a maximum width of 1.5mm and minimum length of 150mm per m2 Reference: Teambinder MA number: | Document review Measure | Each wall | HP | Nominated Authority | Material approval
3 | Preliminaries-Documents
3.1 | RSS Panels | IFC drawings | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate - 1. Concrete strength; - 2.Date of manufacture; - 3.Unique Identification number; - 4.Mass; - 5.Confirmation of number, type and capacity of lifting inserts; - 6.Quality assurance sign-off. ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Post-pour check sheet / ITP vi. Covermeter check record vii. Record of dimensional measurements Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here) [Free text]: Reference: Precast panels MDR Lot in TeamBinder: | Document Review | Once for each type of panels | HP | PE | Precast panels Birth certificates and MDR Lot
| Wire Face Units | IFC Drawings
4 | Pre-Construction Activities
4.1 | Foundation | IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007 MRP-080-C-SME-DRG-34-CPV-CSF-3012 MRP-080-C-SME-DRG-34-CPV-CSF-3013 | Foundation material under RSS shall adhere with minimum design bearing capacity. RW2: 150 kPa RW3: 200 kPa RW4: 200 kPa RW5: 250 kPa | Test Document Review Visual | Each retaining Wall | HP* | PE/Geotechnical Engineer Foundation geotechnical assessment | This ITP Signed off Test results
4.2 | Foundation | VR 204.12 VR 204.11 | Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173 No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant | Visual | Each retaining Wall | HP | PE/Niminated Authority | This ITP Signed off
4.3 | Levelling Pad-Survey Set out | IFC Drawings VR 682.20 MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205 | Survey to set up and validate all works meets levels and locations with the right tolerances as per IFC Drawings and Vicroads Specification. Levelling course level shall not deviate from the specified level by more than +/- 3mm | Measure Visual | Each retaining Wall | IP | Surveyor SE/PE | This ITP Signed off
5 | Construction / Installation Activities
5.1 | Form Levelling pad | IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205 | Form timber shutters or Earth form to edge of levelling pad - Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing | Measure Visual | Each Lot | IP | SE/Site Supervisor | This ITP Signed off
5.2 | Leveling Pad Concrete Pour | IFC Drawings VR610 | Concrete to be placed in accordance with VR610. Attach: Concrete Delivery Docket | Visual | Each Lot | IP | SE/Site Supervisor | Concrete Pour record Concrete Delivery Docket
5.3 | Leveling Pad Concrete Testing | IFC Drawings VR Section 610.16 (b) | Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b) Concrete strength (Min): N25 MPa Attach: Concrete test report | Document Review | Each Lot | IP | PE | Attach Concrete Test Report
5.4 | Levelling Pad-Post Pour Survey-Levelling Course | IFC Drawings MRP-080-C-RFL-DRG-33-CPV-CSW-1202 to 1205 | - Levelling course level shall not deviate from the specified level by more than ±3mm - 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations) | Measure Visual | Each retaining Wall | IP | PE/Surveyor | Attach Survey Report
5.5 | Wall Panels Installation | VR682.17 | The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions. Refer to checklist for each course of panels Attach: Lot map | Visual Measure | Each course of facing panel | HP* | SE/PE | Inspection record checklist: CHK-008-STR-CPD-RSS Walls-Precast Panel installation
5.6 | Drainage-base of the Wall | IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3031 | to install 300mmx300mmGranular backfill in Geotextile BIDIM A24 around 100mm Dia. Perforted plastic pipewith 0.5% min fall to weepholes in RSS panels. - Geotextile BIDIM A24 - 300mmx300mm Granular backfill - 100mm Dia. Perforted plastic pipe - Perforated pipe to have 0.5% minimum fall | Visual | Each wall | IP | SE/PE | This ITP Signed off
5.7 | Fill | VR682.16 | The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed. Refer to checklist for each fill layer Attach: Lot map | Visual Test Measure | Each layer of fill | HP* | SE/PE | Inspection record checklist: CHK-009-STR-CPD-RSS Walls-Fill Placement
5.8 | Settlement Monitoring horizontal inclinometer | IFC drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007 VR 682.15 | Survey Pin and Inclinometer survey procedure us as follows: Inclinometers shall be installed prior ro placement of any fill RSS Wall and abutment wall survey pins shall be installed immediately following construction of the first level of RSS wall/Abutment wall and prior to any fill placement Traffic barrier survey pins shall be installed following construction of pavement and barriers All survey pins shall have appopriate stick-up from finished surface level for continous settlement throughout construction/post construction Pavement construction shall not commence until monitoring from inclinometers and RSS wall/abutment wall survey pins indicate ground movements have reached at least 90% of construction settlements and confirmed by the geoechnical engineer Settlment Monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) unitl settlement stablisers or advised by the geotechnical engineer If at any stage prior ro the to the completion of the RSS placement, the total settlement exceeds 50mm, fill placement must be suspendedm and direction sought from the design engineer. Survey pins and horizontal inclinometer shall be installed to monitor ground movement throughout and after the RSS wall construction. Only hand operated equipment shall be used within 1m distance from inclinometers Geotechnical instruments shall be preserved and protected for monitoring until the conclusion of post construction. Damaged or malfuctioning inclinometers shall be reported and replaced where possible. | Document Review | Each Inclinometer | HP | SE/PE | Teambinder approval
6 | Post-construction / Post-installation Activities
6.1 | As-built Survey | MRPA Quality Management Plan IFC Drawings | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances as per IFC drawings. a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm; (b) Relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall; (c) Local deviation of the wall face measured at any location with a 3m straight edge shall not exceed 15mm; (d) The tolerance on position measured at the top of the wall face shall not exceed 5mm per 1m of wall height; (e) The wall level shall not deviate from the specified level by more than ±20mm; (f) Variation in gap width between facing panels shall not exceed 5mm per metre length and 10mm over the full length of the gap. (g) The levelling course level shall not deviate from the specified level by more than ±3 mm; (h) The vertical deviation of the soil reinforcement shall be within +1% (upwards) & -0.3% (downwards) of the soil reinforcement length, relative to the connection height unless noted otherwise Attach: Survey As-built / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | Survey Report
6.2 | Wall Post construction monitoring | IFC Drawings VR 682.20 VR 682.151 | The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period. | Measure Survey | Each wall | IP | Surveyor SE/PE/SPE | Survey Report
6.3 | Settlement Monitoring | IFC Drawings VR 682.15 VR 682.20 | RSS wall base level: - Start of wall construction to completion of wall construction (before pavement placement) Approx vertical settlement < 20mm - Completion of pavement construction to end of defects liability period (2 years after practical completion) Approx vertical settlement < 15mm Pavement level (Top of RSS wall): - Start of Pavement construction to completion of pavement construction Approx vertical settlement < 20mm - 10 years following practical completion of payment < 50mm Settlement monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) until settlement stabilised or advised by the geotechnical engineer If RSS fill placement total settlement >50mm, fill placement must be suspended, and the mitigation method reviewed by the superintendent and DTP before recommencing fill placement. | Measure Survey Document Review | 1m of fill | HP | Surveyor SE/PE/SPE | Settlement monitoring results
6.4 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /

## ITP-CIV-Wire Walls
ConQA Team Notes:
Document Title: |  | ITP-126-CIV-CPD-Wire Facing Wall Main
ITP Description: |  | CPD-Wire Facing Wall Main
Discipline (e.g. CIV/STR/RAIL) |  | CIV
Revision Number: |  | 0
Revision Date: |  | 01/12/2023
ITP created by: |  | Matthew Dib
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP to be available for Calder Park Drive Project Only
Inspection & Test Plan - Wire Wall Main
[9 empty] | Revision: | 0
[9 empty] | Date: | 01/12/2023
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 682 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.2 | Non Dependent | VicRoads Section 204 December 2015 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
1.3 | Non Dependent | IFC drawings | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | Preliminaries-Materials
2.1 | Select fill | IFC Drawings VR 682 | Select fill shall comply with the requirements of the RSS designer: UNIT WEIGHT (Max): ≤ 16 kN/m³ COHESION (Min): ≥ 0 kPa INTERNAL FRICTION ANGLE (Min): ≥ 36° Gradation: 150mm : 100% PASSING 37.5mm : 60 TO 100% PASSING 9.5mm : 25 TO 100% PASSING 2.36mm : 15 TO 100% PASSING 0.6mm : 10 TO 100% PASSING 0.075mm : 0 TO 15% PASSING Electrochemical Properties: pH: 5 - 10 RESISTIVITY >1000 Ω-cm CHLORIDES <200 mg/kg SULPHATES <200 mg/kg ORGANIC CONTENT 0% Structural Properties: LIQUID LIMIT ≤ 30% PLASTICITY INDEX ≤ 12 The select backfill must meet the minimum requirements of Vicroads Type A filling Reference: Material approval in Teambinder | Document Review | Each material specification | HP | Nominated Authority | Material approval
2.2 | General fill | IFC Drawings VR 204 | Backfill behind the reinforced block shall be Vicroads Type B or better in accordance with Vicroads standard specification 204: Select General fill shall comply with the requirements of the RSS designer: UNIT WEIGHT: ≤ 19 kN/m³ COHESION (MIN): ≤ 2 kPa INTERNAL FRICTION ANGLE (Min): ≥ 30° Reference: Material approval in Teambinder | Document Review | Each material specification | HP | Nominated Authority | Material approval
2.3 | Cobble stone backfill | IFC Drawings VR 801 VR 715 | Cobble stone backfill shall have a minimum dimension of 100mm, and maximum dimension of 150mm. Cobble shall comply with the material requirements of 'sound' rock as specified in VR section 801: Cobble shall comply with the Los Angeles Value (LAV) for requirements for Gabion Fill. Reference: Material approval in Teambinder | Document Review | Each material specification | HP | Nominated Authority | Material approval
3 | Preliminaries-Documents
3.1 | Wire Facing Units | IFC drawings | Supplier is required to provide the following Quality Assurance documentation, typically this consists of: i. Inspection & Test Plans ii. Manufacturer Accreditations iii. Material Certificates & Test Reports iv. Welding Records | Document Review |  | HP | PE | MDR
4 | Pre-Construction Activities
4.1 | Foundation | IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007 MRP-080-C-SME-DRG-34-CPV-CSF-3012 MRP-080-C-SME-DRG-34-CPV-CSF-3013 | Foundation material under RSS shall adhere with minimum design bearing capacity. RW1: 200kPa RW6: 250kPa | Test Document Review Visual | Each retaining Wall | HP* | PE/Geotechnical Engineer Foundation geotechnical assessment | This ITP Signed off Test results
4.2 | Foundation | VR 204.12 VR 204.11 | Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173 No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant | Visual | Each retaining Wall | HP | PE/Niminated Authority | This ITP Signed off
5 | Construction / Installation Activities
5.1 | Wire Facing Unit Installation | IFC Drawings MRP-DPK-080-00-CSW-0033-0-1201 MRP-DPK-080-00-CSW-0033-0-1206 VR 682.20 | The level and alignment of lift of wire units shall be checked progressively after placement of each lift and prior to placement of the lift to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions. Refer to checklist for row of wire units Attach: Lot map | Visual Measure | Each row of wire units | HP* | SE/PE | Inspection record checklist: CHK-00X-STR-CPD-Wire Walls- Wire Face Wall Installation
5.2 | Fill | VR682.16 | The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance. No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed. Refer to checklist for each fill layer Attach: Lot map | Visual Test Measure | Each layer of fill | HP* | SE/PE | Inspection record checklist: CHK-009-STR-CPD-RSS Walls-Fill Placement
6 | Post-construction / Post-installation Activities
6.1 | As-built Survey | MRPA Quality Management Plan IFC Drawings | Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances as per IFC drawings. a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm; (b) Relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall; (c) Local deviation of the wall face measured at any location with a 3m straight edge shall not exceed 15mm; (d) The tolerance on position measured at the top of the wall face shall not exceed 5mm per 1m of wall height; (e) The wall level shall not deviate from the specified level by more than ±20mm; (f) Variation in gap width between facing panels shall not exceed 5mm per metre length and 10mm over the full length of the gap. (g) The levelling course level shall not deviate from the specified level by more than ±3 mm; (h) The vertical deviation of the soil reinforcement shall be within +1% (upwards) & -0.3% (downwards) of the soil reinforcement length, relative to the connection height unless noted otherwise Attach: Survey As-built / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | Survey Report
6.2 | Wall Post construction monitoring | IFC Drawings VR 682.20 VR 682.151 | The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period. | Measure Survey | Each wall | IP | Surveyor SE/PE/SPE | Survey Report
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed off
ci | Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /