## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | CHK-010-CIV-CPD-Wire faced wall Installation | itp |  |  |  |  | CHK-010-CIV-CPD-Wire faced wall Installation Rev 0
checkpoint-no-status | Referenced Documentation
label | Document Title: CHK-010-CIV-CPD-Wire faced wall Installation
label | ITP Description: CPD - Wire Faced Wall Installation
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 1/12/2023
label | ITP created by: Matthew Dib
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1 - Wire Facing Units-survey set out-Tolerance
label | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1201, MRP-DPK-080-00-CSW-0033-0-1206 VR 682.20
label | Acceptance Criteria - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
label | Method - Measure
label | Frequency - Base course units
label | Category - IP
label | Responsibility - Surveyor/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 2 - Wire facing installation
label | Acceptance Criteria Wire facing units are to be installed as per IFC Drawings and specified schedule.
label | – Connect adjacent wire facing units with stainless steel zip ties
label | – Attach grid-strips at locations shown in Drawing 1957 for appropriate quantity given in elevations. Bottom layer of grid-strips to be attached with stainless steel zip tie shown in Drawing 1955
label | – Cut the half-height panels at top of wall to correct height (refer Drawing MRP-DPK-080-00-CSW-0033-0-1953)
label | Method - Visual, Measure
label | Frequency - Each wire facing unit
label | Category - WP
label | Responsibility - SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 3 - Wire facing installation-Abutment interfaces
label | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1106
label | Acceptance Criteria - Cut any transverse wires as required for bends at abutments and wingwalls (refer Drawing 1955).
label | – Wire facing unit to be in contact with rear of panel (RW01) and side of wingwall (RW06).
label | – Geofabric to extend along abutment as shown in Drawing 1106.
label | Method - Measure
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 4 - Geotextile - Installation
label | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1955
label | Acceptance Criteria - Install geotextile between cobble and select fill for all panels
label | Method - Visual
label | Frequency - Each wire facing unit
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 5 - Wire facing installation-Survey reference points
label | Reference - VR 682.21
label | Acceptance Criteria - To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
label | Method - Visual
label | Frequency - Each course of wire facing installation
label | Category - IP
label | Responsibility - Surveyor/SE
label | Verifying Documents - This Checklist
date | Date Completed:
checkpoint | 7 - Panels installation-Conformance Survey
label | Reference - IFC Drawings VR 682.06, VR 682.17, VR 682.20
label | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The
label | – Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
label | ○ Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
label | ○ Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
label | ○ the wall level shall not deviate from the specified level by more than ±20mm
label | ○ the tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
label | ○ The wire facing walls shall be vertical when measured at the corresponding point for each row of wire facing units.
label | Attach: Survey Report
label | Method - Survey, Measure
label | Frequency - Each course of panel installation
label | Category - HP*
label | Responsibility - Surveyor/PE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP