## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-126-CIV-RSS Wire Facing Wall Main | itp |  |  |  |  | ITP-126-CIV-RSS Wire Facing Wall Main Rev 0
section | 1. Referenced Documentation
checkpoint-no-status | 1. Referenced Documentation
label | Document Title: ITP-126-CIV-CPD-Wire Facing Wall Main
label | ITP Description: CPD-Wire Facing Wall Main
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 01/12/2023
label | ITP created by: Matthew Dib
label | ITP approved for use by: Pradeep Talasila
checkpoint | 1.1 - Non Dependent
label | Reference - VicRoads Section 682 November 2018
checkpoint | 1.2 - Non Dependent
label | Reference - VicRoads Section 204 December 2015
checkpoint | 1.3 - Non Dependent
label | Reference - IFC drawings
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Select fill
label | Reference - IFC Drawings VR 682
label | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
label | ○ UNIT WEIGHT (Max): ≤ 16 kN/m³
label | ○ COHESION (Min): ≥ 0 kPa
label | ○ INTERNAL FRICTION ANGLE (Min): ≥ 36°
label | Gradation:
label | ○ 150mm : 100% PASSING
label | ○ 37.5mm : 60 TO 100% PASSING
label | ○ 9.5mm : 25 TO 100% PASSING
label | ○ 2.36mm : 15 TO 100% PASSING
label | ○ 0.6mm : 10 TO 100% PASSING
label | ○ 0.075mm : 0 TO 15% PASSING
label | Electrochemical Properties:
label | ○ pH: 5 - 10
label | ○ RESISTIVITY >1000 Ω-cm
label | ○ CHLORIDES <200 mg/kg
label | ○ SULPHATES <200 mg/kg
label | ○ ORGANIC CONTENT 0%
label | Structural Properties:
label | ○ LIQUID LIMIT ≤ 30%
label | ○ PLASTICITY INDEX ≤ 12
label | The select backfill must meet the minimum requirements of Vicroads Type A filling
label | Reference: Material approval in Teambinder
label | Method - Document Review
label | Frequency - Each material specification
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - General fill
label | Reference - IFC Drawings VR 204
label | Acceptance Criteria - Backfill behind the reinforced block shall be Vicroads Type B or better in accordance with Vicroads standard specification 204:
label | Select General fill shall comply with the requirements of the RSS designer:
label | ○ UNIT WEIGHT: ≤ 19 kN/m³
label | ○ COHESION (MIN): ≤ 2 kPa
label | ○ INTERNAL FRICTION ANGLE (Min): ≥ 30°
label | Reference: Material approval in Teambinder
label | Method - Document Review
label | Frequency - Each material specification
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Cobble stone backfill
label | Reference - IFC Drawings VR 801, VR 715
label | Acceptance Criteria - Cobble stone backfill shall have a minimum dimension of 100mm, and maximum dimension of 150mm.
label | ○ Cobble shall comply with the material requirements of 'sound' rock as specified in VR section 801:
label | ○ Cobble shall comply with the Los Angeles Value (LAV) for requirements for Gabion Fill.
label | Reference: Material approval in Teambinder
label | Method - Document Review
label | Frequency - Each material specification
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Material approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries-Documents
checkpoint | 3.1 - Wire Facing Units
label | Reference - IFC drawings
label | Acceptance Criteria - Supplier is required to provide the following Quality Assurance documentation, typically this consists of:
label | i. Inspection & Test Plans
label | ii. Manufacturer Accreditations
label | iii. Material Certificates & Test Reports
label | iv. Welding Records
label | Method - Document Review
label | Category - HP
label | Responsibility - PE
label | Verifying Documents - MDR
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Foundation
label | Reference - IFC Drawings MRP-080-C-SME-DRG-34-CPV-CSF-3007, MRP-080-C-SME-DRG-34-CPV-CSF-3012, MRP-080-C-SME-DRG-34-CPV-CSF-3013
label | Acceptance Criteria - Foundation material under RSS shall adhere with minimum design bearing capacity.
label | ○ RW1: 200kPa
label | ○ RW6: 250kPa
label | Method - Test, Document Review, Visual
label | Frequency - Each retaining Wall
label | Category - HP*
label | Responsibility - PE/Geotechnical Engineer, Foundation geotechnical assessment
label | Verifying Documents - This ITP Signed off, Test results
date | Date Completed:
checkpoint | 4.2 - Foundation
label | Reference - VR 204.12, VR 204.11
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
label | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
label | Method - Visual
label | Frequency - Each retaining Wall
label | Category - HP
label | Responsibility - PE/Nominated Authority
label | Verifying Documents - This ITP Signed off
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Wire Facing Unit Installation
label | Reference - IFC Drawings MRP-DPK-080-00-CSW-0033-0-1201, MRP-DPK-080-00-CSW-0033-0-1206 VR 682.20
label | Acceptance Criteria - The level and alignment of lift of wire units shall be checked progressively after placement of each lift and prior to placement of the lift to ensure compliance with the dimensional and positional tolerances stated in the design.
label | ○ The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions.
label | ○ Refer to checklist for row of wire units
label | Attach: Lot map
label | Method - Visual Measure
label | Frequency - Each row of wire units
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - Inspection record checklist: CHK-00X-STR-CPD-Wire Walls- Wire Face Wall Installation
date | Date Completed:
checkpoint | 5.2 - Fill
label | Reference - VR682.16
label | Acceptance Criteria - The Contractor shall submit compaction test results for each layer of fill placement to the Superintendent for review and acceptance.
label | ○ No further fill placement shall be allowed if the total thickness of fill placement is greater than 1 m measured from the last layer that has been accepted. If any layer is found to be not in compliance with the compaction requirement, that layer and the layers above it shall be removed.
label | ○ Refer to checklist for each fill layer
label | Attach: Lot map
label | Method - Visual, Test, Measure
label | Frequency - Each layer of fill
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - Inspection record checklist: CHK-009-STR-CPD-RSS Walls-Fill Placement
date | Date Completed:
section | 6. Post-construction / Post-installation Activities
checkpoint | 6.1 - As-built Survey
label | Reference - MRPA Quality Management Plan, IFC Drawings
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances as per IFC drawings.
label | (a) Plan position shown on the drawings, at base of wall shall not exceed ±15 mm;
label | (b) Relative displacement of adjoining smooth panel faces shall not exceed 15 mm measured normal to face of wall;
label | (c) Local deviation of the wall face measured at any location with a 3m straight edge shall not exceed 15mm;
label | (d) The tolerance on position measured at the top of the wall face shall not exceed 5mm per 1m of wall height;
label | (e) The wall level shall not deviate from the specified level by more than ±20mm;
label | (f) Variation in gap width between facing panels shall not exceed 5mm per metre length and 10mm over the full length of the gap.
label | (g) The levelling course level shall not deviate from the specified level by more than ±3 mm;
label | (h) The vertical deviation of the soil reinforcement shall be within +1% (upwards) & -0.3% (downwards) of the soil reinforcement length, relative to the connection height unless noted otherwise
label | Attach: Survey As-built / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | 6.2 - Wall Post construction monitoring
label | Reference - IFC Drawings VR 682.20, VR 682.151
label | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
label | Method - Measure, Survey
label | Frequency - Each wall
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP