## Pavement Construction
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | E3001B - SH05 - SIP-Site 2 |  | CPS Approver | Quality Approver | CPS Eng. | David Hooker
|  |  |  | Procedure: | Pavement Construction |  | Name / Signature | Name / Signature | Site Engineer | Genald Sebastian
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng. | Dharminder Singh
Lot No: E3001B |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:w:/s/ZONEE-SH5-HAWKESBAY/Efsr89PX3wtAjhV5bC0Wy-MBaC2NTThx4aN5wedK-KmcBQ?e=eLqbGQ |  | Compliance with Work Instructions and Specifications
Detailed Location :South of Dillon’s Hill Site 2
Chainage:RP249/0.530 to RP 249/2.040
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | M | Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction | Prior to commencement | Survey |  | Survey receipt | Site Engineer
Sub Grade
2 | Sub Grade Strength | H | Determine Bearing strength of Sub Grade | After Dig out Every 5m | Testing | Min. 4 blows /100mm | QA measurement Sheet CS-4000 1m Scala | Site Engineer | CPS Engineer
3 | Proof Roll of subgrade | H | Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement | Prior to Sub Base Construction | Visual Inspection | Engineers Acceptance | Emails | Site Engineer | CPS Engineer
Sub base
4 | Material Compliance | H | Aggregate material compliance for Subbase stockpiles | Prior to commencement | Lab Testing | Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC | Notice to Supplier and Lab Test results for the stockpiles used during construction | Site Engineer | CPS Engineer
5 | Material Compliance | M | All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number | During construction | Measurement and recording | Comply with TNZ M/3 Specification. NZTA B/2 Specification | Delivery Dockets, Aggregate Deliveries Register | Site Engineer
6 | Saw cutting | H | proposed Sawcut line to be inspected by the engineer | During construction | Visual Inspection | project spec 6.6 | Photos | Site Engineer | CPS Engineer
7 | Sub Base Construction | M | Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant | During construction | Visual Inspection |  | Photos | Site Engineer
8 | Sub Base Construction | M | Carry out a Level Check on the trimmed Sub base | 1/100m if machine control is used or 1/20m if no machine control | Measurement | Tolerance = -5mm/+15mm | QA measurement Sheet CS-4100a Subbase Approval | Site Engineer
9 | Sub Base Construction | M | Degree of Compaction | 5 per Lot | NDM Lab Testing | Avg. >= 95% MDD and Min. >= 92% MDD | Pavement Lab Testing Spreadsheet | Site Engineer
10 | Sub Base Construction | H | Surface shape check | Prior to base course Construction | Measurement | No point of the surface shall vary more than 10mm over a 3m long straight edge | QA measurement Sheet CS-4100a Subbase Approval | Site Engineer | CPS Engineer
Base Course Construction
11 | Material Compliance | H | Aggregate material compliance for base Course stockpiles | Prior to commencement | Lab Testing | Aggregate shall comply with TNZ M/4 | Notice to Supplier and Lab Test results for the stockpiles used during construction | Site Engineer | CPS Engineer
12 | Material Compliance | M | All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number | During construction | Measurement and recording | Comply with TNZ M/4 Specification. Traceability of all materials delivered to site | Delivery Dockets, Aggregate Deliveries Register | Site Engineer
13 | Base Course Construction | W | Mat sampling of Basecourse Material | 1 mat sample for the job. Pavement CPS Engineer for further instruction | Lab testing | Grading to comply with specification | Mat sample lab test result | Site Engineer
14 | Base Course Construction | M | Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant | During construction | Visual Inspection |  | Photos | Site Engineer
15 | Base Course Construction | M | Carry out a Level Check on the trimmed Basecourse | 1/100m if machine control is used or 1/20m if no machine control | Measurement | Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm | QA measurement Sheet CS-4100b Basecourse Approval | Site Engineer
16 | Base Course Construction | M | Degree of Compaction | 5 per Lot | NDM Lab Testing | Avg. >= 98% MDD and Min. >= 95% MDD | Pavement Lab Testing Spreadsheet | Site Engineer
17 | Base Course Construction | H | Surface shape check | Prior to sealing | Measurement | No point of the surface shall vary more than 10mm over a 3m long straight edge | QA measurement Sheet CS-4100b Basecourse Approval | Site Engineer | CPS Engineer
18 | Base Course Construction | H | Surface finish check | Prior to sealing | Visual inspection by CPS Engineer after site sweeping | The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping | Site photos, Emails | Site Engineer | CPS Engineer
Extension of Culvert
19 | Foundation Compliance | H | Test formation level on completion of excavation to check if undercut required | One test per 5 linear metres | Scala Penetrometer | Min 4 Blows/100 | Lab Test Report | Site Engineer | CPS Engineer
20 | Foundation Compliance | H | Test formation level on completion of excavation to check if undercut required | As stated | Visual | Designer to inspect formation level at outfalls / inlets. | Photos, Visual | Site Engineer | CPS Engineer
21 | Materials (Pipes and drainage aggregate) | W | Specification Compliance | Each delivery to site | Certification | Compliance with requirements from Specifications | Delivery Dockets | Site Engineer
Sealing
22 | Seal design | H | Seal design to be reviewed prior to sealing | Prior to Sealing | Review |  | Emails/NTE | Site Engineer | CPS Engineer
23 | Location/Size Confirmation | W | Mark up extent of Chipseal | Prior to Sealing | Mark out |  | Photos | Site Engineer
24 | Surface Cleanliness | W | To confirm that all loose material is removed from the surface and surrounding area. | Prior to application of binder | Visual inspection |  | Photos | Site Engineer
25 | Binder Application | W | Ensure the Binder application is according to the seal design | During sealing | Measure | According to seal design | Sealing sheet | Site Engineer
26 | Chip Application | W | Ensure the Chip application is according to the seal design | During sealing | Measure | According to seal design | Sealing sheet | Site Engineer |  |  | `
27 | Compaction | W | At completion of rolling | During sealing | Visual | Ensure sufficient passes with roller to embed chip (typically 4-5 passes) | Photos, QA measurement Sheet | Site Engineer
28 | Compaction | M | Removal of excess chip | Within 48 Hours of Sealing | Visual | Ensure all excess chip removed from site. No chip windrows left on site in Shoulders. | Photos, Site logs | Site Engineer
29 | Compaction | H | Surface finish check | After sealing | Visual | Engineers Acceptance | Photos Email | Site Engineer | CPS Engineer
Road Marking
30 | Road Marking | H | The engineer is to be given the opportunity to inspect the proposed location & type of markings | Prior to the final line marking | Visual | Engineers Acceptance | Photos Email | Site Engineer | CPS Engineer
Hydroseeding
31 | Hydroseeding | H | Engineer to inspect and confirm satisfactory cover achieved | At the completion of the Lot of work | Visual | Engineers Acceptance | Photos Email | Site Engineer | CPS Engineer
Final Inspection and Handover
32 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
33 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
`
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: