## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: PIT-12500
ITR-I-15 Pressure Instrument Installation | checklist |  |  | Tier 2: PIT-12500 - MP02-M02-SC104 PRESSURE TX
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: PIT-12501
ITR-I-15 Pressure Instrument Installation | checklist |  |  | Tier 2: PIT-12501 - MP02-M02-PU140 DESILTER FEED PUMP PRESSURE TRANSMITTER
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: PIT-12502
ITR-I-15 Pressure Instrument Installation | checklist |  |  | Tier 2: PIT-12502 - MP02-M02-PU141 CENTRIFUGE FEED PUMP PRESSURE TRANSMITTER
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: PIT-12503
ITR-I-15 Pressure Instrument Installation | checklist |  |  | Tier 2: PIT-12503 - MP02-M02-PU142 PRESSURE TX
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: LIT-12504
ITR-I-16 Level Instrument Installation | checklist |  |  | Tier 2: LIT-12504 - MP02-M02-TK140 LEVEL TX
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: LIT-12505
ITR-I-16 Level Instrument Installation | checklist |  |  | Tier 2: LIT-12505 - MP02-M02-TK141 LEVEL TX
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: LIT-12506
ITR-I-16 Level Instrument Installation | checklist |  |  | Tier 2: LIT-12506 - MP02-M02-TK142 LEVEL TX
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: FS-12515
ITR-I-14 Flow Meter Installation | checklist |  |  | Tier 2: FS-12515 - CENTRIFUGE FEED PUMP DISCHARGE
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: FIT-12040
ITR-I-14 Flow Meter Installation | checklist |  |  | Tier 2: FIT-12040 - RECYCLER FLOW TX
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: PIT-12520
ITR-I-15 Pressure Instrument Installation | checklist |  |  | Tier 2: PIT-12520 - MP02-M02-PU149 MUD MIX 2 PUMP PRESSURE TRANSMITTER
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: PIT-12521
ITR-I-15 Pressure Instrument Installation | checklist |  |  | Tier 2: PIT-12521 - MP02-M02-PU148 MUD MIX TRANSFER PUMP PRESSURE TRANSMITTER
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: LIT-12522
ITR-I-16 Level Instrument Installation | checklist |  |  | Tier 2: LIT-12522 - MP02-M02-TK148 LEVEL TX
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration
| step |  |  | Tier 1: LIT-12523
ITR-I-16 Level Instrument Installation | checklist |  |  | Tier 2: LIT-12523 - MP02-M02-TK149 LEVEL TX
ITR-I-07 Instrument Calibration | checklist |  |  | Tier 2: ITR-I-07 Instrument Calibration