## Site QA Structure
Folder Structure
Site QA
Templates
Lot Break Ups
Terminal
|  |  |  | Basement | LOT BREAK UP
|  |  |  | Basement Upper | LOT BREAK UP
|  |  |  | Ground Floor | LOT BREAK UP
|  |  |  | Level 1 | LOT BREAK UP
|  |  |  | Level 2 | LOT BREAK UP
|  |  |  | Level 3 | LOT BREAK UP
|  |  |  | Level 4 | LOT BREAK UP
|  |  |  | Roof | LOT BREAK UP
Landside
|  |  |  | Per Drawings | LOT BREAK UP
TER
|  |  |  | TER 1 | LOT BREAK UP
|  |  |  | TER 2 | LOT BREAK UP
Fuel Farm
|  |  |  | Inground | LOT BREAK UP
|  |  |  | Buildings | LOT BREAK UP
Quality - ITP's
|  |  | Quality - In Ground conduit install. | ITP
|  |  | Quality - Cable Tray / Ladder | ITP
Commissioning - ITPs
|  |  | Quality - In Ground conduit install. | ITP
|  |  | Quality - Cable Tray / Ladder | ITP
Terminal
Lots - Cable Tray & Conduits
Basement
|  |  |  | B1.1 |  | Quality - Cable Tray / Ladder
|  |  |  | B1.2 |  | Same as B1.1
|  |  |  | B1.3 |  | Same as B1.1
|  |  |  | B1.4 |  | Same as B1.1
|  |  |  | B1.5 |  | Same as B1.1
|  |  |  | B1.6 |  | Same as B1.1
|  |  |  | B1.7 |  | Same as B1.1
Upper Basement
|  |  |  | BU1.1 |  | Same as B1.1
|  |  |  | BU1.2 |  | Same as B1.1
|  |  |  | BU1.3 |  | Same as B1.1
|  |  |  | BU1.4 |  | Same as B1.1
|  |  |  | BU1.5 |  | Same as B1.1
|  |  |  | BU1.6 |  | Same as B1.1
Ground floor
|  |  |  | GF1.1 |  | Same as B1.1
|  |  |  | GF1.2 |  | Same as B1.1
|  |  |  | GF1.3 |  | Same as B1.1
|  |  |  | GF1.4 |  | Same as B1.1
|  |  |  | GF1.5 |  | Same as B1.1
|  |  |  | GF1.6 |  | Same as B1.1
|  |  |  | GF1.7 |  | Same as B1.1
|  |  |  | GF1.8 |  | Same as B1.1
|  |  |  | GF1.9 |  | Same as B1.1
|  |  |  | GF1.10 |  | Same as B1.1
|  |  |  | GF-PE-1.1 |  | Same as B1.1
|  |  |  | GF-PE-1.2 |  | Same as B1.1
|  |  |  | GF-PE-1.3 |  | Same as B1.1
|  |  |  | GF-PW-1.1 |  | Same as B1.1
|  |  |  | GF-PW-1.2 |  | Same as B1.1
|  |  |  | GF-PW-1.3 |  | Same as B1.1
Second floor
|  |  |  | SF1.1 |  | Same as B1.1
|  |  |  | SF1.2 |  | Same as B1.1
|  |  |  | SF1.3 |  | Same as B1.1
|  |  |  | SF1.4 |  | Same as B1.1
|  |  |  | SF1.5 |  | Same as B1.1
|  |  |  | SF1.6 |  | Same as B1.1
|  |  |  | SF1.7 |  | Same as B1.1
|  |  |  | SF1.8 |  | Same as B1.1
|  |  |  | SF1.9 |  | Same as B1.1
|  |  |  | SF1.10 |  | Same as B1.1
|  |  |  | SF-PE-1.1 |  | Same as B1.1
|  |  |  | SF-PE-1.2 |  | Same as B1.1
|  |  |  | SF-PE-1.3 |  | Same as B1.1
|  |  |  | SF-PW-1.1 |  | Same as B1.1
|  |  |  | SF-PW-1.2 |  | Same as B1.1
|  |  |  | SF-PW-1.3 |  | Same as B1.1
Third Floor
TBC
Landside
In Ground HV CONDUITS
Lots
[6 empty] | LS1.01 | Quality - In Ground conduit install.
[6 empty] | LS1.02 | same as LS1.01
[6 empty] | LS1.03 | same as LS1.01
[6 empty] | LS1.04 | same as LS1.01
[6 empty] | LS1.05 | same as LS1.01
[6 empty] | LS1.06 | same as LS1.01
[6 empty] | LS1.07 | same as LS1.01
[6 empty] | LS1.08 | same as LS1.01
[6 empty] | LS1.09 | same as LS1.01
[6 empty] | LS1.10 | same as LS1.01
[6 empty] | LS1.11 | same as LS1.01
[6 empty] | LS1.12 | same as LS1.01
[6 empty] | LS1.13 | same as LS1.01
[6 empty] | LS1.14 | same as LS1.01
[6 empty] | LS1.15 | same as LS1.01
[6 empty] | LS1.16 | same as LS1.01
[6 empty] | LS1.17 | same as LS1.01
[6 empty] | LS1.18 | same as LS1.01
[6 empty] | LS1.19 | same as LS1.01
[6 empty] | LS1.20 | same as LS1.01
[6 empty] | LS1.21 | same as LS1.01
[6 empty] | LS1.22 | same as LS1.01
[6 empty] | LS1.23 | same as LS1.01
[6 empty] | LS1.24 | same as LS1.01
[6 empty] | LS1.25 | same as LS1.01
[6 empty] | LS1.26 | same as LS1.01
[6 empty] | LS1.27 | same as LS1.01
[6 empty] | LS1.28 | same as LS1.01
[6 empty] | LS1.29 | same as LS1.01
[6 empty] | LS1.30 | same as LS1.01
[6 empty] | LS1.31 | same as LS1.01
[6 empty] | LS1.32 | same as LS1.01
[6 empty] | LS1.33 | same as LS1.01
[6 empty] | LS1.34 | same as LS1.01
[6 empty] | LS1.35 | same as LS1.01
[6 empty] | LS1.36 | same as LS1.01
[6 empty] | LS1.37 | same as LS1.01
[6 empty] | LS1.38 | same as LS1.01
[6 empty] | LS1.39 | same as LS1.01
[6 empty] | LS1.40 | same as LS1.01
[6 empty] | LS1.41 | same as LS1.01
[6 empty] | LS1.42 | same as LS1.01
[6 empty] | LS1.43 | same as LS1.01
[6 empty] | LS1.44 | same as LS1.01
[6 empty] | LS1.45 | same as LS1.01
[6 empty] | LS1.46 | same as LS1.01
[6 empty] | LS1.47 | same as LS1.01
[6 empty] | LS1.48 | same as LS1.01
[6 empty] | LS1.49 | same as LS1.01
[6 empty] | LS1.50 | same as LS1.01
[6 empty] | LS1.51 | same as LS1.01
[6 empty] | LS1.52 | same as LS1.01
[6 empty] | LS1.53 | same as LS1.01
[6 empty] | LS1.54 | same as LS1.01
[6 empty] | LS1.55 | same as LS1.01
[6 empty] | LS1.56 | same as LS1.01
[6 empty] | LS1.57 | same as LS1.01
[6 empty] | LS1.58 | same as LS1.01
[6 empty] | LS1.59 | same as LS1.01
[6 empty] | LS1.60 | same as LS1.01
[6 empty] | LS1.61 | same as LS1.01
[6 empty] | LS1.62 | same as LS1.01
[6 empty] | LS1.63 | same as LS1.01
[6 empty] | LS1.64 | same as LS1.01
[6 empty] | LS1.65 | same as LS1.01
[6 empty] | LS1.66 | same as LS1.01
[6 empty] | LS1.67 | same as LS1.01
[6 empty] | LS1.68 | same as LS1.01
[6 empty] | LS1.69 | same as LS1.01
[6 empty] | LS1.70 | same as LS1.01
[6 empty] | LS1.71 | same as LS1.01
[6 empty] | LS1.72 | same as LS1.01
[6 empty] | LS1.73 | same as LS1.01
[6 empty] | LS1.74 | same as LS1.01
[6 empty] | LS1.75 | same as LS1.01
[6 empty] | LS1.76 | same as LS1.01
[6 empty] | LS1.77 | same as LS1.01
[6 empty] | LS1.78 | same as LS1.01
[6 empty] | LS1.79 | same as LS1.01
[6 empty] | LS1.80 | same as LS1.01
[6 empty] | LS1.81 | same as LS1.01
[6 empty] | LS1.82 | same as LS1.01
[6 empty] | LS1.83 | same as LS1.01
[6 empty] | LS1.84 | same as LS1.01
[6 empty] | LS1.85 | same as LS1.01
[6 empty] | LS1.86 | same as LS1.01
[6 empty] | LS1.87 | same as LS1.01
[6 empty] | LS1.88 | same as LS1.01
[6 empty] | LS1.89 | same as LS1.01
[6 empty] | LS1.90 | same as LS1.01
[6 empty] | LS1.91 | same as LS1.01
[6 empty] | LS1.92 | same as LS1.01
[6 empty] | LS1.93 | same as LS1.01
[6 empty] | LS1.94 | same as LS1.01
[6 empty] | LS1.95 | same as LS1.01
[6 empty] | LS1.96 | same as LS1.01
HV Pit Install
[5 empty] | EL-CPP-LS-1-001 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-002 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-003 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-004 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-005 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-006 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-007 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-008 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-009 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-010 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-011 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-012 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-013 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-014 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-015 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-016 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-017 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-018 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-019 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-020 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-021 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-022 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-023 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-024 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-025 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-026 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-027 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-028 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-029 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-030 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-031 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-032 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-033 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-034 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-035 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-036 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-037 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-038 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-039 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-040 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-041 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-042 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-043 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-044 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-045 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-046 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-047 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-048 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-049 |  | Quality - Precast Pit Install
[5 empty] | EL-CPP-LS-1-050 |  | Quality - Precast Pit Install
LV AND ICN CONDUIT INSTALL
CPD - 1.1
QUALITY - Inground LV & Communication Conduits
QUALITY - Inground LV & Communication Conduits
[5 empty] | CPD - 1.2 | SAME AS CPD-1.1
[5 empty] | CPD - 1.3 | SAME AS CPD-1.1
[5 empty] | CPA - 1.1 | SAME AS CPD-1.1
[5 empty] | CPA - 1.2 | SAME AS CPD-1.1
[5 empty] | CPA - 1.3 | SAME AS CPD-1.1
[5 empty] | FC - 1.1 | SAME AS CPD-1.1
[5 empty] | FC - 1.2 | SAME AS CPD-1.1
[5 empty] | FC - 1.3 | SAME AS CPD-1.1
[5 empty] | FC - 1.4 | SAME AS CPD-1.1
[5 empty] | FC - 1.5 | SAME AS CPD-1.1
[5 empty] | PE - 1.1 | SAME AS CPD-1.1
[5 empty] | PW - 1.1 | SAME AS CPD-1.1
LV and Communication - Pit and Pipe inspection
FOCB
[6 empty] | 4000-CMP-50001 | LV and Communication - Pit and Pipe Inspection
[6 empty] | 4000-CMP-50002 | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-50003 | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-50004 | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-50005 | Same as 4000-CMP-50001
[6 empty] | continues adding test in sequential order | Same as 4000-CMP-50001
[6 empty] | Stop when number of test reaches the below. | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-50017 | Same as 4000-CMP-50001
ICN
[6 empty] | 4000-CMP-00001 | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-00002 | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-00003 | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-00004 | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-00005 | Same as 4000-CMP-50001
[6 empty] | continues adding test in sequential order | Same as 4000-CMP-50001
[6 empty] | Stop when number of test reaches the below. | Same as 4000-CMP-50001
[6 empty] | 4000-CMP-00147 | Same as 4000-CMP-50001
LV
[6 empty] | 4000-PTT-00001 | Same as 4000-CMP-50001
[6 empty] | 4000-PTT-00002 | Same as 4000-CMP-50001
[6 empty] | 4000-PTT-00003 | Same as 4000-CMP-50001
[6 empty] | 4000-PTT-00004 | Same as 4000-CMP-50001
[6 empty] | 4000-PTT-00005 | Same as 4000-CMP-50001
[6 empty] | continues adding test in sequential order | Same as 4000-CMP-50001
[6 empty] | Stop when number of test reaches the below. | Same as 4000-CMP-50001
[6 empty] | 4000-PTT-00088 | Same as 4000-CMP-50001
Switchrooms
Pier East
[6 empty] | In Ground | Quality - In Ground conduit install.
[6 empty] | Cable Tray / Ladder | Quality - Cable Tray / Ladder
[5 empty] | Pier West |  | Same as Pier East
[5 empty] | Car park |  | Same as Pier East
Distribution Boards
Pending checklist |  |  | TRANSFORMERS
|  |  |  | EL-SUB-01-301 (T1) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-203 (T3) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-401 (T2) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-201 (PC-1) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-202 (PC-2) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-701 (COOLING) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-103 (PW-1) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-104 (PW-2) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-205 (PE-1) |  |  | Quality - Transformer installation
|  |  |  | EL-SUB-01-206 (PE-2) |  |  | Quality - Transformer installation
MAIN DISTRIBUTION BOARDS
EL-MSBE-01-301 (T1)
[5 empty] | Main Switchboard Install |  | Quality - Main switchboard Install
[5 empty] | Mains and Sub Mains |  | REFER TO THE TAB - MSB-Submain List - Table "Terminal" | Quality Mains and Sub Mains
[5 empty] | Busduct |  | REFER TO THE TAB - MSB-Busduct List - Table "Terminal" | Quality - Busduct
[5 empty] | Earthing & Lighting Protection |  | Quality - Earthing & Lightning protection
|  |  |  | EL-MSBN-01-301 (T1) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSB-01-203 (T3) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBE-01-203 (T3) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBN-01-203 (T3) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBE-01-401 (T2) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBN-01-401 (T2) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSB-01-201 (PC) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBE-01-201 (PC) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBN-01-201 (PC) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSB-01-701 (COOLING) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-SBD-01-701 (COOLING) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-SBD-01-702 (COOLING) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-SBD-01-703 (COOLING) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSB-01-103 (PW) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBE-02-103 (PW) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBN-02-103 (PW) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSB-02-205 (PE) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBE-02-205 (PE) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSBN-02-205 (PE) |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-MSB-02-801 (CARPARK) |  |  | SAME AS EL-MSBE-01-301 (T1)
UPS MDBs
|  |  |  | EL-UPSIO-01-301 |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-UPSIO-01-201 |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-UPSIO-01-102 |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-UPSIO-01-203 |  |  | SAME AS EL-MSBE-01-301 (T1)
|  |  |  | EL-UPSIO-01-801 |  |  | SAME AS EL-MSBE-01-301 (T1)
DISTRIBUTION BOARDS
CDBU
[5 empty] | EL-CDBU-01-301 |  | Quality - Distribution boards
[5 empty] | EL-CDBU-01-302 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-402 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-403 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-404 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-502 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-503 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-504 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-01-602 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-111 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-112 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-113 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-114 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-201 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-202 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-203 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-204 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-211 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-212 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-213 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-214 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-302 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-402 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-502 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-02-602 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-111 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-112 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-113 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-114 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-201 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-202 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-203 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-204 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-211 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-212 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-213 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-214 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-302 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-402 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-502 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-05-602 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-111 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-112 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-113 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-114 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-302 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-CDBU-06-402 |  | Same as EL-CDBU-01-301
[5 empty] | EL-DBU-01-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-DBU-01-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-DBU-02-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-DBU-05-204 |  | Same as EL-CDBU-01-301
[5 empty] | EL-DBU-05-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-DBU-05-601 |  | Same as EL-CDBU-01-301
HOUSE DB - E
[5 empty] | EL-HDBE-01-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-01-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-01-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-01-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-01-701 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-201 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-202 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-203 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-204 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-02-703 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-201 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-202 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-203 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-204 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-05-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-06-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-06-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-06-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-06-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-06-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-06-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-06-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBE-06-601 |  | Same as EL-CDBU-01-301
HOUSE DB - N
[5 empty] | EL-HDBN-01-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-01-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-01-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-01-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-01-701 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-201 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-202 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-203 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-204 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-02-703 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-201 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-202 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-203 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-204 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-05-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-06-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-06-102 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-06-103 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-06-104 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-06-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-06-401 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-06-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HDBN-06-601 |  | Same as EL-CDBU-01-301
HYD DBs
[5 empty] | EL-HYDDB-01-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-HYDDB-01-702 |  | Same as EL-CDBU-01-301
Apron DBs
[5 empty] | EL-APRONDB-02-19 |  | Same as EL-CDBU-01-301
[5 empty] | EL-APRONDB-02-20 |  | Same as EL-CDBU-01-301
[5 empty] | EL-APRONDB-02-21 |  | Same as EL-CDBU-01-301
[5 empty] | EL-APRONDB-02-22 |  | Same as EL-CDBU-01-301
[5 empty] | EL-APRONDB-02-23 |  | Same as EL-CDBU-01-301
[5 empty] | EL-APRONDB-02-24 |  | Same as EL-CDBU-01-301
[5 empty] | EL-APRONDB-02-25 |  | Same as EL-CDBU-01-301
eGSE DBs
[5 empty] | EL-eGSE-02-19 |  | Same as EL-CDBU-01-301
[5 empty] | EL-eGSE-02-20 |  | Same as EL-CDBU-01-301
[5 empty] | EL-eGSE-02-21 |  | Same as EL-CDBU-01-301
[5 empty] | EL-eGSE-02-22 |  | Same as EL-CDBU-01-301
[5 empty] | EL-eGSE-02-23 |  | Same as EL-CDBU-01-301
[5 empty] | EL-eGSE-02-24 |  | Same as EL-CDBU-01-301
[5 empty] | EL-eGSE-02-25 |  | Same as EL-CDBU-01-301
GPU DBs
[5 empty] | EL-GPUDB-02-19 |  | Same as EL-CDBU-01-301
[5 empty] | EL-GPUDB-02-20 |  | Same as EL-CDBU-01-301
[5 empty] | EL-GPUDB-02-21 |  | Same as EL-CDBU-01-301
[5 empty] | EL-GPUDB-02-22 |  | Same as EL-CDBU-01-301
[5 empty] | EL-GPUDB-02-23 |  | Same as EL-CDBU-01-301
[5 empty] | EL-GPUDB-02-24 |  | Same as EL-CDBU-01-301
[5 empty] | EL-GPUDB-02-25 |  | Same as EL-CDBU-01-301
PCA DBs
[5 empty] | EL-PCADB-02-19 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PCADB-02-20 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PCADB-02-21 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PCADB-02-22 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PCADB-02-23 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PCADB-02-24 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PCADB-02-25 |  | Same as EL-CDBU-01-301
PV DBs
[5 empty] | EL-PVDB-02-101 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PVDB-02-202 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PVDB-06-501 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PVDB-06-601 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PVDB-07-301 |  | Same as EL-CDBU-01-301
[5 empty] | EL-PVDB-07-302 |  | Same as EL-CDBU-01-301
TERS
LOTS - CABLE TRAY & CONDUIT
TER 1
|  |  |  | Lot Break Up |  |  | LOT BREAK UP
|  |  |  | ITP |  |  | ITP
|  |  |  | Cable Tray / Ladder |  |  | Quality - Cable Tray / Ladder
|  |  | TER 2 |  |  |  | SAME AS TER 1
LOTS - DISTRIBUTION BOARDS
FUEL FARM
LOTS - CABLE TRAY & CONDUIT
|  |  | LOT AREA MARKUP |  |  |  | LOT BREAK UP
AREA 1
|  |  |  | ITP |  |  | ITP
|  |  |  | In Ground Conduit Install |  |  | Quality - In Ground conduit install.
|  |  | AREA 2 |  |  |  | SAME AS AREA 1
|  |  | AREA 3 |  |  |  | SAME AS AREA 1
|  |  | AREA 4 |  |  |  | SAME AS AREA 1
|  |  | AREA 5 |  |  |  | SAME AS AREA 1
|  |  | AREA 6 |  |  |  | SAME AS AREA 1
BUILDING 2.01
|  |  |  | ITP |  |  | ITP
|  |  |  | Cable Tray / Ladder |  |  | Quality - Cable Tray / Ladder
|  |  | BUILDING 2.02 | SAME AS BUILDING 2.01
|  |  | BUILDING 2.03 | SAME AS BUILDING 2.01
|  |  | BUILDING 2.04 | SAME AS BUILDING 2.01
|  |  | BUILDING 2.05 | SAME AS BUILDING 2.01
|  |  | BUILDING 2.06 | SAME AS BUILDING 2.01
|  |  | BUILDING 2.07 | SAME AS BUILDING 2.01
|  |  | BUILDING 2.08 | SAME AS BUILDING 2.01
|  |  | BUILDING 3.03 | SAME AS BUILDING 2.01
|  |  | BUILDING 3.06 | SAME AS BUILDING 2.01
|  |  | FIRE WATER TANKS | SAME AS BUILDING 2.01
|  |  | DIESEL TANK | SAME AS BUILDING 2.01
|  |  | GENERATOR PAD | SAME AS BUILDING 2.01
|  |  | FUEL TANKS | SAME AS BUILDING 2.01
Poles
Area 1
PML-10066
|  |  |  | Pole Light Pier Installation ITP |  |  | Pole Light Pier Installation ITP
|  |  |  | Pole light Pier Installation ITC |  |  | Pole light Pier Installation ITC
PML-10084
PML-10068
PML-10008
PML-10022
PML-10002
PML-10010
PML-10007
PML-10027
PML-10067
PML-10087
PML-10089
PML-10012
PML-10031
PML-10032
PML-10033
Area 2
PML-10069
PML-10070
PML-10071
PML-10072
PML-10039
PML-10040
PML-10041
PML-10023
PML-10024
PML-10025
PML-10026
PML-10078
PML-10020
PML-10021
PML-10034
PML-10035
PML-10018
PML-10077
PML-10090
PML-10095
Area 3
PML-10042
PML-10043
PML-10044
PML-10045
PML-10046
PML-10047
PML-10048
PML-10091
PML-10036
PML-10037
PML-10081
PML-10082
Area 4
PML-10057
PML-10058
PML-10059
PML-10060
PML-10061
PML-10062
PML-10063
PML-10074
PML-10076
PML-10038
PML-10083
Area 5
PML-10096
PML-10097
PML-10019
PML-10088
PML-10064
PML-10065
PML-10085
PML-10086
PML-10009
PML-10017
PML-10093
PML-10094
Area 6
PML-10013
PML-10014
PML-10015
PML-10016
PML-10028
PML-10029
PML-10030
PML-10011
PML-10001
PML-10003
PML-10004
PML-10005
PML-10006
PML-10075
Area 7
PML-10049
PML-10050
PML-10051
PML-10052
PML-10053
PML-10054
PML-10055
PML-10056
PML-10092
PML-10073
PML-10079
PML-10080

## Site QA - Checklists
type | name | values
checklist | Quality - In Ground conduit install - HV ONLY
checkpoint | Receipt of conduit delivery to site & storage. (ITP Reference Item 1)
checkpoint | Set out. (ITP Reference Item 2)
checkpoint | Excavation - Correct trenching alignment & depth. (ITP Reference Item 3)
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Conduit Installation. (ITP Reference Item 4) |  |  | NEW
checkpoint | Spacer Frame Installation. (ITP Reference Item 5) |  |  | Changes
checkpoint | Change of direction/bend Installation, correct bending radius used as per drawing. (ITP Reference Item 6) |  |  | Delete
checkpoint | Bellmouths installed within Insitu Pits. (ITP Reference Item 7)
checkpoint | Glue Conduits together. (ITP Reference Item 8)
checkpoint | TSB Installation around & above conduits. (ITP Reference Item 9)
signoff | Signoff Required from Heyday & Multiplex
checkpoint | 150mm cover of backfill above TSB. (ITP Reference Item 10)
checkpoint | Warning tape installation above 150mm cover. (ITP Reference Item 11)
checkpoint | Back fill & compact. (ITP Reference Item 12)
checkpoint | Rope & pathway test. (ITP Reference Item 13)
checkpoint | Sealing of conduits. (ITP Reference Item 14) HOLD POINT
signoff | Signoff Required from Heyday & Multiplex
checklist | ITP
checkpoint | Please attach copy of ITP
checklist | LOT BREAK UP
checkpoint | Attached Mark up of Lot Breakup
checklist | Quality Mains and Sub Mains
checkpoint | Receipt of cable containment delivery to site & storage. (ITP Reference Item 1)
checkpoint | Cable storage & handling. (ITP Reference Item 2)
checkpoint | Correct cable size & type. (ITP Reference Item 3)
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Cable pulling tension to not exceed manufacturer's recommendations. (ITP Reference Item 4)
checkpoint | Cable lubrication if required. (ITP Reference Item 5)
checkpoint | Installed to latest drawings – schematics/single line diagram & cable containment drawings. (ITP Reference Item 6)
checkpoint | Correct cable tag installed. (ITP Reference Item 7)
checkpoint | Photo evidence captured for cable containment install. (ITP Reference Item 8)
signoff | Signoff Required from Heyday & Multiplex
checklist | Quality - Power and Lighting Subcircuits
checkpoint | Receipt of cable containment delivery to site & storage. (ITP Reference Item 1)
checkpoint | Correct size & cable type. (ITP Reference Item 2)
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Installed to correct cable routing arrangements & circuit number. (ITP Reference Item 3)
checkpoint | Installed to final location. (ITP Reference Item 4)
checkpoint | Photo evidence captured for cable containment install. (ITP Reference Item 5)
signoff | Signoff Required from Heyday & Multiplex
checklist | Quality - Cable Tray / Ladder
checkpoint | Receipt of Cable Tray delivery to site & storage
checkpoint | Set out to be confirmed with latest AFC Drawings
checkpoint | Accessories to be factory made items
checkpoint | Correct Levelling & Alignment
checkpoint | correct bracket and safe fixing
checkpoint | Correct Bends used (Cable Ladder)
checkpoint | Cable Tray Checked For Sharp Edges
checkpoint | Containment Earthing - As Per the Standards
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Photos attached.
checklist | Quality - Main switchboard Install
checkpoint | Receipt of switchboard delivery to site
checkpoint | set out to be confirmed with latest Switchboards Shop drawings
checkpoint | Correct alightment to set out drawings
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Correct bracket and safe fixing
checkpoint | Photos of boards attached
checklist | Quality - Distribution boards
checkpoint | Receipt of switchboard delivery to site
checkpoint | set out to be confirmed with latest Switchboards Shop drawings
checkpoint | Correct alightment to set out drawings
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Correct bracket and safe fixing
checkpoint | Photos of boards attached
checklist | Quality - Earthing & Lightning protection
checkpoint | Receipt of Cable & test point delivery to site
checkpoint | Correct cable size and Cable type installed per the shop drawing
checkpoint | Installed and Terminated to final locations
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Photos of test piont and bonds attached
checklist | Quality - Busduct
checkpoint | Receipt of busduct/ busway & take off box's delivery to site
checkpoint | Set out - Ensure correct size, type and spare capacity
checkpoint | Accessories to be factory made items
checkpoint | Hangers installed as per the drawings
checkpoint | IR Test of Busduct - Separate - Test Result Above 1M Ω
checkpoint | Busduct Piece are installed safely
checkpoint | Busduct Touqed to 95Nm
checkpoint | IR Test of Busduct - Joined - Test Result Above 1M Ω
checklist | Photos attached of installed piece |  | Manditory Photo
checklist | Quality - Transformer installation
Checkpoint | TBC
checklist | Quality - Precast Pit Install
checkpoint | Receipt of Precast pit delivery to site & storage
checkpoint | pit is build to approved shopdrawings (photos attached
checkpoint | correct trenching and alignment & depth
checkpoint | installed to correct finish level
checkpoint | correct back fill installed around pit
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Install correct pit lid
checkpoint | Photo of pit installed attached.
QUALITY - Inground LV & Communication Conduits
checkpoint | Receipt of conduit delivery to site & storage. (ITP Reference Item 1)
checkpoint | Set out. (ITP Reference Item 2)
checkpoint | Excavation - Correct trenching alignment & depth. (ITP Reference Item 3) HOLD POINT
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Conduit Installation. (ITP Reference Item 4)
checkpoint | Spacer Frame Installation if required. (ITP Reference Item 5)
checkpoint | Change of direction/bend Installation, correct bending radius used as per drawing. (ITP Reference Item 6)
checkpoint | Glue Conduits together. (ITP Reference Item 7)
checkpoint | 300mm cover of backfill above conduits. (ITP Reference Item 9)
checkpoint | Warning tape installation above 300mm cover. (ITP Reference Item 10)
checkpoint | Back fill & compact. (ITP Reference Item 11)
signoff | Signoff Required from Heyday & Multiplex
checkpoint | Record photo evidence. (ITP Reference Item 14)
checklist | Pole Light Pier Installation ITP
checkpoint | Approved IFC Drawings
label | Review drawings and revision status with Heyday drawing register, ensuring to only work to AFC drawings, and approved documents:
label | WSA50-MPX-02702-EL-DRG-000321[05]
label | WSA50-MPX-02702-EL-DRG-000324[01]
label | WSA50-MPX-02702-EL-DRG-000304[03]
label | WSA50-MPX-02702-ST-DRG-001202[04]
checkpoint | Material
label | Only use material approved by MPX through the required sample process listed on Heyday samples register as approved:
checkpoint | Receipt of foundation cages delivery to site& storage.
label | Review all delivered against approved product submission and confirm conformance. Components parts list, as stated on the purchase order/invoice, to be validated against received items
checkpoint | Set out (Correct location set out as per approved shop drawings) .
label | Set out to be confirmed with latest AFC drawings. WSA50-MPX-02702-EL-DRG-000321[05] WSA50-MPX-02702-EL-DRG-000324[01]
checkpoint | Correct trenching alignment & depth with Excavator and Auger. If rock is struck, geotech will be required to confirm socket depth
label | WSA50-MPX-02702-EL-DRG-000321[05] WSA50-MPX-02702-EL-DRG-000324[01]
checkpoint | Install cage and Ragbolts to correct finish level.
label | WSA50-MPX-02702-EL-DRG-000321[05] WSA50-MPX-02702-EL-DRG-000324[01]
checkpoint | Install conduits & Formatube.
label | WSA50-MPX-02702-EL-DRG-000321[05] WSA50-MPX-02702-EL-DRG-000324[01]
checkpoint | Concrete installation using Tremie Pipe
label | WSA50-MPX-02702-EL-DRG-000321[05] WSA50-MPX-02702-EL-DRG-000324[01]
checkpoint | Photo evidence captured for asset install
label | Photo evidence to be captured, stored and provided for formal submission where applicable/outlined within ITP
checkpoint | Completion of installation
label | Heyday supervisor to ensure that all work has been completed to relevant standards & approved drawings
checkpoint | Photo Evidence
label | Heyday supervisor to capture & submit photo evidence as part of completed works specified within ITC
checkpoint | As-built survey & report
label | Heyday supervisor to submit As-built drawings as part of completed works
signoff | Signoff Required from Heyday & Multiplex
checklist | Pole light Pier Installation ITC
checkpoint | Receipt of foundation cages delivery to site & storage. (ITP Reference Item 1)
checkpoint | Set out (Correct pier locations as per approved shop drawings). (ITP Reference Item 2)
checkpoint | Correct trenching alignment & depth with excavator and auger. (ITP Reference Item 3)
checkpoint | Install cage and rag bolts to correct finish level. (ITP Reference Item 4)
checkpoint | Install conduits and formatube. (ITP Reference Item 5)
signoff | HOLD POINT inspection prior to concrete
checkpoint | Concrete installation with tremie pipe. (ITP Reference Item 6)
checkpoint | Photo evidence captured for cable containment install. (ITP Reference Item 7)
signoff | Signoff Required from Heyday & Multiplex
Checklist | LV and Communication - Pit and Pipe Inspection
checkpoint | Cover Slab and correct Pit installed per shop drawing.
checkpoint | Pit Lid installed to correct FSL
checkpoint | Conduits from pit out have been mandueled using correct size.
checkpoint | Ropes installed in conduits
signoff | Signoff Required from Heyday
checkpoint | Photo of pits installed.

## Commissioning - Structure
Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9 | Resource to use | Notes Only
Testing & Commissioning
Terminal
Transformers
EL-SUB-01-301 (T1)
Tier 5: HV/LV Transformers | HV/LV Transformers
Tier 4: EL-SUB-01-203 (T3) | SAME AS EL-SUB-01-301 (T1)
Tier 4: EL-SUB-01-401 (T2) | SAME AS EL-SUB-01-301 (T1)
Tier 4: EL-SUB-01-201 (PC-1) | SAME AS EL-SUB-01-301 (T1)
Tier 4: EL-SUB-01-202 (PC-2) | SAME AS EL-SUB-01-301 (T1)
Tier 4: EL-SUB-01-701 (COOLING) | SAME AS EL-SUB-01-301 (T1)
Tier 4: EL-SUB-01-103 (PW-1) | SAME AS EL-SUB-01-301 (T1)
Tier 4: EL-SUB-01-104 (PW-2) | SAME AS EL-SUB-01-301 (T1)
Tier 4: EL-SUB-01-205 (PE-1) | SAME AS EL-SUB-01-301 (T1)
Tier 4: EL-SUB-01-206 (PE-2) | SAME AS EL-SUB-01-301 (T1)
Main Switchboards
Tier 4: EL-MSBE-01-301 (T1) |  |  | Checklists
Tier 5: Main Switchboards |  |  | Low Voltage Cables (Mains/Submains)
Tier 6: WSA20-MPX-04000-EL-ITC-31032000 - Construction Tests (Pre-energisation) | Main Switchboards (Pre-Energisation) |  | HV/LV Transformers
Tier 6: WSA20-MPX-04000-EL-ITC-31033000 - Component (Energised) | Main Switchboards (Energised) |  | Main Switchboards
Tier 5: Low Voltage Cables (Mains/Submains) |  |  | Distribution Boards
Tier 6: Refer to TAB "MSB-Submain List" - Table "Terminal" - Columns "SUBMAIN ID" + "SUPPLY TO" |  |  | Low Voltage Busduct
Tier 7: WSA20-MPX-04000-EL-ITC-31052000 Construction Tests (Pre-energisation) | Low Voltage Cables - Mains/Submains (Pre-Energisation) |  | Subcircuits
Tier 7: WSA20-MPX-04000-EL-ITC-31053000 Component (Energised) | Low Voltage Cables - Mains/Submains (Energised) |  | Earthing Systems
Tier 5: Low Voltage Busduct |  |  | PFC
Tier 6: Refer to TAB "MSB-Busduct List" - Table "Terminal" - Column "BUSDUCT ID" |  |  | UPS
Tier 7: WSA20-MPX-04000-EL-ITC-31062000 - Construction Tests (Pre-energisation) | Low Voltage Busduct (Pre-Energisation) |  | Load Bank
Tier 7: WSA20-MPX-04000-EL-ITC-31063000 - Component (Energised) | Low Voltage Busduct (Energised) |  | Emergency Lighting
Tier 5: Earthing Systems |  |  | Lighting Control
Tier 6: WSA20-MPX-04000-EL-ITC-31092000a - Construction Tests (Main Earth System) | Earthing Systems - Construction Tests (Main Earth System) |  | PMCS
Tier 6: WSA20-MPX-04000-EL-ITC-31092000b – Construction Tests (Earth System Reticulation) | Earthing Systems - Construction Tests (Earth System Reticulation)
Tier 4: EL-MSBE-01-203 (T3) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBN-01-203 (T3) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBE-01-401 (T2) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBN-01-401 (T2) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSB-01-201 (PC) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBE-01-201 (PC) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBN-01-201 (PC) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSB-01-701 (COOLING) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-SBD-01-701 (COOLING) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-SBD-01-702 (COOLING) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-SBD-01-703 (COOLING) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSB-01-103 (PW) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBE-02-103 (PW) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBN-02-103 (PW) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSB-02-205 (PE) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBE-02-205 (PE) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSBN-02-205 (PE) | SAME AS EL-MSBE-01-301 (T1)
Tier 4: EL-MSB-02-801 (CP) | SAME AS EL-MSBE-01-301 (T1)
UPS MDBs
EL-UPSIO-01-301 (T)
UPS
Tier 6: WSA20-MPX-04000-EL-ITC-31122000 - Construction Tests (Pre-energisation) | UPS (Pre-Energistation)
Tier 6: WSA20-MPX-04000-EL-ITC-31123000 - Component (Energised) | UPS (Energised)
Tier 6: WSA20-MPX-04000-EL-ITC-31124000 - System Commissioning | UPS (System Commissioning)
Low Voltage Cables (Mains/Submains)
Refer to TAB "UPS-Submain List" - Columns "SUBMAIN ID" + "SUPPLY TO"
Tier 7: WSA20-MPX-04000-EL-ITC-31052000 Construction Tests (Pre-energisation) | Low Voltage Cables - Mains/Submains (Pre-Energisation)
Tier 7: WSA20-MPX-04000-EL-ITC-31053000 Component (Energised) | Low Voltage Cables - Mains/Submains (Energised)
Low Voltage Busduct
Refer to TAB "UPS-Busduct List" - Column "BUSDUCT ID"
Tier 7: WSA20-MPX-04000-EL-ITC-31062000 - Construction Tests (Pre-energisation) | Low Voltage Busduct (Pre-Energisation)
Tier 7: WSA20-MPX-04000-EL-ITC-31063000 - Component (Energised) | Low Voltage Busduct (Energised)
Tier 4: EL-UPSIO-01-201 (PC) | SAME AS EL-UPSIO-01-301
Tier 4: EL-UPSIO-02-102 (PW) | SAME AS EL-UPSIO-01-301
Tier 4: EL-UPSIO-02-203 (PE) | SAME AS EL-UPSIO-01-301
Tier 4: EL-UPSIO-02-801 (CP) | SAME AS EL-UPSIO-01-301
SAME AS EL-UPSIO-01-301
Distribution Boards
CDBU
EL-CDBU-01-301
Distribution Boards
Tier 7: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation) | Distribution Boards (Pre-Energisation)
Tier 7: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised) | Distribution Boards (Energised)
Subcircuits
Power
CB-01
Tier 9: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation) | Subcircuits (Pre-Energisation)
Tier 9: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised) | Subcircuits (Energised)
Tier 5: EL-CDBU-01-302 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-401 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-402 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-403 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-404 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-501 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-502 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-503 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-504 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-601 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-01-602 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-101 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-102 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-103 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-104 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-111 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-112 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-113 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-114 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-201 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-202 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-203 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-204 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-211 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-212 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-213 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-214 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-301 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-302 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-401 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-402 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-501 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-502 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-601 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-02-602 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-101 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-102 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-103 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-104 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-111 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-112 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-113 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-114 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-201 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-202 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-203 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-204 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-211 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-212 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-213 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-214 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-301 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-302 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-401 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-402 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-501 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-502 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-601 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-05-602 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-101 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-102 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-103 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-104 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-111 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-112 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-113 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-114 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-301 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-302 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-401 | SAME AS EL-CDBU-01-301
Tier 5: EL-CDBU-06-402 | SAME AS EL-CDBU-01-301
Tier 5: EL-DBU-01-301 | SAME AS EL-CDBU-01-301
Tier 5: EL-DBU-01-401 | SAME AS EL-CDBU-01-301
Tier 5: EL-DBU-02-501 | SAME AS EL-CDBU-01-301
Tier 5: EL-DBU-05-204 | SAME AS EL-CDBU-01-301
Tier 5: EL-DBU-05-501 | SAME AS EL-CDBU-01-301
Tier 5: EL-DBU-05-601 | SAME AS EL-CDBU-01-301
HOUSE DB - E
EL-HDBE-01-301
Distribution Boards
Tier 7: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation) | Distribution Boards (Pre-Energisation)
Tier 7: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised) | Distribution Boards (Energised)
Subcircuits
Lighting
CB-01
Tier 9: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation) | Subcircuits (Pre-Energisation)
Tier 9: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised) | Subcircuits (Energised)
[7 empty] | CB-02 | SAME AS CB-01
[7 empty] | CB-03 | SAME AS CB-01
[7 empty] | CB-04 | SAME AS CB-01
[7 empty] | CB-05 | SAME AS CB-01
[7 empty] | CB-06 | SAME AS CB-01
[7 empty] | CB-07 | SAME AS CB-01
[7 empty] | CB-08 | SAME AS CB-01
[7 empty] | CB-09 | SAME AS CB-01
[7 empty] | CB-10 | SAME AS CB-01
Power
CB-01
Tier 9: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation) | Subcircuits (Pre-Energisation)
Tier 9: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised) | Subcircuits (Energised)
[7 empty] | CB-02 | SAME AS CB-01
[7 empty] | CB-03 | SAME AS CB-01
[7 empty] | CB-04 | SAME AS CB-01
[7 empty] | CB-05 | SAME AS CB-01
[7 empty] | CB-06 | SAME AS CB-01
[7 empty] | CB-07 | SAME AS CB-01
[7 empty] | CB-08 | SAME AS CB-01
[7 empty] | CB-09 | SAME AS CB-01
[7 empty] | CB-10 | SAME AS CB-01
Tier 5: EL-HDBE-01-401 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-01-501 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-01-601 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-01-701 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-101 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-102 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-103 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-104 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-201 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-202 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-203 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-204 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-301 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-401 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-501 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-601 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-02-703 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-101 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-102 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-103 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-104 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-201 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-202 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-203 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-204 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-301 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-401 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-501 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-05-601 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-06-101 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-06-102 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-06-103 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-06-104 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-06-301 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-06-401 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-06-501 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBE-06-601 | SAME AS EL-HDBE-01-301
HOUSE DB - N
Tier 5: EL-HDBN-01-301 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-01-401 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-01-501 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-01-601 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-01-701 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-101 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-102 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-103 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-104 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-201 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-202 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-203 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-204 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-301 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-401 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-501 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-601 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-02-703 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-101 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-102 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-103 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-104 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-201 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-202 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-203 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-204 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-301 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-401 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-501 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-05-601 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-06-101 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-06-102 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-06-103 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-06-104 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-06-301 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-06-401 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-06-501 | SAME AS EL-HDBE-01-301
Tier 5: EL-HDBN-06-601 | SAME AS EL-HDBE-01-301
HYD DBs
Tier 5: EL-HYDDB-01-601 | SAME AS EL-HDBE-01-301
Tier 5: EL-HYDDB-01-702 | SAME AS EL-HDBE-01-301
Apron DBs
Tier 5: EL-APRONDB-02-19 | SAME AS EL-HDBE-01-301
Tier 5: EL-APRONDB-02-20 | SAME AS EL-HDBE-01-301
Tier 5: EL-APRONDB-02-21 | SAME AS EL-HDBE-01-301
Tier 5: EL-APRONDB-02-22 | SAME AS EL-HDBE-01-301
Tier 5: EL-APRONDB-02-23 | SAME AS EL-HDBE-01-301
Tier 5: EL-APRONDB-02-24 | SAME AS EL-HDBE-01-301
Tier 5: EL-APRONDB-02-25 | SAME AS EL-HDBE-01-301
eGSE DBs
EL-eGSE-02-19
Tier 5: EL-eGSE-02-20 | SAME AS EL-CDBU-01-301
Tier 5: EL-eGSE-02-21 | SAME AS EL-CDBU-01-301
Tier 5: EL-eGSE-02-22 | SAME AS EL-CDBU-01-301
Tier 5: EL-eGSE-02-23 | SAME AS EL-CDBU-01-301
Tier 5: EL-eGSE-02-24 | SAME AS EL-CDBU-01-301
Tier 5: EL-eGSE-02-25 | SAME AS EL-CDBU-01-301
GPU DBs
Tier 5: EL-GPUDB-02-19 | SAME AS EL-CDBU-01-301
Tier 5: EL-GPUDB-02-20 | SAME AS EL-CDBU-01-301
Tier 5: EL-GPUDB-02-21 | SAME AS EL-CDBU-01-301
Tier 5: EL-GPUDB-02-22 | SAME AS EL-CDBU-01-301
Tier 5: EL-GPUDB-02-23 | SAME AS EL-CDBU-01-301
Tier 5: EL-GPUDB-02-24 | SAME AS EL-CDBU-01-301
Tier 5: EL-GPUDB-02-25 | SAME AS EL-CDBU-01-301
PCA DBs
Tier 5: EL-PCADB-02-19 | SAME AS EL-CDBU-01-301
Tier 5: EL-PCADB-02-20 | SAME AS EL-CDBU-01-301
Tier 5: EL-PCADB-02-21 | SAME AS EL-CDBU-01-301
Tier 5: EL-PCADB-02-22 | SAME AS EL-CDBU-01-301
Tier 5: EL-PCADB-02-23 | SAME AS EL-CDBU-01-301
Tier 5: EL-PCADB-02-24 | SAME AS EL-CDBU-01-301
Tier 5: EL-PCADB-02-25 | SAME AS EL-CDBU-01-301
PV DBs
EL-PVDB-02-101
Distribution Boards
Tier 7: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation) | Distribution Boards (Pre-Energisation)
Tier 7: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised) | Distribution Boards (Energised)
Solar Photovoltaic System
Tier 7: WSA20-MPX-04000-EL-ITC-31152000 - Construction Tests (Pre-energisation) | Solar Photovoltaic System (Pre-energisation)
Tier 7: WSA20-MPX-04000-EL-ITC-31152000 - Construction Tests (Energised) | Solar Photovoltaic System (Energised)
Tier 5: EL-PVDB-02-202 | SAME AS EL-PVDB-02-101
Tier 5: EL-PVDB-06-501 | SAME AS EL-PVDB-02-101
Tier 5: EL-PVDB-06-601 | SAME AS EL-PVDB-02-101
Tier 5: EL-PVDB-07-301 | SAME AS EL-PVDB-02-101
Tier 5: EL-PVDB-07-302 | SAME AS EL-PVDB-02-101
TERS
TER 1
Main Switchboards
EL-EMSB-02-1001
Main Switchboards
Tier 7: WSA20-MPX-04000-EL-ITC-31032000 - Construction Tests (Pre-energisation) | Main Switchboards (Pre-Energisation)
Tier 7: WSA20-MPX-04000-EL-ITC-31033000 - Component (Energised) | Main Switchboards (Energised)
Low Voltage Cables (Mains/Submains)
Refer to TAB "MSB-Submain List" - Table "TER 1" - Columns "SUBMAIN ID" + "SUPPLY TO"
Tier 8: WSA20-MPX-04000-EL-ITC-31052000 Construction Tests (Pre-energisation) | Low Voltage Cables - Mains/Submains (Pre-Energisation)
Tier 8: WSA20-MPX-04000-EL-ITC-31053000 Component (Energised) | Low Voltage Cables - Mains/Submains (Energised)
Earthing Systems
Tier 7: WSA20-MPX-04000-EL-ITC-31092000a - Construction Tests (Main Earth System) | Earthing Systems - Construction Tests (Main Earth System)
Tier 7: WSA20-MPX-04000-EL-ITC-31092000b – Construction Test (Earth System Reticulation) | Earthing Systems - Construction Tests (Earth System Reticulation)
UPS MDBs
EL-UPSIO-01-1001
UPS
Tier 7: WSA20-MPX-04000-EL-ITC-31122000 - Construction Tests (Pre-energisation) | UPS (Pre-Energistation)
Tier 7: WSA20-MPX-04000-EL-ITC-31123000 - Component (Energised) | UPS (Energised)
Tier 7: WSA20-MPX-04000-EL-ITC-31124000 - System Commissioning | UPS (System Commissioning)
Low Voltage Cables (Mains/Submains)
Refer to TAB "UPS-Submain List" - Table "TER 1" - Columns "SUBMAIN ID" + "SUPPLY TO"
Tier 8: WSA20-MPX-04000-EL-ITC-31052000 Construction Tests (Pre-energisation) | Low Voltage Cables - Mains/Submains (Pre-Energisation)
Tier 8: WSA20-MPX-04000-EL-ITC-31053000 Component (Energised) | Low Voltage Cables - Mains/Submains (Energised)
TER 2
Main Switchboards
EL-EMSB-02-2001
Main Switchboards
Tier 7: WSA20-MPX-04000-EL-ITC-31032000 - Construction Tests (Pre-energisation) | Main Switchboards (Pre-Energisation)
Tier 7: WSA20-MPX-04000-EL-ITC-31033000 - Component (Energised) | Main Switchboards (Energised)
Low Voltage Cables (Mains/Submains)
Refer to TAB "MSB-Submain List" - Table "TER 2" - Columns "SUBMAIN ID" + "SUPPLY TO"
Tier 8: WSA20-MPX-04000-EL-ITC-31052000 Construction Tests (Pre-energisation) | Low Voltage Cables - Mains/Submains (Pre-Energisation)
Tier 8: WSA20-MPX-04000-EL-ITC-31053000 Component (Energised) | Low Voltage Cables - Mains/Submains (Energised)
Earthing Systems
Tier 7: WSA20-MPX-04000-EL-ITC-31092000a - Construction Tests (Main Earth System) | Earthing Systems - Construction Tests (Main Earth System)
Tier 7: WSA20-MPX-04000-EL-ITC-31092000b – Construction Test (Earth System Reticulation) | Earthing Systems - Construction Tests (Earth System Reticulation)
UPS MDBs
EL-UPSIO-02-2001
UPS
Tier 7: WSA20-MPX-04000-EL-ITC-31122000 - Construction Tests (Pre-energisation) | UPS (Pre-Energistation)
Tier 7: WSA20-MPX-04000-EL-ITC-31123000 - Component (Energised) | UPS (Energised)
Tier 7: WSA20-MPX-04000-EL-ITC-31124000 - System Commissioning | UPS (System Commissioning)
Low Voltage Cables (Mains/Submains)
Refer to TAB "UPS-Submain List" - Table "TER 2" - Columns "SUBMAIN ID" + "SUPPLY TO"
Tier 8: WSA20-MPX-04000-EL-ITC-31052000 Construction Tests (Pre-energisation) | Low Voltage Cables - Mains/Submains (Pre-Energisation)
Tier 8: WSA20-MPX-04000-EL-ITC-31053000 Component (Energised) | Low Voltage Cables - Mains/Submains (Energised)

## Commissioning - Checklists
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
checklist | Low Voltage Cables - Mains/Submains (Pre-Energisation)
section | Pre-requisite Works
checkpoint | Insulation Damage
checkpoint | Correct Type of Termination
checkpoint | Correct Cable Size and Labelling
signoff | Checked By (Heyday):
section | Insulation Resistance
checkpoint | R-W
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | R-B
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | W-B
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | R-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | W-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | B-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | R-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | W-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | B-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | N-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC/1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
signoff | Checked By (Heyday):
section | Continuity Testing
checkpoint | Red Phase
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
checkpoint | White Phase
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
checkpoint | Blue Phase
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
checkpoint | Neutral
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
checkpoint | Earth
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
signoff | Checked By (Heyday):
checklist | Low Voltage Cables - Mains/Submains (Energised)
section | Phase Rotation
button | Direction | Clockwise,Anti-Clockwise
signoff | Checked By (Heyday):
section | Voltage
checkpoint | Red - White
textbox | Voltage (V)
checkpoint | Red - Blue
textbox | Voltage (V)
checkpoint | White - Blue
textbox | Voltage (V)
checkpoint | Red - Neutral
textbox | Voltage (V)
checkpoint | White - Neutral
textbox | Voltage (V)
checkpoint | Blue - Neutral
textbox | Voltage (V)
checkpoint | Red - Earth
textbox | Voltage (V)
checkpoint | White - Earth
textbox | Voltage (V)
checkpoint | Blue - Earth
textbox | Voltage (V)
signoff | Checked By (Heyday):
checklist | HV/LV Transformers
checkpoint | Schneider Electric Transformer QA/QC Test Report – Installation Configuration Page 3.
checkpoint | Schneider Electric Transformer QA/QC Test Report – Pre-Testing inspection Page 4.
checkpoint | Schneider Electric Transformer QA/QC Test Report – Transformer Test - Page 4:
label | Continuity test on HV and LV Windings • Insulation Resistance Test LV Winding to Earth • Winding Resistance • Winding Ration verification (taps: +2.5%, +1.25%, 0, -1.25%, -2.5% ) • Vector Groups • Check bushings • Control cubicle visual inspection • Control Cabling within the control cubicle visual inspection and connection verification against approved schematics • Confirm opening of LV door operates “normally open contact when doors are closed”
signoff | Checked By (Heyday):
checklist | Main Switchboards (Pre-Energisation)
section | Physical Checks
checkpoint | 1. Confirm boards dimensions are in accordance with approved shop drawings (provide drawings reference in the Comments section)
checkpoint | 2. Confirm correct MSB Form of Separation, Provide actual Form of Separation in Comments section
checkpoint | 3. Confirm the Layout of fitted components (ACBs, MCCBs, MEN, ATS) is in accordance with approved shop drawings (provide drawings reference in the Comments section)
checkpoint | 4. Confirm that Brand of fitted components is in accordance with approved shop drawings (provide drawings reference in the Comments section)
checkpoint | 5. Confirm meters location, types and labels are in accordance with approved shop drawings
checkpoint | 6. Confirm the circuit breakers rating is in accordance with discrimination study (provide discrimination study reference in the Comments section)
checkpoint | 7. Confirm Trip units and protection relay settings are set in accordance with discrimination study
checkpoint | 8. Confirm correct circuit identification and labelling
checkpoint | 9. Confirm easy access to controls termination
checkpoint | 10. Confirm correct location, access and sufficient support for incoming cables
checkpoint | 11. Confirm correct location, access and sufficient support for outgoing cables
checkpoint | 12. Confirm the board busbars and cables are tighten as per manufacturer recommendations and standards. Provide applied torque in a Comment section
checkpoint | 13. Confirm correct phase identification of busbars and cables inside the board
checkpoint | 14. Confirm correct size of incoming power cables as per approved cable schedule
checkpoint | 15. Confirm correct size of earthing conductors
checkpoint | 16. Confirm no visual damage to the equipment or meters. Mark the observed issues in a Comment section (if any)
signoff | Checked By (Heyday):
section | Mechanical Checks
checkpoint | 1. Repeat closing and opening of air circuit breakers for 3 times using the front panel operating buttons and charging handle
checkpoint | 2. Repeat racking of air circuit breaker in and out of chassis for 2 times to verify correct functionality of sliding mechanism
checkpoint | 3. Repeat closing and opening of air circuit breakers for 3 times using the front panel operating buttons and charging handle
checkpoint | 4. Repeat manual closing and opening of moulded case circuit breakers for 3 times
checkpoint | 5. Repeat manual closing and opening of miniature circuit breakers for 3 times
checkpoint | 6. Repeat mounting and dismounting of control fuses 1 time
checkpoint | 7. Repeat mounting and dismounting of control fuses 1 time
checkpoint | 8. Verify integrity of mechanical interlocking system between ASBs (MCCBs) by closing Source 1 Breaker and confirm that Source 2 Breaker is mechanically interlocked
checkpoint | 9. Verify integrity of mechanical interlocking system between ASBs (MCCBs) by closing Source 2 Breaker and confirm that Source 1 Breaker is mechanically interlocked
checkpoint | 10. Conduct the torque test for all bolted connections and confirm the torque is in accordance with manufacturer recommendations and standards
signoff | Checked By (Heyday):
section | Switch Gear Busbar - Preliminary Checks
checkpoint | 1. Confirm all fuses Removed in board’s Control Sections
checkpoint | 2. Confirm Main Incomers ACBs/MCCBs are Closed
checkpoint | 3. Confirm Bus-coupler is Closed (if exist)
checkpoint | 4. Confirm Outgoing Feeders is Closed
checkpoint | 5. Confirm Main Panel Neutral to Earth Link(s) was Removed
checkpoint | 6. Confirm Neutral link on Transient Voltage Surge Suppressor is Opened
checkpoint | 7. Confirm All Long Time rating Plugs From ACB's are Removed (if applicable)
section | Switch Gear Busbar - Insulation Resistance (1000V)
checkpoint | 1. Between L1 Phase and Neutral
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 2. Between L2 Phase and Neutral
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 3. Between L3 Phase and Neutral
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 4. Between Neutral and Earth
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 5. Between L1 Phase and Earth
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 6. Between L2 Phase and Earth
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 7. Between L3 Phase and Earth
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 8. Between L1 Phase and L2 Phase
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 9. Between L1 Phase and L3 Phase
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 10. Between L2 Phase and L3 Phase
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
signoff | Checked By (Heyday):
section | Circuit Breaker Settings Check |  | Refer to tab "MSB-Board List" for quantities of placeholder sections required
checkpoint | Circuit Breaker Settings Check
textbox | Cubicle ID
textbox | Feeder Name
button | Setup as per Discrimiation settings (YES/NO) | YES,NO
signoff | Checked By (Heyday):
section | Current Transformer Checks
checkpoint | Current Transformer Checks
textbox | CT ID | YES,NO
button | CT Polarity is Correct | YES,NO
button | No crossed phase CT connections | YES,NO
button | No phase sequence CT connection errors | YES,NO
signoff | Checked By (Heyday):
checklist | Main Switchboards (Energised)
section | Phase Voltage Reading
checkpoint | Red - Earth
textbox | Voltage (V)
checkpoint | White - Earth
textbox | Voltage (V)
checkpoint | Blue - Earth
textbox | Voltage (V)
checkpoint | Neutral - Earth
textbox | Voltage (V)
checkpoint | Red - White
textbox | Voltage (V)
checkpoint | Red - Blue
textbox | Voltage (V)
checkpoint | Red - Neutral
textbox | Voltage (V)
checkpoint | White - Blue
textbox | Voltage (V)
checkpoint | White - Neutral
textbox | Voltage (V)
checkpoint | Blue - Neutral
textbox | Voltage (V)
section | Phase Rotation
checkpoint=no status | Direction
button |  | Clockwise,Anti-Clockwise
signoff | Checked By (Heyday):
checklist | Distribution Boards (Pre-Energisation)
section | Physical Checks
checkpoint | Confirm board's dimensions are in accordance with approved shop drawings (provide drawings reference in the Comments section)
checkpoint | Confirm correct circuit identification and labelling
checkpoint | Confirm the board busbars and cables are tighten as per manufacturer recommendations and standards. Provide applied torque in the Comment section
checkpoint | Confirm correct phase identification of busbars and cables inside the board
checkpoint | Confirm correct size of earthing conductors
checkpoint | Confirm no visual damage to the equipment or meters. Mark the observed issues in a Comment section (if any)
section | Mechanical Checks
checkpoint | Repeat manual closing and opening of moulded case circuit breakers for 3 times
checkpoint | Repeat manual closing and opening of miniature circuit breakers for 3 times
checkpoint | Repeat mounting and dismounting of power fuses for 1 time
checkpoint | Repeat mounting and dismounting of control fuses 1 time
checkpoint | Conduct the torque test for all bolted connections and confirm the torque is in accordance with manufacturer recommendations and standards.
checkpoint | Conduct pull test for all cables connected to MCBs and Termination blocks
section | Preliminary Checks
checkpoint | 1. Confirm all fuses Removed in board’s Control Sections
checkpoint | 2. Confirm Main Breaker Closed
checkpoint | 3. Confirm Outgoing Breakers Closed
section | Insulation Resistance (500V)
checkpoint | 1. Between L1 Phase and Neutral
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 2. Between L2 Phase and Neutral
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 3. Between L3 Phase and Neutral
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 4. Between Neutral and Earth
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 5. Between L1 Phase and Earth
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 6. Between L2 Phase and Earth
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 7. Between L3 Phase and Earth
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 8. Between L1 Phase and L2 Phase
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 9. Between L1 Phase and L3 Phase
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
checkpoint | 10. Between L2 Phase and L3 Phase
button | >10MΩ | YES,NO
textbox | Actual Reading if <10MΩ
signoff | Checked By (Heyday):
section | Earth Continuity Test
textbox | Incoming Earth Size (mm²)
textbox | From (MSB/DB)
textbox | Resistance (Ω)
signoff | Checked By (Heyday):
checklist | Distribution Boards (Energised)
section | Phase Voltage Reading
checkpoint | Red- Earth
textbox | Voltage (V)
checkpoint | White - Earth
textbox | Voltage (V)
checkpoint | Blue - Earth
textbox | Voltage (V)
checkpoint | Neutral - Earth
textbox | Voltage (V)
checkpoint | Red- White
textbox | Voltage (V)
checkpoint | Red - Blue
textbox | Voltage (V)
checkpoint | Red - Neutral
textbox | Voltage (V)
checkpoint | White - Blue
textbox | Voltage (V)
checkpoint | White - Neutral
textbox | Voltage (V)
checkpoint | Blue - Neutral
textbox | Voltage (V)
section | Phase Rotation
button | Direction | Clockwise,Anti-Clockwise
signoff | Checked By (Heyday):
checklist | Low Voltage Busduct (Pre-Energisation)
section | Pre-requisite Works
checkpoint | Insulation Damage
checkpoint | Correct Type of Termination
checkpoint | Correct Colour Code
checkpoint | Correct Size and Labelling
checkpoint | Correct Routing
signoff | Checked By (Heyday):
section | Continuity Testing
checkpoint | Red Phase
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
checkpoint | White Phase
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
checkpoint | Blue Phase
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
checkpoint | Neutral
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
checkpoint | Earth
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
signoff | Checked By (Heyday):
section | Insulation Resistance
checkpoint | R-W
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | R-B
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | W-B
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | R-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | W-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | B-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | R-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | W-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | B-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
checkpoint | N-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 500VDC, 1000VDC) | >500MΩ,>1000MΩ,N/A
textbox | Actual Reading if <500MΩ/<1000MΩ
signoff | Checked By (Heyday):
checklist | Low Voltage Busduct (Energised)
section | Phase Rotation
button | Direction | Clockwise,Anti-Clockwise
signoff | Checked By (Heyday):
section | Voltage
checkpoint | Red - White
textbox | Voltage (V)
checkpoint | Red - Blue
textbox | Voltage (V)
checkpoint | White - Blue
textbox | Voltage (V)
checkpoint | Red - Neutral
textbox | Voltage (V)
checkpoint | White - Neutral
textbox | Voltage (V)
checkpoint | Blue - Neutral
textbox | Voltage (V)
checkpoint | Red - Earth
textbox | Voltage (V)
checkpoint | White - Earth
textbox | Voltage (V)
checkpoint | Blue - Earth
textbox | Voltage (V)
signoff | Checked By (Heyday):
checklist | Subcircuits (Pre-Energisation)
section | Pre-requisite Works
checkpoint | Insulation Damage
checkpoint | Correct Type of Termination
checkpoint | Correct Colour Code
checkpoint | Correct Outlet Rating and Size
signoff | Checked By (Heyday):
checkpoint | Earth Continuity
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
signoff | Checked By (Heyday):
checkpoint | Polarity Check
button | No Transposition | YES,NO
button | Switch in Active | YES,NO
signoff | Checked By (Heyday):
section | Insulation Resistance
checkpoint | R-W
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | R-B
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | W-B
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | R-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | W-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | B-N
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | R-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | W-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | B-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
checkpoint | N-E
button | Insulation Resistance shall not be less than 1MΩ (Tested at 250VDC/500VDC) | >200MΩ,>500MΩ,N/A
textbox | Actual Reading if <200MΩ/<500MΩ
signoff | Checked By (Heyday):
checklist | Subcircuits (Energised)
section | Voltage
checkpoint | Red - White
textbox | Voltage (V)
checkpoint | Red - Blue
textbox | Voltage (V)
checkpoint | White - Blue
textbox | Voltage (V)
checkpoint | Red - Neutral
textbox | Voltage (V)
checkpoint | White - Neutral
textbox | Voltage (V)
checkpoint | Blue - Neutral
textbox | Voltage (V)
checkpoint | Red - Earth
textbox | Voltage (V)
checkpoint | White - Earth
textbox | Voltage (V)
checkpoint | Blue - Earth
textbox | Voltage (V)
signoff | Checked By (Heyday):
section | Earth Fault Loop Impedance Test - (N/A if the circuit is RCD Protected)
checkpoint | Impedance
textbox | Record Inpedance (Ω)
textbox | Target Impedance (Ω)
checkpoint | RCD/RCBO Tripping Test
textbox | Trip Current (mA)
textbox | Trip Time (ms)
signoff | Checked By (Heyday):
checklist | Earthing Systems - Construction Tests (Main Earth System)
checkpoint | RWV Industries – Earthing Test Report. Steel Reinforcement Continuity
checkpoint | RWV Industries – Earthing Test Report. Footing Earthing
checklist | Earthing Systems - Construction Tests (Earth System Reticulation)
checkpoint | Correct Cable Size and Labelling
checkpoint | Earth Continuity
textbox | Resistance (Ω)
textbox | Target Resistance (Ω)
signoff | Checked By (Heyday):
checklist | PFC
checkpoint | WSA20-MPX-04000-EL-ITC-31102000 - Construction Tests (Pre-energisation)
checkpoint | WSA20-MPX-04000-EL-ITC-31073000 - Component Test (Energised)
checkpoint | CT Ratio Verification (V,A,kVA) L1/L2/L3 - Component Test (Energised)
checkpoint | Power Factor Correction Controller Configuration as per manufacturers recommendations - Component Test (Energised)
signoff | Checked By (Heyday):
checklist | UPS (Pre-Energistation)
checkpoint | Commissioning & Installation / Start-up Report - System Room Check – Page 6
checkpoint | Commissioning & Installation / Start-up Report - System Check – Page 6.
checklist | UPS (Energised)
checkpoint | Commissioning & Installation / Start-up Report - Unit pre start-up check – Page 7
checkpoint | Commissioning & Installation / Start-up Report - Unit Functional Check – Page 7
checkpoint | Commissioning & Installation / Start-up Report - Unit Final Inspection – Page 8
checklist | UPS (System Commissioning)
checkpoint | UPS – Functional Performance Test Report
label | The following tests are conducted (see Schneider Electric - Site Acceptance test protocol for results and trends): • Load Transfer test • Inverter to bypass transition on NO LOAD • Inverter to bypass transition on FULL LOAD • Load step test (0%-50%-0%) • Load step test (25%-75%-25%) • Load step test (50%-100%-50%) • Load step test (75%-100%-75%) • Load step test (0%-100%-0%) • THDi and THDv measurements (0%, 25%, 50%,75%, 100%) • Expected Results: Total Harmonic Distortion (THD) is to be under 5% • UPS efficiency calculation (Unity PF@0%, 25%, 50%, 75%, 100%) • UPS battery discharge test (15min EOL) | [6 empty] | The Dot Points are not displayed correctly. Can you please take a look
signoff | Checked By (Heyday):
checklist | Load Bank
section | WSA20-MPX-04000-EL-ITC-31143000 - Component Tests (Pre-commissioning)
checkpoint | Sephco Commissioning Checklist
signoff | Checked By (Heyday):
checklist | Solar Photovoltaic System (Pre-energisation)
checkpoint | SCS Commissioning Checklist Section 5 (System Measurements – Inverter)
checklist | Solar Photovoltaic System (Energised)
checkpoint | SCS Commissioning Checklist Section 5 (System Measurements – AC Measurements)
signoff | Checked By (Heyday):
checklist | Communications Cabling
checkpoint | Cable installed to Manufacturers requirements
checkpoint | Cable Labelled
checkpoint | Cable Terminated
checkpoint | Cable Tested
checkpoint | As-Builts reflects installed Cable Number and Location
signoff | Checked By (Heyday):
checklist | Emergency Lighting
section | Pre-requisite Works
checkpoint | Correct Location & Labelling
checkpoint | Correct Software Mapping
checkpoint | Discharge Autonomy Test
signoff | Checked By (Heyday):
checklist | Lighting Control
section | Pre-requisite Works
checkpoint | Correct Location & Labelling
checkpoint | Manual Control
checkpoint | Occupancy Sensor or PE Cell Control
signoff | Checked By (Heyday):
checklist | PMCS - (Pre-Energisation)
section | WSA20-MPX-04000-EL-ITC-31183000 - Component Tests
checkpoint | Schneider Point to Point Validation ITP - RIOM
checkpoint | Schneider Point to Point Validation ITP - PAC
checkpoint | Schneider Point to Point Validation ITP - EPS
checkpoint | Schneider Point to Point Validation ITP - PFC
checkpoint | Schneider Point to Point Validation ITP - UPS
checkpoint | Schneider Point to Point Validation ITP - EV
checkpoint | Schneider Point to Point Validation ITP - IEM
checkpoint | Schneider Point to Point Validation ITP - eGSE
checkpoint | Schneider Point to Point Validation ITP - GEN
checkpoint | Schneider Point to Point Validation ITP - LCS
checkpoint | Schneider Point to Point Validation ITP - EML
checkpoint | Schneider Point to Point Validation ITP - PV
signoff | Checked By (Heyday):
checklist | PMCS - Energised
section | WSA20-MPX-04000-EL-ITC-31184000 - System Acceptance Tests
checkpoint | Schneider WSA LV PMCS Cx ITP - RIOM
checkpoint | Schneider WSA LV PMCS Cx ITP - PAC
checkpoint | Schneider WSA LV PMCS Cx ITP - EPS
checkpoint | Schneider WSA LV PMCS Cx ITP - PFC
checkpoint | Schneider WSA LV PMCS Cx ITP - UPS
checkpoint | Schneider WSA LV PMCS Cx ITP - EV
checkpoint | Schneider WSA LV PMCS Cx ITP - IEM
checkpoint | Schneider WSA LV PMCS Cx ITP - eGSE
checkpoint | Schneider WSA LV PMCS Cx ITP - GEN
checkpoint | Schneider WSA LV PMCS Cx ITP - LCS
checkpoint | Schneider WSA LV PMCS Cx ITP - EML
checkpoint | Schneider WSA LV PMCS Cx ITP - PV
signoff | Checked By (Heyday):

## Fire Rating QA - Checklists
Type | Name | Values | Prefix | Postfix | Usage Count | User Addable | Template Name
checklist | Heyday On-site Penetration Register
checkpoint=no status | Fire Stopping System No.
dropdown | Select System No. | FAS190329 - Conduits within concrete, 27912900 - Conduit through FRL
checkpoint=no status | Penetration Type
dropdown | Select Type | Floor, Wall, Ceiling
checkpoint=no status | Location
textbox
checkpoint=no status | FRL
dropdown | Select FRL | ~ / 120 / 120
checkpoint=no status | Service Description
dropdown | Select Description | Conduits within concrete, Concrete through FR compartment
checkpoint | Photo of Fire Sealing & Label

## MSB-Board List
MSB Name | Location | Cubicle/ Section Qty
EL-MSBE-01-301 (T1) | T1 | 36
EL-MSBN-01-301 (T1) | T1 | 26
EL-MSB-01-203 (T3) | T3 | 6
EL-MSBE-01-203 (T3) | T3 | 12
EL-MSBN-01-203 (T3) | T3 | 33
EL-MSBE-01-401 (T2) | T2 | 34
EL-MSBN-01-401 (T2) | T2 | 4
EL-MSB-01-201 (PC) | PC | 5
EL-MSBE-01-201 (PC) | PC | 29
EL-MSBN-01-201 (PC) | PC | 59
EL-MSB-01-701 (COOLING) | COOLING | 15
EL-SBD-01-701 (COOLING) | COOLING | 9
EL-SBD-01-702 (COOLING) | COOLING | 5
EL-SBD-01-703 (COOLING) | COOLING | 6
EL-MSB-01-103 (PW) | PW | 4
EL-MSBE-02-103 (PW) | PW | 60
EL-MSBN-02-103 (PW) | PW | 21
EL-MSB-02-205 (PE) | PE | 4
EL-MSBE-02-205 (PE) | PE | 63
EL-MSBN-02-205 (PE) | PE | 23
EL-MSB-02-801 (CP) | CAR PARK | 30
EL-UPSIO-01-201 (PC) | PC | 16
EL-UPSIO-01-301 (T) | T | 15
EL-UPSIO-02-102 (PW) | PW | 6
EL-UPSIO-02-203 (PE) | PE | 6
EL-UPSIO-02-801 (CP) | CAR PARK | 13
EL-EMSB-02-1001 (TER1) | TER 1 | 13
EL-GCP-02-1001 (TER1) | TER 1 | 3
EL-UPSIO-02-1001 (TER1) | TER 1 | 11
EL-EMSB-02-2001 (TER2) | TER 2 | 13
EL-GCP-02-2001 (TER2) | TER 2 | 3
EL-UPSIO-02-2001 (TER2) | TER 2 | 11

## MSB-Submain List
Terminal |  |  | TER 1 |  |  | TER 2
DB NAME | SUBMAIN ID | SUPPLY TO | DB NAME | SUBMAINS ID | SUPPLY TO | DB NAME | SUBMAIN ID | SUPPLY TO
EL-MSBE-01-301 (T1) | [301-001] | EL-SUB-01-301 | EL-EMSB-02-1001 | [1001-6] | EL-UP-01-1001 | EL-EMSB-02-2001 | [1002-1] | TER-2 LV SUPPLY 1
| [301E-001] | 450kVAR PFC |  | [1001-7] | EL-UP-01-1001 |  | [1002-2] | TER-2 LV SUPPLY 2
| [301-003] | EL-MSBN-01-301 |  | [1001-8] | EL-UPSIO-02-1001 |  | [1002-4] | TER-2 LV SUPPLY 2
| [301E-022] | EL-SUBDB-01-301 |  | [1001-9] | EL-HDBE-02-1001 |  | [1002-6] | EL-UPSINV-02-2001
| [301E-023] | EL-UPSIO-01-301 |  | [1001-10] | ME-EMSSB-02-1002 |  | [1002-7] | EL-UPSINV-02-2001
| [301E-024] | BHS-SDB-01-502 |  | [1001-11] | ME-EMSSB-02-1001 |  | [1002-8] | EL-UPSIO-02-2001
| [301E-026] | BHS-SDB-01-503 |  | [1001-12] | EL-PFC-02-1001 |  | [1002-9] | EL-HDBE-02-2001
| [301E-027] | EL-PVDB-06-501 |  | [1001-13] | EL-FDAB-01 (SECONDARY FIRE PANEL) |  | [1002-10] | ME-EMSSB-02-2002
| [301E-029] | ME-EMSSB-[01,02,06]-501 T-OFFS |  | [1001-14] | EL-FDAB-02 (GAS SYSTEM) |  | [1002-11] | ME-EMSSB-02-2001
| [301E-033] | ME-EMSSB-07-301 |  |  |  |  | [1002-12] | EL-PFC-02-2001
| [301E-066] | ME-EMSSB-02-[101-102] T-OFFS |  |  |  |  | [1002-13] | EL-FDAB-01
| [301E-040] | ME-LSMSSB-07-301 |  |  |  |  | [1002-14] | EL-FDAB-02
| [301E-065] | EL-LSDB-01-301
| [301E-039] | ME-LSMSSB-06-501
| [301-002] | EL-GENBOX-02-701
EL-MSBN-01-301 (T1) | [301N-001] | VT-PGLCP-06-305
| [301N-002] | VT-PGLCP-06-306
| [301N-003] | VT-ESC-05-314
| [301N-004] | VT-ESC-05-315
| [301N-005] | VT-PGLCP-02-501
| [301N-006] | VT-PGLCP-06-502
| [301N-007] | VT-PGLCP-02-515
| [301N-008] | VT-PGLCP-06-516
| [301N-009] | VT-ESC-05-501
| [301N-010] | VT-ESC-05-502
| [301N-011] | EL-PVDB-07-301
| [301N-012] | EL-PVDB-07-302
| [301N-013] | ME-MSSB-[01,07]-301 T-OFFS
| [301N-016] | ME-MSSB-06-501
EL-MSB-01-203 (T3) | [203-002] | EL-MSBE-01-301
| [203-003] | EL-MSBN-01-203
| [203-004] | EL-MSBE-01-203
| [203-005] | EL-MSBE-01-401
EL-MSBE-01-203 (T3) | [203E-002] | EL-SUBDB-01-203
| [203E-003] | BHS-SDB-01-502
| [203E-005] | BHS-SDB-01-503
| [203E-006] | BHS-SDB-01-601
| [203E-007] | BHS-SDB-01-604
| [203E-008] | BHS-SDB-02-406
EL-MSBN-01-203 (T3) | [203N-001] | VG-PGLCP-05-604
| [203N-002] | VT-PGLCP-005-604
| [203N-003] | VT-PLLCP-05-601
| [203N-004] | VT-PLLCP-05-602
| [203N-005] | VT-PLLCP-05-603
| [203N-006] | VT-ESC-05-603
| [203N-007] | VT-ESC-05-604
| [203N-008] | VT-PGLCP-02-414
| [203N-009] | VT-PGLCP-06-407
| [203N-010] | VT-PGLCP-06-408
| [203N-011] | VT-PLLCP-05-406
| [203N-012] | VT-PLLCP-05-407
| [203N-013] | VT-PLLCP-06-410
| [203N-014] | VT-PLLCP-06-411
| [203N-015] | VT-ESC-05-407
| [203N-016] | VT-ESC-05-408
| [203N-039] | 100kVAR PFC
| [203N-041] | ME-MSSB-06-601
| [203N-040] | ME-MSSB-07-401
EL-MSBE-01-401 (T2) | [401E-001] | 500kVAR PFC
| [401E-024] | EL-UPSIO-01-301
| [401E-025] | ME-EMSSB-01-401
| [401E-028] | EL-SUBDB-01-401
| [401E-029] | EL-HYDDB-01-601
| [401E-030] | ME-EMSSB-[01,06]-601
| [401E-033] | ELPVDB-06-601
| [401E-035] | BHS-SDB-02-406
| [401E-036] | BHS-SDB-01-601
| [401E-037] | BHS-SDB-01-604
| [401E-069] | ME-EMSSB-01-502
| [401E-038] | ME-LSMSSB-01-401
| [401E-039] | ME-LSMSSB-07-401
| [401E-040] | ME-LSMSSB-06-601
| [401E-041] | EL-LSDB-01-401
EL-MSBN-01-401 (T2) | [401N-002] | EL-PVDB-07-401
| [401N-003] | EL-PVDB-07-402
EL-MSB-01-201 (PC) | [201-003] | EL-MSBN-01-201
| [201-004] | EL-MSBE-01-201
| [201-006] | BHS-SDB-02-205
EL-MSBE-01-201 (PC) | [201E-002] | EL-PCADB-02-21
| [201E-003] | EL-PCADB-02-22
| [201E-004] | EL-GPUDB-02-21
| [201E-005] | EL-GPUDB-02-22
| [201E-006] | EL-PVDB-02-101
| [201E-007] | EL-TMDB-[02,05]-101, EL-RDB-05-[103,301], EL-TDB-06-302 T-OFFS
| [201E-082] | EL-RDB-05-[306,403,405,407,418] T-OFFS
| [201E-085] | BHS-SDB-02-205
| [201E-008] | EL-UPSIO-01.201
| [201E-009] | EL-FUEL-CP-02-201
| [201E-010] | EL-APRONDB-02-21
| [201E-011] | EL-APRONDB-02-22
| [201E-021] | ME-EMSSB-02-[201-203] T-OFFS
| [201E-016] | ME-EMSSB-05-[101-104] T-OFFS
| [201E-025] | ME-EMSSB-05-[201-203] T-OFFS
| [201E-029] | EL-EHMDB-02-101
| [201E-030] | EL-EHMDB-01-201
| [201E-031] | EL-SUBDB-01-201
| [201E-032] | EL-SUBDB-01-202
| [201E-033] | EL-LSDB-02-204
| [201E-034] | ME-LSMSSB-02-201
| [201E-035] | ME-LSMSSB-02-202
| [201E-087] | ME-LSMSSB-02-101
| [201E-088] | ME-LSMSSB-02-102
| [201E-090] | VT-ESC-06-420
| [201E-091] | VT-ESC-06-421
| [201E-001] | 400kVAR
EL-MSBN-01-201 (PC) | [201N-002] | EL-HMDBN-02-101
| [201N-003] | EL-HMDBN-01-201
| [201N-004] | VT-PGLCP-07-209
| [201N-005] | VT-PLLCP-06-304
| [201N-006] | VT-PLLCP-06-305
| [201N-007] | VT-PLLCP-06-308
| [201N-008] | VT-PLLCP-06-309
| [201N-009] | VT-PLLCP-06-114
| [201N-010] | VT-PLLCP-06-115
| [201N-011] | VT-PLLCP-06-116
| [201N-012] | VT-PLLCP-06-117
| [201N-013] | VT-PLLCP-06-122
| [201N-014] | VT-PLLCP-06-123
| [201N-017] | VT-PGLCP-06-310
| [201N-018] | VT-PGLCP-06-311
| [201N-019] | VT-PLLCP-05-212
| [201N-020] | VT-PLLCP-05-218
| [201N-021] | VT-PLLCP-05-219
| [201N-022] | VT-PLLCP-05-220
| [201N-023] | VT-PLLCP-05-221
| [201N-024] | VT-PGLCP-02-312
| [201N-025] | VT-PGLCP-02-313
| [201N-026] | VT-ESC-06-305
| [201N-027] | VT-ESC-06-306
| [201N-028] | VT-ESC-06-109
| [201N-029] | VT-ESC-06-110
| [201N-030] | VT-ESC-06-111
| [201N-031] | VT-ESC-06-112
| [201N-032] | VT-ESC-06-316
| [201N-033] | VT-ESC-06-317
| [201N-034] | VT-ESC-06-123
| [201N-035] | VT-ESC-05-124
| [201N-036] | VT-ESC-05-125
| [201N-037] | VT-ESC-05-218
| [201N-038] | VT-ESC-05-219
| [201N-039] | EL-PVDB-02-202
| [201N-040] | EL-eGSE-02-22
| [201N-041] | EL-eGSE-02-21
| [201N-001] | 300kVAR PFC
EL-MSB-01-701 (COOLING) | [701-004] | EL-SBD-01-703
| [701-005] | 300kVAR PFC
| [701-006] | EL-SBD-01-701
| [701-007] | EL-SBD-01-702
| [701-008] | EL-LSDB-01-701
| [701-009] | ME-LSMSSB-01-701
EL-SBD-01-701 (COOLING) | [701-014] | ME-EMSSB-01-702
| [701-015] | ME-EMSSB-01-704
| [701-016] | ME-EMSSB-01-701
| [701-018] | EL-HDBE-01-701
| [701-020] | EL-SUBDB-01-701
| [701-025] | EL-HYDDB-01-702
EL-SBD-01-702 (COOLING) | [701-021] | ME-EMSSB-01-703
| [701-022] | ME-EMSSB-01-705
| [701-024] | EL-HDBE-02-703
EL-SBD-01-703 (COOLING) | [701-010] | EL-HDBN-01-701
| [701-011] | EL-HYDDB-01-701
| [701-012] | EL-HDBN-02-703
| [701-013] | ME-MSSB-01-701
EL-MSB-02-103 (PW) | [103-003] | EL-MSBN-02-103
| [103-004] | EL-MSBE-02-103
EL-MSBE-02-103 (PW) | [103E-001] | 200kVAR PFC
| [103E-002] | EL-GPUDB-02-23
| [103E-003] | EL-GPUDB-02-24
| [103E-004] | EL-GPUDB-02-25
| [103E-005] | EL-GPUDB-02-26
| [103E-006] | EL-GPUDB-02-27
| [103E-007] | EL-GPUDB-02-28
| [103E-008] | EL-PCADB-02-23
| [103E-009] | EL-PCADB-02-24
| [103E-010] | EL-PCADB-02-25
| [103E-011] | EL-PCADB-02-26
| [103E-012] | EL-PCADB-02-27
| [103E-013] | EL-PCADB-02-28
| [103E-014] | EL-UPSIO-02-102
| [103E-015] | EL-APRONDB-02-23
| [103E-016] | EL-APRONDB-02-24
| [103E-017] | EL-APRONDB-02-25
| [103E-018] | EL-APRONDB-02-26
| [103E-019] | EL-APRONDB-02-27
| [103E-020] | EL-APRONDB-02-28
| [103E-021] | EL-SUBDB-02-101
| [103E-022] | EL-SUBDB-02-102
| [103E-023] | EL-SUBDB-02-105
| [103E-031] | ME-EMSSB-01-2002A
| [103E-032] | ME-EMSSB-01-2002B
EL-MSBN-02-103 (PW) | [103N-001] | EL-eGSEDB-02-23
| [103N-002] | EL-eGSEDB-02-24
| [103N-003] | EL-eGSEDB-02-25
| [103N-004] | EL-eGSEDB-02-26
| [103N-005] | EL-eGSEDB-02-27
| [103N-006] | EL-eGSEDB-02-28
| [103N-008] | 50kVAR PFC
EL-MSB-02-205 (PE) | [205-003] | EL-MSBN-02-205
| [205-004] | EL-MSBE-02-205
EL-MSBE-02-205 (PE) | [205E-001] | 150kVAR PFC
| [205E-002] | EL-GPUDB-02-16
| [205E-003] | EL-GPUDB-02-17
| [205E-004] | EL-GPUDB-02-18
| [205E-005] | EL-GPUDB-02-19
| [205E-006] | EL-GPUDB-02-20
| [205E-007] | EL-PCADB-02-16
| [205E-008] | EL-PCADB-02-17
| [205E-009] | EL-PCADB-02-18
| [205E-010] | EL-PCADB-02-19
| [205E-011] | EL-PCADB-02-20
| [205E-012] | EL-UPIO-02-203
| [205E-013] | EL-SUBDB-02-205
| [205E-014] | EL-APROBDB-02-16
| [205E-015] | EL-APROBDB-02-17
| [205E-016] | EL-APROBDB-02-18
| [205E-017] | EL-APROBDB-02-19
| [205E-018] | EL-APROBDB-02-20
| [205E-019] | EL-SUBDB-02-206
| [205E-020] | EL-HDBE-02-205
| [205E-027] | ME-EMSSB-01-2001A
| [205E-028] | ME-EMSSB-01-2001B
EL-MSBN-02-205 (PE) | [205N-001] | EL-eGSEDB-02-16
| [205N-002] | EL-eGSEDB-02-17
| [205N-003] | EL-eGSEDB-02-18
| [205N-004] | EL-eGSEDB-02-19
| [205N-005] | EL-eGSEDB-02-20
| [205N-007] | 50kVAR PFC
EL-MSB-02-801 (CARPARK) | [801-003] | EL-EVDB-02-801
| [801-004] | EL-EVDB-02-802
| [801-005] | EL-PVDB-02-801
| [801-006] | EL-SECDB-02-801
| [801-007] | EL-EDB-02-801
| [801-008] | EL-EDB-02-802
| [801-009] | EL-EDB-02-803
| [801-010] | EL-EDB-02-804
| [801-011] | EL-EDB-02-805
| [801-012] | EL-EDB-02-806
| [801-013] | EL-EDB-02-807
| [801-014] | EL-EDB-02-808
| [801-015] | EL-UPSIO-02-801
| [801-025] | 250kVAR PFC
| [801-026] | ME-EMSSB-01-2003A
| [801-027] | ME-EMSSB-01-2003B
| [801-028] | EL-SUB-02-801
| [801-029] | EL-SUB-02-801

## MSB-Busduct List
Terminal
DB NAME | BUSDUCT ID
EL-MSBE-01-301 (T1) | C1a
C1b
C1c
C1
C2
C3
C4
C5
C6
C7
C8
C9
C10
C11
C12
C13
C14
C15
C16
C17
C18
C19
C20
C21
C22
C23
C24
C25
C26
C27
C28
C29
C30
C31
C32
C33
C34
C35
C36
C37
C38
C39
C40
C41
C42
C43
C44
C45
C46
C47
C48
C49
C50
C51
C52
C53
C54
C55
C56
C57
C58
C59
C60
C61
C62
C63
C64
C65
C66
C67
C68
C69
C70
C71
C72
C73
C74
C75
C76
C77
C78
C79
C80
C81
C82
C83
C84
C85
C86
F1
F2
F3
F4
F5
F6
F7
F8
F9
F10
F11
F12
F13
F14
F15
F16
F17
F18
F19
F20
F21
F22
F23
F24
F25
F26
F27
F28
F29
F30
F31
F32
F33
F34
F35
F36
F37
F38
F39
F40
F41
E1
E2
E3
E4
E5
E6
E7
E8
E9
E10
E11
E12
E13
E14
E15
E16
E17
E18
E19
E20
E21
E22
E23
E24
E25
E26
E27
E28
E29
E30
E31
E32
E33
E34
E35
E36
E37
E38
E39
E40
E41
E42
E43
E44
B1
B2
B3
B4
B5
B6
B7
B8
B9
B10
B11
B12
B13
B14
B15
B16
B17
B18
B19
B20
B21
B22
B23
B24
B25
B26
B27
B28
B29
B30
B31
B32
B33
B34
B35
B36
B37
B38
B39
B40
B41
B42
B43
B44
B45
B46
B47
B48
B49
B50
B51
B52
B53
B54
B55
B56
B57
B58
B59
B60
B61
B62
B63
B64
B65
B66
B67
B68
B69
B70
B71
B72
B73
B74
B75
B76
B77
B78
B79
B80
B81
B82
B83
B84
B85
EL-MSBE-01-401 (T2) | R1A
R1B
R1C
R1D
R1E
R1F
R1G
R2
R3
R4
R5
R6
R7
R8
R9
R10
R10A
R11
R12
R13
R14
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25
R26
R27
R28
R29
R30
R31
R31A
R32
R33
R34
R35
R36
R37
R38
R39
R40
R41
R42
R43
R44
R45
R46
R47
R48
R49
R50
R51
R52
R53
R54
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
M13
M14
M15
M16
M17
M18
M19
M20
M21
M22
M23
M24
M25
M26
M27
M28
M29
M30
M31
M32
M33
M34
M35
M36
M37
M38
M39
M40
M41
M42
M43
M44
M45
M46
M47
M48
M49
M50
M51
M52
M53
M54
M55
M56
M57
M58
M59
M60
M61
M62
M63
M64
M65
M66
M67
M68
M69
M70
M71
M72
M73
M74
M75
M76
M77
M78
M79
M80
M81
M82
M83
M84
M85
M86
M87
M88
M89
M90
M91
M92
M93
M94
M95
M96
M97
M98
M99
M100
M101
M102
Q1
Q2
Q3
Q4
Q5
Q6
Q7
Q8
Q9
Q10
Q11
Q12
Q13
Q14
Q15
Q16
Q17
Q18
Q19
Q20
Q21
Q22
Q23
Q24
Q25
Q26
Q27
Q28
Q29
Q30
Q31
Q32
Q33
Q34
Q35
Q36
Q37
Q38
Q39
Q40
Q41
Q42
Q43
Q44
Q45
Q46
Q47
Q48
Q49
Q50
Q51
Q52
Q53
Q54
Q55
Q56
Q57
N1
N2
N3
N4
N5
N6
N7
N8
N9
N10
N11
N12
N13
N14
N15
N16
N17
N18
N19
N20
N21
N22
N23
N24
N25
N26
N27
N28
N29
N30
N31
N32
N33
N34
N35
N36
N37
N38
N39
N40
N41
N42
N43
N44
N45
N46
N47
N48
N49
N50
N51
N52
N53
N54
N55
N56
N57
N58
N59
N60
N61
N62
N63
N64
N65
N66
N67
N68
N69
N70
N71
N72
N73
N74
N75
N76
N77
N78
N79
N80
N81
N82
N83
N84
N85
N86
N87
N88
N89
N90
N91
N92
N93
N94
N95
N96
N97
N98
N99
N100
N101
EL-MSBN-01-203 (T3) | P1
P2
P3
P4
P5
P6
P7
P8
P9
P10
P11
P12
P13
P14
P15
P16
P17
P18
P19
P20
P20A
P21
P22
P23
P24
P25
P26
P27
P28
P29
P30
P31
P32
P33
P34
P35
P36
P37
P38
P39
P40
P41
P41A
P42
P43
P44
P45
P46
P47
P48
P49
P50
P51
P52
P53
P54
P55
P56
P57
P58
P59
P60
P61
L1
L2
L3
L4
L5
L6
L7
L8
L9
L10
L11
L12
L13
L14
L15
L16
L17
L18
L19
L20
L21
L22
L23
L24
L25
L26
L27
L28
L29
L30
L31
L32
L33
L34
L35
L36
L37
L38
L39
L40
L41
L42
L43
L44
L45
L46
L47
L48
L49
L50
L51
L52
L53
L54
L55
L56
L57
L58
L59
L60
L61
L62
L63
L64
L65
L66
L67
L68
L69
L70
L71
L72
L73
L74
L75
L76
L77
L78
L79
L80
L81
L82
L83
L84
L85
L86
L87
L88
L89
L90
L91
L92
L93
L94
L95
L96
H1
H2
H3
H4
H5
H6
H7
H8
H9
H10
H11
H12
H13
H14
H15
H16
H17
H18
H19
H20
H21
H22
H23
H24
H25
H26
H27
H28
H29
H30
H31
H32
H33
H34
H35
H36
H37
H38
H39
H40
H41
H42
H43
H44
H45
H46
H47
H48
H49
H50
H51
H52
H53
H54
H55
H56
H57
H58
H59
H60
H61
H62
H63
H64
H65
H66
H67
H68
H69
H70
H71
H72
H73
H74
H75
H76
H77
H78
H79
H80
H81
H82
H83
H84
H85
H86
H87
H88
H89
H90
H91
D1
D2
D3
D4
D5
D6
D7
D8
D9
D10
D11
D12
D13
D14
D15
D16
D17
D18
D19
D20
D21
D22
D23
D24
D25
D26
D27
D28
D29
D30
D31
D32
D33
D34
D35
D36
D37
D38
D39
D40
D41
D42
D43
D44
D45
D46
D47
D48
D49
D50
D51
D52
D53
D54
D55
D56
D57
D58
D59
D60
D61
D62
D63
D64
D65
D66
D67
D68
D69
D70
D71
D72
D73
D74
D75
D76
D77
D78
D79
D80
D81
D82
D83
D84
D85
D86
D87
D88
D89
D90
D91
D92
D93
D94
D95
D96
D97
D98
D99
D100
D101
D102
D103
D104
D105
D106
D107
D108
D109
D110
D111
D112
D113
D114
D115
D116
D117
D118
D119
D120
D121
D122
D123
D124
D125
D126
D127
D128
D129
D130
D131
D132
D133

## UPS-Submain List
Terminal |  |  | TER 1 |  |  | TER 2
DB NAME | SUBMAIN ID | SUPPLY TO | DB NAME | SUBMAIN ID | SUPPLY TO | DB NAME | SUBMAIN ID | SUPPLY TO
EL-UPSIO-01-301 (T) | [301U-001] | EL-UPS-01-301 | EL-UPSIO-02-1001 | [1001-17] | MMR-EL-CDBU-02-1006 | EL-UPSIO-02-2001 | [1002-17] | EL-CDBU-02-2006
| [301U-002] | EL-UPS-01-301 |  | [1001-18] | MMR-EL-CDBU-02-1005 |  | [1002-18] | MMR-EL-CDBU-02-2005
| [301U-003] | EL-UPS-01-301 |  | [1001-19] | DAS-EL-CDBU-02-1004 |  | [1002-19] | DAS-EL-CDBU-02-2004
| [301U-004] | EL-UBHSDB-01-301 |  | [1001-20] | DAS-EL-CDBU-02-1003 |  | [1002-20] | DAS-EL-CDBU-02-2003
| [301U-005] | TERMINAL NW RISER T-OFFS |  | [1001-21] | TER-EL-CDBU-02-1002 |  | [1002-21] | TER-EL-CDBU-02-2002
| [301U-018] | TERMINAL SW RISER T-OFFS |  | [1001-22] | TER-EL-CDBU-02-1001 |  | [1002-22] | TER-EL-CDBU-02-2001
| [301U-030] | TERMINAL NE RISER T-OFFS |  | [1001-23] | BAF-EL-CDBU-02-1008
| [301U-045] | TERMINAL SE RISER T-OFFS |  | [1001-24] | BAF-EL-CDBU-02-1007
EL-UPSIO-01-201 (PC) | [201U-001] | EL-UPS-01-201
| [201U-002] | EL-UPS-01-201
| [201U-004] | PIER WEST RISER 101
| [201U-015] | PIER WEST RISER 102
| [201U-025] | PIER WEST RISER 103
| [201U-035] | PIER WEST RISER 104
| [201U-045] | PIER EAST RISER 201
| [201U-053] | PIER EAST RISER 202
| [201U-060] | PIER EAST RISER 203
| [201U-067] | PIER EAST RISER 204
EL-UPSIO-02-102 (PW) | [103U-001] | EL-UPS-02-102
| [103U-002] | EL-UPS-02-102
| [103U-003] | EL-UPS-02-102
| [103U-004] | TBA
| [103U-005] | TBA
| [103U-006] | TBA
| [103U-007] | TBA
| [103U-008] | TBA
| [103U-009] | TBA
| [103U-010] | TBA
| [103U-011] | TBA
| [103U-012] | TBA
| [103U-013] | TBA
| [103U-014] | TBA
| [103U-015] | TBA
EL-UPSIO-02-203 (PE) | [205U-001] | EL-UPS-02-203
| [205U-002] | EL-UPS-02-203
| [205U-004] | EL-UPS-02-203
| [205U-005] | TBA
| [205U-006] | TBA
| [205U-007] | TBA
| [205U-008] | TBA
| [205U-009] | TBA
| [205U-010] | TBA
| [205U-011] | TBA
| [205U-012] | TBA
| [205U-013] | TBA
EL-UPSIO-02-801 (CP) | [801-016] | EL-UDB-02-801
| [801-017] | EL-UDB-02-802
| [801-018] | EL-UDB-02-803
| [801-019] | EL-UDB-02-804
| [801-020] | EL-UDB-02-805

## UPS-Busduct List
Terminal
DB NAME | BUSDUCT ID
EL-UPSIO-01-301 | S1
S2
S3
S4
S5
S6
S7
S8
S9
S10
S11
S12
S13
S14
S15
S16
S17
S18
S19
S20
S21
S22
S23
S24
S25
S26
S27
S28
S29
S30
S31
S32
S33
S34
S35
S36
S37
S38
S39
S40
S41
S42
S43
S44
S45
S46
S47
S48
S49
S50
S51
S52
S53
S54
S55
S56
S57
S58
S59
S60
S61
S62
S63
S64
G1
G2
G3
G4
G5
G6
G7
G8
G9
G10
G11
G12
G13
G14
G15
G16
G17
G18
G19
G20
G21
G22
G23
G24
G25
G26
G27
G28
G29
G30
G31
G32
G33
G34
G35
G36
G37
G38
G39
G40
G41
G42
G43
G44
G45
G46
G47
G48
G49
G50
G51
G52
G53
G54
G55
G56
G57
G58
G59
G60
G61
A1
A2
A3
A4
A5
A6
A7
A8
A9
A10
A11
A12
A13
A14
A15
A16
A17
A18
A19
A20
A21
A22
A23
A24
A25
A26
A27
A28
A29
A30
A31
A32
A33
A34
A35
A36
A37
A38
A39
A40
A41
A42
A43
A44
A45
A46
A47
A48
A49
A50
A51
A52
A53
A54
A55
A56
A57
A58
A59
A60
A61
A62
A63
A64
A65
A66
A67
A68
A69
A70
A71
A72
A73
A74
A75
A76
A77
A78
A79
A80
A81
A82
A83
A84
A85
A86
A87
A88
A89
A90
A91
A92
A93
A94
A95
A96
A97
A98
A99
A100
A101
A102
A103
K1
K2
K3
K4
K5
K6
K7
K8
K9
K10
K11
K12
K13
K14
K15
K16
K17
K18
K19
K20
K21
K22
K23
K24
K25
K26
K27
K28
K29
K30
K31
K32
K33
K34
K35
K36
K37
K38
K39
K40
K41
K42
K43
K44
K45
K46
K47
K48
K49
K50
K51
K52
K53
K54
K55
K56
K57
K58
K59
K60
K61
K62
K63
K64
K65
K66
K67
K68
K69
K70
K71
K72
K73
K74
K75
K76
K77
K78
K79
K80
K81
K82
K83
K84
K85
K86
K87
K88
K89
K90
K91
K92
K93
K94
K95
K96
K97
K98
K99
K100
K101
K102
K103
K104
K105
K106
K107
K108
K109