## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Preliminary Activities and Materials Approval |  |  |  |  | Yes | Preliminary Activities and Materials Approval Checklist | 04dc540a-9dbf-4ca0-8572-2e0246b6e7dd
checkpoint-group |  |  | section | Preliminary Activities (Approved by Client)
checkpoint-status |  |  | checkpoint | Compliance to AS/NZ ISO 9001:2015
checkpoint-status |  |  | checkpoint | Permacast Project Quality Management Plan
checkpoint-status |  |  | checkpoint | Inspection & Test Plan
checkpoint-status |  |  | checkpoint | MDR Index
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Prestress
checkpoint-status |  |  | checkpoint | Work Method Statement (WMS) - Curing
checkpoint-status |  |  | checkpoint | Concrete Repair Methodology
checkpoint-status |  |  | checkpoint | Shop Drawings
checkpoint-status |  |  | checkpoint | Test Panel Prepared and Inspected by Client
checkpoint-status |  |  | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
checkpoint-group |  |  | section | Concrete
checkpoint-status |  |  | checkpoint | S65 Concrete Mix Design Approved by Client
checkpoint-group |  |  | section | Steel Reinforcement
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
checkpoint-group |  |  | section | Prestressing Tendons
checkpoint-status |  |  | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
checkpoint-status |  |  | checkpoint | Ensure that all Coil Numbers are recorded
checkpoint-status |  |  | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
checkpoint-status |  |  | checkpoint | Stressing Jack Calibration Certificates
checkpoint-group |  |  | section | Lifting Anchors
checkpoint-status |  |  | checkpoint | Lifting Design Approved by Client
checkpoint-status |  |  | checkpoint | Lifting Devices Approved by Client
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality
checkpoint-group |  |  | section | Cast-in Items and Ferrules
checkpoint-status |  |  | checkpoint | All Cast in Materials Approved
checkpoint-status |  |  | checkpoint | Inspection of Delivery for Completeness and Quality
checklist-sectioned |  |  | checklist | Byford U-Beam Stage-2 Casting Checklist |  |  |  |  | Yes | Byford U-Beam Stage-2 Casting Checklist | 7dc999ee-a3bf-4d63-ae37-d3dafcb0f98a
checkpoint-group |  |  | section | Pre-Pour Checklist
checkpoint-no-status |  |  | checkpoint | Details
text | 1233fbbe-8a90-5695-bf6b-28144e51953d |  | textbox | Cast Number
text | d6de33d6-1d6a-59cc-aab5-58e1f9ee90b2 |  | textbox | Beam Number and Orientation
text | acb384d1-e98c-5a02-9f7c-1128a2c5f72b |  | textbox | End Diaphragm
checkpoint-status |  |  | checkpoint | Shop Drawings approved for Works
checkpoint-status |  |  | checkpoint | Mould and Sacrificial formwork Dimensions are within Shop Drawings Tolerance
label | 4c1b674a-8bd8-50e8-959b-bec5d6dadc3e |  | note | Length
label | 822d1104-8a27-5ed9-980e-888b7bf6caaf |  | note | Width
label | 830ee2ae-8950-5298-a691-e9600cf10537 |  | note | Height
label | bab4373d-5276-50ed-954e-45ea96aec8c3 |  | note | Straightness
label | b82d264a-3d32-5473-8664-32a90bab9013 |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Condek Surface Checked
label | a0273126-e254-5157-8d98-f128fa5c6b52 |  | note | Cleaned
label | 9bb4e700-f5d2-5e02-883e-e5072418e64b |  | note | Sealed
label | 3ec0752e-0691-5a4f-86ac-8445eadef662 |  | note | Oiled
checkpoint-status |  |  | checkpoint | Reinforcement in Accordance with Drawings
label | 800fadac-1be9-5858-94f4-5d4746740084 |  | note | Reinforcement size
label | 0f320d4a-3d88-5e76-9d42-76621d58e218 |  | note | Lap Length
label | f61d890c-4ba6-5c8f-bcd8-10b22c2f1c07 |  | note | Splicing
label | 62881279-32c4-593b-b849-3eefda69eb96 |  | note | Bar Chairs
text | b31c7adc-8ff0-5948-b00d-593cf326b1e2 |  | textbox | Stitch pour Reinforcement lapping bars spacing maintained and template plate installed
text | 12cb8723-6db8-5a57-b575-655471779936 |  | textbox | Blockout recess around lifting Hoops
checkpoint-status |  |  | checkpoint | Detailed inspection of Mould and cage
checkpoint-status |  |  | checkpoint | Condek (Top Slab) - Verify all brackets fixed at slab thickening
checkpoint-status |  |  | checkpoint | Cover maintained and within tolerance
checkpoint-status |  |  | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
text | 9f215da9-19e9-5047-a80a-c229bb1325f1 |  | textbox | Ferrules M16x70 (Handrails)
text | 8d90112a-ec60-5a67-a2f3-d316d5261991 |  | textbox | Ferrules M10x45 (Expansion Joint Cover)
text | d1b00e18-ceba-57fe-9b5e-6d4e7db97304 |  | textbox | Ferrules M16x45 (Ladder)
text | 49d2450b-c55f-5f52-8737-b23eef564e73 |  | textbox | Ferrules (Other type, specify)
checkpoint-status |  |  | checkpoint | All Stainless Items are installed in accordance with Drawings
text | 1e328254-d184-5f54-943a-e1976e1eb331 |  | textbox | Other type, specify
checkpoint-status |  |  | checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | 87db205a-a14e-5be0-b795-5d53984ab585 |  | textbox | Earthing Terminals (FDB-16)
text | 09abc58f-8a0f-5f60-96e2-32bee1276a84 |  | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
text | a020b351-e865-5d5e-a4b5-b441cabfd625 |  | textbox | <20 mOhm across cage Length
text | 4ef34acd-9e10-5711-9e70-4735a0a2bbd0 |  | textbox | Checklist Completed (North & South) (attach results)
checkpoint-status |  |  | checkpoint | QA Engineer Check Completed by
checkpoint-status |  |  | checkpoint | Client Inspector (if present)
checkpoint-group |  |  | section | Supervisor Release
checkpoint-status |  |  | checkpoint | Supervisor Release to Engineering Team
checkpoint-group |  |  | section | Casting Checklist
checkpoint-status |  |  | checkpoint | Casting Information
text | 1a647942-8258-57e6-b6ff-621161085e77 |  | textbox | Cast Date
checkpoint-status |  |  | checkpoint | Concrete Delivery Dockets
text | d392af45-5195-5119-892d-80cfe0b6a20e |  | textbox | Concrete Delivery Dockets (list all)
checkpoint-status |  |  | checkpoint | Total Concrete Volume
text | 60fa028a-b7ea-54d1-954a-1213bd11e8e1 |  | textbox | Volume (m3)
checkpoint-status |  |  | checkpoint | Mix Design Verified
text | f8a395fa-8391-5639-a09e-c5241875a63d |  | textbox | Specify mix used
checkpoint-status |  |  | checkpoint | Ambient Temperature within Limits
label | a4f51cbb-ff6a-5071-bca5-5481459038f1 |  | note | max 38°C
checkpoint-status |  |  | checkpoint | Concrete Temperature
label | 897bf355-b709-54f5-9399-3a7efa254455 |  | note | max 32°C
checkpoint-status |  |  | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
text | 51a0000b-6d9c-512b-afdd-7d5a45ae465e |  | textbox | Slump (list all)
checkpoint-status |  |  | checkpoint | Trucks Tested for strength
text | 1db14c07-5972-5f2c-9497-617ae1c2a547 |  | textbox | Test Report Reference Number (list all)
checkpoint-status |  |  | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
checkpoint-status |  |  | checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint-status |  |  | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
checkpoint-status |  |  | checkpoint | Required Finish Applied as per Drawings
checkpoint-status |  |  | checkpoint | Retarders applied on Green Cut areas as shown in drawings
checkpoint-status |  |  | checkpoint | Concrete Covered Overnight
checkpoint-status |  |  | checkpoint | Cylinders Stored next to Bed
checkpoint-group |  |  | section | Stripping Checklist
checkpoint-status |  |  | checkpoint | Date Stripped
text | 901c78d2-ef96-5ae6-a1f7-9a653c24de1a |  | textbox | Enter Date
checkpoint-status |  |  | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
label | f0b85fdc-6c4d-511a-a42b-626445232756 |  | note | Conversion KN to MPa = Reading / 7.851
label | 786038d6-bea8-5d36-850d-c5b0f8eeb594 |  | note | Stripping strength 20MPa
text | ab2f98ba-453f-546d-8399-ab6d61235c1c |  | textbox | Stripping Strength (Stage-2 Casting)
checkpoint-status |  |  | checkpoint | Lifting Strength Achieved
label | ddd53939-10f1-5062-be90-0c69a5b2b2d6 |  | note | Lifting strength required for stage 2 casting - 45MPa
text | 990eb32e-733a-5942-8ad7-1dc6175f29d7 |  | textbox | Specify strength at time of lifting
checkpoint-status |  |  | checkpoint | Curing Strength (Stage-2 Casting)
label | 775b182d-e021-55ec-9a45-7abb946c1815 |  | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
label | c4a6b006-d64b-56cc-af22-7a32fa98085e |  | note | Tarped until the curing strength achieved
checkpoint-status |  |  | checkpoint | Lifted and Handled as per Drawings
checkpoint-status |  |  | checkpoint | Product Clearly Labelled
checkpoint-status |  |  | checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint-status |  |  | checkpoint | Secondary Curing as per Approved Methodology
checkpoint-status |  |  | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | df44e42b-2e80-5f94-ac7f-80765b72e6f9 |  | note | Length
label | e4265a90-0641-5ae7-9983-17040cae58b3 |  | note | Width
label | 7bb4ba7f-c14e-56fd-9171-dbeee66caa97 |  | note | Height
label | ff36979f-97bd-5709-a920-421e847495e8 |  | note | Straightness
label | f932effb-f869-5bc3-b54d-3dc7703f8e53 |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Specified Finish Achieved
checkpoint-status |  |  | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | a4c9f700-bb5d-5e3a-a5ae-51c28d8141b9 |  | textbox | Ferrules
text | 3cde73a1-6070-5769-9afb-cb3e15618119 |  | textbox | Stainless Items
text | f6ffd1c4-9b9b-50c3-aac9-88cfb320a9fb |  | textbox | Lifters
text | 8d91365d-45e2-5a6d-abc6-191ce31f5767 |  | textbox | Blockouts
checkpoint-status |  |  | checkpoint | Post-Pour Works Completed (As Required)
text | 7a542891-b623-52f8-ae88-77c1c09fb89f |  | textbox | Ferrules are Cleaned and Capped
text | 80630288-7f59-5868-b4d3-3428afa34d9b |  | textbox | Roughened Surfaces are Greencut
text | 915898d3-a5d9-5e68-9706-7a0fa68a24a2 |  | textbox | All Miscellaneous Items are Completed
checkpoint-group |  |  | section | Any Defect Identified
checkpoint-status |  |  | checkpoint | Punchlist Completed
checkpoint-status |  |  | checkpoint | Repairs Required (if applicable)
checkpoint-status |  |  | checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint-status |  |  | checkpoint | Crack Map Completed
checkpoint-status |  |  | checkpoint | Any NCR Required (if applicable)
checkpoint-status |  |  | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
checkpoint-group |  |  | section | As-Built Drawings
checkpoint-status |  |  | checkpoint | As-Built Drawings Completed, Stamped and Attached
checkpoint-group |  |  | section | Concrete Strength Test Report
checkpoint-status |  |  | checkpoint | Concrete Strength Test Report Received
text | 72ed3bf3-f25d-562e-9513-1b400cbb5e33 |  | textbox | Concrete Test Report
text | 009f2cbd-af76-54bf-99ce-3bcdafdfefd1 |  | textbox | 7 Day Strength (List all)
text | bde663bb-3906-572f-9122-80785c06ca94 |  | textbox | 28 Day Strength (List all)
checklist-sectioned |  |  | checklist | Byford U-Beam Stage-1 Casting |  |  |  |  | Yes | Byford U-Beam Stage-1 Casting Checklist | f4ec28cb-7524-40fa-abb8-e58488e927f4
checkpoint-group |  |  | section | Pre-Pour Checklist
checkpoint-no-status |  |  | checkpoint | Details
text | 84eac92c-86ff-5566-8337-b87e1ef14eb6 |  | textbox | Cast Number
text | 75a33415-823d-5126-accd-f72809d0c49b |  | textbox | Beam Number and Orientation
text | 4c40ea98-703e-5a88-971d-0e5838a1947d |  | textbox | Strand Arrangement Type
text | 680f5732-e19a-5002-9534-d84f51fa7bb4 |  | textbox | End Diaphragm
checkpoint-status |  |  | checkpoint | Shop Drawings approved for Works
checkpoint-status |  |  | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
label | 680f89df-1b74-5e63-9f59-f8799a7ad308 |  | note | Length
label | 3c33b51a-3cbc-50f3-93eb-6c7590cae521 |  | note | Width
label | a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 |  | note | Height
label | 7194fabe-f0ee-5be9-8f99-a7423d45323e |  | note | Straightness
label | b51604f1-02a2-5440-83f1-3d0aeb55bde2 |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Mould Surface Checked
label | 1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e |  | note | Cleaned
label | 94f4d1ab-6d65-5851-892b-115f1e586c1a |  | note | Sealed
label | 0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 |  | note | Rubbers in Place
label | b2e0da86-c42e-56d1-9030-39bacada7fb4 |  | note | Oiled
label | 97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 |  | note | Chamfers in Place
checkpoint-status |  |  | checkpoint | Reinforcement in Accordance with Drawings
label | b476357f-248b-5b10-abc1-d42d03816a8e |  | note | Reinforcement size
label | 6f5d001f-932f-5ae7-8115-3ad8bbbb8098 |  | note | Lap Length
label | 8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 |  | note | Splicing
label | db0fffd1-8336-5af1-9463-af8265ed743d |  | note | Bar Chairs
text | 49b53a33-9b54-5098-917e-55cdba66c91e |  | textbox | Reinforcement bars with couplers
text | 80919775-87b1-590c-9ca3-d4cb161e9e60 |  | textbox | Reinforcement around lifting loops
checkpoint-status |  |  | checkpoint | Detailed inspection of Mould and cage
checkpoint-status |  |  | checkpoint | Cover maintained and within tolerance
checkpoint-status |  |  | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
text | 5e2a1847-41d2-530b-9fa9-4cf64e68df9a |  | textbox | Ferrules KSN16M (Web)
text | e9ada671-1b5b-58a4-a99e-f530176c0cc3 |  | textbox | Ferrules M20x96 (Bottom Flange)
text | 75fc6791-ed0c-5a86-a260-96a9d7622c35 |  | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
text | 45645bb9-a703-58c4-8d0e-65d8bd2296ca |  | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
text | 8685bdbd-bb9e-5e95-8334-dce0cbc1386a |  | textbox | Ferrules (Other type, specify)
checkpoint-status |  |  | checkpoint | All Stainless Items are installed in accordance with Drawings
text | 5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a |  | textbox | Other type, specify
checkpoint-status |  |  | checkpoint | All Blockout Conduits are installed in accordance with Drawings
text | 21d53c60-f325-5c19-9fe0-fa15ad759824 |  | textbox | 20NB PVC Pipe
checkpoint-status |  |  | checkpoint | All Lifting Inserts are installed in accordance with Drawings
text | 2b55e49e-5a59-584c-8811-9b25b6343349 |  | textbox | Lifting Hoops
checkpoint-status |  |  | checkpoint | All Bartek Couplers are installed in accordance with Drawings
text | c700dabb-ef68-5077-88f3-67d5d942f34e |  | textbox | BPB28
text | b5aee04a-e510-5aee-9709-21141122f742 |  | textbox | BPB36
text | ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 |  | textbox | BPB20
checkpoint-status |  |  | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered aith KSN16M in web
text | cc0e0ef4-342e-58b4-b477-05411c0d50d8 |  | textbox | LENTON EL20A12
checkpoint-status |  |  | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
text | bb71e454-6a7e-571a-af19-a0aa625a7ff1 |  | textbox | Specify Bearing plate Size/Type
checkpoint-status |  |  | checkpoint | Earthing and Bonding is installed in accordance with Drawings
text | 03f2c87f-f42e-50ea-ae46-4819f1f74dbb |  | textbox | Earthing Terminals (FDB-16)
text | a767f51c-e95d-5a15-a991-a3ecd21931cb |  | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
text | abb17c43-bb30-581a-8764-791d88ae9397 |  | textbox | <20 mOhm across cage Length
text | 88a643de-b2ad-5b34-bb61-f01864ddd335 |  | textbox | Checklist Completed (North & South) (attach results)
checkpoint-status |  |  | checkpoint | Prestressing Strands
text | 4966043b-97c1-5923-889b-a979f69eddae |  | textbox | Coil Number Used for this Cast
text | fce23d34-bfc8-5931-bc15-396166fe50f1 |  | textbox | Dia and No. of strands
text | afab0b2f-1cd4-56d8-ab47-1ce1d55163de |  | textbox | Strands arrangementr verified
label | 4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 |  | note | Sag Load all Strands
label | de160996-9edb-59e3-a614-d4537ec95dd6 |  | note | Mutli-Stress as per Pre-stressing Procedures
label | 46296c35-9e45-5fac-8a30-a7879817b087 |  | note | Verify debonding strands if any
checkpoint-status |  |  | checkpoint | Stressing Records subject to Client Review
holdpoint |  |  | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
checkpoint-status |  |  | checkpoint | All Temperature Loggers are installed as per Approved WMS
text | 11270652-5c46-5496-960d-62f8e87a5af7 |  | textbox | Ensure All temperature Loggers are Working (Check Maturix)
checkpoint-status |  |  | checkpoint | All Cooling tubes installed as per drawings
checkpoint-status |  |  | checkpoint | Installation of tubs
label | 816660b8-2669-5678-a1f2-9f6f5d3f2be7 |  | note | Tubs are tightened and positioned correctly
label | dbc035e3-e77a-527a-9838-af412f46e224 |  | note | All Sliding arms are locked in position
label | 50a4732b-f130-5d16-9374-980e801e00b4 |  | note | All accrow props are locked in position
label | 14f3bf7d-041f-57e4-8c12-b5d81574ae58 |  | note | Dimensions of Tub and Webb are correct
label | 62294d53-0f5e-5084-a28e-af2a8444db2f |  | note | All feet for tubs resting on mould & bolted down
label | a758a314-83ed-5e9c-b5e8-c4438ca441c2 |  | note | Tubs have release agent
checkpoint-status |  |  | checkpoint | QA Engineer Check Completed by
checkpoint-status |  |  | checkpoint | Client Inspector (if present)
checkpoint-group |  |  | section | Supervisor Release
checkpoint-status |  |  | checkpoint | Supervisor Release to Engineering Team
checkpoint-group |  |  | section | Casting Checklist
checkpoint-status |  |  | checkpoint | Casting Information
text | 06533039-ce09-58fb-9d67-4a1a88419714 |  | textbox | Cast Date
checkpoint-status |  |  | checkpoint | Concrete Delivery Dockets
text | edb15e75-557c-552f-bdd8-bc51a1f190c8 |  | textbox | Concrete Delivery Dockets (list all)
checkpoint-status |  |  | checkpoint | Total Concrete Volume
text | 4471e4f4-eb75-5de5-8a96-28f2d19a67b2 |  | textbox | Volume (m3)
checkpoint-status |  |  | checkpoint | Mix Design Verified
text | 3c381e37-ec23-52a9-98d2-458a151f3da5 |  | textbox | Specify mix used
checkpoint-status |  |  | checkpoint | Ambient Temperature within Limits
label | f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c |  | note | max 38°C
checkpoint-status |  |  | checkpoint | Concrete Temperature
label | 1f816455-4ea0-530a-a522-938704426215 |  | note | max 32°C
checkpoint-status |  |  | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
text | ddeeae4d-65b5-5238-8db0-d3c954bf8722 |  | textbox | Slump (list all)
checkpoint-status |  |  | checkpoint | Trucks Tested for strength
text | 2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 |  | textbox | Test Report Reference Number (list all)
checkpoint-status |  |  | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
checkpoint-status |  |  | checkpoint | Concrete Placed within allowable time from Batching Plant
checkpoint-status |  |  | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
checkpoint-status |  |  | checkpoint | Required Finish Applied as per Drawings
checkpoint-status |  |  | checkpoint | Retarders applied on Green Cut areas as shown in drawings
checkpoint-status |  |  | checkpoint | Concrete Covered Overnight
checkpoint-status |  |  | checkpoint | Cylinders Stored next to Bed
checkpoint-group |  |  | section | Stripping Checklist
checkpoint-status |  |  | checkpoint | Date Stripped
text | 5d5d3825-48cb-5137-8a1b-913727a9a156 |  | textbox | Enter Date
checkpoint-status |  |  | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
label | 86a95e24-144f-554a-a852-cbf0778c2285 |  | note | Conversion KN to MPa = Reading / 7.851
label | b2f06dfb-0a24-5b8e-834c-f0845fd530af |  | note | Stripping strength 45.5MPa
text | 61c985c8-560e-55c1-9375-a9a1e181026f |  | textbox | Stripping Strength (Stage-1 Casting)
checkpoint-status |  |  | checkpoint | Verify Destressing/Transfer of stress required strength
label | 82bed7df-c8c4-594b-8379-cdb40b9ed36f |  | note | Destress at 45.5MPa
text | 8fc99148-2253-53c6-9364-d6f1a47d1eed |  | textbox | Specify Strength at time of destressing
checkpoint-status |  |  | checkpoint | Lifting Strength Achieved
label | c2002260-6794-5a8a-85b2-f3bdaafc0669 |  | note | Lifting strength required for stage 1 casting - 40MPa
text | 0edb6e72-9025-5215-adb8-64d55f2d38fd |  | textbox | Specify strength at time of lifting
checkpoint-status |  |  | checkpoint | Curing strength (Stage-1 Casting)
label | 3a2279aa-862d-54cf-972c-f3a24f8ff27b |  | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
label | 70e29e2c-bada-54fb-b525-34784d33223f |  | note | Mould and Steam Cured until the curing strength achieved
checkpoint-status |  |  | checkpoint | Lifted and Handled as per Drawings
checkpoint-status |  |  | checkpoint | Product Clearly Labelled
checkpoint-status |  |  | checkpoint | Storage as per Approved Temporary Works Drawings
checkpoint-status |  |  | checkpoint | Secondary Curing as per Approved Methodology if required
label | 36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 |  | note | Temperature 5 degrees less than its peak value
label | bf472b03-0cdd-51e3-95a8-72fb49a0b484 |  | note | Max temperature doesnot exceed 70°C
label | 9020a31c-1699-5f14-8de5-0e965cb554b9 |  | note | Differential between Core and Ambient within 30°C
label | e7f352e5-4475-5356-8cbe-e9732c413159 |  | note | Differential between Core and Cover within 25°C
checkpoint-status |  |  | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
label | 3623ef49-bc71-5143-a19b-77b46e62a3fa |  | note | Length
label | ebeb0b65-36f5-53ea-93de-bedcac9d8320 |  | note | Width
label | a7aae39a-4425-5218-b2f1-74a7fb644c6d |  | note | Height
label | 41fe9fd4-0604-5daa-b1fe-b7f247d63607 |  | note | Straightness
label | c17424ee-d019-552e-b666-96fb936eda3c |  | note | Cross-section
checkpoint-status |  |  | checkpoint | Specified Finish Achieved
checkpoint-status |  |  | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
text | 9f60ae23-ea2a-5950-9617-bd7575abd6ff |  | textbox | Ferrules
text | 3bc39844-eaf8-5b72-af90-3bd4206e9ca4 |  | textbox | Couplers
text | 6e79de90-817f-537f-ac39-f47f454ba290 |  | textbox | Stainless Items
text | 666d9cb3-04f1-557f-812d-c116e0625b5e |  | textbox | Lifters
text | 39b376a6-f073-5359-9137-905dd42ae620 |  | textbox | Blockouts
checkpoint-status |  |  | checkpoint | Post-Pour Works Completed (As Required)
text | 787e9a74-5d8d-57ec-8927-fc4d1b197e65 |  | textbox | Strands are Cut Flush and Epoxied except debonding strands
text | b393264c-8248-5af0-8c80-89b93db73a8b |  | textbox | Couplers are Cleaned and Capped
text | 02502447-d30e-51b6-89fb-751c4fdc9a97 |  | textbox | Roughened Surfaces are Greencut
text | 79303072-88ba-5e1d-b7ee-e9b30ee6ab98 |  | textbox | Water Removed out of Cooling Pipes
text | ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc |  | textbox | All Miscellaneous Items are Completed
text | 8698f9e6-b507-5bf5-947d-42d9481f618f |  | textbox | Bottom surface clear from tie wire (Attach Pictures)
checkpoint-status |  |  | checkpoint | Survey Hog of Beams (Dumpy)
text | a49a273a-d8be-5e4e-be3d-46673489cd83 |  | textbox | First Reading (Within 2 days of Stripping)
text | 552cd361-fbb9-5dfe-94a6-f95910f1d211 |  | textbox | Second Reading (After casting stage 2 top slab and atleast 7days after stage 1 casting)
text | 40b90e4d-e5f2-55fd-8945-130eb08b17a2 |  | textbox | Third Reading (At 28 days after stage 1 casting)
text | c8bce997-9181-56ff-ac96-2b314604cdcd |  | textbox | Final Reading (7 days prior to scheduled delivery)
checkpoint-status |  |  | checkpoint | Temperature Logging Completed and Conforming. Attach Results
checkpoint-group |  |  | section | Any Defect Identified
checkpoint-status |  |  | checkpoint | Punchlist Completed
checkpoint-status |  |  | checkpoint | Repairs Required (if applicable)
checkpoint-status |  |  | checkpoint | Repairs Completed as per approved WMS (if applicable)
checkpoint-status |  |  | checkpoint | Crack Map Completed
checkpoint-status |  |  | checkpoint | Any NCR Required (if applicable)
checkpoint-status |  |  | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
checkpoint-group |  |  | section | As-Built Drawings
checkpoint-status |  |  | checkpoint | As-Built Drawings Completed, Stamped and Attached
checkpoint-group |  |  | section | Concrete Strength Test Report
checkpoint-status |  |  | checkpoint | Concrete Strength Test Report Received
text | 8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 |  | textbox | Concrete Test Report
text | ca1bcf36-7597-52c4-8784-5c1fdd1c1310 |  | textbox | 7 Day Strength (List all)
text | 787cebda-6ab9-5fc2-9497-4450a4efbda7 |  | textbox | 28 Day Strength (List all)
checkpoint-group |  |  | section | Transportation Requirements
checkpoint-status |  |  | checkpoint | Certificate of Conformance
checkpoint-status |  |  | checkpoint | Inspection Release Certificate
checkpoint-status |  |  | checkpoint | Punchlist signed copy
checkpoint-status |  |  | checkpoint | Delivery Notes
checkpoint-status |  |  | checkpoint | Delivery Docket
checkpoint-group |  |  | section | Final Acceptance
checkpoint-status |  |  | checkpoint | Completed by
checkpoint-status |  |  | checkpoint | Reviewed by
checkpoint-status |  |  | checkpoint | Client Representative (if applicable)