## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Hot Water Mixing Valve Installation (TMV/TV) |  |  |  |  | Yes | Hot Water Mixing Valve Installation (TMV/TV) | 0cd5a851-ba58-44ee-a26e-1d30d3addd75
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check TMV wall box is correct
checkpoint-status |  |  | checkpoint | Check isolation valves, non-return valves & flow direction are correct
checkpoint-status |  |  | checkpoint | Check operation & controls are correct (if hot water available)
checkpoint-status |  |  | checkpoint | Check TMV water temperature does not exceed 45 degC (if hot water available)
checkpoint-status |  |  | checkpoint | Check TV water temperature does not exceed 50 degC (if hot water available)
checkpoint-status |  |  | checkpoint | Check warm water delivery should not exceed 30 seconds (if hot water available)
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Testing Potable Water Including Pressure Sensitive Valves (900 kPa) |  |  |  |  | Yes | Testing Potable Water Including Pressure Sensitive Valves (900 kPa) | 153d85b7-82c6-44ac-ad06-7860f0d55f71
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves isolating the test zone are securely shut off & tagged
checkpoint-status |  |  | checkpoint | Nominate an air purging valve point
checkpoint-status |  |  | checkpoint | Nominate a pressure testing valve point (if none at meter manifold)
checkpoint-status |  |  | checkpoint | Check valves within the test zone are open as required
checkpoint-status |  |  | checkpoint | Check lugged elbows & open ends are capped
checkpoint-status |  |  | checkpoint | Slowly open a feeder valve & fill the test zone with water until completely purged of any air
checkpoint-status |  |  | checkpoint | Connect pressure testing device to the nominated test point
checkpoint-status |  |  | checkpoint | Shut off the water feeder valve
checkpoint-status |  |  | checkpoint | Commence testing by slowly increasing pressure up to 900 kPa and hold
checkpoint-status |  |  | checkpoint | Testing is deemed successful if the water pressure remains unchanged after at least 30 minutes
checkpoint-status |  |  | checkpoint | Take a photo at the start & end of static pressure test
checkpoint-status |  |  | checkpoint | Following a succussful test, slowly release the pressure and return the system back to operational condition
checklist-flat |  |  | checklist | Toilet & Cistern Installation |  |  |  |  | Yes | Toilet & Cistern Installation | 20d49a01-e696-4c89-8573-d5ca9eec876e
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check mini stops are correct
checkpoint-status |  |  | checkpoint | Check flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check button assembly is securely fitted
checkpoint-status |  |  | checkpoint | Check seat & lid functions correctly
checkpoint-status |  |  | checkpoint | Check special DDA accessories are correct (if applicable)
checkpoint-status |  |  | checkpoint | Check operation, controls & remote sensors are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Water Service Installation (Mains/Risers) |  |  |  |  | Yes | Water Service Installation (Mains/Risers) | 216d3849-e6df-463c-b3b4-104263f7165d
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check crimp fittings are correct
checkpoint-status |  |  | checkpoint | Check for cross connections
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check branch valve assemblies alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check inline valve assemblies & brackets are correct
checkpoint-status |  |  | checkpoint | Check valves flow directions & disconnection unions are correct
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check pipe expansion assemblies are correct
checkpoint-status |  |  | checkpoint | Check pipe bends thrust bracing & fixings are correct
checkpoint-status |  |  | checkpoint | Check pipework is clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check heat trace installation is correct (if specified)
checkpoint-status |  |  | checkpoint | Check hot water pipe clips & thermal insulation are correct
checkpoint-status |  |  | checkpoint | Check pipe labelling, flow direction & colour coding is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Bath & Tapware Installation |  |  |  |  | Yes | Bath & Tapware Installation | 2b884939-7dc9-4afe-891a-725f6557f043
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check bath frame is adjustment & bedding is correct
checkpoint-status |  |  | checkpoint | Check wall plates, mixers & diversion valves correct
checkpoint-status |  |  | checkpoint | Check outlets, wall rails & hand showers are correct
checkpoint-status |  |  | checkpoint | Check special DDA accessories are correct (if applicable)
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check operation & controls are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Commission Hot Water Generating Plant |  |  |  |  | Yes | Commission Hot Water Generating Plant | 2e4b0480-0fdc-4449-b25c-47e8a64c71a6
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018) or AS/NZS-5600 (2013)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves are fully open
checkpoint-status |  |  | checkpoint | Check valve flow directions
checkpoint-status |  |  | checkpoint | Check water filters are clean
checkpoint-status |  |  | checkpoint | Check gas supply inlet pressure
checkpoint-status |  |  | checkpoint | Check burners roll-over on system fault or pre-program
checkpoint-status |  |  | checkpoint | Check circulating pumps roll-over on system fault or pre-programming
checkpoint-status |  |  | checkpoint | Check room ventilation (Mech)
checkpoint-status |  |  | checkpoint | Check power flue operation
checkpoint-status |  |  | checkpoint | Check system shut-down on ventilation or gas fault
checkpoint-status |  |  | checkpoint | Check system auto re-start
checkpoint-status |  |  | checkpoint | Check system operations & fault status in control panel digital display
checkpoint-status |  |  | checkpoint | Check hot water flow & return temperature sensors or gauges
checkpoint-status |  |  | checkpoint | Check BMS connection as specified
checkpoint-status |  |  | checkpoint | Attach a PDF copy or photo of the suppliers test report to this ITP
checkpoint-status |  |  | checkpoint | Following successful commissioning, return the system back to operational condition
checklist-flat |  |  | checklist | Gas Service Installation (In-ground) |  |  |  |  | Yes | Gas Service Installation (In-ground) | 2ffed8c5-da3b-4cdb-bd97-219388ba9186
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-5600 (2013)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check existing services are confirmed & located
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check Authority connections are correct
checkpoint-status |  |  | checkpoint | Check pipe alignment, inverts levels & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe bedding & clearances are correct
checkpoint-status |  |  | checkpoint | Check valve pits & covers alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check stainless steel hangers & clips are correct (if specified)
checkpoint-status |  |  | checkpoint | Check pipework is clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed or valves are installed
checkpoint-status |  |  | checkpoint | Check pipe trench marking tape is correct (if specified)
checkpoint-status |  |  | checkpoint | Check trench backfill & compaction is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checklist-flat |  |  | checklist | Water Heating, Boiling, Chilling, Unit Installation |  |  |  |  | Yes | Water Heating, Boiling, Chilling, Unit Installation | 36a8549b-c814-48fc-aab8-995c87c8fda1
checkpoint-status |  |  | checkpoint | Installation complies with current AS3500.4 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check mini stops are correct
checkpoint-status |  |  | checkpoint | Check isolation valves, non-return valves & flow direction are correct
checkpoint-status |  |  | checkpoint | Check pressure reduction valve is correct (if specified)
checkpoint-status |  |  | checkpoint | Check flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check operation & controls are correct
checkpoint-status |  |  | checkpoint | Check water delivery temperatures are as specified
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Cleaners Sink & Tapware Installations |  |  |  |  | Yes | Cleaners Sink & Tapware Installations | 3a66d892-b563-4e31-a2e4-ee3d07b201d2
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check bucket grate is correct
checkpoint-status |  |  | checkpoint | Check tapware height above bucket grate is correct
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check operation & controls are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Authority Main to Meter Installation |  |  |  |  | Yes | Authority Main to Meter Installation | 3cb02f42-3293-4781-b100-bbcb54645197
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check existing services are confirmed & located
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check Authority connections are correct
checkpoint-status |  |  | checkpoint | Check pipe alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe bedding & clearances are correct
checkpoint-status |  |  | checkpoint | Check valves & covers are correct
checkpoint-status |  |  | checkpoint | Check Denso wrapping is correct (if specified)
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check pipe trench marking tape is correct (if specified)
checkpoint-status |  |  | checkpoint | Check trench backfill & compaction is correct
checkpoint-status |  |  | checkpoint | Check water proofing around pipework entering buildings is correct
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check construction & location of the water meter assemblies are correct
checkpoint-status |  |  | checkpoint | Check construction & location of the RPZD assemblies are correct
checkpoint-status |  |  | checkpoint | Check pipe labelling, flow direction & colour coding is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checkpoint-status |  |  | checkpoint | Check Authority acceptance & sign-off has been provided
checklist-flat |  |  | checklist | Testing Drainage Pipework (Static Water Test) |  |  |  |  | Yes | Testing Drainage Pipework (Static Water Test) | 45c1ae94-54fb-45ac-9e6c-35a95943b4ba
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check internal bore is clear of blockages, constrictions or debris
checkpoint-status |  |  | checkpoint | Check pipe-work is secure to eliminate movement during test
checkpoint-status |  |  | checkpoint | Plug & seal open ends of pipe-work section to be tested
checkpoint-status |  |  | checkpoint | Extend a test riser 1 metre above the highest overflow point
checkpoint-status |  |  | checkpoint | Slowly fill the test riser with water until full and hold
checkpoint-status |  |  | checkpoint | Testing is deemed successful if the water level remains unchanged after at least 30 minutes
checkpoint-status |  |  | checkpoint | Take a photo at the start & end of static pressure test
checkpoint-status |  |  | checkpoint | Following a succussful test, slowly release the pressure and return the system back to operational condition
checklist-flat |  |  | checklist | Commission Water Storage Tank |  |  |  |  | Yes | Commission Water Storage Tank | 46dd0cb6-85a9-4191-a490-fca034415a14
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves are fully open
checkpoint-status |  |  | checkpoint | Check valve flow directions
checkpoint-status |  |  | checkpoint | Check water level sensor or float tree is set correctly
checkpoint-status |  |  | checkpoint | Check water auto fill valve or ball valve is set correctly
checkpoint-status |  |  | checkpoint | Check tank-fill pipe physical air break is correct
checkpoint-status |  |  | checkpoint | Check low water level fault
checkpoint-status |  |  | checkpoint | Check high water level fault
checkpoint-status |  |  | checkpoint | Check passive over-flow at least 100mm below outlet
checkpoint-status |  |  | checkpoint | Check system operations & fault status in control panel digital display
checkpoint-status |  |  | checkpoint | Check BMS connection as specified
checkpoint-status |  |  | checkpoint | Check access ladders are installed
checkpoint-status |  |  | checkpoint | Check statutory warning signage is visible
checkpoint-status |  |  | checkpoint | Attach a PDF copy or photo of the suppliers test report to this ITP
checkpoint-status |  |  | checkpoint | Following successful commissioning, return the system back to operational condition
checklist-flat |  |  | checklist | Dish/Glass Washer Installation |  |  |  |  | Yes | Dish/Glass Washer Installation | 4ecf853d-65af-49b2-a23b-0a8f76118bae
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check mini stops are correct
checkpoint-status |  |  | checkpoint | Check pressure reduction valve is correct (if specified)
checkpoint-status |  |  | checkpoint | Check flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check dishwasher waste & water connections are correct
checkpoint-status |  |  | checkpoint | Check stop valves for future connections are capped
checkpoint-status |  |  | checkpoint | Check operation & controls are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Kitchen Sink & Tapware Installation |  |  |  |  | Yes | Kitchen Sink & Tapware Installation | 4f608972-40e1-4d5c-ba59-06a87fa85c53
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check mini stops are correct
checkpoint-status |  |  | checkpoint | Check flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check dishwasher waste & water connections are correct
checkpoint-status |  |  | checkpoint | Check stop valves for future connections are capped
checkpoint-status |  |  | checkpoint | Check operation, controls & remote sensors are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Waste & Vent Installation |  |  |  |  | Yes | Waste & Vent Installation | 5396b911-cfef-4dca-b2b5-a6a9763eb26b
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & invert levels are correct
checkpoint-status |  |  | checkpoint | Check traps & clearance levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check in-wall fixture mounting brackets height & locations are correct
checkpoint-status |  |  | checkpoint | Check in-wall waste pipes & vent heights are correct
checkpoint-status |  |  | checkpoint | Check inspection openings are correct
checkpoint-status |  |  | checkpoint | Check pipework & traps are clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check acoustic insulation is correct (if specified)
checkpoint-status |  |  | checkpoint | Check pipe labelling & flow direction is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checkpoint-status |  |  | checkpoint | Check Authority acceptance & sign-off has been provided
checklist-flat |  |  | checklist | Stack & Vent Installation |  |  |  |  | Yes | Stack & Vent Installation | 53d89149-68d7-4cb1-911d-09297ae8dde2
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & invert levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check branch junctions alignment & invert levels are correct
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check expansion joints & floor brackets are correct
checkpoint-status |  |  | checkpoint | Check stack bends offset & fixings are correct
checkpoint-status |  |  | checkpoint | Check inspection openings are correct
checkpoint-status |  |  | checkpoint | Check cross vents & locations are correct
checkpoint-status |  |  | checkpoint | Check pipework is clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check acoustic insulation is correct (if specified)
checkpoint-status |  |  | checkpoint | Check pipe labelling & flow direction is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Backflow Prevention Device Installation |  |  |  |  | Yes | Backflow Prevention Device Installation | 5bc3b2ce-4ef5-469e-aaa6-bda466c4444f
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers, anchors & support brackets are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check isolation valves, non-return valves & flow direction are correct
checkpoint-status |  |  | checkpoint | Check pressure relief pipe discharges to tundish
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check valve has been certified by an authorised person
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Gas Service Installation (Mains/Risers) |  |  |  |  | Yes | Gas Service Installation (Mains/Risers) | 5c73da5b-266d-45d2-a88e-7cbf88036551
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-5600 (2013)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check crimp fittings are correct
checkpoint-status |  |  | checkpoint | Check for cross connections
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check branch valve assemblies alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check inline valve assemblies & brackets are correct
checkpoint-status |  |  | checkpoint | Check valves flow directions & disconnection unions are correct
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check pipework is clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check pipe labelling, flow direction & pressure rating is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Penetration Installation |  |  |  |  | Yes | Penetration Installation | 5f0945fa-4086-48de-9382-615bed2cbff0
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & missing penos
checkpoint-status |  |  | checkpoint | Check penetration sizes, locations & finished levels are corrrect
checkpoint-status |  |  | checkpoint | Check fire collars types & ratings are correct
checkpoint-status |  |  | checkpoint | Check blank sleeves are correct
checkpoint-status |  |  | checkpoint | Check cast-in outlets location & finished levels are correct
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checklist-flat |  |  | checklist | Testing Gas Service |  |  |  |  | Yes | Testing Gas Service | 670fa284-81fe-4083-9034-50f1e0f425fa
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-5600 (2013)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves isolating the test zone are securely shut off & tagged
checkpoint-status |  |  | checkpoint | Nominate an air purging valve point
checkpoint-status |  |  | checkpoint | Nominate a pressure testing valve point
checkpoint-status |  |  | checkpoint | Check valves isolating the test zone are securely shut off & tagged
checkpoint-status |  |  | checkpoint | Check lugged elbows & open ends are capped
checkpoint-status |  |  | checkpoint | Connect pressure testing device to the nominated test point
checkpoint-status |  |  | checkpoint | Slowly open test feeder valve & fill the test zone with inert gas until completely purged
checkpoint-status |  |  | checkpoint | Shut off the gas feeder valve
checkpoint-status |  |  | checkpoint | For high pressure test: Commence testing by slowly increasing pressure to 1.5 kPa above working pressure
checkpoint-status |  |  | checkpoint | For low pressure test: Commence testing by slowly increasing pressure up to no greater than 7kPa
checkpoint-status |  |  | checkpoint | Testing is deemed successful if the pressure remains unchanged for 5 mins of every 30 litres volume of pipe
checkpoint-status |  |  | checkpoint | Take a photo at the start & end of static pressure test
checkpoint-status |  |  | checkpoint | Following a succussful test, slowly release the pressure and return the system back to operational condition
checklist-flat |  |  | checklist | Temporary Plumbing Installation |  |  |  |  | Yes | Temporary Plumbing Installation | 696d0a1e-fc5a-4ec3-a81d-56cd8694556d
checkpoint-status |  |  | checkpoint | Check installation materials are used in accordance with manufacturer instructions
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check pipe & fittings are new (not used)
checkpoint-status |  |  | checkpoint | Check crimp fittings are correct
checkpoint-status |  |  | checkpoint | Check sanitary waste pipes are glued (no duct tape joints)
checkpoint-status |  |  | checkpoint | Check for cross connections
checkpoint-status |  |  | checkpoint | Check backflow prevention is correct
checkpoint-status |  |  | checkpoint | Check tempering valves are correct
checkpoint-status |  |  | checkpoint | Check tanks are installed correctly
checkpoint-status |  |  | checkpoint | Check pumps operation and set points are correct
checkpoint-status |  |  | checkpoint | Check any open ends are sealed
checkpoint-status |  |  | checkpoint | Check all fixtures & tapware operation & controls are correct
checklist-flat |  |  | checklist | Suction Line Installation |  |  |  |  | Yes | Suction Line Installation | 6b272b44-5143-47b0-93ad-bc7a456cc310
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & invert levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check thrust bracing is correct
checkpoint-status |  |  | checkpoint | Check isolation valves are correct
checkpoint-status |  |  | checkpoint | Check reflux valves & directions of flow are correct
checkpoint-status |  |  | checkpoint | Check pipework is clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check acoustic insulation is correct (if specified)
checkpoint-status |  |  | checkpoint | Check camlock couplings & caps are correct
checkpoint-status |  |  | checkpoint | Check pipe labelling & flow direction is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Urinal & Cistern Installation |  |  |  |  | Yes | Urinal & Cistern Installation | 6e22591f-b26c-4646-a2ef-482deb66a0dc
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check mini stops are correct
checkpoint-status |  |  | checkpoint | Check flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check button assembly is correct
checkpoint-status |  |  | checkpoint | Check operation, controls & remote sensors are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Commission Fixture Groups |  |  |  |  | Yes | Commission Fixture Groups | 8150ca6a-c0c7-40f6-a8db-029f3127224d
checkpoint-status |  |  | checkpoint | Installer is a Registered Plumber (VIC) with endorsements for this work
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018) or AS/NZS-5600 (2013)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check all installation for any damage, leaks or missing components
checkpoint-status |  |  | checkpoint | Check for correct level & alignment of all fixtures
checkpoint-status |  |  | checkpoint | Check all fixtures, seats & covers are securely fastened
checkpoint-status |  |  | checkpoint | Check all valves are fully open
checkpoint-status |  |  | checkpoint | Check all valve flow directions
checkpoint-status |  |  | checkpoint | Check all flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check for water for cross connections
checkpoint-status |  |  | checkpoint | Check fixture wastes & connections
checkpoint-status |  |  | checkpoint | Check pipework & all traps are clear of debris
checkpoint-status |  |  | checkpoint | Check floor waste grates are installed
checkpoint-status |  |  | checkpoint | Check AAV is installed to correct height
checkpoint-status |  |  | checkpoint | Check future connection water valves are securely capped
checkpoint-status |  |  | checkpoint | Check water pressures do not exceed 500 kPa
checkpoint-status |  |  | checkpoint | Check tempering valves do not exceed 50°C
checkpoint-status |  |  | checkpoint | Check thermostatic mixing valves do not exceed 45°C
checkpoint-status |  |  | checkpoint | Check hot or warm water delivery does not exceed 30 seconds
checkpoint-status |  |  | checkpoint | Check dishwasher function through a short cycle
checkpoint-status |  |  | checkpoint | Check gas valves & regulators flow direction
checkpoint-status |  |  | checkpoint | Check all gas burner functions and correct flame settings
checkpoint-status |  |  | checkpoint | Check balcony hose tap
checkpoint-status |  |  | checkpoint | Check balcony floor grate & downpipe
checkpoint-status |  |  | checkpoint | Check all fixtures & tapware are operating as specified
checkpoint-status |  |  | checkpoint | Confirm area has been left clean
checklist-flat |  |  | checklist | Drainage Installation (In-ground) |  |  |  |  | Yes | Drainage Installation (In-ground) | 88a54e28-dbb8-4702-b9a9-47bfb8c0ad47
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check existing services are confirmed & located
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check Authority connections are correct
checkpoint-status |  |  | checkpoint | Check pipe alignment, inverts levels & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe bedding & clearances are correct
checkpoint-status |  |  | checkpoint | Check pits, grates & covers alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check stainless steel hangers & clips are correct (if specified)
checkpoint-status |  |  | checkpoint | Check inspection openings are correct
checkpoint-status |  |  | checkpoint | Check pipework & traps are clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check pipe trench marking tape is correct (if specified)
checkpoint-status |  |  | checkpoint | Check trench backfill & compaction is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check Authority acceptance & sign-off has been provided
checklist-flat |  |  | checklist | Laundry Trough & Tapware Installation |  |  |  |  | Yes | Laundry Trough & Tapware Installation | 89e81fb8-1544-487e-981b-45a8c7ea9b60
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check mini stops are correct
checkpoint-status |  |  | checkpoint | Check flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check stop valves for future connections are capped
checkpoint-status |  |  | checkpoint | Check operation, controls are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Gas Service Installation (Rough-ins) |  |  |  |  | Yes | Gas Service Installation (Rough-ins) | 9a2e567c-a6ee-4dab-b88b-74488e94c47e
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-5600 (2013)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check all crimp fittings are correct
checkpoint-status |  |  | checkpoint | Check for cross connections
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check valves flow directions & disconnection unions are correct
checkpoint-status |  |  | checkpoint | Check lugged elbows alignment & heights are correct
checkpoint-status |  |  | checkpoint | Check sharp edge pipe protection is correct
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check pipe colour coding is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Wash Basin & Tapware Installation |  |  |  |  | Yes | Wash Basin & Tapware Installation | 9ca2dd49-948f-4123-b8c8-b8b898cf4fb4
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check mini stops are correct
checkpoint-status |  |  | checkpoint | Check flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check special DDA accessories are correct (if applicable)
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check stop valves for future connections are capped
checkpoint-status |  |  | checkpoint | Check operation, controls & remote sensors are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Water Service Installation (In-ground) |  |  |  |  | Yes | Water Service Installation (In-ground) | 9ed0dee9-0725-4b86-8167-f4cbac718f39
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check existing services are confirmed & located
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check Authority connections are correct
checkpoint-status |  |  | checkpoint | Check pipe alignment, inverts levels & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe bedding & clearances are correct
checkpoint-status |  |  | checkpoint | Check valve pits & covers alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check stainless steel hangers & clips are correct (if specified)
checkpoint-status |  |  | checkpoint | Check pipework is clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed or valves are installed
checkpoint-status |  |  | checkpoint | Check pipe trench marking tape is correct (if specified)
checkpoint-status |  |  | checkpoint | Check trench backfill & compaction is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checklist-flat |  |  | checklist | Shower & Tapware Installation |  |  |  |  | Yes | Shower & Tapware Installation | a61329f7-d964-4e12-8461-01bad2b79a3b
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check wall plates, mixers & diversion valves correct
checkpoint-status |  |  | checkpoint | Check outlets, wall rails & hand showers are correct
checkpoint-status |  |  | checkpoint | Check special DDA accessories are correct (if applicable)
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check operation & controls are correct
checkpoint-status |  |  | checkpoint | Check floor grate or channel fit & alignment are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check caulking is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Hose Tap Installation |  |  |  |  | Yes | Hose Tap Installation | a808f3a3-badc-4c4d-b4ce-951ee563f643
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check location, alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check back-flow preventer is installed (if specified)
checkpoint-status |  |  | checkpoint | Check operation & controls are correct
checkpoint-status |  |  | checkpoint | Check pipe colour coding is correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Testing Potable Water (1.5 x MWP) |  |  |  |  | Yes | Testing Potable Water (1.5 x MWP) | a890357b-1976-47c9-9652-a6ef4ddb8577
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves isolating the test zone are securely shut off & tagged
checkpoint-status |  |  | checkpoint | Nominate an air purging valve point
checkpoint-status |  |  | checkpoint | Nominate a pressure testing valve point (if none at meter manifold)
checkpoint-status |  |  | checkpoint | Check valves within the test zone are open as required
checkpoint-status |  |  | checkpoint | Check lugged elbows & open ends are capped
checkpoint-status |  |  | checkpoint | Check pressure sensitive mixing valves & meters are isolated from the test zone
checkpoint-status |  |  | checkpoint | Slowly open a feeder valve & fill the test zone with water until completely purged of any air
checkpoint-status |  |  | checkpoint | Connect pressure testing device to the nominated test point
checkpoint-status |  |  | checkpoint | Shut off the water feeder valve
checkpoint-status |  |  | checkpoint | Commence testing by slowly increasing pressure up to one & half (1.5) x working pressure and hold
checkpoint-status |  |  | checkpoint | Testing is deemed successful if the water pressure remains unchanged after at least 30 minutes
checkpoint-status |  |  | checkpoint | Take a photo at the start & end of static pressure test
checkpoint-status |  |  | checkpoint | Following a succussful test, slowly release the pressure and return the system back to operational condition
checklist-flat |  |  | checklist | Plant & Equipment Installation |  |  |  |  | Yes | Plant & Equipment Installation | ac5e9e2f-4e45-40f7-ba6f-cd222ab36fb8
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check installation complies with supplier requirements
checkpoint-status |  |  | checkpoint | Check location, alignment & levels are correct
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check fixings to structure are correct
checkpoint-status |  |  | checkpoint | Check access covers are correct
checkpoint-status |  |  | checkpoint | Check pipe connections are correct
checkpoint-status |  |  | checkpoint | Check isolation valves, non-return valves & flow direction are correct
checkpoint-status |  |  | checkpoint | Check control panels & wiring are correct
checkpoint-status |  |  | checkpoint | Check tundishes are correct (if applicable)
checkpoint-status |  |  | checkpoint | Check electrical power is available (if applicable)
checkpoint-status |  |  | checkpoint | Check BMS is available (if applicable)
checklist-flat |  |  | checklist | Downpipe & Overflow Installation |  |  |  |  | Yes | Downpipe & Overflow Installation | af2f2b80-0e16-4934-819e-d4be8d80ab13
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & invert levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check branch junctions alignment & invert levels are correct
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check expansion joints & floor brackets are correct
checkpoint-status |  |  | checkpoint | Check downpipe offsets & fixings are correct
checkpoint-status |  |  | checkpoint | Check connections to rain water outlets, gutters & tanks are correct
checkpoint-status |  |  | checkpoint | Check inspection openings are correct
checkpoint-status |  |  | checkpoint | Check pipework is clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check acoustic insulation is correct (if specified)
checkpoint-status |  |  | checkpoint | Check pipe labelling & flow direction is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Commission Rain Water Pressure Pump Set |  |  |  |  | Yes | Commission Rain Water Pressure Pump Set | ba2364b1-6936-4481-aa79-e20f752b6df2
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves are fully open
checkpoint-status |  |  | checkpoint | Check valve flow directions
checkpoint-status |  |  | checkpoint | Check dry pump fault
checkpoint-status |  |  | checkpoint | Check low water level fault
checkpoint-status |  |  | checkpoint | Check each pumps specified pressure set points
checkpoint-status |  |  | checkpoint | Check pump auto roll-over function on system fault or pre-programming
checkpoint-status |  |  | checkpoint | Check system operations & fault status in control panel digital display
checkpoint-status |  |  | checkpoint | Check audio/visual alarm functions
checkpoint-status |  |  | checkpoint | Check ultra violet lamps are functioning correctly
checkpoint-status |  |  | checkpoint | Check filters & backwash are functioning correctly
checkpoint-status |  |  | checkpoint | Check back-up water and auto roll-over functions
checkpoint-status |  |  | checkpoint | Check BMS connection connection as specified
checkpoint-status |  |  | checkpoint | Attach a PDF copy or photo of the suppliers test report to this ITP
checkpoint-status |  |  | checkpoint | Following successful commissioning, return the system back to operational condition
checklist-flat |  |  | checklist | Testing Water Pipework (1500 kPa) |  |  |  |  | Yes | Testing Water Pipework (1500 kPa) | c00283cf-46fb-42c6-9471-e0b3f750026d
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves isolating the test zone are securely shut off & tagged
checkpoint-status |  |  | checkpoint | Nominate an air purging valve point
checkpoint-status |  |  | checkpoint | Nominate a pressure testing valve point (if none at meter manifold)
checkpoint-status |  |  | checkpoint | Check valves within the test zone are open as required
checkpoint-status |  |  | checkpoint | Check lugged elbows & open ends are capped
checkpoint-status |  |  | checkpoint | Check pressure sensitive mixing valves & meters are isolated from the test zone
checkpoint-status |  |  | checkpoint | Slowly open a feeder valve & fill the test zone with water until completely purged of any air
checkpoint-status |  |  | checkpoint | Connect pressure testing device to the nominated test point
checkpoint-status |  |  | checkpoint | Shut off the water feeder valve
checkpoint-status |  |  | checkpoint | Commence testing by slowly increasing pressure up to 1500 kPa and hold
checkpoint-status |  |  | checkpoint | Testing is deemed successful if the water pressure remains unchanged after at least 30 minutes
checkpoint-status |  |  | checkpoint | Take a photo at the start & end of static pressure test
checkpoint-status |  |  | checkpoint | Following a succussful test, slowly release the pressure and return the system back to operational condition
checklist-flat |  |  | checklist | Cast-in Waste & Vent Installation |  |  |  |  | Yes | Cast-in Waste & Vent Installation | c1bf198c-35d1-4d61-8b05-1114e073f0d1
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check materials to be used are able to withstand concrete curing temperatures
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & invert levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check pipework & traps are clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check expansion wrapping is correct (if specified)
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Commission Drainage Pump Station |  |  |  |  | Yes | Commission Drainage Pump Station | cc07e960-dda1-4d13-a1e9-b18a235ca7a3
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves are fully open
checkpoint-status |  |  | checkpoint | Check valve flow directions
checkpoint-status |  |  | checkpoint | Check rails & lifting chains
checkpoint-status |  |  | checkpoint | Check level sensor or float tree settings
checkpoint-status |  |  | checkpoint | Check pump motor rotation
checkpoint-status |  |  | checkpoint | Check dry pump fault
checkpoint-status |  |  | checkpoint | Check low water level fault
checkpoint-status |  |  | checkpoint | Check each pumps specified pressure or level set points
checkpoint-status |  |  | checkpoint | Check auto pump roll-over on fault or system programming
checkpoint-status |  |  | checkpoint | Check system operations & fault status in control panel digital display
checkpoint-status |  |  | checkpoint | Check high water level fault
checkpoint-status |  |  | checkpoint | Check access covers for correct fitment
checkpoint-status |  |  | checkpoint | Check audio/visual alarm functions
checkpoint-status |  |  | checkpoint | Check BMS connection as specified
checkpoint-status |  |  | checkpoint | Check statutory warning signage is visible
checkpoint-status |  |  | checkpoint | Attach a PDF copy or photo of the suppliers test report to this ITP
checkpoint-status |  |  | checkpoint | Following successful commissioning, return the system back to operational condition
checklist-flat |  |  | checklist | Water Meter Installation |  |  |  |  | Yes | Water Meter Installation | d875ba42-f65e-4a6e-a4cf-9d18123ca135
checkpoint-status |  |  | checkpoint | Water Meter details entered below
text | c3b900d2-fdc0-5267-b0dd-24c9cd7afc1a |  | textbox | Meter Type:
text | 65fbef54-0816-5823-b1fe-a70b31289c83 |  | textbox | Meter Number:
text | e2b243dc-b1b7-5500-828e-4e12cd5ba83c |  | textbox | Meter Location:
text | f8b8cb2e-5efb-5fe8-8fbf-1c1fcd8ddcb3 |  | textbox | Meter Size:
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers, anchors & support brackets are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check isolation valves, non-return valves & flow direction are correct
checkpoint-status |  |  | checkpoint | Check BMS connection as specified is correct
checkpoint-status |  |  | checkpoint | Check meter delivery in L/S against BMS logs
checkpoint-status |  |  | checkpoint | Check tag number as per schedule is correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check valve has been certified by an authorised person
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Commission Reduced Pressure Zone Device |  |  |  |  | Yes | Commission Reduced Pressure Zone Device | d9107acf-4447-4873-bf8c-ed69a17c5d35
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves are fully open
checkpoint-status |  |  | checkpoint | Check valve flow directions
checkpoint-status |  |  | checkpoint | Check inlet water pressure does not exceed manufacturer specification
checkpoint-status |  |  | checkpoint | Check outlet water pressure is as per manufacturer specification
checkpoint-status |  |  | checkpoint | Check exhaust tundish drain sized to accept a full flush
checkpoint-status |  |  | checkpoint | Use only a licensed RPZD tester for the commissioning
checkpoint-status |  |  | checkpoint | Attach a PDF copy or photo of the test report to this ITP
checkpoint-status |  |  | checkpoint | Following successful commissioning, return the system back to operational condition
checklist-flat |  |  | checklist | Add New Task |  |  |  |  | Yes | Add New Task | d985fdca-79d0-43d4-a1c9-687ed6690595
checkpoint-status |  |  | checkpoint | Installation checked-off as below
checklist-flat |  |  | checklist | Pump Line Installation |  |  |  |  | Yes | Pump Line Installation | da1324a8-b3a6-45a7-a87a-498d993089e6
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & invert levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check bolted clips, hangers & anchors are correct
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check thrust bracing is correct
checkpoint-status |  |  | checkpoint | Check isolation valves are correct
checkpoint-status |  |  | checkpoint | Check reflux valves & directions of flow are correct
checkpoint-status |  |  | checkpoint | Check pipework is clear of debris
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check acoustic insulation is correct (if specified)
checkpoint-status |  |  | checkpoint | Check pipe labelling & flow direction is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Testing Drainage Pipework (Static Air Test) |  |  |  |  | Yes | Testing Drainage Pipework (Static Air Test) | ddb94a5d-a081-4c12-89b6-694c72b46f96
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check internal bore clear of blockages, constrictions or debris
checkpoint-status |  |  | checkpoint | Check pipe-work is secure to eliminate movement during test
checkpoint-status |  |  | checkpoint | Plug & seal open ends of pipe-work section to be tested
checkpoint-status |  |  | checkpoint | Connect pressure testing device to temporary valve point
checkpoint-status |  |  | checkpoint | Commence testing by slowly increasing pressure up to 30 kPa and hold
checkpoint-status |  |  | checkpoint | Discontinue pressurization & allow system to stabilization over 3 minutes
checkpoint-status |  |  | checkpoint | Testing is deemed successful if pressure drop is ≤ 5kPa over at least 30 minutes
checkpoint-status |  |  | checkpoint | Take a photo at the start & end of static pressure test
checkpoint-status |  |  | checkpoint | Following a succussful test, slowly release the pressure and return the system back to operational condition
checklist-flat |  |  | checklist | Tundish Installation |  |  |  |  | Yes | Tundish Installation | e279aee4-4ce0-48de-8f2c-eaeae50861c8
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check waste & trap connections are correct
checkpoint-status |  |  | checkpoint | Check trap is clear of debris
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Water Service Installation (Rough-ins) |  |  |  |  | Yes | Water Service Installation (Rough-ins) | f018816a-86d8-4e9c-90f6-5d7e4aeed874
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage & leaks
checkpoint-status |  |  | checkpoint | Check crimp fittings are correct
checkpoint-status |  |  | checkpoint | Check for cross connections
checkpoint-status |  |  | checkpoint | Check pipe location, alignment & finished levels are correct
checkpoint-status |  |  | checkpoint | Check pipe sizes, materials & joining methods are corrrect
checkpoint-status |  |  | checkpoint | Check pipe separation & clip spacings are correct
checkpoint-status |  |  | checkpoint | Check valves flow directions & disconnection unions are correct
checkpoint-status |  |  | checkpoint | Check TMV/TV installation is correct
checkpoint-status |  |  | checkpoint | Check mixer bodies & lugged elbows alignment & heights are correct
checkpoint-status |  |  | checkpoint | Check in-wall pan & cistern brackets alignment & heights are correct
checkpoint-status |  |  | checkpoint | Check in-wall waste pipes alignment & heights are correct
checkpoint-status |  |  | checkpoint | Check noggings for future fixture installation are correct
checkpoint-status |  |  | checkpoint | Check sharp edge pipe protection is correct
checkpoint-status |  |  | checkpoint | Check open ends are sealed
checkpoint-status |  |  | checkpoint | Check heat trace installation is correct (if specified)
checkpoint-status |  |  | checkpoint | Check hot water pipe clips & thermal insulation are correct (if specified)
checkpoint-status |  |  | checkpoint | Check pipe colour coding is correct
checkpoint-status |  |  | checkpoint | Check floor/wall penetration fire proofing is correct
checkpoint-status |  |  | checkpoint | Check test carried out & is correct
checklist-flat |  |  | checklist | Commission Water Pressure Pump Set |  |  |  |  | Yes | Commission Water Pressure Pump Set | f6f5bd8d-77d0-4e7f-9b71-86cb68d3a12e
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves are fully open
checkpoint-status |  |  | checkpoint | Check valve flow directions
checkpoint-status |  |  | checkpoint | Check dry pump fault
checkpoint-status |  |  | checkpoint | Check low water level fault
checkpoint-status |  |  | checkpoint | Check each pumps specified pressure set points
checkpoint-status |  |  | checkpoint | Check auto pump roll-over on fault or system programming
checkpoint-status |  |  | checkpoint | Check system operations & fault status in control panel digital display
checkpoint-status |  |  | checkpoint | Check audio/visual alarm functions
checkpoint-status |  |  | checkpoint | Check BMS connection as specified
checkpoint-status |  |  | checkpoint | Attach a PDF copy or photo of the suppliers test report to this ITP
checkpoint-status |  |  | checkpoint | Following successful commissioning, return the system back to operational condition
checklist-flat |  |  | checklist | Gas Cook-Top/Gas Appliance Installation |  |  |  |  | Yes | Gas Cook-Top/Gas Appliance Installation | f74afc14-4d72-45d8-881a-cfac70009a06
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-5600 (2013)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check for damage or leaks
checkpoint-status |  |  | checkpoint | Check level & alignment is correct
checkpoint-status |  |  | checkpoint | Check surrounding wall material is fire rated
checkpoint-status |  |  | checkpoint | Check distance from cook-top to range hood complies with manufacturer specification
checkpoint-status |  |  | checkpoint | Check surrounding walls to closest burner distance complies with manufacturer specification
checkpoint-status |  |  | checkpoint | Check flexible connections are not twisted or kinked
checkpoint-status |  |  | checkpoint | Check cover plates are correct
checkpoint-status |  |  | checkpoint | Check gas isolation valve is correct
checkpoint-status |  |  | checkpoint | Check gas pressure regulator is correct
checkpoint-status |  |  | checkpoint | Check operation & controls are correct
checkpoint-status |  |  | checkpoint | Check area has been left clean
checklist-flat |  |  | checklist | Commission Rain Water Drainage Diversion Valve |  |  |  |  | Yes | Commission Rain Water Drainage Diversion Valve | fe24f2a0-13e5-4912-aa6e-2d2940472f1a
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check valves are fully open
checkpoint-status |  |  | checkpoint | Check valve flow directions
checkpoint-status |  |  | checkpoint | Check valve fault defaults to storm-water drainage
checkpoint-status |  |  | checkpoint | Check pneumatic connections to the compressor
checkpoint-status |  |  | checkpoint | Check data connection to the storage tanks
checkpoint-status |  |  | checkpoint | Check storage tank high level alarm defaults valve to storm-water drainage
checkpoint-status |  |  | checkpoint | Check BMS connection as specified
checkpoint-status |  |  | checkpoint | Attach a PDF copy or photo of the suppliers test report to this ITP
checkpoint-status |  |  | checkpoint | Following successful commissioning, return the system back to operational condition
checklist-flat |  |  | checklist | Commission Thermostatic Mixing Valves |  |  |  |  | Yes | Commission Thermostatic Mixing Valves | ffe78bf4-e94c-402b-af1a-8f446cc8332f
checkpoint-status |  |  | checkpoint | Installation complies with current AS/NZS-3500 (2018)
checkpoint-status |  |  | checkpoint | Installation complies with current drawings & specifications
checkpoint-status |  |  | checkpoint | Installation materials were used in accordance with manufacturer requirements
checkpoint-status |  |  | checkpoint | Check inlet water pressure does not exceed 500 kPa
checkpoint-status |  |  | checkpoint | Check warm water temperature does not exceed 45°C (Commercial DDA)
checkpoint-status |  |  | checkpoint | Check warm water temperature does not exceed 43°C (Special needs DDA)
checkpoint-status |  |  | checkpoint | Check warm water delivery time maximum temperature does not exceed 30 seconds
checkpoint-status |  |  | checkpoint | Check minimum warm water delivery volume to furthest point
checkpoint-status |  |  | checkpoint | Following successful commissioning, return the system back to operational condition