## Kerb & Channel
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1004F - Tongoio Falls Steep Underslip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Kerb & Channel |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Dave Hooker Teams note to Josin 21-Dec-23 | Andrew Harrall / behalf of Trudy Guy 08-Jan-24 | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS 608 RP 17.1
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Set out kerb line and level at 1m offset to EOS | Prior to commencement | Survey, Measurement and Visual inspection | Consistency with Construction Drawing | Survey receipt | Site Engineer
2 | Material Compliance | H | Ensure the Concrete Mix is as per the Kerbing Specification | 1/600m3, minimum of 1 per source | Document review Lab Testing | 20MPa at 28 days | Concrete Delivery Dockets and lab test results | Site Engineer
3 |  | H | Ensure the slip form moulds match the dimensions of the design kerb | Prior to commencement | Visual inspection and Measurement | Measurements match the design kerb dimensions | - | Site Engineer
4 | Kerb Foundation | H | Ensure Sub base construction is completed | Prior to commencement | Visual inspection | Pavement depth and type under the kerb varies depending on location | CS-4045 Kerb Construction Record Check Sheet | Site Engineer
5 | Stringing | H | Check weather forecast and avoid adverse conditions | Prior to commencement | Document review | No concrete to be placed in adverse weather conditions | CS-4045 Kerb Construction Record Check Sheet | Site Engineer
6 |  | W | Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations | Prior to commencement | Visual inspection and Measurement | Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width | CS-4045 Kerb Construction Record Check Sheet | Site Engineer
7 |  | H | Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits. | Prior to commencement | Visual inspection and Measurement | Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width | CS-4045 Kerb Construction Record Check Sheet | Site Engineer
8 | Slip forming | H | Check correct Kerb & Channel profile is installed onto kerb Machine | Prior to slip forming | Visual inspection and Measurement | To ensure the correct kerb types are installed at the correct locations | CS-4045 Kerb Construction Record Check Sheet | Site Engineer
9 |  | W | Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested | During Slip forming | Document review | To ensure the correct concrete mix is delivered | Concrete Delivery Dockets and lab test results | Site Engineer
10 |  | W | Expansion joints to be formed at 5m centres | During Slip forming | Visual inspection | Kerbing Specification | CS-4045 Kerb Construction Record Check Sheet | Site Engineer
11 | Tie-in with pre-cast components | H | Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components. | During Slip forming | Visual inspection | Consistency with Work Instruction | CS-4045 Kerb Construction Record Check Sheet | Site Engineer
12 | Protection | H | Backfilling behind kerbs to commence only after a curing time of 72 hours | Prior to backfilling | Visual inspection | Backfilling to commence only after 72 hours | - | Site Engineer
13 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
14 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: