## Basecourse Construction
[5 empty] | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
[5 empty] | Contract Name: | B1401A - Captain's Culvert Inlet Remediation |  | CPS Approver | Quality Approver | CPS Eng.
[5 empty] | Procedure: | Parking bay Construction |  | Name / Signature | Name / Signature | Site Engineer
| Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
| Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:SH 05 RS220 RP 3.3
Chainage:
| No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
| 1 | Survey Setout | H | Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction | Prior to commencement | Survey |  | Survey receipt | Site Engineer
| 2 | Proof Roll of subgrade | H | Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement | Prior to Sub Base Construction | Visual Inspection | Engineers Acceptance | Emails | Site Engineer | CPS Engineer
Sub base
| 3 | Material Compliance | H | Aggregate material compliance for Subbase stockpiles | Prior to commencement | Lab Testing | Crushed AP65 with 30% Crushed face. Lab test for MDD at OWC | Notice to Supplier and Lab Test results for the stockpiles used during construction | Site Engineer | CPS Engineer
| 4 |  | H | All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number | During construction | Measurement and recording | Comply with TNZ M/4 Specification. Traceability of all materials deliveresd to site | Delivery Dockets, Aggregate Deliveries Register | Site Engineer
| 5 | Sub Base Construction | W | Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant | During construction | Visual Inspection |  | Photos | Site Engineer
| 6 |  | H | Carry out a Level Check on the trimmed Basecourse | 1/100m if machine control is used or 1/20m if no machine control | Measurement | Tolerance = -5mm/+15mm | QA measurement Sheet | Site Engineer
| 7 |  | H | Degree of Compaction | 5 per Lot | NDM Lab Testing | Avg. >= 95% MDD and Min. >= 92% MDD | Pavement Lab Testing Spreadsheet | Site Engineer
| 8 |  | H | Surface shape check | Prior to base course Construction | Measurement | No point of the surface shall vary more than 10mm over a 3m long straight edge | QA measurement Sheet | Site Engineer
Base Course Construction
| 9 | Material Compliance | H | Aggregate material compliance for base Course stockpiles | Prior to commencement | Lab Testing | Aggreate shall comply with TNZ M/4 | Notice to Supplier and Lab Test results for the stockpiles used during construction | Site Engineer | CPS Engineer
| 10 |  | H | All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number | During construction | Measurement and recording | Comply with TNZ M/4 Specification. Traceability of all materials deliveresd to site | Delivery Dockets, Aggregate Deliveries Register | Site Engineer
| 11 | Base Course Construction | H | Mat sampling of Basecourse Material | 1 mat sample for the job. Pavement CPS Engineer for further instruction | Lab testing | Grading to comply with specification | Mat sample lab test result | Site Engineer
| 12 |  | W | Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant | During construction | Visual Inspection |  | Photos | Site Engineer
| 9 |  | H | Carry out a Level Check on the trimmed Basecourse | 1/100m if machine control is used or 1/20m if no machine control | Measurement | Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm | QA measurement Sheet | Site Engineer
| 10 |  | H | Degree of Compaction | 5 per Lot | NDM Lab Testing | Avg. >= 98% MDD and Min. >= 95% MDD | Pavement Lab Testing Spreadsheet | Site Engineer
| 11 |  | H | Surface shape check | Prior to sealing | Measurement | No point of the surface shall vary more than 10mm over a 3m long straight edge | QA measurement Sheet | Site Engineer
| 12 |  | H | Surface finish check | Prior to sealing | Visual inspection by CPS Engineer after site sweeping | The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping | Site photos,Emails | Site Engineer | CPS Engineer
Sealing
| 13 | Seal design | H | Seal design to be reviewed prior to sealing | Prior to Sealing | Review |  | Emails/NTE | Site Engineer | CPS Engineer
| 14 | Location/Size Confirmation | W | Mark up extent of chipseal | Prior to Sealing | Markout |  | Photos | Site Engineer
| 15 | Surface Cleanliness | W | To confirm that all loose material is removed from the surface and surrounding area. | Prior to application of binder | Visual inspection |  | Photos | Site Engineer
| 16 | Binder Application | W | Ensure the Binder application is according to the seal design | During sealing | Measure | According to seal design | Sealing sheet | Site Engineer
| 17 | Chip Application | W | Ensure the Chip application is according to the seal design | During sealing | Measure | According to seal design | Sealing sheet | Site Engineer
| 18 | Compaction | W | At completion of rolling | During sealing | Visual | Ensure sufficient passes with roller to embed chip (typically 4-5 passes) | Photos,QA measurement Sheet | Site Engineer
| 19 |  | W | Removal of excess chip | Within 48 Hours of Sealing | Visual | Ensure all excess chip removed from site. No chip windrows left on site in Shoulders. | Photos, Site logs | Site Engineer
| 20 |  | H | Surface finish check | After sealing | Visual | Engineers Acceptance | Photos Email | Site Engineer | CPS Engineer
| 21 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
`
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
| QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
| QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
| QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
| Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: