## Subsoil Drainage
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | B1401A - Captain's Culvert Inlet Remediation |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Subsoil Drainage |  | Name / Signature | Name / Signature | Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: |  |  |  | Compliance with Work Instructions and Specifications
Detailed Location:SH 05 RS220 RP 3.3
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Setout | H | Engineer to confirm the extend of sub soil drain on site | Prior to commencement | Markout | Engineer acceptance | Site Visits,Emails | Site Engineer | CPS Engineer
2 | Locate existing services by hand digging | W | Ensure all services in conflict with the line of trench are exposed by hand digging | Prior to Installation | Potholing | All conflicts have been located | Permit To Dig | Site Engineer
3 | Material Compliance | H | Ensure Subsoil Drainage pipe is TNZ F2 Grade and 110 Diameter | Upon delivery to site | Ensure delivery docket matches materials delivered | 110mm diameter Drain flow TNZ F/2 Grade pipe | Delivery docket | Site Engineer
4 |  | H | Free draining granular Fill Comply with NZTA F/5 2013 | Upon delivery to site | Ensure delivery docket matches materials delivered | Ensure clean drainage chip | Delivery docket | Site Engineer
5 |  | H | Ensure the geotextile filter fabric,strenght Class D in Accordance with TNZ F/7 2003 | Upon delivery to site | Ensure delivery docket matches materials delivered | Strenght Class D in Accordance with TNZ F/7 2003 | Delivery docket | Site Engineer
6 | Trenching | H | Inspect trench profile | 10m intervals | Visual inspection and measurement | Record levels of base of trench on dip sheet | Photo & CS-4001 Subsoil Dipsheet | Site Engineer
7 |  | H | Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings. | 10m intervals | Visual inspection and measurement | Ensure trench line and levels match the design drawings | Photo & CS-4001 Subsoil Dipsheet | Site Engineer
8 |  | H | CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works. | As required | Visual Inspection | CPS Engineer to instruct action and record on dip sheet and as built drawing | Photo,Emails | Site Engineer | CPS Engineer
9 | Bedding, pipe installation and Backfill. | H | Upon completion of trenching Geotextile Filter fabricto be placed into the trench. Accordance with with TNZ F/7 :2003 | 10m intervals | Visual inspection | Ensure material covers the trench and is pinned in place | Photo & CS-4001 Subsoil Dipsheet | Site Engineer
10 |  | W | Ensure 100mm thick Free draining granular Fill bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo & CS-4001 Subsoil Dipsheet | Site Engineer
11 |  | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
12 |  | H | As built Survey the Pipe before backfill | 10m intervals | Document review | Consistency with Subsoil Details | As-built receipt | Site Engineer
13 |  | W | Free draining granular Fill into the trench | - | Visual inspection | Ensure good coverage | Photos | Site Engineer
14 |  | W | Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place |  | Visual inspection |  |  | Site Engineer
15 | SubSoil Flushing eye | W | Hynds Round 250mmm Lamphole cover and frame or simislar approved | Upon delivery to site | Visual inspection | Consistency with Subsoil Details | Delivery docket | Site Engineer
16 | Final Inspection | H | The Engineer needs to inspect the subsoil drain installed | After subsoil drain has been installed | Visual inspection | Engineer acceptance | Site visits, emails | Site Engineer | CPS Engineer
17 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager |  |  |  |  | Signature: |  |  | Date: