## Guardrail
|  |  |  | Inspection Test Plan |  |  | Approved / Signature
|  |  |  | Contract Name: | F3002D Mangahuini long drop site |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Guard railing |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | 11.01.2024 | 17.01.24 | Quality Eng.
Lot No: F5001A |  |  |  | Corresponding Work Instruction: |  | https://trecnz.sharepoint.com/:f:/s/ZONEF-SH35-TAIRAWHITI/Es4022E44SVGrVoRrYmNAr4BExrkT-CsDDn6vlhwfcnB1A?e=YTx1Q7 |  | Compliance with Work Instructions and Specifications
Detailed Location: SH35 RS225. RP7.802
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 |  | H | Design check locations of Poles and check for any clashes with underground services or similar | Prior to commencement | Document review | National Standard for Traffic Signal | Site pics, NTE/NTC | Site Engineer | CPS Engineer
2 | Survey Setout | H | Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred. | Prior to commencement | Survey | Consistency with latest revision of Approved Construction Drawing. | Approved Construction Drawing | Site Engineer | CPS Engineer
3 | Material Compliance | W | All roadside barriers shall comply with TNZ M/23:2009. Only NZTA mash TL3 approved systems to be installed as specified in the specification & guidelines for road safety hardware and devices, Appendix A: permanent road safety hardware. | Prior to commencement | Visual inspection/ Document review | Comply with TNZ M/23:2009. NZTA mash TL3 approved systems only | Manufacturing certificates, delivery dockets | Site Engineer
4 | Guardrail Installation | W | Guard railing shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. Laps to be in direction of traffic | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with manufacturers specifications | Guardrail Installation Record (CS-4117), Photo's | Site Engineer
5 |  | W | Hazard markers to be installed at terminal ends. Edge markers posts to be secured to the guard rail. Guardrail to be a minimum of 1.2m from white line. Engineer to confirm min of 1m support width behind the barrier | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with manufacturers specifications | Guardrail Installation Record (CS-4117), Photo's | Site Engineer
6 |  | W | Barrier face to be max clearance of 200mm from kerb face where kerbed. Design speed 100Km/hr AADT <1000 V/D run out length 64m. Existing signs to be placed behind the barrier. Offset of fence is to be confirmed to ensure there is sufficient room for barrier installation | During installation and on completion | Visual inspection, measurement | Each section inspected to comply with manufacturers specifications | Guardrail Installation Record (CS-4117), Photo's | Site Engineer
7 | As-built Survey | H |  | At completion of Lot | Survey / Drawings | As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer | As-builts, CPS COR Report | Site Engineer | CPS Engineer
Final Inspection and Handover
8 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
9 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Engineer: |  |  |  |  | Signature: |  |  | Date: