## Earthworks - Bulk Fill
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1503B - Mautaua Under Slip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Earthworks - Bulk Fill |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: 1 |  |  |  | Corresponding Work Instruction: |  | C1503B - Mautaua Under Slip - SH2 RS562 RP13.287 Construction Approval.docx |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS562 RP13.287
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | W | Set out extents of fill and check against design drawings | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
2 | Topsoil Strip | W | Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out | Prior to commencement | Document Review |  | QA-6002 Process Control PlanTree Felling &Vegn Clearance Check Sheet | Site Engineer
3 |  | W | Topsoil to be stockpile in an area approved by designer | Prior to commencement |  |  |  | Site Engineer
4 |  | H | Inspect fill foundation | At completion of topsoil strip, before Toe construction | Inspection by the Geotechnical Design Manager | Fill foundation must be approved, in writing, before filling commences | CS-4100 Subgrade Approval Check Sheet | Site Engineer | CPS Engineer
5 | Ground Improvements | W | Any area that requires Ground Improvements must be completed as per ACE-CS-6003 and be signed off and closed before bulk earthwork operations commence | Prior to commencement | Document Review |  | QA-6003 Process Control Plan Ground Improvmts (Wick Drains) Check Sheet | Site Engineer
6 | Fill Material Compliance Testing | W | Material to meet specifications dependant on material type selected | Each material used | Document Review | Rock of GAP65, 100, or 150 GAP65 specifically within top 1.2m of buttress | CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt | Site Engineer
7 |  | W | Fill Construction Material | Prior to commencement | Lab Testing | Granular aggregate with broken faces | Lab Test Report | Site Engineer
8 | Filling Operation | W | Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately | Daily | Visual inspection |  |  | Site Engineer
10 |  | W | Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge | Daily visual survey check | Visual inspection | As built drawings | Survey receipt | Site Engineer
11 | Filling Testing Requirements | W | Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing | 1 test per layer of fill | Visual inspection and Lab Testing | Fill shall be compacted in accordance with NZ4431: 2022 | CS-4020 Bulk Fill Earthworks Record Check Sheet | Site Engineer
12 | Survey As Built | W | Ensure cut/fill slopes comply with design prior to next process taking place | Prior to placing topsoil/pavement/ finished surfaces | Measurement |  | Survey receipt | Site Engineer
13 | Confirm testing requirements met | W | Ensure correct no. of test sets performed for fill testing | At completion of Lot | Document Review | l GAP65 testing l Compaction testing | Test results and calculations of fill volume | Site Engineer | CPS Engineer
14 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
15 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date:
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The extent of the buttress are to be confirmed with the Engineer
Note on K10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CPS Engineer