## Rock Armouring
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1503B - Mautaua Under Slip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Rock Armouring |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: 1 |  |  |  | Corresponding Work Instruction: |  | C1503B - Mautaua Under Slip - SH2 RS562 RP13.287 Construction Approval.docx |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS562 RP13.287
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Foundation Inspection | W | Inspect fill foundation | Per area as required | Inspection by the Geotechnical Design Manager | Fill foundation must be approved, in writing, before filling commences | CS-4100 Subgrade Approval Checksheet | Site Engineer
2 | Material Compliance Testing | W | Material to meet specifications dependant on material type selected | Each material used | Document Review | ROCK ARMOUR SHALL HAVE A D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3 | Lab Test Report, delivery docket | Site Engineer
3 |  | W | Rock Construction Material | 1 test per batch purchase | Lab Testing | ROCK ARMOUR SHALL BE HARD, DURABLE, CRUSHED, QUARRIED OR NATURAL STONE FREE FROM DUST, CLAY, ORGANIC MATTER AND OTHER DELETERIOUS MATERIAL. THE STONE SHALL BE FREE FROM LAMINATIONS AND CLEAVAGES AND SHALL NOT DISINTEGRATE ON EXPOSURE TO WEATHERING | Lab Test Report | Site Engineer
4 |  | W | Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 and Tencate PES 1000/Tencate PES 2000 | Prior to commencement of placement | Visual Inspection | Conformance with Specification | Delivery Dockets | Site Engineer
5 | Construction of Engineered Fill Embankment | W | Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap | Prior to commencement | Visual Inspection | Intake Earthworks ITP completed | Backfill ITP | Site Engineer
6 | Geotextile Placement | H | Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps. | Daily visual check | Visual inspection | Installed in 0.5m trench laid back, as outlined in drawing | Photo's, insepction log | Site Engineer | CPS Engineer
7 | Riprap Placement | W | Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material | Daily visual check | Visual inspection | Specification | Photo's | Site Engineer
8 | Survey As Built | W | Ensure rock slopes comply with design prior to next process taking place | At completion of Lot | Measurement |  | Survey receipt | Site Engineer
9 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
10 | As-builts | W | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: