## Subsoil Drainage
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1503B - Mautaua Under Slip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Subsoil Drainage |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: 1 |  |  |  | Corresponding Work Instruction: |  | C1503B - Mautaua Under Slip - SH2 RS562 RP13.287 Construction Approval.docx |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS562 RP13.287
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | W | Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain. | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
2 | Material Compliance | W | Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter | Upon delivery to site | Ensure delivery docket matches materials delivered | 100mm diameter Drain flow TNZ F/2 Grade pipe | Delivery docket | Site Engineer |  |  | no diameter specified in drawings - have left template 100mm requirements
3 |  | W | Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip) |  | Visual inspection | In accordance with TNZ F/2 | Delivery docket | Site Engineer
4 |  | W | Ensure the bidim material is A19, Class B. | Upon delivery to site | Ensure delivery docket matches materials delivered | Ensure geotextile is approved for use | Delivery docket | Site Engineer
5 | Trenching | H | Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works. |  | Visual Inspection | Design Engineer to instruct action and record on dip sheet and as built drawing | Photo / CS-4001 Subsoil Dipsheet Check Sheet | Site Engineer | CPS Engineer |  | Add location to be decided by CPS enginner between row 5 and row 6
|  | H | Location to be detemined by CPS engineer | Prior to install | Visual Inspection | Trenching location and direction to be confirmed by CPS Engineer | Phots, Log TBD | Site Engineer | CPS Engineer
6 | Bedding, pipe installation and Backfill. | H | Upon completion of trenching approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material | 10m intervals | Visual inspection | Ensure material covers the trench and is pinned in place | Photo / CS-4001 Subsoil Dipsheet Check Sheet | Site Engineer
7 |  | W | Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench. | 10m intervals | Visual inspection | Record levels of top of bedding on dip sheet | Photo / CS-4001 Subsoil Dipsheet Check Sheet | Site Engineer
8 |  | W | Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench | 10m intervals | Visual inspection | Consistency with Subsoil Details | Photos | Site Engineer
9 |  | W | Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench | - | Visual inspection | Ensure good coverage | Photos | Site Engineer
10 |  | W | Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place |  | Visual inspection |  |  | Site Engineer
11 | Outlet to any open areas | H | If a subsoil drain outlets to a swale drain/grassed area ensure that a concrete plinth is construction and a marker post is installed - survey to pick up immediately | As required | Survey |  | Survey receipt | Site Engineer | CPS Engineer
12 | Survey As Built | H | Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process | At completion of sub soil drainage line | Survey |  | Survey receipt | Site Engineer
13 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
14 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: