## Kerb & Channel
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | C1503B - Mautaua Under Slip |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Geogrids and Geotextiles Placement |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [8 empty] | Quality Eng.
Lot No: 1 |  |  |  | Corresponding Work Instruction: |  | C1503B - Mautaua Under Slip - SH2 RS562 RP13.287 Construction Approval.docx |  | Compliance with Work Instructions and Specifications
Detailed Location: SH2 RS562 RP13.287
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Prerequisites | W | Testing of underlined layer is compliant | Prior to commencement | Field Test reports review | All minimum requirements for each fill unit is detailed in the Earthworks Specification | This ITP signed | Site Engineer | CPS Engineer
2 |  | W | Proof roll of foundation surface passed | Prior to commencement | Visual Inspection | Proof roll completed with a fully loaded load truck with 8 tonnes per axle or equivalent. | COR | Site Engineer | CPS Engineer
3 | Survey Setout | H | Geogrid or geofabric set out - Set out as per Earthworks and Ground Improvement Layout Plans | Prior to commencement | GPS | Site engineer to confirm | This ITP signed | Site Engineer
4 | Material Conformance | M | Ensure fill material compliance | Prior to commencement | Visual Inspection | Site engineer to confirm GAP65 | COR or Photos | Site Engineer | CPS Engineer
5 |  | M | Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings. | Prior to commencement | Visual Inspection | Delivery dockets with roll details Bidim A19 (class B) placed at backand base of cut | Delivery docket | Site Engineer
|  | M | Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings. | Prior to commencement | Visual Inspection | Delivery dockets with roll details Bidim A49 placed between rock armour and slope face | Delivery docket | Site Engineer
7 | Placement of Geogrid/Geofabric | W | Installation and inspection of geogrids and geofabrics: Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged. | Prior to backfill | Submission | Completed and signed Check sheet. | No log or checksheet for this, will create and update | Site Engineer
9 | Filling Operation | W | Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced | Daily | Visual Inspection | Construction Observation reports and Photos | COR or photos | Site Engineer
10 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
11 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: