## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - B1004F - Tongoio Falls Steep Underslip - Kerb & Channel | itp |  |  |  |  | ITP - B1004F - Tongoio Falls Steep Underslip - Kerb & Channel | 61fb0043-01fa-4c72-802b-95b80aa741a9
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out kerb line and level at 1m offset to EOS
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
label | Frequency - 1/600m3, minimum of 1 per source
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
label | Conformance Criteria - 20MPa at 28 days
label | Records - Concrete Delivery Dockets and lab test results
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the slip form moulds match the dimensions of the design kerb
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Measurements match the design kerb dimensions
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Kerb Foundation
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Sub base construction is completed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Stringing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Check weather forecast and avoid adverse conditions
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - No concrete to be placed in adverse weather conditions
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Slip forming
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
label | Frequency - Prior to slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - To ensure the correct concrete mix is delivered
label | Records - Concrete Delivery Dockets and lab test results
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Expansion joints to be formed at 5m centres
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Kerbing Specification
label | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint | 11 - Tie-in with pre-cast components
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
label | Frequency - During Slip forming
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Work Instruction
label | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Protection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Backfilling to commence only after 72 hours
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - B1401A - Captain's Culvert Inlet Remediation - Parking bay Construction | itp |  |  |  |  | ITP - B1401A - Captain's Culvert Inlet Remediation - Parking bay Construction | b91c12cd-11d6-4fc8-b33c-5bcb92aab5bf
section | Setout
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Proof Roll of subgrade
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | Frequency - Prior to Sub Base Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineers Acceptance
label | Records - Emails
holdpoint | AUTHORITY HOLDPOINT
section | Sub base
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Aggregate material compliance for Subbase stockpiles
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Crushed AP65 with 30% Crushed face. Lab test for MDD at OWC
label | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials deliveresd to site
label | Records - Delivery Dockets, Aggregate Deliveries Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Sub Base Construction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Carry out a Level Check on the trimmed Basecourse
label | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Tolerance = -5mm/+15mm
label | Records - QA measurement Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Degree of Compaction
label | Frequency - 5 per Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | Records - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface shape check
label | Frequency - Prior to base course Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - QA measurement Sheet
holdpoint | AUTHORITY HOLDPOINT
section | Base Course Construction
checkpoint | 9 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Aggregate material compliance for base Course stockpiles
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Aggreate shall comply with TNZ M/4
label | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials deliveresd to site
label | Records - Delivery Dockets, Aggregate Deliveries Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Base Course Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Mat sampling of Basecourse Material
label | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | Conformance Criteria - Grading to comply with specification
label | Records - Mat sample lab test result
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Carry out a Level Check on the trimmed Basecourse
label | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | Records - QA measurement Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Degree of Compaction
label | Frequency - 5 per Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | Records - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface shape check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - QA measurement Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | Records - Site photos, Emails
holdpoint | AUTHORITY HOLDPOINT
section | Sealing
checkpoint | 13 - Seal design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Seal design to be reviewed prior to sealing
label | Frequency - Prior to Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Records - Emails/NTE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Location/Size Confirmation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mark up extent of chipseal
label | Frequency - Prior to Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | Records - Photos
checkpoint | 15 - Surface Cleanliness
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | Frequency - Prior to application of binder
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photos
checkpoint | 16 - Binder Application
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the Binder application is according to the seal design
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - According to seal design
label | Records - Sealing sheet
checkpoint | 17 - Chip Application
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the Chip application is according to the seal design
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - According to seal design
label | Records - Sealing sheet
checkpoint | 18 - Compaction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - At completion of rolling
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | Records - Photos,QA measurement Sheet
checkpoint | 19 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Removal of excess chip
label | Frequency - Within 48 Hours of Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | Records - Photos, Site logs
checkpoint | 20 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - After sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 21 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - B1401A - Captain's Culvert Inlet Remediation - Subsoil Drainage | itp |  |  |  |  | ITP - B1401A - Captain's Culvert Inlet Remediation - Subsoil Drainage | 75e8ab36-4838-4cce-a723-1c1edd15ebc7
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Engineer to confirm the extend of sub soil drain on site
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | Conformance Criteria - Engineer acceptance
label | Records - Site Visits, Emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Locate existing services by hand digging
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all services in conflict with the line of trench are exposed by hand digging
label | Frequency - Prior to Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located
label | Records - Permit To Dig
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 110 Diameter
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - 110mm diameter Drain flow TNZ F/2 Grade pipe
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Free draining granular Fill Comply with NZTA F/5 2013
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Ensure clean drainage chip
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the geotextile filter fabric,strenght Class D in Accordance with TNZ F/7 2003
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Strenght Class D in Accordance with TNZ F/7 2003
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Trenching
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect trench profile
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Record levels of base of trench on dip sheet
label | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Ensure trench line and levels match the design drawings
label | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS Engineer to instruct action and record on dip sheet and as built drawing
label | Records - Photo, Emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Bedding, pipe installation and Backfill.
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Upon completion of trenching Geotextile Filter fabricto be placed into the trench. Accordance with with TNZ F/7 :2003
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure 100mm thick Free draining granular Fill bedding is placed in base of trench.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Record levels of top of bedding on dip sheet
label | Records - Photo & CS-4001 Subsoil Dipsheet
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - Photos
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - As built Survey the Pipe before backfill
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - As-built receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Free draining granular Fill into the trench
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure good coverage
label | Records - Photos
checkpoint | 14 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint | 15 - SubSoil Flushing eye
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Hynds Round 250mmm Lamphole cover and frame or simislar approved
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - Delivery docket
checkpoint | 16 - Final Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Engineer needs to inspect the subsoil drain installed
label | Frequency - After subsoil drain has been installed
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist | ITP - F3002D - Mangahuini Long Drop Site - Guard Railing | itp |  |  |  |  | ITP - F3002D - Mangahuini Long Drop Site - Guard Railing | 4db5d008-47c7-4541-93a2-e3491da36cc1
section | Inspection & Test Plan / Checklist
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - National Standard for Traffic Signal
label | Records - Site pics, NTE/NTC
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | Records - Approved Construction Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All roadside barriers shall comply with TNZ M/23:2009. Only NZTA mash TL3 approved systems to be installed as specified in the specification & guidelines for road safety hardware and devices, Appendix A: permanent road safety hardware.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | Conformance Criteria - Comply with TNZ M/23:2009. NZTA mash TL3 approved systems only
label | Records - Manufacturing certificates, delivery dockets
checkpoint | 4 - Guardrail Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Guard railing shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. Laps to be in direction of traffic
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Hazard markers to be installed at terminal ends. Edge markers posts to be secured to the guard rail. Guardrail to be a minimum of 1.2m from white line. Engineer to confirm min of 1m support width behind the barrier
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Barrier face to be max clearance of 200mm from kerb face where kerbed. Design speed 100Km/hr AADT <1000 V/D run out length 64m. Existing signs to be placed behind the barrier. Offset of fence is to be confirmed to ensure there is sufficient room for barrier installation
label | Frequency - During installation and on completion
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint | 7 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Final Inspection and Handover
checkpoint | 8 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 9 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist | ITP - F3002D - Mangahuini Long Drop Site - ITP for works | itp |  |  |  |  | ITP - F3002D - Mangahuini Long Drop Site - ITP for works | c26c115f-33e7-4ae6-9c0c-177c7ec0243e
section | Section 1: RECEIVING INSPECTIONS
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Buttress Rock Armour (D50=800mm)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 800mm with a minimum specific Gravity SG of 2350kg/m3.
label | Records - Material source test results, Delivery dockets, Photo's
checkpoint | 1.2 - Culvert Rip rap rock (D50 = 500mm)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 500mm with a minimum specific Gravity SG of 2350kg/m
label | Records - Material source test results, Delivery dockets, Photo's
checkpoint | 1.3 - Drainage material
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | Conformance Criteria - Comply with TNZ F/2 or approved equivalent.
label | Records - Material source test results, Delivery dockets
checkpoint | 1.4 - AP65 Granular fill
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Particle size distribution test
label | Conformance Criteria - Test results from a representative general fill sample tested in an independent accredited laboratory
label | Records - Material compliance cert, delivery dockets
checkpoint | 1.5 - Class D A49 Geotextile
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA F/7
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Non-woven & NZTA F/7 compliant, On dry bed below fill
label | Records - Material compliance cert, photo's, delivery dockets
checkpoint | 1.6 - Perforated lateral drains
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved.
label | Records - Material compliance cert, photo's, delivery dockets
checkpoint | 1.7 - Precast concrete box culverts
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Delivery Dockets are collected and signed before precast wing walls are removed from the truck.
label | Records - Material compliance cert, photo's, delivery dockets
checkpoint | 1.8 - Precast concrete wing walls
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | Conformance Criteria - Delivery Dockets are collected and signed before precast wing walls are removed from the truck.
label | Records - Material compliance cert, photo's, delivery dockets
checkpoint | 1.9 - Precast materials
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - Prior to unloading
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | Records - Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.10 - AP40 (Basecourse)
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/4
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Source property testing, Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery dockets
checkpoint | 1.11 - AP65 (Sub-base)
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | Records - Lab test report, Delivery dockets
checkpoint | 1.12 - Grade 2/4 Chip
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Source property testing, Traceability of all materials delivered to site
label | Records - Lab test reports, Delivery dockets
checkpoint | 1.13 - Cement Material cert
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Records - Material certificate(s)
checkpoint | 1.14 - Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ M/1
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | Records - E2 Certificate
section | Section 2: REVETMENT & BACKFILL INSPECTIONS
checkpoint | 2.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - Consistency with Construction Drawing
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Set out extents of fill and check against design drawings
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Unsuitable loose material and vegetation
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Remove and clear any vegetation, trees and unsuitable material
label | Records - Photo's
checkpoint | 2.3 - Subgrade Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Inspect fill foundation, Fill foundation must be approved, in writing, before filling commences
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Class D (A49) Geotextile placement
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Excavation undercut to be underlain with Bidim A49 or similar approved before placing granular fill. Bidim layer required between granular fill and rock armour.
label | Records - Photo's
checkpoint | 2.5 - Sub soil drainage
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
label | Frequency - At lower bench level and mid bench prior to placing granular fill.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved. To be inspected and approved by CPS Engineer prior to install.
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Imported Granular Fill Placement
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS4431:2022
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade.
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Imported Granular Fill Compaction
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS 4402:1986, Test 4.1.3
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM & Clegg hammer testing
label | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3. Testing done as per Site Instruction by CPS Engineer.
label | Records - Test results, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 - Form and cut fill batter as per design 1.5H:1V
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Benches to be cut and profiled to suit slope profile
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.9 - Rock Armour (50-800dia) to form revetment
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - The buttress is to be keyed in to ground directly behind existing displaced reno mattresses and existing railway line timber panel retaining wall
label | Records - Photo's
section | Section 3: CULVERT EXTENSION INSPECTIONS
checkpoint | 3.1 - Clear, reshape & apply rip rap to culvert inlet
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - As agreed on site with CPS Engineer
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Form foundation for culvert extension
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Expose the end of the existing concrete culvert
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Once exposed, CPS Engineer is required to carry out a Structural Integrity inspection on the culvert
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Install precast concrete culvert units & headwalls
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Precast materials will be placed in accordance with the manufacturers recommendations & as per design
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.5 - Rock Rip rap (50-500dia) placed at culvert outlet
label | ACTION (Hold, Monitor, Witness) - H
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Riprap rock to be placed around culvert outlets. Bidim A49 to be placed at base
label | Records - CPS COR Report, Photo's
holdpoint | AUTHORITY HOLDPOINT
section | Section 4: PAVEMENT INSPECTIONS
checkpoint | 4.1 - Saw cut existing pavement
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Prior to pavement construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Smooth and straight saw cut
label | Records - Photo's
checkpoint | 4.2 - Subgrade construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m and/or at random
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | Records - Subgrade Approval Check sheet, Test (CS-4100) reports
checkpoint | 4.3 - Subgrade Cement Application rate
label | ACTION (Hold, Monitor, Witness) - W
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | Records - Bag test records
checkpoint | 4.4 - Pavement construction: Sub base and base course
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Sub base and base course to be placed in accordance with TNZ B2. Compaction required in accordance with NZS 4407:2015. Cement supplied to NZS3122 and stabilised in accordance with TNZ B/5.
label | Records - Photo's
checkpoint | 4.5 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m and/or at random
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%, Average 95% of MDD with nothing less than 92%
label | Records - Test reports
checkpoint | 4.6 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m and/or at random
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
checkpoint | 4.7 - Sub-base construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as-builts
checkpoint | 4.8 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m and/or at random
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%, Average 98% of MDD with nothing less than 95%
label | Records - Test reports, Photo's
checkpoint | 4.9 - Basecourse Cement application rate
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B/5
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | Records - Photo's
checkpoint | 4.10 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | Records - Survey as-builts
checkpoint | 4.11 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Every 20m and/or at random
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | Conformance Criteria - CIV>=25
label | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
checkpoint | 4.12 - Basecourse construction
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ B2
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Mosaic surface
label | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint | 4.13 - Applying Bitumen
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - NZTA M/6
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint | 4.14 - Degree of saturation
label | ACTION (Hold, Monitor, Witness) - W
label | Frequency - Before sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | Conformance Criteria - Degree of saturation should not exceed 80%
label | Records - Pre-seal checksheet (CS-4060)
checkpoint | 4.15 - Chip seal laying
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA M/6
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Chip seal will match existing seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
label | Records - Photo's
checkpoint | 4.16 - Verge
label | ACTION (Hold, Monitor, Witness) - M
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Verge reinstatement to match existing
label | Records - Photo's
checkpoint | 4.17 - Sweep & Line mark new chip seal road
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - TNZ P/12:2000
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As per TNZ P/12:2000
label | Records - Photo's
checkpoint | 4.18 - Install Traffic services
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - F3002D 2-U3436.BM
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Traffic services including signs and edge marker posts to be supplied and placed in accordance with TNZ C/20
label | Records - Photo's
checkpoint | 4.19 - As-built Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | Records - As-builts, CPS COR Report
holdpoint | AUTHORITY HOLDPOINT
section | Section 5: Final Inspection and Handover
checkpoint | 5.1 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 5.2 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - C1503B - Mautaua Under Slip - Earthworks - Bulk Fill | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Earthworks - Bulk Fill | 0934ada7-6fab-45c4-ac41-de41d91a6b78
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out extents of fill and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Topsoil Strip
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - QA-6002 Process Control PlanTree Felling &Vegn Clearance Check Sheet
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Topsoil to be stockpile in an area approved by designer
label | Frequency - Prior to commencement
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect fill foundation
label | Frequency - At completion of topsoil strip, before Toe construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | Records - CS-4100 Subgrade Approval Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Any area that requires Ground Improvements must be completed as per ACE-CS-6003 and be signed off and closed before bulk earthwork operations commence
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - QA-6003 Process Control Plan Ground Improvmts (Wick Drains) Check Sheet
checkpoint | 6 - Fill Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Rock of GAP65, 100, or 150, GAP65 specifically within top 1.2m of buttress
label | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill Construction Material
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Granular aggregate with broken faces
label | Records - Lab Test Report
checkpoint | 8 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
label | Frequency - Daily visual survey check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As built drawings
label | Records - Survey receipt
checkpoint | 11 - Filling Testing Requirements
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing
label | Frequency - 1 test per layer of fill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Lab Testing
label | Conformance Criteria - Fill shall be compacted in accordance with NZ4431: 2022
label | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet
checkpoint | 12 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
checkpoint | 13 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure correct no. of test sets performed for fill testing
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - GAP65 testing, Compaction testing
label | Records - Test results and calculations of fill volume
checkpoint | 14 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 15 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - C1503B - Mautaua Under Slip - Rock Armouring | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Rock Armouring | a50cb28c-1f87-4b06-8391-ffc4e21a6c87
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Foundation Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect fill foundation
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | Records - CS-4100 Subgrade Approval Checksheet
checkpoint | 2 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - ROCK ARMOUR SHALL HAVE A D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
label | Records - Lab Test Report, delivery docket
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Rock Construction Material
label | Frequency - 1 test per batch purchase
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - ROCK ARMOUR SHALL BE HARD, DURABLE, CRUSHED, QUARRIED OR NATURAL STONE FREE FROM DUST, CLAY, ORGANIC MATTER AND OTHER DELETERIOUS MATERIAL. THE STONE SHALL BE FREE FROM LAMINATIONS AND CLEAVAGES AND SHALL NOT DISINTEGRATE ON EXPOSURE TO WEATHERING
label | Records - Lab Test Report
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 and Tencate PES 1000/Tencate PES 2000
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 5 - Construction of Engineered Fill Embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Intake Earthworks ITP completed
label | Records - Backfill ITP
checkpoint | 6 - Geotextile Placement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Installed in 0.5m trench laid back, as outlined in drawing
label | Records - Photo's, insepction log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photo's
checkpoint | 8 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure rock slopes comply with design prior to next process taking place
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
checkpoint | 9 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 10 - As-builts
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
checklist-flat | ITP - C1503B - Mautaua Under Slip - Subsoil Drainage | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Subsoil Drainage | 250b0a90-79df-40ce-ad7b-f9574acb0824
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - 100mm diameter Drain flow TNZ F/2 Grade pipe
label | Records - Delivery docket
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - In accordance with TNZ F/2
label | Records - Delivery docket
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the bidim material is A19, Class B.
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Ensure geotextile is approved for use
label | Records - Delivery docket
checkpoint | 5 - Trenching
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Design Engineer to instruct action and record on dip sheet and as built drawing
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Bedding, pipe installation and Backfill.
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Upon completion of trenching approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Record levels of top of bedding on dip sheet
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - Photos
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure good coverage
label | Records - Photos
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint | 11 - Outlet to any open areas
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - If a subsoil drain outlets to a swale drain/grassed area ensure that a concrete plinth is construction and a marker post is installed - survey to pick up immediately
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
label | Frequency - At completion of sub soil drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 14 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checklist-flat | ITP - C1503B - Mautaua Under Slip - Geogrids and Geotextiles Placement | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Geogrids and Geotextiles Placement | 745f8f0f-997e-4616-9b85-c20e3d9cef3b
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Prerequisites
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Testing of underlined layer is compliant
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Field Test reports review
label | Conformance Criteria - All minimum requirements for each fill unit is detailed in the Earthworks Specification
label | Records - This ITP signed
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Proof roll of foundation surface passed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Proof roll completed with a fully loaded load truck with 8 tonnes per axle or equivalent.
label | Records - COR
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Geogrid or geofabric set out - Set out as per Earthworks and Ground Improvement Layout Plans
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - GPS
label | Conformance Criteria - Site engineer to confirm
label | Records - This ITP signed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Conformance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure fill material compliance
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Site engineer to confirm GAP65
label | Records - COR or Photos
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery dockets with roll details. Bidim A19 (class B) placed at backand base of cut.
label | Records - Delivery docket
checkpoint | -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery dockets with roll details. Bidim A49 placed between rock armour and slope face.
label | Records - Delivery docket
checkpoint | 7 - Placement of Geogrid/Geofabric
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Installation and inspection of geogrids and geofabrics: Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged.
label | Frequency - Prior to backfill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Completed and signed Check sheet.
label | Records - No log or checksheet for this, will create and update
checkpoint | 9 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Construction Observation reports and Photos
label | Records - COR or photos
checkpoint | 10 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 11 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT