## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - B1401A - Captain's Culvert Inlet Remediation - Subsoil Drainage | itp |  |  |  |  | ITP - B1401A - Captain's Culvert Inlet Remediation - Subsoil Drainage
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Engineer to confirm the extend of sub soil drain on site
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | Conformance Criteria - Engineer acceptance
label | Records - Site Visits, Emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Locate existing services by hand digging
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all services in conflict with the line of trench are exposed by hand digging
label | Frequency - Prior to Installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located
label | Records - Permit To Dig
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 110 Diameter
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - 110mm diameter Drain flow TNZ F/2 Grade pipe
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Free draining granular Fill Comply with NZTA F/5 2013
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Ensure clean drainage chip
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the geotextile filter fabric,strenght Class D in Accordance with TNZ F/7 2003
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Strenght Class D in Accordance with TNZ F/7 2003
label | Records - Delivery docket
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Trenching
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect trench profile
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Record levels of base of trench on dip sheet
label | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | Conformance Criteria - Ensure trench line and levels match the design drawings
label | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - CPS Engineer to instruct action and record on dip sheet and as built drawing
label | Records - Photo, Emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Bedding, pipe installation and Backfill.
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Upon completion of trenching Geotextile Filter fabricto be placed into the trench. Accordance with with TNZ F/7 :2003
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure 100mm thick Free draining granular Fill bedding is placed in base of trench.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Record levels of top of bedding on dip sheet
label | Records - Photo & CS-4001 Subsoil Dipsheet
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - Photos
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - As built Survey the Pipe before backfill
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - As-built receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Free draining granular Fill into the trench
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure good coverage
label | Records - Photos
checkpoint | 14 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint | 15 - SubSoil Flushing eye
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Hynds Round 250mmm Lamphole cover and frame or simislar approved
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - Delivery docket
checkpoint | 16 - Final Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The Engineer needs to inspect the subsoil drain installed
label | Frequency - After subsoil drain has been installed
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Engineer acceptance
label | Records - Site visits, emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT