## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - C1503B - Mautaua Under Slip - Earthworks - Bulk Fill | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Earthworks - Bulk Fill
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out extents of fill and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Topsoil Strip
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - QA-6002 Process Control PlanTree Felling &Vegn Clearance Check Sheet
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Topsoil to be stockpile in an area approved by designer
label | Frequency - Prior to commencement
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect fill foundation
label | Frequency - At completion of topsoil strip, before Toe construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | Records - CS-4100 Subgrade Approval Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Ground Improvements
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Any area that requires Ground Improvements must be completed as per ACE-CS-6003 and be signed off and closed before bulk earthwork operations commence
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - QA-6003 Process Control Plan Ground Improvmts (Wick Drains) Check Sheet
checkpoint | 6 - Fill Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Rock of GAP65, 100, or 150, GAP65 specifically within top 1.2m of buttress
label | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill Construction Material
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Granular aggregate with broken faces
label | Records - Lab Test Report
checkpoint | 8 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
label | Frequency - Daily visual survey check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - As built drawings
label | Records - Survey receipt
checkpoint | 11 - Filling Testing Requirements
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing
label | Frequency - 1 test per layer of fill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Lab Testing
label | Conformance Criteria - Fill shall be compacted in accordance with NZ4431: 2022
label | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet
checkpoint | 12 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
checkpoint | 13 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure correct no. of test sets performed for fill testing
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - GAP65 testing, Compaction testing
label | Records - Test results and calculations of fill volume
checkpoint | 14 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 15 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT