## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - C1503B - Mautaua Under Slip - Rock Armouring | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Rock Armouring
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Foundation Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect fill foundation
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | Records - CS-4100 Subgrade Approval Checksheet
checkpoint | 2 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - ROCK ARMOUR SHALL HAVE A D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
label | Records - Lab Test Report, delivery docket
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Rock Construction Material
label | Frequency - 1 test per batch purchase
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - ROCK ARMOUR SHALL BE HARD, DURABLE, CRUSHED, QUARRIED OR NATURAL STONE FREE FROM DUST, CLAY, ORGANIC MATTER AND OTHER DELETERIOUS MATERIAL. THE STONE SHALL BE FREE FROM LAMINATIONS AND CLEAVAGES AND SHALL NOT DISINTEGRATE ON EXPOSURE TO WEATHERING
label | Records - Lab Test Report
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 and Tencate PES 1000/Tencate PES 2000
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 5 - Construction of Engineered Fill Embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Intake Earthworks ITP completed
label | Records - Backfill ITP
checkpoint | 6 - Geotextile Placement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Installed in 0.5m trench laid back, as outlined in drawing
label | Records - Photo's, insepction log
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photo's
checkpoint | 8 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure rock slopes comply with design prior to next process taking place
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
checkpoint | 9 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 10 - As-builts
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing