## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - C1503B - Mautaua Under Slip - Subsoil Drainage | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Subsoil Drainage
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - 100mm diameter Drain flow TNZ F/2 Grade pipe
label | Records - Delivery docket
checkpoint | 3 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - In accordance with TNZ F/2
label | Records - Delivery docket
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the bidim material is A19, Class B.
label | Frequency - Upon delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | Conformance Criteria - Ensure geotextile is approved for use
label | Records - Delivery docket
checkpoint | 5 - Trenching
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Design Engineer to instruct action and record on dip sheet and as built drawing
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Bedding, pipe installation and Backfill.
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Upon completion of trenching approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench.
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Record levels of top of bedding on dip sheet
label | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | Frequency - 10m intervals
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Consistency with Subsoil Details
label | Records - Photos
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Ensure good coverage
label | Records - Photos
checkpoint | 10 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint | 11 - Outlet to any open areas
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - If a subsoil drain outlets to a swale drain/grassed area ensure that a concrete plinth is construction and a marker post is installed - survey to pick up immediately
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
label | Frequency - At completion of sub soil drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 14 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT