## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - C1503B - Mautaua Under Slip - Geogrids and Geotextiles Placement | itp |  |  |  |  | ITP - C1503B - Mautaua Under Slip - Geogrids and Geotextiles Placement
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Prerequisites
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Testing of underlined layer is compliant
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Field Test reports review
label | Conformance Criteria - All minimum requirements for each fill unit is detailed in the Earthworks Specification
label | Records - This ITP signed
checkpoint | 2 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Proof roll of foundation surface passed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Proof roll completed with a fully loaded load truck with 8 tonnes per axle or equivalent.
label | Records - COR
checkpoint | 3 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Geogrid or geofabric set out - Set out as per Earthworks and Ground Improvement Layout Plans
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - GPS
label | Conformance Criteria - Site engineer to confirm
label | Records - This ITP signed
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Material Conformance
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure fill material compliance
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Site engineer to confirm GAP65
label | Records - COR or Photos
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery dockets with roll details. Bidim A19 (class B) placed at backand base of cut.
label | Records - Delivery docket
checkpoint | -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Delivery dockets with roll details. Bidim A49 placed between rock armour and slope face.
label | Records - Delivery docket
checkpoint | 7 - Placement of Geogrid/Geofabric
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Installation and inspection of geogrids and geofabrics: Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged.
label | Frequency - Prior to backfill
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | Conformance Criteria - Completed and signed Check sheet.
label | Records - No log or checksheet for this, will create and update
checkpoint | 9 - Filling Operation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Construction Observation reports and Photos
label | Records - COR or photos
checkpoint | 10 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 11 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT