## Erosion & Sediment Control
|  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  | Contract Name: | G1202A - Waikaretaheke Riverbend Recovery |  | CPS Approver | Quality Approver | CPS Eng.
|  |  | Procedure: | Compliance and Environmental |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [5 empty] | Robert Loomes | J Addis | Quality Eng.
Lot No: |  |  |  | Corresponding Work Instruction: | https://trecnz.sharepoint.com/:w:/s/ZONEG-SH38-HAWKESBAY/ES3qCup35rBNqJf0bUFRkC8BpQO-dTZgqN1_SQYCHVXt0w?e=rfp3r7 | Compliance with Work Instructions and Specifications
Detailed Location: SH38 at RS 161 RP 7.171
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Approved Consents | M | Is a copy of approved consent(s) available on site | Check latest consents and SSESCP's are at each site office | Copy of Consent | Site Engineer
2 | Internal ESC Pre-Construction | H | Internal pre-construction meeting held with Environment Team | Environmental Advisor to organise | Meeting minutes or similar record | Site Engineer | Environmental Advisor
3 | Type and Location of Erosion & Sedimentation Control | H | Confirm type and location of erosion and sedimentation control, based on relevant drawing/s | Relevant ESCP drawing | Drawings | Site Engineer | Environmental Advisor
4 | Channel Bund (if required) | M | Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted. | Work Instruction, Drawings and Checklist | Photos and Checklist | Site Engineer | ES Supervisor
5 | Silt Fence (SF) (if required) | M | Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings | Work Instruction, Drawings and Checklist | Photos and Checklist | Site Engineer | ES Supervisor
7 | Maintenance Inspections | W | Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance | Approved ESC Plan. Complete weekly and upload to ConQA / Procore | Inspection Record | ES Supervisor | Environmental Advisor
8 | Decommissioning of Erosion Sediment Controls | H | Decommissioning Plan submitted to HBRC for Approval |  | Decommissioning Plan and Email record | Site Engineer | Environmental Advisor
9 | Decommissioning of Erosion Sediment Controls | H | HBRC to issue an approval document so that Decommissioning works can commence | Approval for Decommissioning | HBRC approval Doc | Site Engineer | Environmental Advisor
10 | Completion Sign Off From Fields Below |  |  |  |  | Signatures |  | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  | Signature: |  |  | Date: