## Rock Armouring & Bulk Filling
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | G1202A - Waikaretaheke Riverbend Recovery |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Rock Armouring / Bulk Fill |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Robert Loomes |  | Quality Eng.
Lot No: G1202A - Recovery |  |  |  | Corresponding Work Instruction: |  | G1202A - Waikare Riverbend Recovery RP7 - TREC Quick Wins.docx |  | Compliance with Work Instructions and Specifications
Detailed Location: SH38 Waikaretaheke Riverbend
Chainage: RS 161 RP 7.171
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | H | Set out lateral extents of buttress. Geotech Engineer to confirm extent of works | Prior to commencement | Inspection | Fault ID 530 - Underslip Recovery Remediation Design Report | Survey receipt | Site Engineer | Geotechnical Site Engineer (CPS)
2 | Survey Setout | H | The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, this will need to be approved by the Geotechnical Site Engineer | Prior to commencement | Inspection | Fault ID 530 - Underslip Recovery Remediation Design Report | Survey receipt | Site Engineer | Geotechnical Site Engineer (CPS)
3 | Remove all loose materials | W | Once all ESC controls have been installed | Prior to commencement | Document Review |  |  | Site Engineer
4 | Excavate to Sub-Grade | H | Inspect fill foundation | Per area as required | Inspection | Fill foundation must be approved, in writing, before filling commences | CS-4100 Subgrade Approval Checksheet | Site Engineer | Geotechnical Site Engineer (CPS)
5 | Excavate to Sub-Grade | W | Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review. | Per area as required | Scala Penetrometer | >= 1 test per 10 linear metres, where access is practical and available | Engineer or Lab Test Report | Site Engineer | Geotechnical Site Engineer (CPS)
6 | Material Compliance Testing | W | Material to meet specifications dependant on material type selected | Each material used | Document Review | a. GRADATION D85/D15 = 1.9 b. D85 690 (MAX) AND 590 (MIN) c. D15 390 (MAX) AND 275 (MIN) | Supplier Record or Lab Test Report | Site Engineer
7 | Material Compliance Testing | W | Rock Construction Material | 1 test per 1 000m3 | Lab Testing | D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3 | Lab Test Report | Site Engineer
8 | Material Compliance Testing | H | Bulk Construction Material | 1 test SET per 1 000m3 | Lab Testing - OMC Standard Compaction; Grading Curve (wet or dry sieve) | All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel). | Lab Test Reports | Site Engineer | Geotechnical Site Engineer (CPS)
9 | Material Compliance Testing | M | Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar | Prior to commencement of placement | Visual Inspection | Conformance with Specification | Delivery Dockets | Site Engineer
10 | Material Compliance Testing | M | Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar | Prior to commencement of placement | Visual Inspection | Conformance with Specification | Delivery Dockets | Site Engineer
11 | Geotextile Placement - Backface | W | Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps. | Daily visual check | Visual inspection |  | Photo's | Site Engineer
12 | Perforated Drainage Coils | W | TAP ANY SEEPAGE OR GROUNDWATER FLOW WITH MEGA FLOW/ PERFORATED DRAINAGE COIL. THE OUTLET SHOULD BE AT THE TOE OF THE BUTTRESS. | Daily visual check | Visual inspection |  | Photo's | Site Engineer
13 | Backfilling of Engineered Fill Embankment | W | Engineered bulk construction material 250mm lifts with material and regular compaction testing | 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill). | Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer. | 95% of MDD or clegg equivalent | Lab Test Reports | Site Engineer | Geotechnical Site Engineer (CPS)
14 | Backfilling of Engineered Fill Embankment | W | Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap | At completion of bulk filling | Visual Inspection |  | Photo's | Site Engineer
15 | Geotextile Placement - front face | W | Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps. | At completion of bulk filling | Visual inspection |  | Photo's | Site Engineer | Geotechnical Site Engineer (CPS)
16 | Riprap Placement | W | Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material | Daily visual check | Visual inspection | Specification | Photo's | Site Engineer | Geotechnical Site Engineer (CPS)
17 | Survey As Built | H | Ensure rock slopes comply with design prior to next process taking place | At completion of Lot | Measurement |  | Survey receipt | Site Engineer
18 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
19 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
20 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
21 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date:
Note on F16: Insert Frequency here
Note on H16: List Tests required from Spec & PRs here with criteria for a passing test - use multiple rows if required
Note on F17: Insert Frequency here