## Swales & Overland Drainage
|  |  |  | Inspection Test Plan |  |  | Approver / Signatures |  | Project Site reps.
|  |  |  | Contract Name: | G1202A - Waikaretaheke Riverbend Recovery |  | CPS Approver | Quality Approver | CPS Eng.
|  |  |  | Procedure: | Swales & Overland Drainage |  | Name / Signature | Name / Signature | Site Engineer
Inspection & Test Plan / Checklist | [6 empty] | Robert Loomes |  | Quality Eng.
Lot No: G1202A |  |  |  | Corresponding Work Instruction: |  | G1202A - Waikare Riverbend Recovery RP7 - TREC Quick Wins.docx |  | Compliance with Work Instructions and Specifications
Detailed Location: SH38 Waikaretaheke Riverbend
Chainage: RS 161 RP 7.171
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | CPS Engineer Initials (Grey if not required) | Date(s)
1 | Survey As Built | H | Ensure cut/fill slopes comply with design prior to swale drain or over land drain construction | Prior to commencement | Measurement |  | Survey receipt | Site Engineer
2 | Previous Lots | H | Are all previous Earthworks & Topsoil Respread ITP's are completed and signed off | Prior to commencement | Document Review |  | Earthworks & Topsoil Respread ITP's | Site Engineer
3 | Previous Lots | H | ANY OTHER SITE WORKS THAT WILL CAUSE REWORK TO SWALES HAS BEEN COMPLETED | Prior to commencement | Document Review |  | Snag Lists for previous Lots | Site Engineer
4 | Excavation of Swale Drain | H | Swale drains shall be excavated, shaped and constructed to the dimensions and the types on the For Construction Drawings/ existing swales | During Construction | Visual Inspection |  | Photos | Site Engineer
5 | Profiling of Swales | W | Level check prior to topsoiling | During Construction | Measurement and Visual Inspection |  | Photos, measurement sheet | Site Engineer
6 | Profiling of Swales | W | Level shape upon completion of topsoiling by As Built survey | During Construction | Measurement and Visual Inspection |  | Survey receipt | Site Engineer | CPS Engineer
7 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
8 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
9 | Quality Assurance deliverables | W | Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file | At completion of Lot | Document Review | Ensure all QA is uploaded into ConQA / Procore | As-builts, NCR's and RFI's | Site Engineer
10 | Completion Sign Off From Fields Below | [5 empty] | Signatures | PM | CPS | QM
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Construction Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By CPS Manager: |  |  |  |  | Signature: |  |  | Date: