## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - G1202A - Waikaretaheke Riverbend Recovery - Compliance and Environmental | itp |  |  |  |  | ITP - G1202A - Waikaretaheke Riverbend Recovery - Compliance and Environmental | b01d59ef-d668-43e1-a1e5-39144e7bc786
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Approved Consents
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Is a copy of approved consent(s) available on site
label | Conformance Criteria - Check latest consents and SSESCP's are at each site office
label | Records - Copy of Consent
checkpoint | 2 - Internal ESC Pre-Construction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Internal pre-construction meeting held with Environment Team
label | Conformance Criteria - Environmental Advisor to organise
label | Records - Meeting minutes or similar record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Type and Location of Erosion & Sedimentation Control
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Confirm type and location of erosion and sedimentation control, based on relevant drawing/s
label | Conformance Criteria - Relevant ESCP drawing
label | Records - Relevant ESCP drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Channel Bund (if required)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted.
label | Conformance Criteria - Work Instruction, Drawings and Checklist
label | Records - Photos and Checklist
checkpoint | 5 - Silt Fence (SF) (if required)
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings
label | Conformance Criteria - Work Instruction, Drawings and Checklist
label | Records - Photos and Checklist
checkpoint | 7 - Maintenance Inspections
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance
label | Conformance Criteria - Approved ESC Plan. Complete weekly and upload to ConQA / Procore
label | Records - Inspection Record
checkpoint | 8 - Decommissioning of Erosion Sediment Controls
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Decommissioning Plan submitted to HBRC for Approval
label | Records - Decommissioning Plan and Email record
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Decommissioning of Erosion Sediment Controls
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - HBRC to issue an approval document so that Decommissioning works can commence
label | Conformance Criteria - Approval for Decommissioning
label | Records - HBRC approval Doc
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - G1202A - Waikaretaheke Riverbend Recovery - Network Drainage | itp |  |  |  |  | ITP - G1202A - Waikaretaheke Riverbend Recovery - Network Drainage | a237353b-2194-49c6-b9aa-762b2474f4bb
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
checkpoint | 2 - Locate existing services by hand digging/hydro excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | Records - As-built Drawings Doc. Review
checkpoint | 3 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Line and level is correct
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 4 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 5 - Foundation Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test formation level on completion of excavation to check if undercut required
label | Frequency - One test per 20 linear metres
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Pipe Bedding Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Reject chip 10-20mm
label | Records - Supplier Documentation / Lab Test Report
checkpoint | 7 - Bedding
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - 100 mm thick bedding for all mm dia pipe
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 8 - Pipes and Precast Units
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Frequency - Each delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
label | Records - Delivery Dockets
checkpoint | 9 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 10 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | Records - Photos
checkpoint | 11 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - As-built survey of pipes installed
label | Frequency - Once line is completed between 2 structures
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
label | Records - Survey Receipt
checkpoint | 12 - CPS Engineer Pre backfill Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compliance with the Specification
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - CPS Engineer Pre backfill Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 5mm
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Vertical tolerance +/- 5mm
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 14 - CPS Engineer Pre backfill Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Vertical tolerance +/- 5mm
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 15 - Pipe Backfill Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with requirements from Specifications
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Pipe Backfill Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material
label | Frequency - 1 test per 50m, or per 500m3 of source.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction Curve; Grading Curve (wet or dry sieve)
label | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Backfilling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | Frequency - 1 test per 20 m length of trench per 300mm lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
label | Records - Lab test results
checkpoint | 18 - Structure installation (Manhole, Catchpit, Wingwall)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Structures to be installed to the design survey location and level
label | Frequency - During structure construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - As Built Survey
label | Records - ACE-CS-4006 Manhole Catchpit Board Check Sheet and Survey receipt (or equivalent)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Structure installation (Manhole, Catchpit, Wingwall)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All joints are to be sealed including rungs and lids
label | Frequency - During structure construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Pipe joint to structure shall be encased in 200mm (min.) thick 20MPa concrete
label | Records - CS-4006 Manhole Catchpit Board Check Sheet (or equivalent)
checkpoint | 20 - Structure installation (Manhole, Catchpit, Wingwall)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Arrange as-built survey of the structure and all invert levels
label | Frequency - Once installed
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - As Built Survey
label | Records - Survey Receipt
checkpoint | 21 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all drainage lines comply with design prior to carrying on with next construction process
label | Frequency - At completion of drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - 65
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 23 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 24 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 25 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - G1202A - Waikaretaheke Riverbend Recovery - Rock Armouring / Bulk Fill | itp |  |  |  |  | ITP - G1202A - Waikaretaheke Riverbend Recovery - Rock Armouring / Bulk Fill | f787917b-d7d8-4d41-8a02-33791c141049
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Set out lateral extents of buttress. Geotech Engineer to confirm extent of works
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, this will need to be approved by the Geotechnical Site Engineer
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Remove all loose materials
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Once all ESC controls have been installed
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
checkpoint | 4 - Excavate to Sub-Grade
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect fill foundation
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | Records - CS-4100 Subgrade Approval Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Excavate to Sub-Grade
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review.
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Per area as required
label | Conformance Criteria - >= 1 test per 10 linear metres, where access is practical and available
label | Records - Engineer or Lab Test Report
checkpoint | 6 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - a. GRADATION D85/D15 = 1.9
label | b. D85 690 (MAX) AND 590 (MIN)
label | c. D15 390 (MAX) AND 275 (MIN)
label | Records - Supplier Record or Lab Test Report
checkpoint | 7 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Rock Construction Material
label | Frequency - 1 test per 1 000m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
label | Records - Lab Test Report
checkpoint | 8 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Bulk Construction Material
label | Frequency - 1 test SET per 1 000m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction; Grading Curve (wet or dry sieve)
label | Conformance Criteria - All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel).
label | Records - Lab Test Reports
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 10 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets
checkpoint | 11 - Geotextile Placement - Backface
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photo's
checkpoint | 12 - Perforated Drainage Coils
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - TAP ANY SEEPAGE OR GROUNDWATER FLOW WITH MEGA FLOW/ PERFORATED DRAINAGE COIL. THE OUTLET SHOULD BE AT THE TOE OF THE BUTTRESS.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photo's
checkpoint | 13 - Backfilling of Engineered Fill Embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Engineered bulk construction material 250mm lifts with material and regular compaction testing
label | Frequency - 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill).
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer.
label | Conformance Criteria - 95% of MDD or clegg equivalent
label | Records - Lab Test Reports
checkpoint | 14 - Backfilling of Engineered Fill Embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | Frequency - At completion of bulk filling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photo's
checkpoint | 15 - Geotextile Placement - front face
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - At completion of bulk filling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photo's
checkpoint | 16 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photo's
checkpoint | 17 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure rock slopes comply with design prior to next process taking place
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 18 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 19 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 20 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file.
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 21 - Completion Sign Off From Fields Below
label | Records - Signatures
checklist-flat | ITP - G1202A - Waikaretaheke Riverbend Recovery - Swales & Overland Drainage | itp |  |  |  |  | ITP - G1202A - Waikaretaheke Riverbend Recovery - Swales & Overland Drainage | c831da04-a99c-4a80-8b82-3903692b5503
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to swale drain or over land drain construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Previous Lots
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Are all previous Earthworks & Topsoil Respread ITP's are completed and signed off
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Earthworks & Topsoil Respread ITP's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Previous Lots
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - ANY OTHER SITE WORKS THAT WILL CAUSE REWORK TO SWALES HAS BEEN COMPLETED
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Snag Lists for previous Lots
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Excavation of Swale Drain
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Swale drains shall be excavated, shaped and constructed to the dimensions and the types on the For Construction Drawings/ existing swales
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Profiling of Swales
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Level check prior to topsoiling
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and Visual Inspection
label | Records - Photos, measurement sheet
checkpoint | 6 - Profiling of Swales
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Level shape upon completion of topsoiling by As Built survey
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and Visual Inspection
label | Records - Survey receipt
checkpoint | 7 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 8 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures