## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - G1202A - Waikaretaheke Riverbend Recovery - Network Drainage | itp |  |  |  |  | ITP - G1202A - Waikaretaheke Riverbend Recovery - Network Drainage
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
checkpoint | 2 - Locate existing services by hand digging/hydro excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | Records - As-built Drawings Doc. Review
checkpoint | 3 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Line and level is correct
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 4 - Trenching and Excavation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 5 - Foundation Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test formation level on completion of excavation to check if undercut required
label | Frequency - One test per 20 linear metres
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Pipe Bedding Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Reject chip 10-20mm
label | Records - Supplier Documentation / Lab Test Report
checkpoint | 7 - Bedding
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - 100 mm thick bedding for all mm dia pipe
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 8 - Pipes and Precast Units
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | Frequency - Each delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
label | Records - Delivery Dockets
checkpoint | 9 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 10 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | Records - Photos
checkpoint | 11 - Pipe Laying
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - As-built survey of pipes installed
label | Frequency - Once line is completed between 2 structures
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
label | Records - Survey Receipt
checkpoint | 12 - CPS Engineer Pre backfill Inspection
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Compliance with the Specification
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - CPS Engineer Pre backfill Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 5mm
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Vertical tolerance +/- 5mm
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 14 - CPS Engineer Pre backfill Inspection
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
label | Frequency - Prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Vertical tolerance +/- 5mm
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint | 15 - Pipe Backfill Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with requirements from Specifications
label | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 - Pipe Backfill Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Backfill Construction Material
label | Frequency - 1 test per 50m, or per 500m3 of source.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction Curve; Grading Curve (wet or dry sieve)
label | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Backfilling
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | Frequency - 1 test per 20 m length of trench per 300mm lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
label | Records - Lab test results
checkpoint | 18 - Structure installation (Manhole, Catchpit, Wingwall)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Structures to be installed to the design survey location and level
label | Frequency - During structure construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - As Built Survey
label | Records - ACE-CS-4006 Manhole Catchpit Board Check Sheet and Survey receipt (or equivalent)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Structure installation (Manhole, Catchpit, Wingwall)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - All joints are to be sealed including rungs and lids
label | Frequency - During structure construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | Conformance Criteria - Pipe joint to structure shall be encased in 200mm (min.) thick 20MPa concrete
label | Records - CS-4006 Manhole Catchpit Board Check Sheet (or equivalent)
checkpoint | 20 - Structure installation (Manhole, Catchpit, Wingwall)
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Arrange as-built survey of the structure and all invert levels
label | Frequency - Once installed
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - As Built Survey
label | Records - Survey Receipt
checkpoint | 21 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all drainage lines comply with design prior to carrying on with next construction process
label | Frequency - At completion of drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - 65
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 23 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 24 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 25 - Completion Sign Off From Fields Below
label | Records - Signatures