## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - G1202A - Waikaretaheke Riverbend Recovery - Swales & Overland Drainage | itp |  |  |  |  | ITP - G1202A - Waikaretaheke Riverbend Recovery - Swales & Overland Drainage
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure cut/fill slopes comply with design prior to swale drain or over land drain construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Previous Lots
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Are all previous Earthworks & Topsoil Respread ITP's are completed and signed off
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Earthworks & Topsoil Respread ITP's
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Previous Lots
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - ANY OTHER SITE WORKS THAT WILL CAUSE REWORK TO SWALES HAS BEEN COMPLETED
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Snag Lists for previous Lots
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Excavation of Swale Drain
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Swale drains shall be excavated, shaped and constructed to the dimensions and the types on the For Construction Drawings/ existing swales
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Profiling of Swales
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Level check prior to topsoiling
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and Visual Inspection
label | Records - Photos, measurement sheet
checkpoint | 6 - Profiling of Swales
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Level shape upon completion of topsoiling by As Built survey
label | Frequency - During Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and Visual Inspection
label | Records - Survey receipt
checkpoint | 7 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 8 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Quality Assurance deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10 - Completion Sign Off From Fields Below
label | Records - Signatures