## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: Mains Reticulation
| step |  |  | Tier 2: MSB Installation
AE-ITCX-011 - Main Switchboard Inspection Sheet (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-011 - MSB1
AE-ITCX-011 - Main Switchboard Inspection Sheet (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-011 - MSB2
| step |  |  | Tier 2: MEN and MSB CT & Meter Panel Installation
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MSB1
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MSB2
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T-L1-01
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T-L1-02
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T-L1-03
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T-L1-04
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T-L1-05
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T1-Mech Riser 1
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T1-Mech Riser 2
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T2-Mech Riser 1
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T2-Mech Riser 2
AE-ITCX-012 - MEN & MSB Meter Panel Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-012 - MP-T2-Mech Riser 3
| step |  |  | Tier 2: Tray Installation
| step |  |  | Tier 3: Basement - Level 3
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Basement (Horizontal)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Ground (Horizontal)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Level 01 Horizontal (Substation to MSB-1 and MSB-2)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Level 02 Horizontal
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Level 03 Horizontal
| step |  |  | Tier 3: TOWER 1
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Riser B1 - Level 3 (Vertical)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Riser Lvl 4 - LVl 12 (Vertical)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Riser Lvl 13 - Lvl 21 (Vertical)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Riser Lvl 22 - Lvl 30 (Vertical/Horizontal)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Roof (Vertical/Horizontal)
| step |  |  | Tier 3: TOWER 2
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Riser B1 - Level 3 (Vertical)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Riser Lvl 4 - LVl 12 (Vertical)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Riser Lvl 13 - Lvl 21 (Vertical)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Riser Lvl 22 - Lvl 29 (Vertical)
AE-ITCX-008 - Cable Tray Checklist (Rev 0 +Names) | checklist |  |  | Tier 4: AE-ITCX-008 - Roof (Vertical/Horizontal)
| step |  |  | Tier 2: Consumer Mains Installation
| step |  |  | Tier 3: Basement - Level 3
| step |  |  | Tier 4: MSB1
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 5: AE-ITCX-015 - Mandatory Testing
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 5: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: MSB2
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 5: AE-ITCX-015 - Mandatory Testing
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 5: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 1
| step |  |  | Tier 5: TOB-T1-H-L1
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 5: TOB-T1-H-L1.1
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 2
| step |  |  | Tier 5: TOB-T1-H-L2
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 3: TOWER 1
| step |  |  | Tier 4: Level 4
| step |  |  | Tier 5: TOB-T1-M-4
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 5
| step |  |  | Tier 5: TOB-T1-L5
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 7
| step |  |  | Tier 5: TOB-T1-H-L7
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 5: TOB-T1-M-7
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 9
| step |  |  | Tier 5: TOB-T1-L9
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 10
| step |  |  | Tier 5: TOB-T1-M-10
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 12
| step |  |  | Tier 5: TOB-T1-H-L12
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 13
| step |  |  | Tier 5: TOB-T1-L13
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 5: TOB-T1-M-13
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 16
| step |  |  | Tier 5: TOB-T1-M-16
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 17
| step |  |  | Tier 5: TOB-T1-L17
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 18
| step |  |  | Tier 5: TOB-T1-H-L18
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 19
| step |  |  | Tier 5: TOB-T1-L19
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 5: TOB-T1-M-19
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 22
| step |  |  | Tier 5: TOB-T1-M-22
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 23
| step |  |  | Tier 5: TOB-T1-L23
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 24
| step |  |  | Tier 5: TOB-T1-H-L24
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 25
| step |  |  | Tier 5: TOB-T1-M-25
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 27
| step |  |  | Tier 5: TOB-T1-L27
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 28
| step |  |  | Tier 5: TOB-T1-M-28
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 29
| step |  |  | Tier 5: TOB-T1-H-L29
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
step
| step |  |  | Tier 3: TOWER 2; Tier 4: Level 4
| step |  |  | Tier 5: TOB-T2-M-L4
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 6
| step |  |  | Tier 5: TOB-T2-L6
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 7
| step |  |  | Tier 5: TOB-T2-H-L7
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 5: TOB-T2-M-L7
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 8
| step |  |  | Tier 5: TOB-T2-L8
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 10
| step |  |  | Tier 5: TOB-T2-M-L10
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 12
| step |  |  | Tier 5: TOB-T2-L12
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 13
| step |  |  | Tier 5: TOB-T2-H-L13
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 5: TOB-T2-M-L13
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 16
| step |  |  | Tier 5: TOB-T2-M-L16
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 17
| step |  |  | Tier 5: TOB-T2-L17
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 18
| step |  |  | Tier 5: TOB-T2-H-L18
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 19
| step |  |  | Tier 5: TOB-T2-M-L19
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 21
| step |  |  | Tier 5: TOB-T2-L21
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 22
| step |  |  | Tier 5: TOB-T2-M-L22
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 24
| step |  |  | Tier 5: TOB-T2-H-L24
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 5: TOB-T2-M-L24
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 25
| step |  |  | Tier 5: TOB-T2-L25
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 28
| step |  |  | Tier 5: TOB-T2-M-L28
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 29
| step |  |  | Tier 5: TOB-T2-H-L29
AE-ITCX-013 - T-Off Visual Inspection Test (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-013 - Visual Inspection
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 2: Submain Installation
| step |  |  | Tier 4: 1 - TRANSFORMER #2 - MSB-1 (Bus A)
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 5: AE-ITCX-015 - Mandatory Testing
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 5: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: 2 - TRANSFORMER #1 - MSB-2 (Bus A)
| step |  |  | Tier 4: RE1(e) - MSB-1 (Bus LIFE SAFETY SERVICES) - RE1
| step |  |  | Tier 4: RE2(e) - MSB-2 (Bus METERED BUS)
| step |  |  | Tier 4: 3 - MSB-1 (Bus LIFE SAFTEY SERVICES) - T1-LIFT-1
| step |  |  | Tier 4: 4 - MSB-1 (Bus LIFE SAFETY SERVICES) - T2-LIFT4
| step |  |  | Tier 4: 4(E) - MSB-1 (Bus LIFE SAFETY SERVICES) - T2-LIFT4
| step |  |  | Tier 4: 5 - MSB-1 (Bus LIFE SAFETY SERVICES) - T2-LIFT-5
| step |  |  | Tier 4: 5(E) - MSB-1 (Bus LIFE SAFETY SERVICES) - T2-LIFT-5
| step |  |  | Tier 4: 6 - MSB-1 (Bus LIFE SAFETY SERVICES) - T1-LIFT-2
| step |  |  | Tier 4: 7 - MSB-1 (Bus LIFE SAFTEY SERVICES) - T1-LIFT-3
| step |  |  | Tier 4: 8 - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-T2-30.02
| step |  |  | Tier 4: 8(E) - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-T2-30.02
| step |  |  | Tier 4: 9 - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-T1-31.02
| step |  |  | Tier 4: 9(E) - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-T1-31.02
| step |  |  | Tier 4: 10 - MSB-1 (Bus LIFE SAFTEY SERVICES) - MSSB-02.02
| step |  |  | Tier 4: 11 - MSB-1 (Bus LIFE SAFTEY SERVICES) - JOCKEY PUMP
| step |  |  | Tier 4: 14 - MSB-1 (Bus LIFE SAFTEY SERVICES) - TANK INDICATOR
| step |  |  | Tier 4: 17 - MSB-1 (Bus LIFE SAFTEY SERVICES) - DIESEL PUMP
| step |  |  | Tier 4: 19 - MSB-1 (Bus LIFE SAFTEY SERVICES) - ELECTRIC PUMP
| step |  |  | Tier 4: 20A - MSB-1 (Bus METERED BUS) - TOB-T1-H-L1.1
| step |  |  | Tier 4: 20.1 - TOB-T1-H-L1.1 - DB-H-DAS
| step |  |  | Tier 4: 20.2 - TOB-T1-H-L1.1 - DB-H-COMMS
| step |  |  | Tier 4: 21A - MSB-1 (Bus METERED BUS) - TOB-T1-H-L2
| step |  |  | Tier 4: 21.1 - TOB-T1-H-L2 - DB-H-T1-L2
| step |  |  | Tier 4: 21.2 - TOB-T1-H-L2 - DB-H-T1-L3
| step |  |  | Tier 4: 22 - MSB-1 (Bus METERED BUS) - TOB-T1-H-L29
| step |  |  | Tier 4: 23 - MSB-1 (Bus METERED BUS) - MSSB-T1-31.01
| step |  |  | Tier 4: 24 - MSB-1 (Bus METERED BUS) - MSSB-T1-03.01
| step |  |  | Tier 4: 25 - MSB-2 (Bus UNMETERED BUS) - TOB-T1-L17
| step |  |  | Tier 4: 26 - MSB-2 (Bus UNMETERED BUS) - TOB-T1-L27
| step |  |  | Tier 4: 27 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-01
| step |  |  | Tier 4: 27(e) - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-01
| step |  |  | Tier 4: 28 - MSB-2 (Bus UNMETERED BUS) - DB-T-G-01
| step |  |  | Tier 4: 29 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-02
| step |  |  | Tier 4: 30 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-03
| step |  |  | Tier 4: 31 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-04
| step |  |  | Tier 4: 32 - MSB-2 (Bus UNMETERED BUS) - DB-T-L1-05
| step |  |  | Tier 4: 33 - MSB-2 (Bus UNMETERED BUS) - MP-RETAIL.01
| step |  |  | Tier 4: 33.1 - MP-RETAIL.01 - DB-T-L1-06
| step |  |  | Tier 4: 33.2 - MP-RETAIL.01 - DB-T-L1-07
| step |  |  | Tier 4: 34 - MSB-1 (Bus UNMETERED BUS) - TOB-T1-M-L28
| step |  |  | Tier 4: 35 - MSB-2 (Bus METERED BUS) - DB-H-T1-G
| step |  |  | Tier 4: 35(e) - MSB-2 (Bus METERED BUS) - DB-H-T1-G
| step |  |  | Tier 4: 35.1 - DB-H-T1-G - DB-H-T1-B1
| step |  |  | Tier 4: 36 - MSB-2 (Bus METERED BUS) - MSSB-B1-01
| step |  |  | Tier 4: 37 - MSB-2 (Bus METERED BUS) - TOB-T2-H-L29
| step |  |  | Tier 4: 38 - MSB-2 (Bus METERED BUS) - T2-LIFT-3
| step |  |  | Tier 4: 39 - MSB-2 (Bus METERED BUS) - MSSB-T2-03.01
| step |  |  | Tier 4: 40 - MSB-2 (Bus METERED BUS) - MSSB-T2-30.01
| step |  |  | Tier 4: 41 - MSB-2 (Bus METERED BUS) - MSSB-2.01
| step |  |  | Tier 4: 42 - MSB-2 (Bus UNMETERED BUS) - TOB-T2-L12
| step |  |  | Tier 4: 43 - MSB-2 (Bus UNMETERED BUS) - TOB-T2-L25
| step |  |  | Tier 4: 44 - MSB-2 (Bus UNMETERED BUS) - MSSB-2-01-AFL
| step |  |  | Tier 4: 45- MSB-2 (Bus UNMETERED BUS) - TOB-T2-M-L28
| step |  |  | Tier 4: 46 - MSB-2 (Bus UNMETERED BUS) - MP-B-01-EV
| step |  |  | Tier 4: 46(e) - MSB-2 (Bus UNMETERED BUS) - MP-B-01-EV
| step |  |  | Tier 4: 47 - MSB-2 (Bus UNMETERED BUS) - MP-B-02-EV
| step |  |  | Tier 4: 47(e) - MSB-2 (Bus UNMETERED BUS) - MP-B-02-EV
| step |  |  | Tier 4: 48 - MSB-2 (Bus UNMETERED BUS) - MP-B-03-EV
| step |  |  | Tier 4: 48(e) - MSB-2 (Bus UNMETERED BUS) - MP-B-03-EV
| step |  |  | Tier 4: 49 - MSB-1 (Bus LIFE SAFETY SERVICES) - LOADING DOCK LIFT
step
| step |  |  | Tier 2: DB Installation - (Top of Main Switch Only)
| step |  |  | Tier 3: Basement - Level 3
| step |  |  | Tier 4: Basement 1
| step |  |  | Tier 5: DB-H-T1-B1
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-B1-01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Ground
| step |  |  | Tier 5: FIP
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-H-T1-G
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-T-G-01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 01
| step |  |  | Tier 5: JOCKEY PUMP
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: TANK INDICATOR
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DIESEL PUMP
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: ELECTRIC PUMP
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-H-COMMS
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-H-DAS
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-H-T1-L1
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-T-L1-01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-T-L1-02
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-T-L1-03
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-T-L1-04
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 02
| step |  |  | Tier 5: LOADING DOCK LIFT
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-02.02
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-H-T1-L2
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-2-01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-2-01-AFL
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 03
| step |  |  | Tier 5: MSSB-T2-03-01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-H-T2-L3
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-T1-03.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: DB-H-T1-L3
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 3: TOWER 1
| step |  |  | Tier 4: Level 04
| step |  |  | Tier 5: MSSB-T1-L4.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 07
| step |  |  | Tier 5: DB-H-T1-L7
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-T1-L7.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 10
| step |  |  | Tier 5: MSSB-T1-L10.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 12
| step |  |  | Tier 5: DB-H-T1-L12
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 13
| step |  |  | Tier 5: MSSB-T1-L13.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 16
| step |  |  | Tier 5: MSSB-T1-L16.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 18
| step |  |  | Tier 5: DB-H-T1-L18
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 19
| step |  |  | Tier 5: MSSB-T1-L19.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 22
| step |  |  | Tier 5: MSSB-T1-L22.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 24
| step |  |  | Tier 5: DB-H-T1-L24
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 25
| step |  |  | Tier 5: MSSB-T1-L25.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 28
| step |  |  | Tier 5: MSSB-T1-L28.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 29
| step |  |  | Tier 5: DB-H-T1-L29
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 31
| step |  |  | Tier 5: MSSB-T1-31.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-T1-31.02
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: T1-LIFT-1
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: T1-LIFT-2
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: T1-LIFT-3
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 3: TOWER 2
| step |  |  | Tier 4: Level 04
| step |  |  | Tier 5: MSSB-T2-L4.05
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 07
| step |  |  | Tier 5: DB-H-T2-L7
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-T2-L7.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 10
| step |  |  | Tier 5: MSSB-T2-L10.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 13
| step |  |  | Tier 5: DB-H-T2-L13
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-T2-L13.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 16
| step |  |  | Tier 5: MSSB-T2-L16.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 18
| step |  |  | Tier 5: DB-H-T2-L18
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 19
| step |  |  | Tier 5: MSSB-T2-L19.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 22
| step |  |  | Tier 5: MSSB-T2-L22.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 24
| step |  |  | Tier 5: DB-H-T2-L24
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-T2-L24.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 28
| step |  |  | Tier 5: MSSB-T2-L28.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 29
| step |  |  | Tier 5: DB-H-T2-L29
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 4: Level 30
| step |  |  | Tier 5: MSSB-T2-30.01
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: MSSB-T2-30.02
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: T2-LIFT-1
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: T2-LIFT-2
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 5: T2-LIFT-3
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
| step |  |  | Tier 2: Meter Panel Installation - (Mount and connection to panel Isolator only)
| step |  |  | Tier 3: Basement - Level 3
| step |  |  | Tier 4: Basement 01
| step |  |  | Tier 5: MP-B-01-EV
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
step
| step |  |  | Tier 5: MP-B-02-EV
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Testing
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 01
| step |  |  | Tier 5: MP-RETAIL.01
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 3: TOWER 1
| step |  |  | Tier 4: Level 05
| step |  |  | Tier 5: MP-T1-L5
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 06
| step |  |  | Tier 5: MP-T1-L6
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 09
| step |  |  | Tier 5: MP-T1-L9
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 10
| step |  |  | Tier 5: MP-T1-L10
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 13
| step |  |  | Tier 5: MP-T1-L13
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 14
| step |  |  | Tier 5: MP-T1-L14
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 17
| step |  |  | Tier 5: MP-T1-L17
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 19
| step |  |  | Tier 5: MP-T1-L19
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 20
| step |  |  | Tier 5: MP-T1-L20
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 23
| step |  |  | Tier 5: MP-T1-L23
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 24
| step |  |  | Tier 5: MP-T1-L24
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 27
| step |  |  | Tier 5: MP-T1-L27
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 28
| step |  |  | Tier 5: MP-T1-L28
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 3: TOWER 2
| step |  |  | Tier 4: Level 04
| step |  |  | Tier 5: MP-T2-L4
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 06
| step |  |  | Tier 5: MP-T2-L6
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 08
| step |  |  | Tier 5: MP-T2-L8
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 10
| step |  |  | Tier 5: MP-T2-L10
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 12
| step |  |  | Tier 5: MP-T2-L12
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 14
| step |  |  | Tier 5: MP-T2-L14
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 17
| step |  |  | Tier 5: MP-T2-L17
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 19
| step |  |  | Tier 5: MP-T2-L19
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 21
| step |  |  | Tier 5: MP-T2-L21
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 23
| step |  |  | Tier 5: MP-T2-L23
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 25
| step |  |  | Tier 5: MP-T2-L25
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings
| step |  |  | Tier 4: Level 27
| step |  |  | Tier 5: MP-T2-L27
AE-ITCX-014 - Meter Panel Visual Inspection Checklist (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-014 - Visual Inspection
AE-ITCX-015 - Mandatory Test Results (Rev 1 +Names) | checklist |  |  | Tier 6: AE-ITCX-015 - Mandatory Test Result Sheet
AE-ITCX-010 - Torque Settings for Bolts (Rev 0 +Names) | checklist |  |  | Tier 6: AE-ITCX-010 - Torque Settings