## QA Folder
QA Folder Structure |  |  | EXPAND THESE OUT | Checklists
Site QA
Foundation Piles
Admin Zone
|  |  | FP1- FP92 | Foundation Pile ITP
Colo1
|  |  | FP93 - FP362 | Foundation Pile ITP
Colo3
|  |  | FP363 - FP632 | Foundation Pile ITP
Colo5
|  |  | FP633 - FP752 | Foundation Pile ITP
Outside Equipment Zone 5
|  |  | FP753 – FP832 | Foundation Pile ITP
Outside Equipment Zone 4
|  |  | FP833 – FP995 | Foundation Pile ITP
Outside Equipment Zone 3
|  |  | FP996 – FP1149 | Foundation Pile ITP
Outside Equipment Zone 1
|  |  | FP1150 – FP1203 | Foundation Pile ITP
Outside Equipment Zone 2
|  |  | FP1204 – FP1223 | Foundation Pile ITP
| Road Subbase & Concrete Road |  |  | FOLDER ONLY
| Bulk Earthwork Infill |  |  | FOLDER ONLY
| Trench & Backfill |  |  | FOLDER ONLY

## Checklists
type | name | values | prefix | postfix | usage count | user addable
checklist | Foundation Pile ITP
section | Documentation & Setout
checkpoint | Documentation
text | Drawing and Revision Number
checkpoint | Survey Set out – Check Position
section | Foundation Pile Information
checkpoint | Pile Diameter
text | Diameter (mm)
checkpoint | Approval of Socket
text | Designed Pile Socket Length (mm)
text | Actual Pile Socket Length (mm)
checkpoint | Pile Detials
text | Top of Steel RL (m)
text | Length of Pile (m)
text | Top of Concrete RL (m)
checkpoint | Check of excessive water in hole
section | Pile Reinforcement & Pre Pour
checkpoint | Reinforcement information
text | Main Bars (e.g 6N24)
text | Ligs (e.g N12-300)
text | Cage Length
label | Attach photos of pile reinforcement
checkpoint | Sign off Required
button | Engineer/Building Surveyor Sign off
checkpoint | Commencement of Pour – Ok to pour
button | Delta Group Representative Signed
button | Besix Watpac Representative Signed
section | Pile Concrete Placement
checkpoint | Date of Pour
text | Date:
checkpoint | Concrete Delivery Docket
text | Docket Number:
label | Attach photos of Concrete Dockets
checkpoint | Pile Concrete Details
text | Concrete Strength (MPA)
text | Cover (mm)
checkpoint | Mud Map (Indicate date and location)
label | Attach the Mud map
section | Pile Post Pour- Sign off
checkpoint | Post Pour requirement
text | Concrete Test Certificate number
text | 28 /56-day Concrete Compressive Strength (MPA)
label | Attach photos of Concrete Crack Test
checkpoint | Post Pour Signed off
button | Browns Piling Representative Signed
button | Delta Group Representative Signed
button | Besix Watpac Representative Signed
checklist | Bulk Earthwork Infill ITP
section | Documentation & Setout
checkpoint | Documentation
text | Drawing and Revision Number
checkpoint | Survey Set out – Check Position
section | Excavation Actvity Inspection
checkpoint | Removal of Unsuitable Spoil (Soft spot & nominal 300 from exsting surface
checkpoint | Stockpile to maximum 2m height
checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | RL (m)
checkpoint | Subgrade preparation of area is ok to receive fill
label | Attach photos of Subgrade
checkpoint | Commencement of Fill
button | Delta Group Representative Signed
button | Besix Watpac Representative Signed
section | Place infill Inspection
checkpoint | Top of Filling level
text | RL (m)
checkpoint | Thickness of Fill
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Mud Map (Indicate date and location)
label | Attach the Mud map
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
checklist | Trench Excavation & Backfill ITP
section | Documentation & Setout
checkpoint | Documentation
text | Drawing and Revision Number
checkpoint | Survey Set out – Check Position
section | Excavation Actvity Inspection
checkpoint | Removal of Unsuitable Spoil (Soft spot & nominal 300 from exsting surface
checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | RL (m)
checkpoint | Depth of Trench
text | (m)
checkpoint | Trench Protection Method
button | Protection Method | Sloping/Benching/Shoring
note | Attach photos of Protection Method
checkpoint | Subgrade preparation of area is ok to Backfill
note | Attach photos of Subgrade
checkpoint | Commencement of Backfill
button | Delta Group Representative Signed
button | Besix Watpac Representative Signed
section | Place Backfill Inspection
checkpoint | Top of Filling level
text | RL (m)
checkpoint | Thickness of Fill
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Mud Map (Indicate date and location)
label | Attach the Mud map
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
checklist | RP1- Rigid Pavement ITP
checklist | Rigid pavement - Light vehicle ITP
section | Documentation & Setout
checkpoint | Documentation
text | Drawing and Revision Number
checkpoint | Survey Set out – Check Position
section | Road Subgrade Inspection
checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | RL (m)
checkpoint | Thickness of Subgrade
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
label | Attach photos of Material Compact Report
section | Road Capping Layer Inspection
checkpoint | Top of Subbase Layer
text | RL (m)
checkpoint | Thickness of Subbase
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
section | Road Subbase Inspection Layer 1 (option)
checkpoint | Top of Subbase Layer
text | RL (m)
checkpoint | Thickness of Subbase
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
section | Road Concrete Pre Pour Inspection (Concrete Road Only)
checkpoint | Vapor Barrier Placed, Lapped and not pierced
checkpoint | Reinforcement Reuqirement
text | Cover (mm)
button | Steel Mesh Type | SL82/SL72/ Other
note | Attach photos of Reinforcement
checkpoint | Commencement of Pour
button | Delta Group Representative Signed
button | Besix Watpac Representative Signed
section | Road Concrete Placement (Concrete Road Only)
checkpoint | Thickness of Concrete
text | Thickness (mm)
checkpoint | Concrete Delivery Docket
text | Docket Number:
note | Attach photos of Concrete Dockets
checkpoint | Pile Concrete Details
button | Concrete Strength (MPA) | 32/40/other
text | Cover (mm)
checkpoint | Mud Map (Indicate date and location)
label | Attach the Mud map
section | Pile Post Pour- Sign off (Concrete Road Only)
checkpoint | Post Pour requirement
text | Concrete Test Certificate number
text | 28 /56-day Concrete Compressive Strength (MPA)
label | Attach photos of Concrete Crack Test
checkpoint | Post Pour Signed off
button | Browns Piling Representative Signed
button | Delta Group Representative Signed
button | Besix Watpac Representative Signed
checklist | Rigid Pavement - Concrete footpath ITP
section | Documentation & Setout
checkpoint | Documentation
text | Drawing and Revision Number
checkpoint | Survey Set out – Check Position
section | Road Subgrade Inspection
checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | RL (m)
checkpoint | Thickness of Subgrade
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
label | Attach photos of Material Compact Report
section | Road Subbase Inspection Layer 1 (option)
checkpoint | Top of Subbase Layer
text | RL (m)
checkpoint | Thickness of Subbase
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
section | Road Concrete Pre Pour Inspection (Concrete Road Only)
checkpoint | Vapor Barrier Placed, Lapped and not pierced
checkpoint | Reinforcement Reuqirement
text | Cover (mm)
button | Steel Mesh Type | SL82/SL72/ Other
note | Attach photos of Reinforcement
checkpoint | Commencement of Pour
button | Delta Group Representative Signed
button | Besix Watpac Representative Signed
section | Road Concrete Placement (Concrete Road Only)
checkpoint | Thickness of Concrete
text | Thickness (mm)
checkpoint | Concrete Delivery Docket
text | Docket Number:
note | Attach photos of Concrete Dockets
checkpoint | Pile Concrete Details
button | Concrete Strength (MPA) | 32/40/other
text | Cover (mm)
checkpoint | Mud Map (Indicate date and location)
label | Attach the Mud map
section | Pile Post Pour- Sign off (Concrete Road Only)
checkpoint | Post Pour requirement
text | Concrete Test Certificate number
text | 28 /56-day Concrete Compressive Strength (MPA)
label | Attach photos of Concrete Crack Test
checkpoint | Post Pour Signed off
button | Browns Piling Representative Signed
button | Delta Group Representative Signed
button | Besix Watpac Representative Signed
checklist | Unsealed Hardstands
section | Documentation & Setout
checkpoint | Documentation
text | Drawing and Revision Number
checkpoint | Survey Set out – Check Position
section | Road Subgrade Inspection
checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | RL (m)
checkpoint | Thickness of Subgrade
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
label | Attach photos of Material Compact Report
section | Road Capping Layer Inspection
checkpoint | Top of Subbase Layer
text | RL (m)
checkpoint | Thickness of Subbase
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
section | Road Subbase Inspection Layer 1 (option)
checkpoint | Top of Subbase Layer
text | RL (m)
checkpoint | Thickness of Subbase
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
section | Road Subbase Inspection Layer 2 (option)
checkpoint | Top of Subbase Layer
text | RL (m)
checkpoint | Thickness of Subbase
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
checklist | Gravel Pathway
checklist | Switchyard Pavement
checklist | Switchyard Unsealed access pavement
section | Documentation & Setout
checkpoint | Documentation
text | Drawing and Revision Number
checkpoint | Survey Set out – Check Position
section | Road Subgrade Inspection
checkpoint | Top of Subgrade Level (Bulk Excavation Level)
text | RL (m)
checkpoint | Thickness of Subgrade
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
label | Attach photos of Material Compact Report
section | Road Subbase Inspection Layer 1 (option)
checkpoint | Top of Subbase Layer
text | RL (m)
checkpoint | Thickness of Subbase
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report
section | Road Subbase Inspection Layer 2 (option)
checkpoint | Top of Subbase Layer
text | RL (m)
checkpoint | Thickness of Subbase
text | Thickness (mm)
label | Attach photos of Subgrade
checkpoint | Material Requirement
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Material Compact Test Report
button | Subbase Material | Class 1/2/3/4/A, other
button | Compaction Method | Standard/ Modified
text | Minimum Dry Density Ratio (%)
checkpoint | Compact Material Test
label | Attach photos of Material Compact Report