## QA Folder Structure
QA Folder Structure |  |  |  | Checklists
Manufacturing / Off-site QA
Site QA
Area 01
Shop Drawing - SKP-MOR-002
|  |  | A1S-20 | ONSITE - Installation of Facade System
|  |  | A1S-73 | ONSITE - Installation of Facade System
|  |  | A1S-91 | ONSITE - Installation of Facade System
|  |  | A1S-100 | ONSITE - Installation of Facade System
|  |  | A1S-118 | ONSITE - Installation of Facade System
|  |  | A1S-132 | ONSITE - Installation of Facade System
|  |  | A1S-143 | ONSITE - Installation of Facade System
|  |  | A1S-167 | ONSITE - Installation of Facade System
|  |  | A1S-178 | ONSITE - Installation of Facade System
|  |  | A1S-187 | ONSITE - Installation of Facade System
Shop Drawing - SKP-MOR-003
|  |  | A1S-103 | ONSITE - Installation of Facade System
|  |  | A1S-111 | ONSITE - Installation of Facade System
|  |  | A1S-193 | ONSITE - Installation of Facade System
|  |  | A1S-194 | ONSITE - Installation of Facade System
|  |  | A1S-204 | ONSITE - Installation of Facade System
|  |  | A1S-210 | ONSITE - Installation of Facade System
|  |  | A1S-217 | ONSITE - Installation of Facade System
|  |  | A1B-27 | ONSITE - Installation of Facade System
|  |  | A1B-44 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-004 | A1S-225 | ONSITE - Installation of Facade System
|  |  | A1S-321 | ONSITE - Installation of Facade System
|  |  | A1B-160 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-005 | A1S-05 | ONSITE - Installation of Facade System
|  |  | A1S-19 | ONSITE - Installation of Facade System
|  |  | A1S-30 | ONSITE - Installation of Facade System
|  |  | A1S-40 | ONSITE - Installation of Facade System
|  |  | A1S-65 | ONSITE - Installation of Facade System
|  |  | A1S-119 | ONSITE - Installation of Facade System
|  |  | A1S-133 | ONSITE - Installation of Facade System
|  |  | A1S-144 | ONSITE - Installation of Facade System
|  |  | A1S-154 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-006 | A1B-08 | ONSITE - Installation of Facade System
|  |  | A1B-64 | ONSITE - Installation of Facade System
|  |  | A1B-79 | ONSITE - Installation of Facade System
|  |  | A1B-103 | ONSITE - Installation of Facade System
|  |  | A1B-113 | ONSITE - Installation of Facade System
|  |  | A1B-117 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-007 | A1S-162 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-008 | A1S-74 | ONSITE - Installation of Facade System
Area 02
|  | Shop Drawing - SKP-MOR-010 | A2S-08 | ONSITE - Installation of Facade System
|  |  | A2S-13 | ONSITE - Installation of Facade System
|  |  | A2S-10 | ONSITE - Installation of Facade System
|  |  | A2S-22 | ONSITE - Installation of Facade System
|  |  | A2S-31 | ONSITE - Installation of Facade System
|  |  | A2S-38 | ONSITE - Installation of Facade System
|  |  | A2S-45 | ONSITE - Installation of Facade System
|  |  | A2S-68 | ONSITE - Installation of Facade System
|  |  | A2S-81 | ONSITE - Installation of Facade System
|  |  | A2S-95 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-011 | A2S-107 | ONSITE - Installation of Facade System
|  |  | A2S-114 | ONSITE - Installation of Facade System
|  |  | A2S-134 | ONSITE - Installation of Facade System
|  |  | A2S-144 | ONSITE - Installation of Facade System
|  |  | A2S-155 | ONSITE - Installation of Facade System
|  |  | A2S-164 | ONSITE - Installation of Facade System
|  |  | A2S-168 | ONSITE - Installation of Facade System
|  |  | A2S-175 | ONSITE - Installation of Facade System
|  |  | A2S-187 | ONSITE - Installation of Facade System
|  |  | A2S-203 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-012 | A2S-219 | ONSITE - Installation of Facade System
|  |  | A2S-220 | ONSITE - Installation of Facade System
|  |  | A2S-221 | ONSITE - Installation of Facade System
|  |  | A2S-238 | ONSITE - Installation of Facade System
|  |  | A2S-239 | ONSITE - Installation of Facade System
|  |  | A2S-256 | ONSITE - Installation of Facade System
|  |  | A2S-264 | ONSITE - Installation of Facade System
|  |  | A2S-265 | ONSITE - Installation of Facade System
|  |  | A2S-282 | ONSITE - Installation of Facade System
|  |  | A2S-283 | ONSITE - Installation of Facade System
|  |  | A2S-302 | ONSITE - Installation of Facade System
|  |  | A2S-303 | ONSITE - Installation of Facade System
Area 03
|  | Shop Drawing - SKP-MOR-015 | A3S-04 | ONSITE - Installation of Facade System
|  |  | A3S-15 | ONSITE - Installation of Facade System
|  |  | A3S-30 | ONSITE - Installation of Facade System
|  |  | A3S-39 | ONSITE - Installation of Facade System
|  |  | A3S-50 | ONSITE - Installation of Facade System
|  |  | A3S-55 | ONSITE - Installation of Facade System
|  |  | A3S-60 | ONSITE - Installation of Facade System
|  |  | A3S-61 | ONSITE - Installation of Facade System
|  |  | A3S-70 | ONSITE - Installation of Facade System
|  |  | A3S-71 | ONSITE - Installation of Facade System
|  |  | A3BL-02 | ONSITE - Installation of Facade System
|  |  | A3BL-10 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-016 | A3S-78 | ONSITE - Installation of Facade System
|  |  | A3S-91 | ONSITE - Installation of Facade System
|  |  | A3S-92 | ONSITE - Installation of Facade System
|  |  | A3S-114 | ONSITE - Installation of Facade System
|  |  | A3S-115 | ONSITE - Installation of Facade System
|  |  | A3S-130 | ONSITE - Installation of Facade System
|  |  | A3S-142 | ONSITE - Installation of Facade System
|  |  | A3S-143 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-017 | A3S-05 | ONSITE - Installation of Facade System
Area 04
|  | Shop Drawing - SKP-MOR-019 | A4B-02 | ONSITE - Installation of Facade System
|  |  | A4B-05 | ONSITE - Installation of Facade System
|  |  | A4B-08 | ONSITE - Installation of Facade System
|  |  | A4B-15 | ONSITE - Installation of Facade System
|  |  | A4B-26 | ONSITE - Installation of Facade System
|  |  | A4B-28 | ONSITE - Installation of Facade System
|  |  | A4B-34 | ONSITE - Installation of Facade System
|  |  | A4B-41 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-020 | A4B-44 | ONSITE - Installation of Facade System
|  |  | A4B-50 | ONSITE - Installation of Facade System
|  |  | A4B-54 | ONSITE - Installation of Facade System
|  |  | A4B-57 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-021 | A4B-64 | ONSITE - Installation of Facade System
|  |  | A4B-76 | ONSITE - Installation of Facade System
|  |  | A4B-83 | ONSITE - Installation of Facade System
|  |  | A4G-04 | ONSITE - Installation of Facade System
|  |  | A4G-15 | ONSITE - Installation of Facade System
|  |  | A4G-32 | ONSITE - Installation of Facade System
|  |  | A4G-39 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-022 | A4B-89 | ONSITE - Installation of Facade System
|  |  | A4B-94 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-023 | A4B-63 | ONSITE - Installation of Facade System
Area 05
|  | Shop Drawing - SKP-MOR-025 | A5P-12 | ONSITE - Installation of Facade System
|  |  | A5P-38 | ONSITE - Installation of Facade System
|  |  | A5P-51 | ONSITE - Installation of Facade System
|  |  | A5P-56 | ONSITE - Installation of Facade System
|  |  | A5P-71 | ONSITE - Installation of Facade System
|  |  | A5P-76 | ONSITE - Installation of Facade System
|  |  | A5P-81 | ONSITE - Installation of Facade System
|  |  | A5P-91 | ONSITE - Installation of Facade System
|  |  | A5P-59 | ONSITE - Installation of Facade System
|  |  | A5P-122 | ONSITE - Installation of Facade System
|  |  | A5P-133 | ONSITE - Installation of Facade System
|  |  | A5P-144 | ONSITE - Installation of Facade System
|  |  | A5P-165 | ONSITE - Installation of Facade System
|  |  | A5P-282 | ONSITE - Installation of Facade System
|  |  | A5P-283 | ONSITE - Installation of Facade System
|  |  | A5P-300 | ONSITE - Installation of Facade System
|  |  | A5P-301 | ONSITE - Installation of Facade System
|  |  | A5P-324 | ONSITE - Installation of Facade System
|  |  | A5P-333 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-026 | A5P-187 | ONSITE - Installation of Facade System
|  |  | A5P-247 | ONSITE - Installation of Facade System
|  |  | A5P-310 | ONSITE - Installation of Facade System
|  |  | A5P-313 | ONSITE - Installation of Facade System
|  |  | A5P-324 | ONSITE - Installation of Facade System
|  |  | A5P-333 | ONSITE - Installation of Facade System
|  |  | A5P-346 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-027 | A5P-07 | ONSITE - Installation of Facade System
|  |  | A5P-24 | ONSITE - Installation of Facade System
|  |  | A5P-39 | ONSITE - Installation of Facade System
|  |  | A5P-98 | ONSITE - Installation of Facade System
|  |  | A5P-108 | ONSITE - Installation of Facade System
|  |  | A5P-166 | ONSITE - Installation of Facade System
|  |  | A5P-183 | ONSITE - Installation of Facade System
|  |  | A5P-215 | ONSITE - Installation of Facade System
|  |  | A5P-219 | ONSITE - Installation of Facade System
|  |  | A5P-239 | ONSITE - Installation of Facade System
|  |  | A5P-248 | ONSITE - Installation of Facade System
|  |  | A5P-265 | ONSITE - Installation of Facade System
Area 06
|  | Shop Drawing - SKP-MOR-033 | A6P-04 | ONSITE - Installation of Facade System
|  |  | A6P-15 | ONSITE - Installation of Facade System
|  |  | A6P-18 | ONSITE - Installation of Facade System
|  |  | A6P-25 | ONSITE - Installation of Facade System
|  |  | A6P-34 | ONSITE - Installation of Facade System
|  |  | A6P-41 | ONSITE - Installation of Facade System
|  |  | A6P-48 | ONSITE - Installation of Facade System
|  |  | A6P-70 | ONSITE - Installation of Facade System
|  |  | A6P-79 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-034 | A6P-59 | ONSITE - Installation of Facade System
|  |  | A6P-60 | ONSITE - Installation of Facade System
|  |  | A6P-88 | ONSITE - Installation of Facade System
|  |  | A6P-94 | ONSITE - Installation of Facade System
|  |  | A6P-101 | ONSITE - Installation of Facade System
|  |  | A6P-105 | ONSITE - Installation of Facade System
|  |  | A6P-111 | ONSITE - Installation of Facade System
|  |  | A6P-118 | ONSITE - Installation of Facade System
|  |  | A6P-124 | ONSITE - Installation of Facade System
|  |  | A6P-127 | ONSITE - Installation of Facade System
|  |  | A6P-140 | ONSITE - Installation of Facade System
|  |  | A6P-143 | ONSITE - Installation of Facade System
|  |  | A6P-157 | ONSITE - Installation of Facade System
|  |  | A6P-164 | ONSITE - Installation of Facade System
|  |  | A6P-173 | ONSITE - Installation of Facade System
|  |  | A6P-183 | ONSITE - Installation of Facade System
|  |  | A6P-190 | ONSITE - Installation of Facade System
|  |  | A6P-200 | ONSITE - Installation of Facade System
|  |  | A6P-213 | ONSITE - Installation of Facade System
|  |  | A6P-214 | ONSITE - Installation of Facade System
|  |  | A6P-236 | ONSITE - Installation of Facade System
|  |  | A6P-313 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-035 | A6P-230 | ONSITE - Installation of Facade System
|  |  | A6P-249 | ONSITE - Installation of Facade System
|  |  | A6P-269 | ONSITE - Installation of Facade System
|  |  | A6P-288 | ONSITE - Installation of Facade System
|  |  | A6P-301 | ONSITE - Installation of Facade System
|  |  | A6P-326 | ONSITE - Installation of Facade System
|  |  | A6P-337 | ONSITE - Installation of Facade System
|  | Shop Drawing - SKP-MOR-036 | A6P-352 | ONSITE - Installation of Facade System
|  |  | A6P-363 | ONSITE - Installation of Facade System
|  |  | A6P-371 | ONSITE - Installation of Facade System
|  |  | A6P-382 | ONSITE - Installation of Facade System
|  |  | A6P-356 | ONSITE - Installation of Facade System

## ITPs Checklists
type | name | values
checklist | OFFSITE - Fabrication of 3mm Solid Vitradual Checklist
section | Pre-fabrication
checkpoint | Ensure CNC machine operator daily checklist has been undertaken
checkpoint | Nest summary and site drawings provided by programmer, file number printed on paperwork corresponds with file programmed in CNC
checkpoint | Check currency of Drawings and Approved
checkpoint | Check Mondoclad 3mm pre-finished sheet is selected.
label | Insert photo of inkjet writing on back of sheet showing product, colour and batch number
checkpoint | Colour and sheet size corresponds with fabrication drawings and nesting.
checkpoint | Sheets are not bent, scratched or damaged before placing on CNC table
checkpoint | No metal filings located on CNC table or sheets prior to placing sheet on bed. Compressed air used to remove any debris
section | Machining
checkpoint | Fluid levels, suction pressures and functions are optimum. Correct tooling is selected and utilized
checkpoint | Panel numbers engraved into back of panel correspond with file numbers and fabrication drawings
label | Insert photo of QA panel showing engraving to back of sheet
checkpoint | Corresponding bracket sizes are written on back of panel as per fabrication drawings
checkpoint | Panels are checked off as machined once machining has terminated
checkpoint | Panels stacked neatly on edge on A frame back to back - face to face.
section | Fabrication
checkpoint | Correct tooling used to fold edges of panels. Panel returns folded neatly and square
checkpoint | Panel cleaned of any excess cutting lubricant or foreign debris. Back of panel is clean
checkpoint | Correct sized mill finished aluminum 6063 -T5 1.6mm 'Z' brackets run full length of folds and finish no more than 30mm from edge of panel. Correctly positioned perimeter Z bracket
checkpoint | Silicon Based adhesive used to adhere stiffeners to back of panel.
checkpoint | Z' brackets fixed to folded returns via #5 Aluminum 5052 Rivets (Hobson - 4mm diameter) at no greater than 300mm centers. Correctly fixed perimeter Z bracket
checkpoint | Correct Mill finished aluminum stiffeners selected 40x20x3 RHS 6060-T5 or 40x40x3 RHS 6060-T5
checkpoint | Stiffeners cut to length to fit neatly between 'Z' brackets. Neat fitting stiffener in correct position fixed to perimeter 'Z' brackets via 40x3 EA and 5052 no.5 rivets
label | Insert photo of completed panel showing stiffener spacings (use tape measure) and general arrangement.
section | Packing
checkpoint | Panels stacked neatly back to back - face to face with protective foam placed between panel faces for transport
checkpoint | Ensure panel numbers are marked off as complete
checkpoint | Panels are secured and wrapped ready for transport
label | Insert Photo of Load
checkpoint | Remove rubbish from work area. Clean workshop for next shift
checklist | ONSITE - Installation of Facade System
section | Pre-constructions and Removal of existing ACP and top hat framing.
checkpoint | Existing condition of surrounding surfaces and finished is documented and photo evidence is obtained and emailed through to Skypanel Management
label | Insert photos of existing surfaces to show general conditions
checkpoint | Removal of sealant in a safe manner, place into bin/bags for disposal and tidy work area.
checkpoint | Removal of composite panels in a safe manner from facade, move to lay down area and secure ensuring work area kept tidy
checkpoint | Removed composite panels stacked neatly and securely strapped within the perimeter of pallets in manner suitable for lifting with a forklift to be transported to recyclers on flatbed truck
label | Insert Photos of packed and strapped palletised panels
section | Assessment of Structure and Aluminium Framing Installation
checkpoint | Visually check existing structure for condition. Identify any visible cracked welds, missing fixtures and connections and take photo graphic evidence
checkpoint | Identify existing structure. Capture images with tape measure showing type, size, spans, centers and connections at selected locations
label | Insert Photos showing member sizing, spans, centers & connections at selected locations and general structure at location.
checkpoint | Refer to design documents to ensure tophat span design sizes are not going to be exceeded for the project. High wind zones within 2m of corner tophat spans not to exceed 900mm for 30mm tophat and 1200mm for 40mm tophat
checkpoint | Ensure mill finished aluminium extrusion are utilized as per Jabin Tophat Design Report, Spans do not exceed 1200mm for 30mm & 40mm primary framing where at center zones. 30mm tophat not to span greater than 900mm when at corner zones (within 2m of corners as indicated on shop drawings)
checkpoint | Check fixings types of aluminium subframe into structure: Fixings to be stainless steel. Fixings into concrete to be galvanised M6 Iccons Thunderbolt Pro 75mm anchors
checkpoint | Ensure aluminium frames setout reflects shop drawing setout are installed plumb, level and are packed to suit existing build out as required with aluminium packers
checkpoint | Prior to commencement of cladding installation: Ensure other services are complete: Ensure all framing requirements are met
label | Insert Photos showing completed aluminum framing with components identified showing spans, tophat sizes, fixings at selected locations
section | Installation of 3mm Mondoclad Cladding
checkpoint | Ensure cladding material and colour is correct by referencing shop drawings - Mondoclad 3mm solid aluminum
checkpoint | Ensure appropriate stiffeners are located in back of panel as per Jabin Design documents & Skypanel Shop drawings
checkpoint | Ensure specific stiffener details are achieved as noted in corner situations i.e. Area 01 high wind corner stiffener support connection
checkpoint | Ensure 3mm aluminum mill finished angles are installed with adhesive to the back of panels to support all corner folds as per Jabin documents
checkpoint | Ensure rivet fixing of Z bracket to panel return edges spaced no more than 300mm apart
checkpoint | Ensure panels are defect free with no scratches and dents
checkpoint | Install cladding panels by mechanically fixing through overlapping 'Z' brackets to tophat support framing with 12ga bimetal SDS screws at nominated fixing centers.
checkpoint | Ensure all panels are installed in the same direction as indicated on the protective film
checkpoint | Ensure panel joints are no larger than 20mm wide with tolerance of +/- 2mm per panel
checkpoint | Ensure panels are installed plumb, square and true, and within Skypanel tolerances
checkpoint | Ensure panels are installed in correct positions by checking engraving on back of sheet corresponds with position on shop drawings
label | Insert Photos of installed panel, panel widths, junctions, 12ga bi metal screws and fixing centers at selected locations
holdpoint | Hold Point - Approval of cladding installation required by Duratec and sign off defect free prior to scaffold drop/demobilisation.
section | Caulking of panels
checkpoint | Ensure 22mm open cell backing rod is applied correctly
checkpoint | Ensure Black Admil Prosil 41LM sealant is installed correctly and consistently. Min depth of sealant to be 8mm
checkpoint | Ensure all penetrations are caulked
checkpoint | Ensure plastic film is removed and caulking and glue residues are properly cleaned from cladding surface
label | Insert photos of sealed panels at selected locations
holdpoint | Hold Point - Approval of caulking required by Duratec before demobilising from area
checklist-flat | Documentation & SWMS
checkpoint | Ensure shop drawings and design documents are approved, current and up to date
checkpoint | Ensure SWMS have been submitted, approved and signed onto by all employers prior to undertaking any works
checklist-flat | Drawing Upload & Access
checkpoint | Ensure safest access method is selected and utilized, ensuring scaffold is signed off as complete and EWP/plant daily pre starts are undertaken and documented
checkpoint | Check dimensions nominated on shop drawings match the dimensions onsite with regard to existing cladding to be removed and replaced