## ITP Cover Page
Kerb & Channel Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 020-001 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 020-001
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Issued for construction
ITP Description: |  |  | Kerb & Channel |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 2-32735.02-WSP-DR-UDL; 2-32735.02-WSP-DR-RSA
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification: 26.7 Kerb and Channel
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-12 |  | Joshua Fraser |  | For approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Issued for construction | 2024-11-29 |  | Rex Humpherson |  | NTC-0336 |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM
Downer QM |  | CORDELIA GIRDLER-BROWN | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Kerb & Channel
Kerb & Channel Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 020-001 - Rev 1
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
3.1 | MATERIAL APPROVALS: Imported Material Testing - AP40 - BASECOURSE FOR KERB PREP - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS -
3.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | < 10% fines passing 2.36mm under a load of minimum of 100kN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.2 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB or CA | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.3 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Fitting within standard AP40 grading curve | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
SECTION 4 – KERB & CHANNEL PREPARATION - INCLUDED IN PAVEMENT ITP
4.1 | VERTICAL KERB & CHANNEL, SEMI MOUNTABLE KERB & CHANNEL, SEMI MOUNTABLE KERB, AND MOUNTABLE KERB & CHANNEL
4.1.1 | Pre-pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | PS21.7.6 | Kerb construction record | Before every pour | I | SE
4.1.2 | Concrete | 17.5 Mpa Concrete | Delivery Dockets | PS 26.7.3 | Concrete Delivery dockets and concrete test results | During construction - Every pour | I | SE
4.1.3 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | PS 27.4.5 | Post Pour Checksheet | After pour | I | SE |  |  | This superseeds 27.4.5 (d) in the project specification
4.1.4 | Final Finish | Slip form kerb and channel | Slip form kerb and channel | PS 26.7.3 | Post Pour Checksheet | After pour | I | SE
SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1 | Final Inspection | Final inspection of all concrete work. | All works meet project specifications and standards. | NZTA P39: 2013 | Final inspection report | 100% of works | HP | ENG
5.2 | As-Builts | Final inspection of all concrete work. | All works meet project specifications and standards. | PS 16.7.6 | Redpen markups | Completion of works | D | SV

## ITP Cover page - Paths, pads &I
Shared Paths, Maintenance Pads & Traffic Islands - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 020-002 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project | [5 empty] | ITP Number: |  |  | 020-002
Project Number: |  |  | DN1210 | [5 empty] | ITP Status: |  |  | Issued for construction
ITP Description: |  |  | Concrete - Footpaths, Pads and Islands | [5 empty] | Revision: | 1000 |  | 1
Contract Number: |  |  | NZTA 8287 | [5 empty] | Drawing Sets: |  |  | 2-32735.02-WSP-DR-UDL; 2-32735.02-WSP-DR-RSA
Customer: |  |  | Waka Kotahi | [5 empty] | Specification: |  |  | Project Specification: 27.4 Hard Landscaping
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [10 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-12 |  | Joshua Fraser |  | For approval |  |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[11 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Issued for construction | 2024-11-29 |  | Rex Humpherson |  | NTC-0336 |  |  |  |  | C | Check |  | PD | Project Director
[11 empty] | D | Dimension Inspection |  | PM | Project Manager
[11 empty] | E | Examine |  | OP | Operations Manager
[11 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[11 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[11 empty] | I | Inspection |  | PE | Project Engineer
[11 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[11 empty] | O | Operation |  | QE | Quality Engineer
[11 empty] | R | Review |  | SUP | Superintendent / Supervisor
[11 empty] | S | Subcontractor |  | SV | Surveyor
[11 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[11 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [8 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: |  | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [6 empty] | Downer PM
Downer QM |  | CORDELIA GIRDLER-BROWN | [6 empty] | Downer QM
Client (If Applicable) | [8 empty] | Client (If Applicable)

## Paths, Pads & Islands
Shared Paths, Maintenance Pads and Traffic Islands Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 020-002 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
1.1 | MATERIAL APPROVALS: Imported Material Testing - AP65-2 Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | Minimum soaked CBR of 25% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 63.0mm 100% passing 37.5mm 68-90% passing 19.0mm 42-76% passing 9.5mm 26-58% passing 4.75mm 16-44% passing 2.36mm 10-33% passing 1.18mm 6-24% passing 0.425mm 3-14% passing 0.075mm 1-6% passing | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.1.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.1.6 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >25 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.7 | Clay Index | NZS4407:2015, Test 3.5 - Clay Index Test Report | Report Value Only | NZS4407:2015 Test 3.5 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wksbefore importing | HP | ENG
1.2 | MATERIAL APPROVALS: Imported Material Testing - AP40-1 - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.2.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN Minimum | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | Minimum soaked CBR of 25% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Sieve Size % Passing 37.5mm 100% passing 19.0mm 60-75% passing 9.5mm 37-50% passing 4.75mm 20-35% passing 2.36mm 12-28% passing 1.18mm 9-20% passing 0.600mm 7-12% Passing 0.300mm 3-10% Passing 0.150mm 0-5% passing 0.075mm 0-5% passing | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.2.6 | Plasticity Index | NZS4407:2015, Test 3.2 Cone Penetration NZS4407:2015, Test 3.4 Plasticity Index | <30 <8 | NZS4407:2015 Test 3.2 NZS4407:2015 Test 3.3 NZS4407:2015 Test 3.4 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.7 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >40 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.8 | Clay Index | NZS4407:2015, Test 3.5 - Clay Index Test Report | Report Value Only | NZS4407:2015 Test 3.5 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wksbefore importing | HP | ENG
1.3 | MATERIAL APPROVALS: Imported Material Testing - AP20 - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.3.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.2 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB or CA | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.3 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Fitting within standard AP20 grading curve | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.3.4 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.4 | SAMPLE PANEL (1000mx1000m) FOR EXPOSED AGGREGATE
1.4.1 | Sample panel (1000 x1000mm) | Contractor to provide a sample panel (1000 x1000mm) of the exposed aggregate specified finish before commencing work | To NZS 3121:2015, use crushed aggregates or rounded coarse gravels for exposing. Allow a mixture of nominal 10-20mm aggregates consisting of a mixture of grey, black and brown colour tones that represent a riverbed, Autumn or Sunrise mixes. Mix design to be confirmed by the Engineer | Project Specifications 27.4.5.e | Visual Inspection | 1 Sample Panel | HP | ENG
1.4.2 | slip resistance | Test sample to comply with NZBC D1/VM1, NZBC D1/AS1 | Level access routes: 2.0 Slip resistance for ramps :3.14 | Project Specifications 27.4.5.e AS/NZS 4586:2013 | British Pendulums | 1 Test | HP | ENG
SECTION 2 - CONSTRUCTION - PREP GENERAL
2.1 | SUBGRADE
2.1.1 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa CBR: >7 Single Test Min SU: >50kPa | Appendix XVIII | Shear Vane Report | 4 test per 400M2 | I | SE
2.1.2 | Cut Subgrade Testing - Granular Soil Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 3 blows per 100mm penetration | Appendix XVIII | Scala Report | 4 test per 400M2 | I | SE
2.1.3 | Proof Roll Subgrade | Visual Inspection of Proof Roll | Visual Inspection | Appendix XVIII | Visual Site Record | Across Finished Area | I | SE
2.1.4 | Final Subgrade Heights | Excavated to the required subgrade level | Using survey pegs as hights and placement. Measure from stringline for depth. Tolerances as follow Vertical: -25mm +5mm | drawings 232735.02-WSP-DR-UDL-0405,406 -TNZ B/02: 2005 | String Check Sheet or Equivalent | Every 15m | D | SE
2.2 | SUBBASE
2.2.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface is below 225mm. | -0mm + 20mm | Standard | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
2.2.2 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | Standard | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
2.3 | BASECOURSE
2.3.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface is below 125mm from finished height. | -0mm + 20mm | Standard | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
2.3.2 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | Standard | IANZ Accredited Report | 1 set (5 tests) 1000m2 | I | SE
SECTION 3 - MAINTENANCE PADS AND SHARED PATHS
3.1 | SUBGRADE
3.1.1 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa CBR: <7 Single Test Min SU: >50kPa | Appendix XVIII | Shear Vane Report | 1 test per 100M2 | I | SE
3.1.2 | Cut Subgrade Testing - Granular Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 3 blows per 100mm penetration | Appendix XVIII | Scala Report | 4 test per 400M2 | I | SE
3.1.3 | Proof Roll Subgrade | Visual Inspection of Proof Roll | Visual Inspection | Appendix XVIII | Visual Site Record | Across Finished Area | I | SE
3.2 | SUBBASE
3.2.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface 225mm Below From Finish Height | -0mm + 20mm | Standard | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
3.2.2 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Min CIV 18 Ave CIV 20 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
3.2.3 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | Standard | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE
3.3 | BASECOURSE
3.3.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | -0mm + 20mm | Standard | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
3.3.2 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Min CIV 18 Ave CIV 20 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
3.3.3 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | Standard | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE
3.4 | FORMWORK
3.4.1 | Surveyor check | Equivalent to check the position of the formwork | +\- 100mm of design | NZS 3109:1997 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
3.4.2 | Surveyor check | Equivalent to check finished height of framework | +\- 10mm of design | NZS 3109:1997 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
3.5 | REINFORCING MESH
3.5.1 | Reinforcing Mesh Check | Ensure the right mesh | 665 Reinforcing mesh | Project Specifications 27.4.2 | Dockets | Measurements | C | SE
3.5.2 | Reinforcing Mesh Check | Ensure that overlap and clearince from edges | 666 Reinforcing mesh | NZS 3109 | photos | Measurements | C | SE
3.6 | CONCRETE
3.6.1 | Concrete | 20.0 MPA concrete. 4kg/m3 black oxide (2.5%) | 28 days concrete strength test of 20MPA | 232735.02-WSP-DR-UDL 0405 | Concrete Delivery dockets | During construction | I | SE
3.6.2 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | PS 27.4.5 | Post Pour Checksheet | After pour | I | SE |  |  | This superseeds 27.4.5 (d) in the project specification
3.6.3 | Final Finish | Finish to be either: - Rough broom finish -Exposed aggregate finish | U5, U5E | 232735.02-WSP-DR-UDL 0405 | Post Pour Checksheet | After pour | I | SE
3.6.4 | Slip Resistance | British Pendulum testing | Level surface: mean coefficient of friction (µ) not less than 0.4. Slopping surface: mean coefficient of friction (µ) not less than 0.4 + 0.0125S (S = slope of surface expressed as a percentage). | Project Specifications 27.4.5.e AS/NZS 4586:2013 | Britsh Pendulum Test Results | Every 20m | I | SE
SECTION 4 - TRAFFIC ISLAND INFILL
4.1 | BASECOURSE
4.1.1 | Stringlines or equivalent | Stringlines or equivalent to check finished height of surface | -0mm + 20mm | NZTA B/06 8.2.2 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.1.2 | Compaction - Clegg | ASTM D5874-16:2016 Clegg Hammer Testing | Min CIV 18 Ave CIV 20 | Appendix XVIII | Clegg Hammer Report | 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift | I | SE
4.1.3 | Compaction - NDM | NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode) | Ave >95% of MDD Min >92% of MDD | Standard | IANZ Accredited Report | 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed | I | SE
4.2 | CONCRETE
4.2.1 | Concrete | 2.5% black oxide by weight of cement | 28 days concrete strength test of 20MPA | PS 27.4.6 | Concrete Delivery dockets | During construction | I | SE
4.2.2 | Final Finish | U3 Finish | U3 Finish | PS 27.4.6 | Post Pour Checksheet | After pour | I | SE
SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1 | Final Inspection | Final inspection of all concrete work. | All works meet project specifications and standards. | NZTA P39: 2013 | Final inspection report | 100% of works | HP | ENG
5.2 | As-Builts | Final inspection of all concrete work. Red Pen Mark up | All works meet project specifications and standards. | PS 16.7.6 | Red Pen Markup | Whole Work | D | SV

## ITP Cover Page - Roundabout
Roundabout Apron & Riverstones - Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 020-003 - Rev 1
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 020-003
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Issued for construction
ITP Description: |  |  | Roundabout |  |  |  |  | Revision: | 1000 |  | 1
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 2-32735.02-WSP-DR-UDL; 2-32735.02-WSP-DR-RSA
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification: 26.7 Kerb and Channel, 27.4 Hard Landscaping
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | 2024-11-12 |  | Joshua Fraser |  | For approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
1 | Issued for construction | 2024-11-29 |  | Rex Humpherson |  | NTC-0336 |  |  |  | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM
Downer QM |  | CORDELIA GIRDLER-BROWN | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## Roundabout
Roundabout Apron & Riverstones Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 020-003 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
1.1 | MATERIAL APPROVALS: Imported Material Testing - GAP65 - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS | [12 empty] | Final
1.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >25% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Fitting within standard GAP 65 grading curve | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.1.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.1.6 | Plasticity Index | NZS4407:2015, Test 3.2 Cone Penetration NZS4407:2015, Test 3.3 Plastic Limit NZS4407:2015, Test 3.4 Plasticity Index | NP | NZS4407:2015 Test 3.2 NZS4407:2015 Test 3.3 NZS4407:2015 Test 3.4 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.7 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >25 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.1.8 | Clay Index | NZS4407:2015, Test 3.5 - Clay Index Test Report | Report Value Only | NZS4407:2015 Test 3.5 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2 | MATERIAL APPROVALS: Imported Material Testing - AP40-1 - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.2.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >25% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Fitting within standard AP40 grading curve | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.2.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.2.6 | Plasticity Index | NZS4407:2015, Test 3.2 Cone Penetration NZS4407:2015, Test 3.3 Plastic Limit NZS4407:2015, Test 3.4 Plasticity Index | NP | NZS4407:2015 Test 3.2 NZS4407:2015 Test 3.3 NZS4407:2015 Test 3.4 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.7 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >25 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.2.8 | Clay Index | NZS4407:2015, Test 3.5 - Clay Index Test Report | Report Value Only | NZS4407:2015 Test 3.5 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wksbefore importing | HP | ENG
1.3 | MATERIAL APPROVALS: Imported Material Testing - AP20 - Source Property Tests for Type A1 Imported Structural Fill - ALL TESTS TO BE NO OLDER THAN 3 MONTHS
1.3.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >25% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Fitting within standard AP20 grading curve | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
1.3.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
1.3.6 | Plasticity Index | NZS4407:2015, Test 3.2 Cone Penetration NZS4407:2015, Test 3.3 Plastic Limit NZS4407:2015, Test 3.4 Plasticity Index | NP | NZS4407:2015 Test 3.2 NZS4407:2015 Test 3.3 NZS4407:2015 Test 3.4 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.7 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >25 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
1.3.8 | Clay Index | NZS4407:2015, Test 3.5 - Clay Index Test Report | Report Value Only | NZS4407:2015 Test 3.5 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wksbefore importing | HP | ENG
SECTION 2 - CONSTRUCTION - PREP GENERAL
2.1 | GENERAL
2.1.1 | Excavate to final depth | Subgrade Level | Using survey pegs as hights and placement. Measure from stringline for depth. Tolerances as follows +0mm -30mm | drawings 232735.02-WSP-DR-UDL-0405,406 -TNZ B/02: 2005 | String checksheet or Equilavent | Every 15m | D | SE
2.1.2 | Cut Subgrade Testing - Cohesive Soil Shear Vane | NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level | Average Minimum SU: > 60kPa CBR: >7 Single Test Min SU: >50kPa | Appendix XVIII | Shear Vane Report | 1 test per 100M2 | I | SE
2.1.3 | Cut Subgrade Testing - Granular Soil Scala Penetrometer | NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material | Minimum 3 blows per 100mm penetration | Appendix XVIII | Scala Report | 4 test per 400M2 | I | SE
2.1.4 | Proof roll | Visual Inspection of Proof Roll | Visual Inspection of Proof Roll | Appendix XVIII | Visual inspection/ Photos | Across Whole are | I | ENG
SECTION 3 - ROUNDABOUT APRON
3.1 | FORMWORK
3.1.1 | Surveyor check | Equivalent to check the position of the formwork | +\- 100mm of design | NZS 3109:1997 (PS 27.4.5 Viii) | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
3.1.2 | Surveyor check | Equivalent to check finished height of framework | +\- 10mm of design | NZS 3109:1997 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
3.2 | CONCRETE
3.2.1 | Concrete | 20 MPA: Include a mixture of nominal 10-20mm aggregate comprising grey, black, and brown-colored stones, resembling a riverbed | 28 days concrete strength test of 20MPA | PS 27.4.5 | Concrete Delivery dockets | During construction | I | SE
3.2.2 | Control Joint | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m. | PS 27.4.5 | Post Pour Checksheet | After pour | I | SE |  |  | This superseeds 27.4.5 (d) in the project specification
3.2.3 | Final Finish | U3 | U3 | PS 27.4.5 | Post Pour Checksheet | After pour | I | SE
SECTION 4 - ROUNDABOUT RIVER STONES
4.1 | FORMWORK
4.1.1 | Surveyor check | Equivalent to check the position of the formwork | +\- 100mm of design | NZS 3109:1997 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.1.2 | Surveyor check | Equivalent to check finished height of framework | +\- 10mm of design | NZS 3109:1997 | Check Sheet | 1 Set Every 20m Centres 1 set = 5 tests | I | SE
4.2 | CONCRETE
4.2.1 | Concrete | 20 MPa unreinforced concrete | 28 days concrete strength test of 20MPA | PS 27.4.6 | Concrete Delivery dockets | During construction | I | SE
4.2.2 | Final Finish | Riverstone from a selected local quarry, with a diameter of 150-250mm, will be set into the concrete. The stones must be embedded at least half their height into the concrete for stability. Place the stones closely, ensuring gaps between them do not exceed 50mm. | The protruding portion of the stone to be 50-75mm above the finish concrete level. | 232735.02-WSP-DR-UDL 0406 | Riverstone delivery docket & photos | 150-250mm Riverstone protruding 50-70mm gaps 50mm | I | SE
SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
13.1.1 | Final Inspection | Final inspection of all concrete work. | All works meet project specifications and standards. | NZTA P39: 2013 | Final inspection report | 100% of works | HP | ENG
13.1.2 | As-Builts Red Pen markup | Final inspection of all concrete work. | All works meet project specifications and standards. | PS 16.7.6 | Survey Records Red Pen Mark up | During Earthworks | D | SV