## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP1-020-001 ITP Kerb & Channel | itp |  |  |  |  | DN1210-SP1-020-001 ITP Kerb & Channel
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 3.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of minimum of 100kN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - NZS4407:2015, Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Fitting within standard AP40 grading curve
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – KERB & CHANNEL PREPARATION - INCLUDED IN PAVEMENT ITP
checkpoint | 4.1.1 - Pre-pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - PS21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - Before every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - Delivery Dockets
label | Standard / Specification - PS 26.7.3
label | Verifying Document - Concrete Delivery dockets and concrete test results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - PS 27.4.5
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.4 - Final Finish
label | Detail - Slip form kerb and channel
label | Acceptance / Conformance Criteria - Slip form kerb and channel
label | Standard / Specification - PS 26.7.3
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - Final Inspection
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - NZTA P39: 2013
label | Verifying Document - Final inspection report
label | Testing Quantity Required (based from schedule qtys) - 100% of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - As-Builts
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Redpen markups
label | Testing Quantity Required (based from schedule qtys) - Completion of works
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-SP1-020-002 ITP Shared Paths, Maintenance Pads & Traffic Islands | itp |  |  |  |  | DN1210-SP1-020-002 ITP Shared Paths, Maintenance Pads & Traffic Islands
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 1.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - Minimum soaked CBR of 25%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - NZS4407:2015, Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 68-90% passing
label | 19.0mm ¦¦ 42-76% passing
label | 9.5mm ¦¦ 26-58% passing
label | 4.75mm ¦¦ 16-44% passing
label | 2.36mm ¦¦ 10-33% passing
label | 1.18mm ¦¦ 6-24% passing
label | 0.425mm ¦¦ 3-14% passing
label | 0.075mm ¦¦ 1-6% passing
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >25
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Clay Index
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407:2015 Test 3.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wksbefore importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN Minimum
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - Minimum soaked CBR of 25%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - NZS4407:2015, Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 37.5mm ¦¦ 100% passing
label | 19.0mm ¦¦ 60-75% passing
label | 9.5mm ¦¦ 37-50% passing
label | 4.75mm ¦¦ 20-35% passing
label | 2.36mm ¦¦ 12-28% passing
label | 1.18mm ¦¦ 9-20% passing
label | 0.600mm ¦¦ 7-12% Passing
label | 0.300mm ¦¦ 3-10% Passing
label | 0.150mm ¦¦ 0-5% passing
label | 0.075mm ¦¦ 0-5% passing
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.6 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - <30, <8
label | Standard / Specification - NZS4407:2015, Test 3.2
label | ○ NZS4407:2015, Test 3.3
label | ○ NZS4407:2015, Test 3.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.7 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >40
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.8 - Clay Index
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407:2015 Test 3.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wksbefore importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.2 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
label | Standard / Specification - NZS4407:2015, Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.3 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Fitting within standard AP20 grading curve
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.4 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.1 - Sample panel (1000 x1000mm)
label | Detail - Contractor to provide a sample panel (1000 x1000mm) of the exposed aggregate specified finish before commencing work
label | Acceptance / Conformance Criteria - To NZS 3121:2015, use crushed aggregates or rounded coarse gravels for exposing. Allow a mixture of nominal 10-20mm aggregates consisting of a mixture of grey, black and brown colour tones that represent a riverbed, Autumn or Sunrise mixes. Mix design to be confirmed by the Engineer
label | Standard / Specification - Project Specifications 27.4.5.e
label | Verifying Document - Visual Inspection
label | Testing Quantity Required (based from schedule qtys) - 1 Sample Panel
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.2 - Slip resistance
label | Detail - Test sample to comply with NZBC D1/VM1, NZBC D1/AS1
label | Acceptance / Conformance Criteria - Level access routes: 2.0 Slip resistance for ramps :3.14
label | Standard / Specification - Project Specifications 27.4.5.e, AS/NZS 4586:2013
label | Verifying Document - British Pendulums
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 - CONSTRUCTION - PREP GENERAL
checkpoint | 2.1.1 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ CBR: >7
label | ○ Single Test Min SU: >50kPa
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.2 - Cut Subgrade Testing - Granular Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.3 - Proof Roll Subgrade
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Site Record
label | Testing Quantity Required (based from schedule qtys) - Across Finished Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.4 - Final Subgrade Heights
label | Detail - Excavated to the required subgrade level
label | Acceptance / Conformance Criteria - Using survey pegs as hights and placement. Measure from stringline for depth. Tolerances as follow
label | ○ Vertical: -25mm +5mm
label | Standard / Specification - drawings 232735.02-WSP-DR-UDL-0405,406 -TNZ B/02: 2005
label | Verifying Document - String Check Sheet or Equivalent
label | Testing Quantity Required (based from schedule qtys) - Every 15m
label | Verification Activity: Activity - D
label | Verification Activity: By - SE
checkpoint | 2.2.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface is below 225mm.
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - Standard
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.2.2 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - Standard
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.3.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface is below 125mm from finished height.
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - Standard
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.3.2 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - Standard
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 3 - MAINTENANCE PADS AND SHARED PATHS
checkpoint | 3.1.1 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ CBR: <7
label | ○ Single Test Min SU: >50kPa
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 1 test per 100M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.1.2 - Cut Subgrade Testing - Granular Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.1.3 - Proof Roll Subgrade
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Visual Inspection
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual Site Record
label | Testing Quantity Required (based from schedule qtys) - Across Finished Area
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface 225mm Below From Finish Height
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - Standard
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.2 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.3 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - Standard
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - Standard
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.2 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.3.3 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - Standard
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.4.1 - Surveyor check
label | Detail - Equivalent to check the position of the formwork
label | Acceptance / Conformance Criteria - +\- 100mm of design
label | Standard / Specification - NZS 3109:1997
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.4.2 - Surveyor check
label | Detail - Equivalent to check finished height of framework
label | Acceptance / Conformance Criteria - +\- 10mm of design
label | Standard / Specification - NZS 3109:1997
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.5.1 - Reinforcing Mesh Check
label | Detail - Ensure the right mesh
label | Acceptance / Conformance Criteria - 665 Reinforcing mesh
label | Standard / Specification - Project Specifications 27.4.2
label | Verifying Document - Dockets
label | Testing Quantity Required (based from schedule qtys) - Measurements
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 3.5.2 - Reinforcing Mesh Check
label | Detail - Ensure that overlap and clearince from edges
label | Acceptance / Conformance Criteria - 666 Reinforcing mesh
label | Standard / Specification - NZS 3109
label | Verifying Document - photos
label | Testing Quantity Required (based from schedule qtys) - Measurements
label | Verification Activity: Activity - C
label | Verification Activity: By - SE
checkpoint | 3.6.1 - Concrete
label | Detail - 20.0 MPA concrete. 4kg/m3 black oxide (2.5%)
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Concrete Delivery dockets
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.6.2 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - PS 27.4.5
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.6.3 - Final Finish
label | Detail - Finish to be either:
label | – Rough broom finish
label | – Exposed aggregate finish
label | Acceptance / Conformance Criteria - U5, U5E
label | Standard / Specification - 232735.02-WSP-DR-UDL 0405
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.6.4 - Slip Resistance
label | Detail - British Pendulum testing
label | Acceptance / Conformance Criteria - Level surface: mean coefficient of friction (µ) not less than 0.4.
label | ○ Slopping surface: mean coefficient of friction (µ) not less than 0.4 + 0.0125S (S = slope of surface expressed as a percentage).
label | Standard / Specification - Project Specifications 27.4.5.e, AS/NZS 4586:2013
label | Verifying Document - Britsh Pendulum Test Results
label | Testing Quantity Required (based from schedule qtys) - Every 20m
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 4 - TRAFFIC ISLAND INFILL
checkpoint | 4.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -0mm + 20mm
label | Standard / Specification - NZTA B/06 8.2.2
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Compaction - Clegg
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min CIV 18
label | ○ Ave CIV 20
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests per 5x5m grid) per 1000m2 of placed per area worked each day, per lift
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.3 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD
label | ○ Min >92% of MDD
label | Standard / Specification - Standard
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) per 400mm lift (every 2nd lift) of fill per 1000m2 of placed
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Concrete
label | Detail - 2.5% black oxide by weight of cement
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - PS 27.4.6
label | Verifying Document - Concrete Delivery dockets
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.2 - Final Finish
label | Detail - U3 Finish
label | Acceptance / Conformance Criteria - U3 Finish
label | Standard / Specification - PS 27.4.6
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - Final Inspection
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - NZTA P39: 2013
label | Verifying Document - Final inspection report
label | Testing Quantity Required (based from schedule qtys) - 100% of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - As-Builts
label | Detail - Final inspection of all concrete work. Red Pen Mark up.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red Pen Markup
label | Testing Quantity Required (based from schedule qtys) - Whole Work
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature
checklist | DN1210-SP1-020-003 ITP Roundabout Apron & Riverstones | itp |  |  |  |  | DN1210-SP1-020-003 ITP Roundabout Apron & Riverstones
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS - MATERIAL, PERSONELL & THIRD PARTY APPROVALS
checkpoint | 1.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >25%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - NZS4407:2015, Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Fitting within standard GAP 65 grading curve
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.6 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | ○ NZS4407:2015, Test 3.3 Plastic Limit
label | ○ NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - NP
label | Standard / Specification - NZS4407:2015, Test 3.2
label | ○ NZS4407:2015, Test 3.3
label | ○ NZS4407:2015, Test 3.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.7 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >25
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.8 - Clay Index
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407:2015 Test 3.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >25%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - NZS4407:2015, Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Fitting within standard AP40 grading curve
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.6 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | ○ NZS4407:2015, Test 3.3 Plastic Limit
label | ○ NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - NP
label | Standard / Specification - NZS4407:2015, Test 3.2
label | ○ NZS4407:2015, Test 3.3
label | ○ NZS4407:2015, Test 3.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.7 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >25
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.8 - Clay Index
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407:2015 Test 3.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wksbefore importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >25%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - NZS4407:2015, Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Fitting within standard AP20 grading curve
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.6 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | ○ NZS4407:2015, Test 3.3 Plastic Limit
label | ○ NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - NP
label | Standard / Specification - NZS4407:2015, Test 3.2
label | ○ NZS4407:2015, Test 3.3
label | ○ NZS4407:2015, Test 3.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.7 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >25
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.8 - Clay Index
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407:2015 Test 3.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wksbefore importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 - CONSTRUCTION - PREP GENERAL
checkpoint | 2.1.1 - Excavate to final depth
label | Detail - Subgrade Level
label | Acceptance / Conformance Criteria - Using survey pegs as hights and placement. Measure from stringline for depth. Tolerances as follows
label | ○ +0mm -30mm
label | Standard / Specification - drawings 232735.02-WSP-DR-UDL-0405,406 -TNZ B/02: 2005
label | Verifying Document - String checksheet or Equilavent
label | Testing Quantity Required (based from schedule qtys) - Every 15m
label | Verification Activity: Activity - D
label | Verification Activity: By - SE
checkpoint | 2.1.2 - Cut Subgrade Testing - Cohesive Soil Shear Vane
label | Detail - NZ Geotechncial Society 2001 - Guideline for Hand Held Shear Vane Test
label | ○ This test shall be undertaken at the design subgrade level to a depth of 2-3m below the design subgrade level
label | Acceptance / Conformance Criteria - Average Minimum SU: > 60kPa
label | ○ CBR: >7
label | ○ Single Test Min SU: >50kPa
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Shear Vane Report
label | Testing Quantity Required (based from schedule qtys) - 1 test per 100M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.3 - Cut Subgrade Testing - Granular Soil Scala Penetrometer
label | Detail - NZS4402:1988, Test 6.5.2 - Dynamic Cone Penetrometer
label | ○ Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material
label | Acceptance / Conformance Criteria - Minimum 3 blows per 100mm penetration
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Scala Report
label | Testing Quantity Required (based from schedule qtys) - 4 test per 400M2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 2.1.4 - Proof roll
label | Detail - Visual Inspection of Proof Roll
label | Acceptance / Conformance Criteria - Visual Inspection of Proof Roll
label | Standard / Specification - Appendix XVIII
label | Verifying Document - Visual inspection/ Photos
label | Testing Quantity Required (based from schedule qtys) - Across Whole are
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
section | SECTION 3 - ROUNDABOUT APRON
checkpoint | 3.1.1 - Surveyor check
label | Detail - Equivalent to check the position of the formwork
label | Acceptance / Conformance Criteria - +\- 100mm of design
label | Standard / Specification - NZS 3109:1997 (PS 27.4.5 Viii)
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.1.2 - Surveyor check
label | Detail - Equivalent to check finished height of framework
label | Acceptance / Conformance Criteria - +\- 10mm of design
label | Standard / Specification - NZS 3109:1997
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.1 - Concrete
label | Detail - 20 MPA: Include a mixture of nominal 10-20mm aggregate comprising grey, black, and brown-colored stones, resembling a riverbed
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - PS 27.4.5
label | Verifying Document - Concrete Delivery dockets
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.2 - Control Joint
label | Detail - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Acceptance / Conformance Criteria - Control joints must be formed while concrete is still wet using trowel with maximum spacing of 3.0m.
label | Standard / Specification - PS 27.4.5
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 3.2.3 - Final Finish
label | Detail - U3
label | Acceptance / Conformance Criteria - U3
label | Standard / Specification - PS 27.4.5
label | Verifying Document - Post Pour Checksheet
label | Testing Quantity Required (based from schedule qtys) - After pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 4 - ROUNDABOUT RIVER STONES
checkpoint | 4.1.1 - Surveyor check
label | Detail - Equivalent to check the position of the formwork
label | Acceptance / Conformance Criteria - +\- 100mm of design
label | Standard / Specification - NZS 3109:1997
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.1.2 - Surveyor check
label | Detail - Equivalent to check finished height of framework
label | Acceptance / Conformance Criteria - +\- 10mm of design
label | Standard / Specification - NZS 3109:1997
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Concrete
label | Detail - 20 MPa unreinforced concrete
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 20MPA
label | Standard / Specification - PS 27.4.6
label | Verifying Document - Concrete Delivery dockets
label | Testing Quantity Required (based from schedule qtys) - During construction
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.2 - Final Finish
label | Detail - Riverstone from a selected local quarry, with a diameter of 150-250mm, will be set into the concrete. The stones must be embedded at least half their height into the concrete for stability. Place the stones closely, ensuring gaps between them do not exceed 50mm.
label | Acceptance / Conformance Criteria - The protruding portion of the stone to be 50-75mm above the finish concrete level.
label | Standard / Specification - 232735.02-WSP-DR-UDL 0406
label | Verifying Document - Riverstone delivery docket & photos
label | Testing Quantity Required (based from schedule qtys) - 150-250mm Riverstone protruding 50-70mm gaps 50mm
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 13.1.1 - Final Inspection
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - NZTA P39: 2013
label | Verifying Document - Final inspection report
label | Testing Quantity Required (based from schedule qtys) - 100% of works
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.1.2 - As-Builts Red Pen markup
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Survey Records, Red Pen Mark up
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature