## ITP Cover Page
Kerb and channel Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 020 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project |  |  |  |  | ITP Number: |  |  | 020
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Kerb and channel |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | 8287 |  |  |  |  | Drawing Sets: |  |  | 2-32735.02-WSP-DR-UDL; 2-32735.02-WSP-DR-RSA
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | Project Specification: 26.7 Kerb and Channel
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval | [8 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | CHRIS BENSON | [5 empty] | Downer PM |  | CHRIS BENSON
Downer QM |  | CORDELIA GIRDLER-BROWN | [5 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master body
Kerb and channel Inspection and Test Plan
Project: Tauriko Enabling Project
Number and Revision: DN1210 - 020 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS
3.1.1 | Crushing Resistance | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | NZS4407:2015 Test 3.10 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.2 | Soaked CBR | NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR) | >25% | NZS4407:2015 Test 3.15 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.3 | Weathering Resistance | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | CA or better | NZS4407:2015 Test 3.11 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.4 | Particle Size Distribution | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | Fitting within standard AP40 grading curve | NZS4407:2015 Test 3.8.1 | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP | ENG
3.1.5 | Maximum Dry Density and Optimum Water Content | NZS4402:1986, Test 4.1.2 - Heavy Compaction Test | Report Value Only | NZS4402:1986 Test 4.1.2 | IANZ Accredited Report | 1 Test Per Material, PerSource | HP | ENG
3.1.6 | Plasticity Index | NZS4407:2015, Test 3.2 Cone Penetration NZS4407:2015, Test 3.3 Plastic Limit NZS4407:2015, Test 3.4 Plasticity Index | NP | NZS4407:2015 Test 3.2 NZS4407:2015 Test 3.3 NZS4407:2015 Test 3.4 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.7 | Sand Equivalent | NZS4407:2015, Test 3.6 Sand Equivalent | >25 | NZS4407:2015 Test 3.6 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wks before importing | HP | ENG
3.1.8 | Clay Index | NZS4407:2015, Test 3.5 - Clay Index Test Report | Report Value Only | NZS4407:2015 Test 3.5 | IANZ Accredited Report | 1 Test Per Material, Per Source Results to Engineer 2 wksbefore importing | HP | ENG
3.2.2 | Concrete mix design | All concrete to be ordianary grade 17.5MPA | Concrete grade, Concrete target mean strength, mix designation, batch weights of cementitious meaterial and aggregates ( saturated and surface only) target slump type and amount of air entainment ( if applicable) yield, free water/cement ratio by weight, free water content | PS26.7.3 (d) and PS19.3.3 | Concrete mix design approval | Once off | HP | ENG
SECTION 4 – KERB & CHANNEL PREPARATION - INCLUDED IN PAVEMENT ITP
4.1.1 | Stringlines or equivalent | Stringlines or equivalent to check height of surface prep | +/-5mm | PS 21.7.6 | Check Sheet | 1 Test along kerb line @ 20m centres | I | SE
4.2.2 | Compaction - Clegg Hammer | ASTM D5874-16:2016 Clegg Hammer Testing | Min 25 CIV |  | Clegg Hammer Report | 1 Test along kerb line @ 20m centres | I | SE
4.3.1 | Pre-pour inspection and post pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | PS21.7.6 | Kerb construction record | Before and after every pour | I | ESE
4.3.2 | Concrete | 17.5 Mpa Concrete | 28 days concrete strength test of 17.5MPA | PS 26.7.3 | Concrete Delivery dockets and concrete test results | During construction - Every pour | I | SE
4.3.1 | Pre-pour inspection and post pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | PS21.7.6 | Kerb construction record | Before and after every pour | I | SE
4.4.2 | Concrete | 17.5 Mpa Concrete | 28 days concrete strength test of 17.5MPA | PS 26.7.3 | Concrete Delivery dockets and test results | During construction - Every pour | I | SE
4.5.1 | Pre-pour inspection and post pour inspection | Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits | Tolerances are +/-5 mm variance to vertical design setout +/- 10mm variance to horizontal design setout The deviation from a 4.0m straight edge shall not exceed 3.0mm. | PS21.7.6 | Kerb construction record | Before and after every pour | I | SE
4.5.2 | Concrete | 17.5 Mpa Concrete | 28 days concrete strength test of 17.5MPA | PS 26.7.3 | Concrete Delivery dockets and test results | During construction - Every pour | I | SE
SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5.1 | As-Builts | Final inspection of all concrete work. | All works meet project specifications and standards. | PS 16.7.6 | Redpen markups | Completion of works | D | SE