## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-SP1-020-001 ITP Kerb & Channel | itp |  |  |  |  | DN1210-SP1-020-001 ITP Kerb & Channel
section | SECTION 3 – PRE-CONSTRUCTION HOLD POINTS
checkpoint | 3.1.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >25%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - NZS4407:2015, Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.4 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Fitting within standard AP40 grading curve
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.5 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, PerSource
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.6 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | ○ NZS4407:2015, Test 3.3 Plastic Limit
label | ○ NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - NP
label | Standard / Specification - NZS4407:2015 Test 3.2
label | ○ NZS4407:2015 Test 3.3
label | ○ NZS4407:2015 Test 3.4
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.7 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - >25
label | Standard / Specification - NZS4407:2015 Test 3.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.8 - Clay Index
label | Detail - NZS4407:2015, Test 3.5 - Clay Index Test Report
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4407:2015 Test 3.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wksbefore importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2.2 - Concrete mix design
label | Detail - All concrete to be ordianary grade 17.5MPA
label | Acceptance / Conformance Criteria - Concrete grade, Concrete target mean strength, mix designation, batch weights of cementitious material and aggregates (saturated and surface only) target slump type and amount of air entainment (if applicable) yield, free water/cement ratio by weight, free water content
label | Standard / Specification - PS26.7.3 (d) and PS19.3.3
label | Verifying Document - Concrete mix design approval
label | Testing Quantity Required (based from schedule qtys) - Once off
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – KERB & CHANNEL PREPARATION - INCLUDED IN PAVEMENT ITP
checkpoint | 4.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check height of surface prep
label | Acceptance / Conformance Criteria - +/-5mm
label | Standard / Specification - PS 21.7.6
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Test along kerb line @ 20m centres
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.2 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min 25 CIV
label | Standard / Specification -
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test along kerb line @ 20m centres
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.1 - Pre-pour inspection and post pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - PS21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - Before and after every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - ESE
checkpoint | 4.3.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 17.5MPA
label | Standard / Specification - PS 26.7.3
label | Verifying Document - Concrete Delivery dockets and concrete test results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.1 - Pre-pour inspection and post pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - PS21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - Before and after every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.4.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 17.5MPA
label | Standard / Specification - PS 26.7.3
label | Verifying Document - Concrete Delivery dockets and test results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.5.1 - Pre-pour inspection and post pour inspection
label | Detail - Subcontractor string line to be checked by Site Engineer to ensure horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits
label | Acceptance / Conformance Criteria - Tolerances are
label | ○ +/-5 mm variance to vertical design setout
label | ○ +/- 10mm variance to horizontal design setout
label | ○ The deviation from a 4.0m straight edge shall not exceed 3.0mm.
label | Standard / Specification - PS21.7.6
label | Verifying Document - Kerb construction record
label | Testing Quantity Required (based from schedule qtys) - Before and after every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.5.2 - Concrete
label | Detail - 17.5 Mpa Concrete
label | Acceptance / Conformance Criteria - 28 days concrete strength test of 17.5MPA
label | Standard / Specification - PS 26.7.3
label | Verifying Document - Concrete Delivery dockets and test results
label | Testing Quantity Required (based from schedule qtys) - During construction - Every pour
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 - POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 5.1 - As-Builts
label | Detail - Final inspection of all concrete work.
label | Acceptance / Conformance Criteria - All works meet project specifications and standards.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Redpen markups
label | Testing Quantity Required (based from schedule qtys) - Completion of works
label | Verification Activity: Activity - D
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature