## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RR-SEPD-BESS-FIC-003-00 - Electrical trenching - | itp |  |  |  |  | RR-SEPD-BESS-FIC-003-00 - Electrical trenching
section | Part 1 – Preliminaries (photos where applicable)
checkpoint | Review of approved construction drawings and specifications
label | All drawings and specifications approved and up to date
label | WBS-SS-CI-SPC-006
checkpoint | Verification of permits
label | All relevant permits (GDA/GDP) in place
label | GDA/GDP
checkpoint | Site access and safety preparation
label | Site access cleared and made safe
label | WBS-SS-CI-SPC-006
checkpoint | Safety inductions and toolbox talks
label | All personnel inducted; safety briefings completed
label | Induction record
checkpoint | Environmental controls in place
label | Dust, noise, and sediment barriers installed and functioning
label | SEPD environmental requirements
checkpoint | Utility identification
label | All utilities marked as per drawings
label | Project as-built drawings
section | Part 2 – Set-out and excavation (photos where applicable)
checkpoint | Site set-out verification
label | Set-out verified and matches IFC drawings
label | Site IFC Drawings
checkpoint | Accurate dimensions
label | Width, depth, and alignment match design drawings
label | WBS-SS-EL-DRG-3005
section | Part 3 – Excavation (photos where applicable)
checkpoint | Dimensions maintained
label | Depth and width meet design specifications
label | WBS-SS-CI-SPC-006, WBS-SS-EL-DRG-3005
checkpoint | Stockpiling of excavated material
label | Material stockpiled properly, no contamination
label | WBS-SS-CI-SPC-006
checkpoint | Stability of trench
label | No loose soil or collapses; protective measures in place if trench is over 1.5m
label | WBS-SS-CI-SPC-006
checkpoint | Subbase inspection
label | Subgrade verified, compacted and stable
label | Geotechnical report
checkpoint | Subbase compaction testing
label | Compaction results meet project criteria. 1 test every 40 linear meters and 1 every two layers.
label | AS 1289 geotechnical report
section | Part 4 – Fill material and compaction (photos where applicable)
checkpoint | Backfill material
label | Approved material used for backfill
label | WBS-SS-CI-SPC-0006
checkpoint | Imported fill material testing
label | Material complies with particle size, moisture content, MMDD
label | WBS-SS-CI-SPC-0006, Test material results
checkpoint | Fill placement in 150mm layers
label | Layers placed in maximum 200mm (loose) thickness
label | WBS-SS-CI-SPC-0006
checkpoint | Compaction testing
label | Compaction >92% MMDD for general fill
label | AS 1289 Compaction test results
checkpoint | Level and grading check
label | Levels and grading match design tolerances (+/-20mm)
label | WBS-SS-CI-SPC-0006, Survey Report
section | Document Sign-off
checkpoint | Prepared by:
textbox | SEPD (Engineer) - Name:
date | SEPD (Engineer) - Date:
signoff | Add Signature
checklist | RR-SEPD-BESS-ITP-003-00 - Electrical trenching - Layer | itp |  |  |  |  | RR-SEPD-BESS-ITP-003-00 - Electrical trenching
section | Section 1: Preliminaries & Permits
checkpoint | 1.1 - Pre-Excavation Site Inspection
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Work area is clear, utilities and exclusion zones are clearly marked, permits are approved.
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 1.2 - Permit approval (GDA/GDP)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Approved excavation permit (GDP) prior to commencing works
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
holdpoint | HOLD POINT
checkpoint | 1.3 - Site set-out
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Verify levels, site boundaries, and physical bounds per IFC drawings
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 1.4 - Sediment control plan
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-PM- PLN-0024, WAE230103- 03-003 TM Rev0
label | Conformance Criteria Summary - Sediment control measures in place
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 1.5 - Dust control plan
label | Responsibility - SE/PE
label | Specification Reference - PP3 section 1.5 and section 4.1
label | Conformance Criteria Summary - Dust control measures in place
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
section | Section 2: Materials
checkpoint | 2.1 - Import fill material inspection
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Material certificate and test report for particle size distribution, moisture content, MMDD
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 2.2 - Verify suitable foundation material (compaction >92% MMDD)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Geotechnical test results showing compliance
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
holdpoint | HOLD POINT
section | Section 3: Electrical trenching
checkpoint | 3.1 - Excavation to subgrade – verify lines, depth and dimensions
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Compliance with design drawings and subgrade preparation
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 3.2 - Stockpiling of excavated material – manage and segregate by type
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-0006
label | Conformance Criteria Summary - Material stockpiled appropriately, no cross contamination
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 3.3 - Base preparation
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-0006
label | Conformance Criteria Summary - Base is level, compacted, and free of debris; compaction meets project specs.
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 3.4 - Initial backfilling and compaction
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-0006
label | Conformance Criteria Summary - Backfill material compacted in 150mm layers to required thickness
label | ○ Material shall be placed to a depth of 150mm above the collars of pipes or conduits, 300mm above pipes and 600mm above culverts
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 3.5 - Compaction density ratio for backfill
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Compaction test report showing >92% MMDD every 40 linear meters and every 2 layers WBS-SS-CI-ITP-920049
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
holdpoint | HOLD POINT
checkpoint | 3.6 - As-built survey pick-up
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006 PPR
label | Conformance Criteria Summary - Survey records and as-built drawings
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
section | Section 4: Final Inspection
checkpoint | 4.1 - Finish level compliance with design drawings
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - As-built drawings
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
checkpoint | 4.2 - Final Inspection Checklist (FIC) completion
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Signed FIC
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
section | Document Sign-off
checkpoint | Prepared by:
textbox | SEPD (Engineer) - Name:
date | SEPD (Engineer) - Date:
signoff | Add Signature