## Sheet1
1.1 | Pre-Excavation Site Inspection | SE/PE | WBS-SS-CI- SPC-0006 | Work area is clear, utilities and exclusion zones are clearly marked, permits are approved. | R | PW | V | NA | NA | 1.1 - Pre-Excavation Site Inspection | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - Work area is clear, utilities and exclusion zones are clearly marked, permits are approved. | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - NA | Hold/Witness Point Requirements: Client - NA | 1.1 - Pre-Excavation Site Inspection
1.2 | Permit approval (GDA/GDP) | SE/PE | WBS-SS-CI- SPC-0006 | Approved excavation permit (GDP) prior to commencing works | R | PW | HP | HP | NA | 1.2 - Permit approval (GDA/GDP) | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - Approved excavation permit (GDP) prior to commencing works | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - HP | Hold/Witness Point Requirements: SEPD - HP | Hold/Witness Point Requirements: Client - NA | Responsibility - SE/PE
1.3 | Site set-out | SE/PE | WBS-SS-CI- SPC-0006 | Verify levels, site boundaries, and physical bounds per IFC drawings | R | PW | V | NA | NA | 1.3 - Site set-out | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - Verify levels, site boundaries, and physical bounds per IFC drawings | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - NA | Hold/Witness Point Requirements: Client - NA | Specification Reference - WBS-SS-CI- SPC-0006
1.4 | Sediment control plan | SE/PE | WBS-SS-PM- PLN-0024 WAE230103- 03-003 TM Rev0 | Sediment control measures in place | R | PW | V | NA | NA | 1.4 - Sediment control plan | Responsibility - SE/PE | Specification Reference - WBS-SS-PM- PLN-0024 WAE230103- 03-003 TM Rev0 | Conformance Criteria Summary - Sediment control measures in place | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - NA | Hold/Witness Point Requirements: Client - NA | Conformance Criteria Summary - Work area is clear, utilities and exclusion zones are clearly marked, permits are approved.
1.5 | Dust control plan | SE/PE | PP3 section 1.5 and section 4.1 | Dust control measures in place | R | PW | V | NA | NA | 1.5 - Dust control plan | Responsibility - SE/PE | Specification Reference - PP3 section 1.5 and section 4.1 | Conformance Criteria Summary - Dust control measures in place | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - NA | Hold/Witness Point Requirements: Client - NA | Method - R
2.1 | Import fill material inspection | SE/PE | WBS-SS-CI- SPC-0006 | Material certificate and test report for particle size distribution, moisture content, MMDD | R | PW | V | V | NA | 2.1 - Import fill material inspection | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - Material certificate and test report for particle size distribution, moisture content, MMDD | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Frequency - PW
2.2 | Verify suitable foundation material (compaction >92% MMDD) | SE/PE | WBS-SS-CI- SPC-0006 | Geotechnical test results showing compliance | R | PW | HP | HP | NA | 2.2 - Verify suitable foundation material (compaction >92% MMDD) | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - Geotechnical test results showing compliance | Method - R | Frequency - PW | Hold/Witness Point Requirements: ROBAR - HP | Hold/Witness Point Requirements: SEPD - HP | Hold/Witness Point Requirements: Client - NA | Hold/Witness Point Requirements: ROBAR - V
3.1 | Excavation to subgrade – verify lines, depth and dimensions | SE/PE | WBS-SS-CI- SPC-0006 | Compliance with design drawings and subgrade preparation | I | PL | V | V | NA | 3.1 - Excavation to subgrade – verify lines, depth and dimensions | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - Compliance with design drawings and subgrade preparation | Method - I | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Hold/Witness Point Requirements: SEPD - NA
3.2 | Stockpiling of excavated material – manage and segregate by type | SE/PE | WBS-SS-CI- 0006 | Material stockpiled appropriately, no cross contamination | I | PL | V | V | NA | 3.2 - Stockpiling of excavated material – manage and segregate by type | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- 0006 | Conformance Criteria Summary - Material stockpiled appropriately, no cross contamination | Method - I | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Hold/Witness Point Requirements: Client - NA
3.3 | Base preparation | SE/PE | WBS-SS-CI- 0006 | Base is level, compacted, and free of debris; compaction meets project specs. | I | PL | V | V | NA | 3.3 - Base preparation | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- 0006 | Conformance Criteria Summary - Base is level, compacted, and free of debris; compaction meets project specs. | Method - I | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | 1.2 - Permit approval (GDA/GDP)
3.4 | Initial backfilling and compaction | SE/PE | WBS-SS-CI- 0006 | Backfill material compacted in 150mm layers to required thickness Material shall be placed to a depth of 150mm above the collars of pipes or conduits, 300mm above pipes and 600mm above culverts | I | PL | V | V | NA | 3.4 - Initial backfilling and compaction | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- 0006 | Conformance Criteria Summary - Backfill material compacted in 150mm layers to required thickness Material shall be placed to a depth of 150mm above the collars of pipes or conduits, 300mm above pipes and 600mm above culverts | Method - I | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Responsibility - SE/PE
3.5 | Compaction density ratio for backfill | SE/PE | WBS-SS-CI- SPC-0006 | Compaction test report showing >92% MMDD every 40 linear meters and every 2 layers WBS-SS-CI-ITP-920049 | T | PL | HP | HP | NA | 3.5 - Compaction density ratio for backfill | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - Compaction test report showing >92% MMDD every 40 linear meters and every 2 layers WBS-SS-CI-ITP-920049 | Method - T | Frequency - PL | Hold/Witness Point Requirements: ROBAR - HP | Hold/Witness Point Requirements: SEPD - HP | Hold/Witness Point Requirements: Client - NA | Specification Reference - WBS-SS-CI- SPC-0006
3.6 | As-built survey pick-up | SE/PE | WBS-SS-CI- SPC-0006 PPR | Survey records and as-built drawings | S | PL | V | V | NA | 3.6 - As-built survey pick-up | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 PPR | Conformance Criteria Summary - Survey records and as-built drawings | Method - S | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Conformance Criteria Summary - Approved excavation permit (GDP) prior to commencing works
4.1 | Finish level compliance with design drawings | SE/PE | WBS-SS-CI- SPC-0006 | As-built drawings | S | PL | V | V | NA | 4.1 - Finish level compliance with design drawings | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - As-built drawings | Method - S | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Method - R
4.2 | Final Inspection Checklist (FIC) completion | SE/PE | WBS-SS-CI- SPC-0006 | Signed FIC | R | PL | V | V | NA | 4.2 - Final Inspection Checklist (FIC) completion | Responsibility - SE/PE | Specification Reference - WBS-SS-CI- SPC-0006 | Conformance Criteria Summary - Signed FIC | Method - R | Frequency - PL | Hold/Witness Point Requirements: ROBAR - V | Hold/Witness Point Requirements: SEPD - V | Hold/Witness Point Requirements: Client - NA | Frequency - PW
Hold/Witness Point Requirements: ROBAR - HP
Hold/Witness Point Requirements: SEPD - HP
Hold/Witness Point Requirements: Client - NA
1.3 - Site set-out
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0006
Conformance Criteria Summary - Verify levels, site boundaries, and physical bounds per IFC drawings
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - NA
Hold/Witness Point Requirements: Client - NA
1.4 - Sediment control plan
Responsibility - SE/PE
Specification Reference - WBS-SS-PM- PLN-0024 WAE230103- 03-003 TM Rev0
Conformance Criteria Summary - Sediment control measures in place
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - NA
Hold/Witness Point Requirements: Client - NA
1.5 - Dust control plan
Responsibility - SE/PE
Specification Reference - PP3 section 1.5 and section 4.1
Conformance Criteria Summary - Dust control measures in place
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - NA
Hold/Witness Point Requirements: Client - NA
2.1 - Import fill material inspection
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0006
Conformance Criteria Summary - Material certificate and test report for particle size distribution, moisture content, MMDD
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
2.2 - Verify suitable foundation material (compaction >92% MMDD)
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0006
Conformance Criteria Summary - Geotechnical test results showing compliance
Method - R
Frequency - PW
Hold/Witness Point Requirements: ROBAR - HP
Hold/Witness Point Requirements: SEPD - HP
[19 empty] | Hold/Witness Point Requirements: Client - NA | NA | IFC Drawings
[19 empty] | 3.1 - Excavation to subgrade – verify lines, depth and dimensions | NA | RR-SEPD-CI- SOW-002-01
[19 empty] | Responsibility - SE/PE | NA | IFC Drawings
[19 empty] | Specification Reference - WBS-SS-CI- SPC-0006 | NA | SEPD environment- al plan
[19 empty] | Conformance Criteria Summary - Compliance with design drawings and subgrade preparation | NA | SEPD environment- al plan
[19 empty] | Method - I | NA | Material certificates
[19 empty] | Frequency - PL | NA | Test results
[19 empty] | Hold/Witness Point Requirements: ROBAR - V | NA | IFC Drawings
[19 empty] | Hold/Witness Point Requirements: SEPD - V | NA | SEPD environment- al plan
[19 empty] | Hold/Witness Point Requirements: Client - NA | NA
[19 empty] | 3.2 - Stockpiling of excavated material – manage and segregate by type | NA | WBS-SS-CI- ITP-920049
[19 empty] | Responsibility - SE/PE | NA | Test results
[19 empty] | Specification Reference - WBS-SS-CI- 0006 | NA | As-built drawings
[19 empty] | Conformance Criteria Summary - Material stockpiled appropriately, no cross contamination | NA | WBS-SS-CI- ITP-920049
[19 empty] | Method - I | NA | WBS-SS-CI- ITP-920049
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
3.3 - Base preparation
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- 0006
Conformance Criteria Summary - Base is level, compacted, and free of debris; compaction meets project specs.
Method - I
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
3.4 - Initial backfilling and compaction
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- 0006
Conformance Criteria Summary - Backfill material compacted in 150mm layers to required thickness Material shall be placed to a depth of 150mm above the collars of pipes or conduits, 300mm above pipes and 600mm above culverts
Method - I
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
3.5 - Compaction density ratio for backfill
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0006
Conformance Criteria Summary - Compaction test report showing >92% MMDD every 40 linear meters and every 2 layers WBS-SS-CI-ITP-920049
Method - T
Frequency - PL
Hold/Witness Point Requirements: ROBAR - HP
Hold/Witness Point Requirements: SEPD - HP
Hold/Witness Point Requirements: Client - NA
3.6 - As-built survey pick-up
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0006 PPR
Conformance Criteria Summary - Survey records and as-built drawings
Method - S
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
4.1 - Finish level compliance with design drawings
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0006
Conformance Criteria Summary - As-built drawings
Method - S
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA
4.2 - Final Inspection Checklist (FIC) completion
Responsibility - SE/PE
Specification Reference - WBS-SS-CI- SPC-0006
Conformance Criteria Summary - Signed FIC
Method - R
Frequency - PL
Hold/Witness Point Requirements: ROBAR - V
Hold/Witness Point Requirements: SEPD - V
Hold/Witness Point Requirements: Client - NA