## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | Enviro 700X - Balconies | [5 empty] | Enviro 700X - Balconies
checkpoint-no-status | Details
label | Specification / Standard
text | Manufacturer's Technical Data Sheet / AS4654.1 - 2012
text | Batch Number
checkpoint | Substrate crack and falls inspection
label | ○ Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.
label | ○ Live cracks to be reffered to engineers for treatment methodolgy.
label | ○ Builder to approve falls on substrate(Min 1:100) prior to application of membrane.
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Moisture Content
label | ○ Note. min. 3 tests per 15m2
label | ○ Enviro Epoxy B-LV up to 6.9%
label | ○ Enviro Prime P2 up to 5%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
label | ○ Reading twice a day- every 4 hours
label | ○ Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane.
label | ○ RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
label | ○ If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | ○ Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint | Applying primer
label | ○ Using a brush or roller apply the chosen primer.
label | ○ Allow to cure prior to over coating with sealants and/or membrane coats. "Primer should be dry to touch and not be tacky when applying pressure to it.
label | ○ Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint | Seal/apply bondbreaker at junctions hob/floor
label | ○ Apply Enviro Flex Pro to form smooth 15mm flexible cove to all internal corners, penetrations and joints.
checkpoint | Application of Enviro-700X
label | ○ Mix Bucket at low speed( 400RPM) unitl thouroghly mixed.
label | ○ Apply two coats of 700X.
label | ○ Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint | QA Testing
label | ○ Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | ○ Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.
label | ○ 5 tests per 15m2 Holiday/ spark testing of area.
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Protection of membrane edge
label | ○ Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | ○ Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
holdpoint | Builder Sign Off
checklist-flat | Enviro 700X - Balcony Set Downs & Window Reveals | [5 empty] | Enviro 700X - Balcony Set Downs & Window Reveals
checkpoint-no-status | Details
label | Specification / Standard
text | Manufacturer's Technical Data Sheet / AS4654.1 - 2012
text | Batch Number
checkpoint | Substrate crack and falls inspection
label | ○ Obtain clearance for work to commence.
label | ○ Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion.
label | ○ For non metal surfaces: ICRI CSP-4 to CSP-6
label | ○ For metal surfaces: ICRI CSP-1 to CSP-2.
checkpoint | Moisture Content
label | ○ Note. min. 3 tests per 15m2
label | ○ Enviro Epoxy B-LV up to 6.9%
label | ○ Enviro Prime P2 up to 5%
label | ○ Enviro Prime 789 up to 5%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
label | ○ Reading twice a day- every 4 hours
label | ○ Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane.
label | ○ RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
label | ○ If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | ○ Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint | Applying primer
label | ○ Using a brush or roller apply the chosen primer.
label | ○ Allow to cure prior to over coating with sealants and/or membrane coats. "Primer should be dry to touch and not be tacky when applying pressure to it.
label | ○ Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint | Application of Enviro-700X
label | ○ Mix Bucket at low speed( 400RPM) unitl thouroghly mixed.
label | ○ Apply two coats of 700X.
label | ○ Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint | Protection of membrane edge
label | ○ Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | ○ Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
checkpoint | QA Testing
label | ○ Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | ○ Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions.
label | ○ 5 tests per 15m2 Holiday/ spark testing of area.
holdpoint | Completion of Work Element
checklist-flat | Enviro 200P Ultra - Internal Wet Areas | [5 empty] | Enviro 200P Ultra - Internal Wet Areas
checkpoint-no-status | Details
label | Specification / Standard
text | Manufacturer's Technical Data Sheet / AS4654.1 - 2012
text | Batch Number
checkpoint | Substrate crack and falls inspection (1)
label | ○ Obtain clearance for work to commence.
label | ○ Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion.
label | ○ For non metal surfaces: ICRI CSP-4 to CSP-6
label | ○ For metal surfaces: ICRI CSP-1 to CSP-2.
label | ○ Ensure all fixings and joints have been set and junction between wall and floor does not exceed more than 10mm.
label | ○ Ensure Puddle flanges reccessed in concrete.
checkpoint | Substrate crack and falls inspection (2)
label | ○ Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.
label | ○ Live cracks to be reffered to engineers for treatment methodolgy.
label | ○ Builder to approve falls on substrate (Min 1:100 outside shower and 1:80 in showers) prior to application of membrane.
checkpoint | Moisture Content
label | ○ Note. min. 3 tests per bathroom
label | ○ Enviro Epoxy B-LV up to 6.9%
label | ○ Enviro Prime WB up to 6.9%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
label | ○ Reading twice a day - every 4 hours
label | ○ Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane.
label | ○ RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
label | ○ If applying Enviro Epoxy B-LV, thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
label | ○ If applying Enviro Prime WB, mix at low speed (400RPM) until thouroghly mixed.
checkpoint | Applying primer
label | ○ Using a brush or roller apply the chosen primer.
label | ○ Allow to cure prior to over coating with sealants and/or membrane coats."Primer should be dry to touch and not be tacky when applying pressure to it.
label | ○ Application range: 5-40 degrees celcius.
checkpoint | Seal/apply bondbreaker at junctions hob/floor
label | ○ Apply Enviro Flex Pro to form smooth 12mm flexible cove to all internal corners, penetrations and joints.
checkpoint | Application of 200P ultra
label | ○ Mix Bucket at low speed( 400RPM) unitl thoroughly mixed.
label | ○ Apply two coats of 200p Ultra to wet area in accordance with Australian Standards
label | ○ Application range 5-40*C
checkpoint | QA Testing
label | ○ Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | ○ Thickness testing of application to the recommended DFT to manufacturers instructions.
label | ○ 0.6mm walls
label | ○ 1.0mm floors
label | ○ 3 tests on floor/ 3 tests on walls.
label | ○ 24 hour Flood testing.
holdpoint | Completion of Work Element
checklist-flat | Enviro 700X + 250NS
checkpoint-no-status | Details
label | Specification / Standard
text | Manufacturer's Technical Data Sheet / AS4654.1 - 2012
text | Batch Number
checkpoint | Substrate crack and falls inspection (1)
label | ○ Obtain clearance for work to commence.
label | ○ Clean substrate so that is free of mould, paint, sealers, coatings, curing agents, loose particles, and other contamination or foreign matter that may interfere with the adhesion.
label | ○ For non metal surfaces: ICRI CSP-4 to CSP-6
label | ○ For metal surfaces: ICRI CSP-1 to CSP-2.
checkpoint | Substrate crack and falls inspection (2)
label | ○ Fill cracks less than 1.6mm with filler compatible (Enviro-Flex Pro) with the membrane system.Live cracks to be reffered to engineers for treatment methodolgy.
label | ○ Builder to approve falls on substrate(Min 1:100) prior to application of membrane.
checkpoint | Moisture Content
label | ○ Note. min. 3 tests per 15m2
label | ○ Enviro Epoxy B-LV up to 6.9%
label | ○ Enviro Prime P2 up to 5%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Ambient temperature and RH
label | ○ Reading twice a day - every 4 hours
label | ○ Mirvac to confirm temperature between the ranges of 5-35 degrees celcius prior to application of membrane.
label | ○ RH must be greater than 50%
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Mechanical Mixing
label | ○ If applying Enviro Epoxy B-LV: Mix Part B, liquid hardener, to the Enviro Epoxy B-LV Part A base.
label | ○ Thoroughly mix with a mechanical mixer at low speed for not less than 5 minutes and until uniform.
checkpoint | Applying primer
label | ○ Using a brush or roller apply the chosen primer.
label | ○ Allow to cure prior to over coating with sealants and/or membrane coats. "Primer should be dry to touch and not be tacky when applying pressure to it.
label | ○ Enviro-Epoxy B-LV will take around 16-48 hrs @ 25 degrees C to dry (but could be longer depending on ambient temp and RH)
checkpoint | Seal/apply bondbreaker at junctions hob/floor
label | ○ Apply Enviro Flex Pro to form smooth 15mm flexible cove to all internal corners, penetrations and joints.
checkpoint | Application of Enviro-700X
label | ○ Mix Bucket at low speed( 400RPM) unitl thouroghly mixed.
label | ○ Apply two coats of 700X.
label | ○ Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint | QA Testing
label | ○ Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
label | ○ Thickness testing of application to the recommended DFT of 1.5mm to manufacturers instructions. 5 tests per 15m2
label | ○ Holiday/ spark testing of area.
holdpoint | Hold Point (Mandatory) - work not to proceed without approval
checkpoint | Application of 250N-S Top Coat
label | ○ Mix Bucket at low speed( 400RPM) unitl thouroghly mixed.
label | ○ Apply 1 coats of 250N-S
label | ○ Where membrane is terminated on a building element: Ensure that the termination height of the membrane above the FFL and/or invert level of a correctly placed overflow/spitter satisfies the Façade engineer's advice
checkpoint | Protection of membrane edge
label | ○ Ensure vertical terminations of membranes on a building element are provided with a pressure seal, reglet or by being overcoated with a waterproof or water resistant material to protect the membrane edge.
label | ○ Ensure vertical membrane termination junctions are caulked with Enviro FC pro.
holdpoint | Completion of Work Element