## Downer - Transport & Infrastruc
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
6ae5f494-0463-4ad5-a3a5-774cae30d614 |  | fail |  | folder | TRUE | FALSE | Site QA
dc0a4c0a-46ef-4245-aa19-7d7403b19b8c |  | fail |  | folder | TRUE | FALSE | Site QA | Stormwater
75d1e6f2-5e53-427d-b5b3-5f88de3242c5 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | N0
f51f7bc1-44de-4204-ad4c-05ed1ae09e84 |  | work-in-progress | ITP - Drilling Rev 4 | checklist | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL
add50832-b9c1-53b1-999d-305c9cb603bd |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction
073ec6f9-2617-5d3c-b52c-e63ac7401e16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.1 - Materials
0d4c0bfd-9118-5939-9706-90667249d1e2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
2a6a75f4-f3b8-5745-8e82-44a25c698e6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.2 - Settlement monitoring and ground deformation (Baseline measurements)
9b6feb05-a418-5d33-b901-2c685e735af1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
aa948e9a-8883-59f2-8f37-e5ac2887e5d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.3 - Qualified staff
32ed0d50-6d39-5d23-a3ab-60b01d55f9ec |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
82efe247-d901-5c94-9083-51d997dc32e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.4 - Tensile Test
5fecf4eb-a8eb-5af3-a135-0fe71f4b6c53 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
b8888ede-2d76-52e0-9851-98d827840f75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.5 - Drilling Fluid Mix
b5b8a3eb-6490-5ebd-b9a4-f2491f473341 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
f392ab74-1c74-573a-a812-e32013ab6035 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.6 - Alignment Pegged out
0e3cb6b5-ca92-56d1-924c-6edc0ef78d69 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
2ec14756-9ff4-5dff-90c0-2aed1926eb03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.7 - Environmental
b9d7c430-9ac2-5332-a1c8-ef7f2c0c16bf |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
c18dcccf-71c8-53ee-b2d2-e895cc7658e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.8 - Existing services
9fd2ab3f-abf6-5002-bd88-9d1e12da3ee3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
8b7414e7-527c-5388-87c2-279c44b17d04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.9 - Abandon Drill Shot
19ca441f-d6d3-5b20-ac72-16060bfe194f |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
6bed8b2e-9ff8-598a-821f-6148392f88ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | 1.10 - Butt Weld Data
7fe90fa0-024f-5b2a-b85c-56cb00098826 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Pre-Construction | AUTHORITY HOLDPOINT
2549a203-6ca5-5dda-b359-9b8290c734cc |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction
31e90c46-3c58-5532-b8aa-312f60e15b28 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | 2.1 - Drill Entry Angle
8ffdfa26-c642-51fe-bb39-7e08040af869 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | AUTHORITY HOLDPOINT
1a8ef881-2b36-5eca-9bb6-540b62ca8d08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | 2.2 - Check levels while drilling
a2d1be74-ac0e-56ea-bfb8-68b49180a69e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | AUTHORITY HOLDPOINT
780b7caa-a1c3-5a62-b97b-ac509e8a42d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | 2.3 - Drilling Fluid Mix
9817eb1a-e8bc-52a6-9616-6395f7333e43 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | AUTHORITY HOLDPOINT
46042660-01ed-5ef7-b5d4-e2c6ec4f3504 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | 2.4 - Correct Reamer used
e8304972-5714-597a-ac57-662e08e6942c |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | AUTHORITY HOLDPOINT
af52a8ee-878e-5e0d-873b-99758eed6997 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | 2.5 - Pipe Damage
8b1a60a7-d5f5-5157-b118-ab93d2fc42e6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | AUTHORITY HOLDPOINT
dfb6838a-4d1a-536b-bff2-0bff54e99ad4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | 2.6 - Pipe Visual Inspection
8ca4bb15-95e7-52d5-8aa0-abe4967f00be |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | AUTHORITY HOLDPOINT
aa95bed1-b060-5c1f-9845-afe803cb2cf0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | 2.7 - Tracer Wire
1eb1f1f7-63c8-5eac-9c64-e25b0a8e7ad2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Construction | AUTHORITY HOLDPOINT
1e6cc791-e4c7-5666-80d5-413652986e2a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction
9dc19cd2-f4a1-5f0f-845c-482eb893a5e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | 3.1 - Drill Report
c0d09dff-e4de-54a7-80dc-3a221c3f1536 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | AUTHORITY HOLDPOINT
9c4d36f5-a151-530a-83cc-6d8ef3a5dd19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | 3.2 - Settlement monitoring and ground deformation (Baseline measurements)
1bb4ef87-bbb9-5da6-a4da-b7b8e979ca5b |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | AUTHORITY HOLDPOINT
b48eb3ab-0de1-52b9-b08a-028fc5ba070a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | 3.3 - CCTV
719e8d1a-bbbd-5d32-b280-c54a636ed358 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | AUTHORITY HOLDPOINT
a8a87152-4b9e-5793-a489-ce31976d9ca3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | 3.4 - As-built including red pen
a44221f3-7f33-53a4-8b66-b305dffc783e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | AUTHORITY HOLDPOINT
a47e0753-17d0-5ca7-8f74-12045ed5f095 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | Additional Notes:
717987cd-7d5d-5d03-a8bb-83541eb6f972 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
0f44968c-fcef-545f-ba4a-686c965fbe51 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Drilling Rev 4 N0-L1-MH1 to N0-OL | Post Construction | Add Signature
45f8d86e-25f7-4205-bbc1-9dd19b958cb7 |  | work-in-progress | ITP - Stormwater | checklist | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater
b4511a6d-b970-5ed1-bbc3-19ae6f2b9c6b |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment
5eb2afee-cab1-5192-94d9-a94f6d179882 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
81341985-25da-5638-9d9a-4165ddaa5a85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
afaeb22d-88b9-533b-b827-559b74ae85ce |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
001dc949-4511-5d63-8607-2fa2cc3029a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
2f62d0e5-6ed1-592a-87e0-da94639165b9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
f068c8a4-0e3a-5f8b-a6f9-93774037846b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater | 2. Material, Personnel & third party approval
a3a776ec-eba9-5be6-a905-d675b623a76e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
71e2f219-c5bd-554f-8398-cf7b2effc284 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
e96ba896-d156-50fe-a749-8438e8b42af9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
7532ef3c-1c34-5fc5-b72c-7c12c2c922ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
fe72c953-7482-5987-b4c8-7fd391382d03 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
c12e6a43-a045-530f-aabc-9011f6b988f7 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
da068469-50f5-548b-9882-0598f6e81229 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction
1c9ab6be-1a38-5e49-ae63-e747aab26190 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
0d9919f3-7033-5c4b-86ea-a89e8674da90 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
bffe834e-da33-5195-8ccb-589f5b87a5f6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
8c57c321-c863-5cae-987b-1d5c3f2b2e7d |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
c7b5ec00-a37c-54e7-8883-f499b6dfb725 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
961fd58b-8f57-57fa-819d-28c43c3ea712 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
f87549f0-c2f7-55bc-88ac-aa362020dc6d |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
dee60254-943f-517e-9e50-00ce6b420dfb |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
7c9f9da6-8a69-508e-9834-141406f509ae |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
ba5cb4f6-acaf-5749-8f60-bd585b5d2462 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
457f739f-90ed-53fb-8f39-816fd716ebda |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
a50972fd-49e6-54c1-8b43-e3c06a07ddbd |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
cfb664ee-bd05-5cb6-badc-1238f648e279 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
c2592c21-a9b2-51c5-b9ad-77e1b28f4b82 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.8 - Survey
b268ef64-21d3-53e4-b691-566af8d3e4de |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
d5554330-3a08-5e76-89b3-08d0daa90572 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
caf8282a-a5ec-5e08-8d62-56bd4df87cf5 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction
4801f4cc-d858-5fbf-9e1f-4d83944ea20d |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
7fc2c075-201a-5113-913f-5d73986a4871 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
7c1dac87-9e7e-5fcc-af85-faf2b7e3a06b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
a13e0b50-f767-5565-8b00-9a3e50f3e7e8 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
48019867-dbad-581f-afaf-1a1fe36a1f37 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
beadc53a-dbce-5b98-9a40-0a4d5024eb5e |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
3e308f0e-f6a8-54d4-8244-c99eff00d65b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
478f7720-f57a-5652-ac17-5f97568d99dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.5 - Survey
9cf33fd9-0d19-58b9-a159-f1b983cf16be |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
ee0e303c-ee32-5aea-a5ab-214922b27068 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
fd490df7-0568-5314-90b5-7ab2073520b7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.7 - Haunching
6cb04da0-467d-521a-8e8e-28400cf9d42c |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction
5c4fd8f6-2ad3-513c-8fb2-de90c3167ac3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
4be2835c-f226-5606-a278-4f5eb2a62398 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
d4396a9e-05d0-5924-a05b-0f1f69cca9c6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
9d96c278-b40a-575b-b385-6335f3208d4c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
ea72ec76-63a1-5830-8bad-7079dadcf918 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
a415d84a-3203-5d97-8025-53f2821668fd |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
60262f7d-ad41-5cbf-a836-0e64042d77f9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
747a66e4-91dd-50ce-a7f9-a2eaedba8632 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.5 - Survey
ee3c272b-e821-5df2-9ef7-f55f7a77833c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
b5f4491b-efc4-5399-9a95-26359990cbdc |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
c92be321-07e2-5ddf-94ab-e466a278ef93 |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation
fdaa7585-e81c-5c5b-adc3-404d4566c4a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
89ad09dd-ffe3-5199-990a-4c6442ee3c3b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
95be2d2f-db81-5b4a-8e34-d00f7f90a0cb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
d4e7a416-a00e-5fe6-93f0-92b8c22155db |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
8c00b9be-16f0-5503-b602-31441ed357d9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
cf7055a4-f254-589f-8c89-a0585a1b6330 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
7c2e1e04-cc46-50fe-9674-7e592b97b360 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
beeaa563-f58f-5f00-86ec-9e48ab8a19e3 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
bf36595c-c031-52fc-ba05-3168cbb8683a |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.5 CCTV & Reinstatement
e9619735-3396-5cce-b86e-0f2c693def01 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
0b3d1223-2f7d-5a13-8cbe-ec52bd2980f4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
b854e592-f46b-5c8e-bae3-fcef6ee459fb |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N0 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover)
34498b6a-b571-51f4-8b19-bd364f708845 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
e3a0d5b1-b9f6-5552-aea5-7bd95e7452a1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
3a54075a-f498-5770-9cfe-4d37c9562584 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
f71ac607-bd43-5024-9401-aa56e1fe5581 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N0 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Add Signature
59bee503-33bd-43a6-8172-ad1241fe0f37 |  | fail |  | folder | TRUE | FALSE | Site QA | Stormwater | N1
a4817768-0cf0-4b05-a3c2-0292069c3fdd |  | fail | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater
ea39b08e-b815-5072-be34-43b2cef55b58 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment
e2cc5759-1331-51a4-995f-c12277b593e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
73d72725-0118-583b-af2e-ce58202b53be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
f8eeb6f4-74a0-5481-b9b5-e6aee35c3738 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
bc25268d-0344-567f-9333-592cefc594e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
721fa315-37ae-5c05-96fc-63bcddef9b2e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
f4a740de-16e3-5bf0-acd8-b26f7a61e82f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater | 2. Material, Personnel & third party approval
b2d8f565-ce7e-5d3b-ad0b-5d808724887e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
4739b626-d092-5d56-8c2e-67c1cf8cbd54 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
52b2864f-0dfc-5a7c-8b02-dbec8d56ba25 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
e7a81086-7184-559a-ad22-45402bc8070c |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
91458ca0-9cb0-5447-bd65-d30ccef9b5a3 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
644c832e-4552-5e36-84ae-bf7f23e3baf9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
0bbfae73-5a2e-5741-affd-5223b0c7a28a |  | fail |  | section | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction
9512c148-eb5e-5939-8601-676a944bbe39 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
1a19d67f-1785-5e2d-b73b-e424927ec62f |  | fail |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
8a8d1952-d053-5ee8-8f5c-4e9e8b9f1b58 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
1c3e21d5-8b7d-5abc-9bd0-b1fe1c29dd07 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
09120443-cf21-580e-9cdf-612301054ece |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
a1eb48f9-87ab-505d-8b25-25649ec77132 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
1b2c3190-7778-5590-aea9-89e2434f2d4e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
bea15d7f-a3d4-5ac7-bcbe-2d3ed1cbde26 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
b63aa1df-af7b-5568-ab82-8f49e66ba882 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
e48b0306-d193-5ed6-aae1-f55b7e7a2278 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
eca83341-aac3-5189-9f0d-f50183338382 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
438cde17-4cb8-53a1-895a-e88e70305948 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
d53176a6-0738-51d2-bc4e-ca81c2cee835 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
463da1d5-9c6e-54a3-b6cf-6f3b570f769e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.8 - Survey
d5aae6e1-f0c4-54a5-ae1f-d6dd67820e11 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
1f4a483c-2dda-582d-aecd-f3732b50bae7 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
1cbb0084-e7ba-54e1-b28d-c3646ebad17f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction
d9e6429d-cd51-5d1b-94db-4a61b50d8cc6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
b64d2a32-dd68-50fb-805f-5188b65d8b0a |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
aed7fbff-778f-5668-b00a-29c0d8cb39e0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
d537c915-9de9-5976-9d14-b14991934715 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
0958e02b-4753-5dd2-a192-3c960434b21e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
6ce97932-c4e4-5b6a-826d-40afa94ea3c7 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
272846d0-8f20-5078-bb72-d0eba7684194 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
291bb6c5-8e51-5525-9863-fa101cae7a39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.5 - Survey
20d4f351-aed7-5cb7-aee6-20bb90f56892 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
61985357-4c5a-5406-9473-bcf9c979c2bf |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
0a2003df-ddab-5e51-9fe9-adbc0204eb27 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.7 - Haunching
8784d3af-ddd8-5c31-8d0d-615c33073c63 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction
178072df-409b-5776-a31f-529d374a8fe2 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
cee7ec7e-04c6-59d7-b3d0-5a813aa5b0ca |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
0594d04c-31fb-5c4f-8c19-49dac114575d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
839cc1e8-dd0c-5218-b0f1-433c769c7c96 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
da980f11-6793-55f4-b838-1778a9760443 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
6a6f5565-0975-594d-9036-ac3d5802441a |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
a7025513-0e44-5615-b394-be9e2dcc681b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
233a21c9-8815-5e99-9805-04e46a8cbe64 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.5 - Survey
8d2346bb-c17c-5bce-88c4-65d74c6c8078 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
6805ca45-389c-5518-8c86-ee22bc85ff0f |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
477115dd-f908-5d9c-9320-97bf5c1fe1ca |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation
40422122-ee2b-5aa4-8e64-1e01433db02d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
e6ce2167-72d3-5702-bd40-304c01d6cf44 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
cab2796f-fd07-5831-9f11-ac5ae0620e87 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
fd40a88b-2ac9-543f-bd7e-5b65e8bea498 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
16be8cb6-8948-597c-adb7-6fbbd9ba4369 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
5b137341-410d-5236-8ba9-2ef9a787bf4e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
8da6b1fb-2f9d-5546-99e9-0b0af9a51899 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
6ff382b1-29f9-5311-8dd8-3e578bddd69e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
3dbd3ad0-4ecf-5c1c-a7e0-f09c256881df |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.5 CCTV & Reinstatement
2c417926-2acc-533a-98b1-7b6d193a41b3 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
8f958fda-554c-5246-b858-bdd53ca9a410 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
cb6f8bb1-195e-533a-af4f-4fb4680ebe30 |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N1 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover)
55158108-2884-5e93-b5b7-6566f21a9f82 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
f9a28590-9231-5a41-b17a-3a5cceb0f49e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
f6e24b0f-1645-4261-9f96-fc8e18ddd820 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cb33ec2f-ab01-5622-ac4f-016bbc8bde86 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N1 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Add Signature
6c5a08ad-8035-4718-9971-b557e514e446 |  | fail |  | folder | TRUE | FALSE | Site QA | Stormwater | N2
5390a5a1-67e5-49a9-9391-74241fcb10a7 |  | fail | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater
d69d45c2-f268-5469-816a-0f0bd0610212 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment
c87ca77a-e4dd-5735-9909-8cc3b53429c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
5e00ce4e-f130-51dd-b946-30331c694652 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
728ea8b4-9fa9-5ed3-98b2-fa7543d7519f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
d3edfd26-4cb9-5b58-80a8-c65af415052f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
1727d001-4ee4-58d3-8539-9082c071b826 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
406b5151-cb03-5aae-8f27-a62600413fc6 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater | 2. Material, Personnel & third party approval
a7068510-4a67-5a03-8b41-0f8193716276 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
ef070172-edb0-53be-b3d7-457d2ecaf591 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
2b278b67-ec83-5155-9223-1dd8426ec5a1 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
160d66ed-8d3a-5ffc-ad92-0f69a03592fc |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
f8809910-fa46-5ab4-a4ad-d485d9dfb419 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
9cbc72a5-07c3-5326-bf59-d1708c1bb2e1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
cae7d015-7286-57be-8944-5df07d835dd1 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction
ad158ec4-06cf-5472-9a2a-9bb7e94f78b3 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
589023ac-22c5-54b0-8c37-fc86505dda5f |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
7dc8a727-bed0-51ea-ada0-e0a286db361c |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
5788e205-3b86-5afc-a155-c25ae6f59930 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
95149a80-1fa7-5dd6-9abf-00e587c5ebc0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
0bde06f7-227f-53ed-96e8-da7aecffb553 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
e16f1247-ad66-5469-b2e8-b10289b0bda9 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
d4535dba-7217-5b1b-8824-9aabe8244cc1 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
9e7ea03e-8c1d-5739-9a90-7c7c21cbb690 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
fe92d533-4830-51f7-ba4b-f492e6e7e408 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
e145402d-c2cf-5781-8c64-d2df9db7bde8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
a63e0bb0-39dc-58d9-bfe7-5d98ca05417a |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
8537291f-2155-5728-b455-8ddd54c67a37 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
950450ac-68b5-5627-811d-c584915a698d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.8 - Survey
52baf022-f0a7-50e3-a3f1-68c99e5278f2 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
c8a565bb-03b0-5a24-ae6c-5d90172c36c3 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
8fc1b57a-3306-5551-8904-d1e9794783a1 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction
c28c1f7d-5232-5477-9680-604a1aa77427 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
4fa1b24c-44aa-5c3f-9773-7e034980c1c0 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
3f6f01e0-47c9-581f-b7c4-4a5268e11d98 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
e7c69a41-a441-544e-a578-42472ad72856 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
d0742cfa-ccb3-5972-8c80-1b02084e1c01 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
de3b2f43-4be2-5134-b525-15d05cf913a9 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
a347ab45-1043-57a9-8061-d916a3b438ca |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
271a5d90-2f37-55f0-bcaa-ef8e1b389705 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.5 - Survey
219f8ad9-7aaa-587e-9b95-b2e921c93098 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
1c42a1f9-4d74-5070-b150-6c30a62c7923 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
b8dc275d-31b6-537c-b988-c2870cb299af |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.7 - Haunching
afdc0c72-12d0-5850-9433-1f648cb121b1 |  | fail |  | section | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction
21880442-358c-5dfc-9124-4eef626ca606 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
b50fff0f-c5a8-5e3f-9a61-36c09934a781 |  | fail |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
3546fb2b-2b95-5efc-89e7-b9fda2c31a7c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
1eef3bad-2043-5d77-8bb2-6369b5309168 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
4d9edc5c-5b12-578d-bcdf-fd7f7a5a59dd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
0f80ca63-ca44-50e6-aa2e-feaccbae999f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
0d044a5e-cba8-5b6a-b4c3-0b209825fc1e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
9bc95d20-5ef3-5584-a1bb-66183194e16e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.5 - Survey
d6463250-6b58-54a7-967e-ccf640d05263 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
6835654b-63ea-5ff7-85f9-03b3b1c48bf5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
b305bf2a-2f96-5ae0-ab51-d28f5b140276 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation
1313035b-a254-5b6b-a124-3d89faf139d6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
a223409b-7ddb-5524-a3b1-97ff1e558268 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
714229a6-f712-5311-b7e5-7d0078937172 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
a244a3e6-e29b-55f3-8313-c1ddbc0c31e8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
b419618b-8392-5250-a340-082d896c7558 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
a4827bc4-5f9b-55f4-afa2-fbc598109f5d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
8755a98f-d587-5674-b329-307a5395ceea |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
315eb17f-8014-513e-ace0-2c35978c98ea |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
8b0f76b0-379a-5c08-ad66-ddd2e25ac691 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.5 CCTV & Reinstatement
c58121ad-9f15-5b38-861f-d1e4b95009f8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
ef3b92c1-7efd-5406-819b-b3a5008ac2dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
e91939a9-8bfe-5c4e-b7a7-8f26687e53ae |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N2 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover)
300cc263-3f63-5514-8290-8d754ada2aef |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
602ce04b-a4d7-5f34-aff9-71e76ad5db6c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
46f331ac-db88-4027-ad1e-3472dbbc0aa4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8d5ed6ad-e02e-53f7-ba09-afed162994c7 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N2 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Add Signature
bce27650-9030-4b71-8810-d2cf2fdb3b98 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | N3
9e17354a-4e33-4c9e-9fdc-2531da8e283e |  | work-in-progress | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater
eb3b445a-0c3e-546a-8c1e-059355c25821 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment
79b5c0c0-c352-5437-a681-85c3d54da5ae |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
a32e99e5-3272-5c5e-af3c-6b523b4d9ebe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
0b342621-5216-59a4-b71a-463bf9236c80 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
e127dd5f-aa6c-5ad5-b7b4-9b6cb77454d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
0395e428-86c3-5c2f-9e10-d1f0aa432e11 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
7de2ec66-ef52-53d3-9675-162621b2a3cd |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater | 2. Material, Personnel & third party approval
5952e46a-c1b3-5de7-b97c-9224b0c9d727 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
73f204b6-eeed-5400-a2c0-e2beec75f163 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
ba07c7ef-66fc-565a-b3c7-e5c26aa99229 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
30f7963f-96d9-5287-b68d-8efe5ab54999 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
7e5bff8b-565e-575a-9d7b-cba26d152dfb |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
c8205445-cf9f-5cc8-8484-c428e86d5754 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
d8087515-232b-58aa-ab66-14c901d96788 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction
c8ccc661-ca96-565e-8070-7c42b0fdadf1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
68fbb0cb-3c2a-51ba-9597-ef906793e6d9 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
46f6d47a-47d3-5f7e-8229-71fdfda743b5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
c72b5191-2928-58b7-9281-ae38271d96ab |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
01c00489-6cd3-566e-9210-846eb6cca920 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
ebe04a79-f928-5d1e-976b-732e503f0d4f |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
d45459e7-fcbd-5c67-a4e7-088e42ec6700 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
b9eb5cb8-c9ac-5749-b4dc-1e41d1190819 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
b3d6686f-6d64-50cb-ac2c-90b19596ec00 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
2f895876-616b-565e-ac4e-3a5dff02e5fc |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
8343f255-a736-5519-b838-e3da1d00754b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
2d2a91ce-1e35-5a29-8637-dd76ea29df79 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
17e1ba55-c9ef-5f92-adcb-3bf1e79e4685 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
7237529e-23eb-52f7-89dd-15f9ae279c8c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.8 - Survey
69212ca3-7a82-568a-a3ff-ba3f1e552444 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
2f59fba5-8106-5611-af3d-53c0fd49e7ab |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
bb3d83ee-a79d-5a65-8fc5-7130eda924e7 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction
bfd78095-4fa9-544b-a857-a0ae17134898 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
05e9eb94-f10c-583e-99ed-2db643c10658 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
a2aa1271-f2d0-5b1b-9719-4a3c80513358 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
26c0002e-7ded-5a5a-b28c-5fc047a04bd7 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
dc308277-2d3e-530a-8cff-2028307688e3 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
106488ea-f98b-52cc-a2e9-0519fbfd2eb5 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
3526e37f-9796-5656-b2f4-12a926b8517f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
5234544d-a36f-5f9e-aa53-47e37f537db6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.5 - Survey
f30a9f1a-6d78-56d1-aed2-c82e34ad536a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
7c49ff8d-9481-5563-9ea8-c977b2dc769d |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
b66dc128-243f-532d-9a7d-3199cc6ef685 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.7 - Haunching
4da61d0e-e666-597f-b0c8-e27b7c5e2e37 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction
6ccc4237-b4f4-5bb4-b154-917534fd77a2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
bd71cf09-1030-5132-900c-bbf7814ee68d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
adc5091b-cc04-5f60-b47f-c5e7b4e9a1be |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
13061cfd-57a1-5d62-9eb6-d0c31441d71d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
45093990-16a4-5fc5-8fb6-19c7ce14c0ff |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
500a8f46-2450-5b64-b9fb-043243bde95e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
257bf4a0-8c82-53e1-988c-ce002165ace8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
bf55b56e-95b0-5f09-81ce-39488d326136 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.5 - Survey
cc02cf3e-5453-5dc1-a503-6d3dd5162d6c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
b68ac8f8-7e2c-5988-b5dd-781867bb7812 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
a4627297-a9bd-57a6-9813-46eaebca74cd |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation
31ad66c1-2fde-5992-9c55-6808248014ab |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
28298221-121e-5623-bf05-af63a4539cc4 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
5ae2ecb1-2435-5d49-b03c-3c478d724c75 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
aa9cb461-9d6f-5e16-9ca7-99f5154530f7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
c79c8fe4-f117-5dcb-b550-a64038efe8c3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
02e6d87e-9466-5a80-a20e-0b25e0a16d9e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
ccef4b96-9f4e-55f6-8165-9595e228fba4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
2ae8ec41-8600-5d49-abc0-28ef96a235f1 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
7cf9e163-98d8-5e27-a15d-d57dc1523197 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.5 CCTV & Reinstatement
afcfbad6-16de-51d7-91fc-0a12e994d7c4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
0bfc8854-139d-5f3e-895a-7a9c557ac636 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
322f7d1e-46e8-5579-80a5-ec8177b8f86c |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover)
340eae89-fc18-5326-94c8-6fe716ce5857 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
91f6a180-f0cd-5d2f-9518-1dbc45417d4a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
8adeef62-de82-4b71-8cf8-f22dc77cbb3d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a705fe72-d410-5bc9-9246-c3ab8c3b3552 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Add Signature
1c9e1e09-605c-43bb-a609-6b5884edca83 |  | work-in-progress | ITP - Drilling Rev 4 | checklist | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1
81e0e4e0-3be3-524b-88c2-e8d61a9153ac |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction
d07d4f6f-ff68-5714-873f-e24e66c3a227 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.1 - Materials
5f8bbcf7-c9f0-5960-8541-de496516e88e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
2f2f99f6-d33c-54ab-af76-d13a54ad6831 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.2 - Settlement monitoring and ground deformation (Baseline measurements)
e411bd1f-8dfa-5f55-971c-5bb652a24726 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
6524dcba-7f79-519f-b21d-412da5bf79cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.3 - Qualified staff
1afbe234-609a-53e1-80b4-9b36682995b7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
261bb1f7-07bb-55b9-bd54-3cb4564f044f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.4 - Tensile Test
13cbeb79-630f-537e-94e4-c6a0727bb1be |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
782793f7-b0b9-549b-846e-73b1cd6096e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.5 - Drilling Fluid Mix
e3ed777b-7f38-5763-8aed-f93f2b597b26 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
02a79199-874e-555b-b31e-225df116b464 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.6 - Alignment Pegged out
29102f6c-1bcc-5cf4-a258-5f29332371df |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
a7605770-a9c5-54d9-ad20-1ecc6d417c48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.7 - Environmental
8e8e46ee-e0f8-5e37-b11d-733a9853f72c |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
b3df69d6-dc32-5adf-a5fe-e11935cc5f81 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.8 - Existing services
bfba0021-190e-5671-b95b-1cf7577dff8a |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
47e42197-3169-58ec-90a8-9ea9a38620d7 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.9 - Abandon Drill Shot
d117f757-5b00-5c38-a6fc-a39ee7c56a29 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
5ac3c2f4-f1f0-5169-8154-1dc4267aa332 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | 1.10 - Butt Weld Data
981195e7-575f-56e3-bc24-bf1a496819a4 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Pre-Construction | AUTHORITY HOLDPOINT
36365cbb-5e8e-50c0-957c-bc805832f909 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction
15ee7cc2-22ca-5578-bc0d-232a773ebff9 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | 2.1 - Drill Entry Angle
7ab01444-a938-56de-9265-999d09625622 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | AUTHORITY HOLDPOINT
8f091b31-83a3-5d21-8e1c-f722704d73a1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | 2.2 - Check levels while drilling
6d5f94f2-b2f4-591b-8925-4c9a896058db |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | AUTHORITY HOLDPOINT
3279cd09-9251-54a2-b0eb-d067943d275b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | 2.3 - Drilling Fluid Mix
9d3b5f32-ff26-5957-abb8-28c1a384cd39 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | AUTHORITY HOLDPOINT
7634ffb2-e527-5b4f-a423-63c6abd44077 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | 2.4 - Correct Reamer used
8c44d54d-696a-57d1-98d7-666ecb4ceb47 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | AUTHORITY HOLDPOINT
699e46ff-896d-5af5-82d6-09cf5ea44b4f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | 2.5 - Pipe Damage
3aca8200-6347-57d4-b169-affab47112e7 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | AUTHORITY HOLDPOINT
0c98f790-39af-52c9-95ae-9e53068cda8b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | 2.6 - Pipe Visual Inspection
cc470acd-65c6-5758-88b0-fac5b7b5c7a6 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | AUTHORITY HOLDPOINT
8799f2e5-6947-5951-a6c3-39e52932a348 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | 2.7 - Tracer Wire
213b9a44-eab1-5f90-b1cc-6e4931eaeaad |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Construction | AUTHORITY HOLDPOINT
d3c18dc0-0446-5c3a-a8d4-d2658efcb5c4 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction
141ce125-1e2d-5c99-b352-4e469026b2f5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | 3.1 - Drill Report
80f6bcdf-253c-56c1-9b79-5e1bca753580 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | AUTHORITY HOLDPOINT
347dc78e-41f9-55f8-91b3-4cbd4c14cf15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | 3.2 - Settlement monitoring and ground deformation (Baseline measurements)
8c4338a7-1611-5e09-9908-13e6d695549f |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | AUTHORITY HOLDPOINT
44c1094f-d2d0-5b53-aca4-1f07a20ae661 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | 3.3 - CCTV
fda7609f-9619-52c1-82ec-21c38e0de22f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | AUTHORITY HOLDPOINT
47443aaa-1790-5474-99a6-8fd50f78ecc9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | 3.4 - As-built including red pen
99cc4647-b891-594d-a848-dfdda80a3d34 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | AUTHORITY HOLDPOINT
0298e5de-2180-54b7-9c46-c2e333d90e26 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | Additional Notes:
5a8aab93-a695-48b7-aa18-c0e79fc6db6c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d3e03757-7a9b-5b28-8832-94c423b67147 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N3 | ITP - Drilling Rev 4 - N3-L1-MH2 to MH1 | Post Construction | Add Signature
80c46f3f-d4e5-4085-9926-572eb7ff2e60 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | N4
b7af94c0-3eb1-4c63-a592-650b6f39cc39 |  | work-in-progress | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4
47f11084-814b-5cf0-8ac9-ab71c21d9085 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 1. Pre-construction (P&G / EStablishment
cfec3d9a-328c-50ce-95e4-42dcaf61000c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
bfd33257-1e85-59a1-93d5-be3637547ffa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
c464f3fa-24b4-5f02-827e-a8404cb50583 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
0c991443-1af4-514b-b5d0-e5220ba49c17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
6109c89c-c108-5781-b83c-722656908364 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
36ecb5f6-560e-5d65-984b-f6c998e093c4 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 2. Material, Personnel & third party approval
e6f84859-68ff-5172-b7a0-645613f77c7b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
9f3cd62d-dc20-5ecc-9cf2-97fec67a0d97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
98633ac7-e0da-5582-bff9-791cc8cad9ac |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
23c113a4-c48b-52e3-b053-15aa357072db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
c7205e47-e956-5175-848f-5f14e251e789 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
d1186146-3a63-51a2-aa79-a688748d1351 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
c2d58273-af55-50e4-83f2-c60708971186 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction
9775561f-af69-5a4f-a67c-ca6207a31d51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
669ada46-811a-5112-a0fd-affd3e78c656 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
912d9133-0e88-594e-9a8d-75729b2d8ae1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
03812c53-503f-5dce-832f-205ec01026eb |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
896c8709-b6a6-5780-b18f-ee7d44a99aeb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
c4f2a7d3-a0ef-575f-b445-c4160c478f22 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
e3c7af29-d912-50d8-8806-4fd7aa61e372 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
5f5e9384-e4c8-5038-8a78-7907eaf3cedb |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
e49df1b6-05a9-5fd8-a538-2b6c94b707b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
21135393-1323-51ca-a0e1-5cf4c4079361 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
dc3bbe3c-03d1-51ee-8712-a709e3d0bc1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
c3c1b3e6-8f7a-5aeb-a8fa-caa9fe1f90b9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
98d9c943-eb09-5066-a5f2-0cfdb1a3e24c |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
e4d51137-b1c1-5870-ab04-8f1995397817 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.8 - Survey
cc5cc67d-3e08-59f2-ada0-74f8c607aa13 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
270752fd-5bdd-5e4e-98ab-c0e2f00292d9 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
de92d805-506e-54bb-9af3-c80db0ce98c0 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction
80ea7dd6-3408-5c58-839f-49f96157c51c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
e6e00d1c-f8ea-55e7-afdf-af18077c8cbc |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
a8ac1966-9913-5f1d-8aed-b85d3fb1aaca |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
9eda4f05-0076-54c4-872a-817a2193931d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
22230476-80b2-502c-9aea-d7c4a3868d0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
e8703cfd-7e9b-5b3b-b104-f17b58f55d4f |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
1b083f0c-aa9b-5eaf-923f-05dfe4f8b895 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
6a5deaff-7990-502b-9294-370031b6f301 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | 3.2.5 - Survey
c0ac8363-fe95-5418-b96b-65ce4c089377 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
d96b9cd4-5ced-5635-8cb9-7077e99b032d |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
a0425290-3612-5491-b51d-c5e5e953fcde |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.2 SW Manhole Construction | 3.2.7 - Haunching
e7ec1d06-66c7-5c12-9959-53708004628e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction
7907f264-909c-56f7-abed-c5a45cd98cdf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
246e929b-bd25-5d3f-8400-1a4858490533 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
43048000-18c5-5a5f-9c41-9174ce628cb8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
fcab4b1e-32f2-5c03-980b-e32d6350ee1e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
907223bd-fbb9-536e-8243-dbb86a610e36 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
2b1d5fa4-036f-5bff-b316-8c484433e866 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
fe83e0cb-0fd6-5555-b68e-c6182ba6e287 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
8ef57c83-f17c-5a42-a72a-13eb06065e0b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | 3.3.5 - Survey
b7ff91d3-113f-54a0-86ff-c9841cdd8b37 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
2cd98268-e0e1-51b0-af4f-63b65b966acd |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
521f2479-f3ba-51da-9105-11df0e6750da |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation
88892d39-9850-52a0-ae20-5b158b406321 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
06e2b1fd-634b-5827-9780-78880fc3c146 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
356aceb6-2802-57f8-8350-f0ca33ab891d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
11241169-a38f-53d9-bc4c-0b176925b435 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
3a5ad035-1bef-5d55-b160-db4ccc6b52c9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
903a8279-b7f1-5c7c-9e98-e8131c396348 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
4be70772-e0e3-5d62-9111-c3b82fc589a1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
edb9978a-5416-59dd-94bd-e645927574c1 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
0c033721-21f9-5351-8cc4-cd34bcec6952 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.5 CCTV & Reinstatement
7ed7e3d6-f22b-519a-a920-8e0912bb8404 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
9462522c-a849-5ace-a57f-cf87c1439a12 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
493c80d1-51b5-5bb5-8cef-16ef7ed60024 |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 4. Post-construction (Final Inspection & Handover)
9fece939-654a-500c-86fc-ed7655f6e9ee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
fb8153f6-83c9-5838-a23c-551386cae893 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
c00d8dd2-ec51-4b89-9638-9b3aa7695ede |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
23f8da41-9fe3-521f-a7bb-a35529d92e31 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N4 | ITP - Stormwater Network 4 | 4. Post-construction (Final Inspection & Handover) | Add Signature
a1a3d6cd-10e6-4deb-a073-59f9e6b4cc9f |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | N5
35b44438-7f45-4402-9fae-deeba9a718fd |  | work-in-progress | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5
4db25b52-edf3-54b2-b851-fc01d0c66cf9 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 1. Pre-construction (P&G / EStablishment
7e4a205d-6368-5053-a322-6b8b1f04e607 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
797ef82d-0123-56d5-8ae8-850776d0e0a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
71a96062-7a60-5f7a-8149-393ceb69ea55 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
6ef97112-b468-5f50-8c2d-a40653f7f663 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
61494b66-85b0-521d-b0d4-0b038fb97fa2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
c602fd39-4eb0-57cf-a748-64dbfee8669e |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 2. Material, Personnel & third party approval
6ec22fc0-c41d-5600-aea7-37d2b54b4d6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
daabd8be-f3a7-5a8e-85a4-2eda14f519c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
d41d0c51-2cc0-5896-9040-e2f77a378c01 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
fc6e68d8-3d2d-5c91-8683-43350d2e13fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
345812a2-4d6b-5b47-a9cd-b82083bbfb56 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
9e75d69e-fb97-5067-b053-4345465060c4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
0715dec2-c410-55e4-82c6-daf21fc627ac |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction
0b079b8d-95df-543f-914b-af2304b0ad27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
da063ffe-5afc-5834-8349-d4ca1f26c675 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
4071e471-5287-5bfc-980e-e961ffeb00e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
2d31a661-583b-5603-81a9-766f32e50819 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
6b78d522-b749-5b7e-a941-c30d253e0937 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
d9841c26-2570-5b31-b37d-2df2e6ba018e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
d94dc9f1-fa1e-5e52-ae94-fe5cf69b0814 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
8d074066-a4e2-5bf3-859e-58b4a9dc1877 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
57e26e7c-edb3-58ff-9af4-4258f9d16f9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
1ab5468b-70ee-5380-8d1f-bd711c5064ff |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
2ee9ca7b-112c-57cb-a995-a0acff6006ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
2af14a59-d48a-56a5-84f7-78e5cffe5d97 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
9b93ae76-ab20-5b69-b2b2-f7d2a29ab93e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
a230486a-e2be-5aad-98a8-a6e016060f01 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.8 - Survey
0e3ad1b4-b844-594d-8640-a46400262f74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
63696f5f-4824-5518-b9de-84d9d3ceada5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
3fe69dd0-202d-5625-928f-e863327e15b4 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction
01e7cae4-c963-54e3-bafc-b04297cf5dd6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
f2afbcaf-db90-54e0-903c-9882cb85afb2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
801e5886-e4ce-5917-946a-6666fb55d721 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
56e06c3c-cba5-5dd8-b4b5-67ecd2c5cf23 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
2d2f021c-3908-5ff0-9c60-4a3d7377a2e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
13e24248-b986-5284-8fde-22af890b8f60 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
7686dcf9-5755-5960-a0c4-7959da277bf6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
1fc327fb-b890-51b6-a93c-9a7b97ba7ca3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | 3.2.5 - Survey
341a42a7-8508-5171-a4ee-7e8cd53035ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
98a46d5c-4029-55b0-b6b2-d01a3aa47628 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
e98c3b7d-d22f-5486-8361-da4609f344b9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.2 SW Manhole Construction | 3.2.7 - Haunching
028e24a5-030a-5e01-8d30-1916841b61aa |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction
7909a4d2-9638-5b17-b240-cdc8a5c47bd7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
60216e92-665d-5295-8520-e499844d4302 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
f385656b-562a-5dd1-86cb-b98215ecc1b2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
46716721-cf4f-56df-88d1-e023fb9536c0 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
46d22904-0724-5fa0-9b19-41ffc8d4a539 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
ee901b0d-04b5-5f2f-8c69-d0d1e18bbcb3 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
6c19583e-1726-5371-a867-462b10678969 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
d8033e78-2ff6-520f-87b4-be9776bc65ea |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | 3.3.5 - Survey
f9377dd2-fe4f-5ba0-b71c-98536ffb5a6b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
521e5276-bb15-5c19-afd0-bff72565ab71 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
7dbf11d1-bf36-5a5e-b142-132b69e666cb |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation
78ccbe47-1962-5c17-968c-203a3b94d58d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
a8767d90-1e6e-5e4c-bfd8-082f57aec33e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
65836fa3-109d-58a6-a975-eb2a8930442d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
8bab6c86-6b22-5126-9819-b781f0c5c711 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
c57697a4-25e7-5293-8e06-fc41c1c59ceb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
1c405f9c-eedb-5e00-9f38-737020ebce92 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
b68b1434-dcb5-5957-b360-dcc6ea28ea6d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
fdee9c74-1feb-5d4b-acd2-381681b62525 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
0dee5f9d-223d-5c74-bac1-6e47bf8595e2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.5 CCTV & Reinstatement
d4133882-0e0e-51f1-bf8b-399e8a08ebbf |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
1dfcae4d-369d-573e-9298-617a48407dbe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
a58771fc-2118-59bb-ae34-bdc28c3528ec |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 4. Post-construction (Final Inspection & Handover)
10dcb6d5-493c-518d-8193-ceb416e10497 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
7a9f5bc0-4217-5273-9827-29530b776ba1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
04fba731-9832-40aa-a740-af071cd3ea8b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7d3be2c3-5e0b-590d-ae03-a95a6e0c449b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Stormwater N5 | 4. Post-construction (Final Inspection & Handover) | Add Signature
6e6550a9-9ab5-4a14-9a65-3af384d1e569 |  | work-in-progress | ITP - Drilling Rev 4 | checklist | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL
dac76974-79dd-5aa4-b53e-47390699d0ec |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction
7ce5ecb6-7b95-56e5-a150-0e1a16ce3fe6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.1 - Materials
e4ee9559-fc30-5991-9f87-0cf76149f542 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
0cdf012d-6506-533d-9929-c80ea28ccdc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.2 - Settlement monitoring and ground deformation (Baseline measurements)
5d73f809-c1be-5822-8004-64cc13821e93 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
eab8d436-252a-58ab-a885-1c5c5dabbdfc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.3 - Qualified staff
9b297c91-c531-5579-a898-50678700032f |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
8ba9a36e-b463-57fb-823e-1c4ab9bb9495 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.4 - Tensile Test
e8f831dc-3a95-5a0a-99f7-ad1af5111128 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
437d2a4f-1dc6-5822-9d11-57989227f8c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.5 - Drilling Fluid Mix
ed0e2f71-65ea-5aab-b740-1cb94ee91676 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
7786ae1b-cf05-55e6-a003-5e872cc66226 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.6 - Alignment Pegged out
180b76b7-97e0-538e-ac6b-8d7dee2ee54d |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
d19ccf0c-0307-5bc1-a9c1-3629121a7435 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.7 - Environmental
3c2dc31f-fedf-5dd6-8960-29a16ddaae04 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
d4508f1f-b112-521b-9ece-336c5a27b085 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.8 - Existing services
f07b2846-669f-5be1-858b-d74f25513cab |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
a6b8c0a2-c0c0-55c3-bea2-bb2b0cb2cc9b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.9 - Abandon Drill Shot
ef1d5e2a-0dea-577a-b09d-a358a4efbee3 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
0ae7e5e6-c951-5ff9-a2bc-e58491eff8a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | 1.10 - Butt Weld Data
cf78d8bf-a430-59f8-ac14-7f8bfcaf22a2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Pre-Construction | AUTHORITY HOLDPOINT
c6bb643f-af31-5656-b599-462b0f59a36f |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction
0e8fba5e-776e-578e-85f0-28fc6ce5385e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | 2.1 - Drill Entry Angle
d4e8bcef-04b5-5f65-b605-663fa319cb14 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | AUTHORITY HOLDPOINT
38031605-92e0-5e3e-8fe4-8c31dd318ee3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | 2.2 - Check levels while drilling
85b69b83-f71d-5a1d-a794-31a5222afbd1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | AUTHORITY HOLDPOINT
2e9aa6ce-11da-5a07-919c-cae7c3b04018 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | 2.3 - Drilling Fluid Mix
6fd83fb8-4638-584d-b845-1d733c916092 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | AUTHORITY HOLDPOINT
a322dc7d-4a80-56b6-bbd0-1919dff880b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | 2.4 - Correct Reamer used
23678364-7488-55ba-a8a8-517d075c163d |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | AUTHORITY HOLDPOINT
111850ed-e395-54f0-a86e-7f342a5243f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | 2.5 - Pipe Damage
490c2539-31e7-51b2-ae0a-69874104405d |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | AUTHORITY HOLDPOINT
745d9ec1-9883-505f-91df-7e4b911fabee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | 2.6 - Pipe Visual Inspection
1b515818-28df-500b-b1fc-dc062c58b99b |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | AUTHORITY HOLDPOINT
e52c9518-ceda-5047-b659-6156f6be85bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | 2.7 - Tracer Wire
4e191dd4-6eb4-574e-80a8-686d1bc47743 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Construction | AUTHORITY HOLDPOINT
b2012d93-a9ee-59c8-89a2-86e592c3fb57 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction
733335f8-bd5e-5d24-85b4-a3726a152ffb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | 3.1 - Drill Report
833b64c3-f760-5fbc-a3a1-660699d99a46 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | AUTHORITY HOLDPOINT
432e335b-3932-55f0-9250-8261771c6cf3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | 3.2 - Settlement monitoring and ground deformation (Baseline measurements)
e87a8c6c-94eb-5c01-9da9-bd2ee8e43de0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | AUTHORITY HOLDPOINT
57f35e56-1e4b-542d-ba13-dbfcc816ea38 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | 3.3 - CCTV
6b406959-2cc8-5ad9-906a-925498f8ec0f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | AUTHORITY HOLDPOINT
e5816935-ecf8-54b7-a7e3-79db3ca3df10 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | 3.4 - As-built including red pen
b1ba7381-7260-5226-a15f-d36fbf193c2b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | AUTHORITY HOLDPOINT
6167491f-8308-58d3-bb99-97139e4f6f6a |  | no-status-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | Additional Notes:
3270e035-a56e-45fa-9b0d-bc344b483562 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
72db7f3f-30fb-52db-b97d-6b1816177ed9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N5 | ITP - Drilling Rev 4 - N5-L1-MH1 to N5-OL | Post Construction | Add Signature
5542c43c-015d-4ee6-ab6e-73b22cbb7a65 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | N6
70b04526-1274-4ddf-b7bb-aad2e8538437 |  | work-in-progress | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6
f51de3e9-6c94-5c1a-bfa9-2ccb8f254ab1 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 1. Pre-construction (P&G / EStablishment
33540963-2970-59a7-82fd-302930243816 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
384003d2-b2b8-5b34-bae9-5b540b404b20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
6f72e733-bc9e-5d8c-9a4f-74cb6934400b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
ec60b827-ace1-5e9d-a0af-547fa47d91a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
1983c2b7-a182-5881-b77b-7e8846830923 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
dc0958d4-246a-5c3c-9e61-0ed4f9f43684 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 2. Material, Personnel & third party approval
444f8940-5fb6-586c-86a5-47d600b67271 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
fb44c21d-d179-50bf-b760-77942234de15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
50335619-2586-5af5-9200-b0dfa96899c1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
91d25fff-72b6-55a1-93a8-bfb370f371a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
560e9e48-f07d-59e6-b47c-4cab348d8679 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
9f21364c-51d4-563f-aedb-edb437f5d5f1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
9f7426f5-5279-5893-b2a9-3a8858f0b30f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction
ad765879-3bd5-512e-8f07-81dd65109ad8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
8499465a-958d-50aa-8cb4-630c498d1a6b |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
a22c50bb-3079-55a6-9d02-03a1f909e906 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
eaef6b3e-269e-5388-9c72-567648907dd9 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
f83750f9-057a-5c1b-a0dc-9db3ce1ceb59 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
239ba692-9dd2-5324-baa9-dc78706c2c9c |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
927d642f-b021-5632-9e87-112b60ae49c5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
350b5d3f-5ad8-5be3-a971-b3fc32b740fd |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
3765ed7d-7e8d-5cc6-a087-0a5c0c9c7eb1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
7b3f167c-311c-556c-8882-3e63c9ce1a31 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
1872d052-16df-58b0-8e3c-6b4b11c2136e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
eb15c8df-2792-5637-ab3c-f6a027463d6a |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
84d1575f-47a8-556b-b641-0377fbdce56f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
3764129a-cc16-5e33-8c38-372fc2f51252 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.8 - Survey
81623138-ba50-5001-a8fb-a2c6c56eec45 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
6bd31766-f918-5c34-bece-702f10d137ab |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
9dc4077e-617d-531a-a3f4-e301179f4638 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction
698cbf6a-7a48-50bf-9d8b-c63d64fc32f1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
b2e06a07-0b81-54c4-9d03-6905fddf18d4 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
d05b0a7b-5224-5e5d-b3f9-0dcfdbeb0ae8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
ca6a8312-21ed-5cb1-baea-9fb387fad953 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
5b83625e-fdda-51bc-ae5e-7f30d66adebe |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
eae5f6ff-a274-5a70-a9bd-2b54687b0eb0 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
f0ed474b-260d-5c59-8604-ffec33a9fbda |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
2a3be92b-b5ae-59ec-b315-b34dcdf8e363 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | 3.2.5 - Survey
af53244a-a152-5086-ac70-ccb68be5ca15 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
656e3fe7-9e14-5624-9cd8-4fc884de0501 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
1177c7cc-6245-5692-b548-54129e14e00d |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.2 SW Manhole Construction | 3.2.7 - Haunching
48299d85-1dc3-54e6-b2b1-94cb6da5c88a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction
933b03bf-8229-5ba3-a35a-b9f11d415782 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
018dd748-69a1-53af-a19e-6f7e2e1f823d |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
4a865c69-58d7-5fc2-affe-f64b0d2b8662 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
a32e2a30-1d10-57aa-947a-30e89fca2f0c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
3779663b-61be-5a21-b5bf-fc916689627a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
50fac391-49da-57c7-9e80-a35446ecff9c |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
d7f8e708-ec1a-5028-a2a2-a5e3647cb9b6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
3279408b-4da0-5049-ae9c-4a3f7e9a12e7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | 3.3.5 - Survey
19469634-3711-5e9c-a21a-987b2e40e3d4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
5cbf6879-7bb5-5b82-9356-38562327487d |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
7954e5a5-064a-55cc-991e-f22e31b13ba5 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation
1e0bf3fc-d66a-51a3-9d72-f29d02bde15b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
bfb3ea1e-7c08-5872-9825-d0e4ab4a26c1 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
c308f89f-63e3-5b32-9d88-b228a4f8918c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
cf227a3d-2606-5a49-856a-199393f14c5c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
a0becb72-1230-526e-be84-408ddf3028fd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
caff5b2a-014d-5ff2-9e73-9afa46350bde |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
1635c686-eafb-5a9d-b67e-e6f7011565bd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
ba7258ee-1fd2-5528-b41b-9ff624da6661 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
09cd638e-6cf9-548f-8c2c-72df03e3afd7 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.5 CCTV & Reinstatement
915582c1-c012-5cb7-bc61-c861f4f000b0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
cc04c3f8-e325-53b6-9656-7b83d4cd3190 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
f289cb72-8ccb-5bdc-8b6e-e5e0a7230bbf |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 4. Post-construction (Final Inspection & Handover)
d78e5ed1-3bb5-5bcd-af1d-a8c0f164acff |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
a859de96-0c4b-5b4e-a0e9-92c2dcf8e4f1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
46d0e607-dcaa-45f1-a5b5-3f06686a6f83 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e41e383e-be9d-5e1c-9e7b-73bff07d1718 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N6 | ITP - Stormwater N6 | 4. Post-construction (Final Inspection & Handover) | Add Signature
6caebf91-d657-4418-be0f-6f65b4e79a31 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | N7
f6ecbe1c-519b-4434-8f3d-11697130c9ad |  | work-in-progress | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7
07ac3b42-6fed-5809-9b88-87075e275ea7 |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 1. Pre-construction (P&G / EStablishment
9cd2d077-8ad5-568a-993a-13d9c85e5899 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
b866ef1d-1d91-5be2-9c6e-bff4969aa77d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
f3175a0d-5c13-59ad-8a99-aa444b2401ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
f2e1cb36-c6ec-5d23-9835-fed9f1f0265e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
d881170d-aa47-5972-bcce-e3fa308c19fb |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
f1ffa0b8-16f8-536c-8406-9ed25c9aeb1f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 2. Material, Personnel & third party approval
f08ca017-423e-5026-92c1-8a444e10b7bc |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
f6c7b085-bbe5-5fff-b7e6-5c26cd9c4eb6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
f0364883-7d25-56db-a77d-dbfd25db3de0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
8e550c60-e940-5d85-9604-5d7fa0e58179 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
4d3bd4e8-ab25-5721-b26f-cad41ecb6fb9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
20d2c9d5-d4f8-5a73-8753-acbe1b5c48ce |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
cb7a64b2-4886-50b2-b204-9f8208cf8e78 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction
9e6429fb-f8f5-55b6-92da-bf2dcfe1659f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
c3b60755-42ac-533a-b4ad-c4be362cd3d4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
6745183d-3253-50ce-8d75-a4c0c1a91218 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
07df0c5e-9344-534d-9028-80358816ff59 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
d4673dd9-565a-5b67-bf18-dd49de55f5ea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
b43b9235-b701-5255-9a8c-c00d7e171858 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
efaa3179-bbf7-5d0f-b97e-407aec28f51f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
ba7ab312-7130-5d3c-9fcc-b26670548e26 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
a43cbb04-1e25-5fb5-926a-251a7ceabdad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
923d4d97-c86a-50df-9d10-9e450b841084 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
ce2df572-82a0-5c52-949e-db86c167aee0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
63adc1e0-c02c-561e-aef3-da333eed7b7b |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
0c6cd9cf-2093-5035-be7d-2370a33cd7ca |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
40080832-97fb-5c8d-8e78-c95502e9475e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.8 - Survey
ce2a4ded-fc31-5acf-a12b-d8ab8115f316 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
18a148e7-7f22-5167-91f7-43c8371ebf93 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
da2137de-097a-5de6-bb51-cde5efade46e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction
7260660a-66e4-583b-b07f-5ab4b34eb51b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
ad1deb8f-d159-58e6-95c0-31df8bad71c0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
ef214446-7e2a-52f7-b746-7b247b8f2182 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
712ad3ff-4035-5451-8579-8274c183c351 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
5f44efd7-db02-5178-b563-e272859b104e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
da0c7090-dffc-5ba1-8080-d736ff0928e0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
7b647cd7-b6fb-5855-bcc0-257d37a0bd06 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
557fee50-bb63-58d2-840b-c750b8a36798 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | 3.2.5 - Survey
589a2a02-7c0f-5bc3-a33e-8545693343ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
9c2bc4a0-1103-5a08-a15d-e3fe807d2cd9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
34c17ce2-42e0-5b97-9da3-3747aaef5f84 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.2 SW Manhole Construction | 3.2.7 - Haunching
cf9d22af-f703-5847-a817-4a48a5ebf9d9 |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction
63e430cc-0fc9-5706-8708-a19bac66f40f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
71e88abb-4519-5db6-bebd-7083c86edb37 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
fe3d4737-679f-51c2-8d57-4f62e3bacc51 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
170f0702-5ebd-5d6c-a9ad-351c1536a507 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
77944117-baf5-5149-9e72-ae053018c48b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
3f5950cc-3adc-5753-b618-2c26c2bd4cde |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
fb9b0415-4190-574f-8f32-a316d99429df |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
295be186-0051-5479-9a43-a06f0ba4eef1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | 3.3.5 - Survey
9daab30c-7d32-5d83-9909-d000bf664ef2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
34517093-8ae6-5909-a4d5-bd9b8524d4d1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
0d0664f0-93b6-5174-9c9f-271a95319237 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation
51a3295f-76a8-5428-92ac-b5c34df34cd7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
53cc2d04-79d7-5630-8b7f-04669d0fff57 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
56c0a8f3-6838-5f62-bf8a-99a521abbc20 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
2d60bfb9-3a1d-5e2a-afce-291eb1129deb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
36096d2a-bbe8-5cf1-b81a-c8c73a50a927 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
4f8273b6-bc7d-5b1d-870b-d6a95386d562 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
14acd130-03e9-5f5a-86b5-73ae950aa27c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
9a02638c-b236-5277-b583-a3cbe9f93d53 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
6f1741e3-1995-55c6-9657-05f56efa4b58 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.5 CCTV & Reinstatement
1d7955e9-d1a4-5f9f-889a-6b24913d706a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
d8bbc7e2-b63a-53c6-9e54-7c0fe0d3b672 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
6ebb0ff2-ff39-5812-b15e-dbbe96606f54 |  | not-started |  | section | FALSE | FALSE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 4. Post-construction (Final Inspection & Handover)
fdad2909-ad2d-518a-b6ea-04e51d5d5746 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
cdbbcf1b-4033-5c4a-b1c2-a57d35e76706 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
db4a5cdc-5018-40cc-a99a-796dfa833fb2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
f3072435-d5ef-539f-90f0-81bbf789862c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N7 | ITP - Stormwater N7 | 4. Post-construction (Final Inspection & Handover) | Add Signature
886d65dc-21d3-4258-9ad0-03454e4e60dc |  | fail |  | folder | TRUE | FALSE | Site QA | Stormwater | N8
510d772d-1485-403c-a9ff-6e2841112b89 |  | fail | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater
b5ee02fa-e2cc-5a34-adff-c702d14b5569 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment
e31759e3-b140-500b-baba-e3b4ddca9846 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
a57fc8ae-8fa7-579e-b82f-64a27e4915cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
034223f3-3591-5e41-82e9-d806995f712b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
b8ee41ee-825b-5010-91f6-439f8cf89b26 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
d5f816f4-fad6-5064-ab36-cf1a65aeabaa |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
3307962c-c52a-51f8-a96d-13f00a5af739 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater | 2. Material, Personnel & third party approval
366ed662-aa3f-5ce5-90f1-384ef309120e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
9611271d-e2aa-50f4-986f-793249d55308 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
232db753-3585-5531-a6c5-5eb2e2579990 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
871894f2-d1de-5905-8a73-bea998b5e1a8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
9aa0762b-9413-5a54-b213-72d0702e2cd9 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
913b95d3-f090-54a9-8e87-78b2d256bd08 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
7d18aec9-867d-54d7-b921-26999b00017e |  | fail |  | section | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction
35ded1e9-ad98-5c3a-9718-586eb05733c7 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
de7dd181-2705-5987-a912-5ed904147cc1 |  | fail |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
5c25c8dd-62d6-5de1-9d32-2b06061a126a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
66417393-ab56-5a62-8105-aae09f9c7ee9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
39e445d3-a0f3-5d91-9cb0-13b7630a2c01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
8789ed1b-3a2e-500f-8dd1-86754998e041 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
848e194a-dfb0-55d0-9cfc-91ab519b040e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
6b5c3bf8-3851-5af4-83d0-9f1db3a5586c |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
cd543fe7-2407-559a-8b25-7144ed4d6099 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
38accf11-fed7-587b-9927-4824cfcc2c90 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
06dea35e-2ea4-5ba9-90a4-70925aa9b1d8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
c7b89cd3-3785-5647-9d5a-3c2a165948f5 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
8e0c369e-9901-5076-996a-b7bc4a9cc48f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
db0aa1db-febe-5542-849e-d0ce30ccd678 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.8 - Survey
aa16bb33-f3bd-5b9b-8ecb-c903a2bcdbe6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
5e47ae1e-ed60-55d6-a3a2-6020246f71f9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
b89c6aeb-7101-5a85-b5e6-acb772cdfbce |  | fail |  | section | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction
1f661d14-0185-5bae-9cb3-b44fdcea13d4 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
108db97d-dd48-5cd3-b76c-061ba45cdbec |  | fail |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
d8317e70-0127-5611-bfb1-398e99b911c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
dd9433b4-82a7-5abd-ad21-b166187de3b3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
c1fddc97-2eca-5752-8af0-e4086daf609b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
599a1bf4-6d6e-5d60-8945-3f6cafa28d76 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
ac13c2a2-449e-5a30-a07c-eb11b1e3c377 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
bc6c3cbb-16d1-5b2c-9e91-83730195410b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.5 - Survey
e33b8b70-c42b-52c9-8d98-1bd6b2be6a57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
abb6ea1b-a80d-5d27-9f45-25f7bac5641e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
1a55a265-8e92-5030-bdd9-1e199d8989fc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.7 - Haunching
3b1d6633-ee1c-5708-a598-b23e3296fe7b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction
386190c9-c311-562f-8f1a-c9a1fe6558f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
cef25b82-07c4-5fca-ab01-1c7054ce43e1 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
4ab31fc8-9d3b-5e03-a69c-da7934ad0267 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
5cd4ea68-6ad3-5138-95e5-1b54fc9d22ce |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
3a74343b-9c2f-5440-bd36-0f254d8e6339 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
93a81fd1-213c-5dfc-b60f-7fb731dc6e78 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
dce51bd6-ddd0-523b-893d-1f212356e18f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
869ec972-fe07-596a-bba2-61ee4cbd8acf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.5 - Survey
548007a7-7ecf-5428-b49e-5ba6f66aed2b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
eef722a1-4b0d-54fc-a8c6-458e9a303eff |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
42cbe052-c4e1-5271-a6f9-52022c176e75 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation
05557726-89b7-5fb6-8464-1cabdde02fd6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
ae42ac5a-01ca-5608-b2c9-c48f53afc887 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
564934b9-b483-53e7-a95a-fddd23d25e81 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
91214d20-10f2-5a11-97dc-880728b1a2f4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
0557b2d9-9b69-5df3-8eac-17fd3e30bc13 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
ad61acfa-258d-5bfa-b788-a7dd96092f07 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
e05f27ce-df90-5a5e-87ef-f6b12b9bde22 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
a9562235-86d6-5866-933b-745bca87ad37 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
9d2714e2-5e52-5b5a-b73d-21135cf1e62b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.5 CCTV & Reinstatement
6a811cca-4043-5c0a-a90b-9c14b0eac560 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
64d996e1-d4c1-579e-8206-e8a45c1cccbb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
0ad9b21e-6997-5fd3-b305-50e41cbec71b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N8 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover)
94182676-4678-5fc5-8d65-7e4e7bb68b37 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
8db7ebe8-5c49-5c90-aad2-27e45f41de84 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
19627017-c50c-4c93-ad28-4d717a2d48ac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
17a9303f-038c-5619-b9c1-c7ba3cad5c42 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N8 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Add Signature
cb34f63f-b5fe-47ad-abcc-2447b31bc454 |  | fail |  | folder | TRUE | FALSE | Site QA | Stormwater | N9
585ade8b-380c-4bda-9ecc-e39ce4613679 |  | fail | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater
ac77b440-5144-5de4-9072-00a98cc85ce8 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment
032b6f84-56a7-5e69-b0e7-87ad9057030b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
55a5b329-baea-5ead-bc22-9f1275058ad3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
7a58c54e-5f20-5fd9-9c4d-959e9c52ede3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
3ed86573-29cc-5a0e-a30c-93179fc279ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
d1e4538b-855d-5ed6-b566-d9488b85a9f2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
cc429176-06fe-51fb-8888-78d58bd6dee5 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater | 2. Material, Personnel & third party approval
32eb7844-7c44-5c33-a1a6-2b4001987334 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
892654d2-9b58-5f0b-9e82-6fc25cd2ed6a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
8c82398d-10e7-5b5c-bdfa-a48e4601ecf2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
9adb4db5-a9bc-5168-8014-8506c10fb826 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
a20431c1-e70b-5036-a646-4519dee062d0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
e5bae97c-c67d-5720-a9d6-0319423d2eaf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
f5b076d9-8777-56d6-9075-6b02b3204226 |  | fail |  | section | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction
a6a48bfe-b993-5b35-9dc7-02253b17cd69 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
587b024d-1467-55ac-bb5d-596ca56a9090 |  | fail |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
a5000ef4-02bd-53a2-af9a-70aec5d644bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
5952dd18-7661-53c6-bb42-07ad2afe06dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
b0ed4301-5ef0-5b7c-947c-79e48155df24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
9d3426d7-e7dd-5a4d-8171-b548bd2acb6e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
073cdd94-fcc2-56aa-9aa3-16629fa08942 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
cebca1b4-7551-54d2-adec-fc0574113490 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
b8fa2546-c9e5-5a1a-ba53-fc2381a2d7e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
783c95bc-3565-5c5f-bfd2-feaf31e1a0b6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
06b81c54-7028-523a-8171-b3efec18acfe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
65e32ebe-b500-5d74-bb29-a69ce449ace0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
24d0c26f-440e-5269-aab1-19c50743e425 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
6fc94ddc-8540-5c2d-925e-ee8a4589a391 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.8 - Survey
6ebba5e3-565d-5f61-90fa-363eed6bcb57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
510a5667-e303-51f5-8b2f-20ed022dc1d7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
46888efc-557a-5c8c-bd91-8dc244639003 |  | fail |  | section | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction
ada102c0-4774-5ae9-8b22-3de5d4a0f373 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
f80a3579-f712-5195-8930-515bd3fc2dff |  | fail |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
7773ab09-019a-5265-abe5-c8fbcd2c1d16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
785b7582-d9cf-54bd-9122-4e4d084c2382 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
bbafdf51-b390-5e30-bbea-8e225271a953 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
4abc0c9c-f41b-5d64-9796-870d301e118d |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
380ddcd0-c85f-5dcf-85cc-116e0c52751d |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
b1ebfe84-8ef9-56ec-8bce-36d9fc607b7c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.5 - Survey
71c75c85-d4ce-528a-b5cc-9ebb6390bb01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
cd6b2257-46bd-53a7-8783-040f02f104b6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
04699498-faf7-5c25-93fc-7aa75113261b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.7 - Haunching
cf81e0fc-322c-5700-854f-c5447feac93b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction
898b8d82-85ce-5ed4-b94b-989df04f9463 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
a7b8ba72-91c9-5042-b9f0-4b9cde5f6064 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
1f979cae-c395-5485-a7eb-9711465b4e36 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
4e10db72-2f7c-562a-b3ea-2e52210d4f76 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
44e04882-dfb8-5a18-8c15-92936928f890 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
2894842c-b370-5230-ad77-20fbf97acf6b |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
f3a3e7a5-f12f-5975-a4ba-3f77b83aa7a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
56fc26d0-b5ab-5bd9-bd3f-39ff3372d72e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.5 - Survey
456979c7-671e-5dcc-be16-4280b2f1cedc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
8479b290-928f-5a81-bd24-2eb8e97caecc |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
99256f42-2efe-537a-a1a9-f09295277876 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation
e83fb8a4-4d0c-562f-8d33-0a89b1c48194 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
fb527d63-f599-520c-b7e9-bed8940548af |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
8e921479-00f9-5a21-966d-ee02761da4db |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
1edfee63-1e28-51f4-8924-0d9ef5098112 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
d82e5f30-a9e8-5bcb-b210-848bbd76474b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
b9c9d854-eb81-5187-b7e6-bd4aac9f7fde |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
e6c26a86-bff2-599a-a61e-51a80e5f319a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
8aca1328-9a8b-54d3-b77f-20bf8357d131 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
a95ec5bb-8aac-58a2-ad0c-f7b3c918de62 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.5 CCTV & Reinstatement
564ac2a6-3744-5705-a724-e3f55f7340a2 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
b80e5981-7c89-57d9-8443-cc417f0a2c63 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
b08e0cf1-fcd3-549c-9ab1-6bede0193b21 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N9 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover)
9cc1e0ed-c15e-51a8-b36d-8785b2c90460 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
dc58a7d9-45fd-5190-ba7d-f32d9086efb8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
2dd6dd38-8f92-44da-aa7c-2c7a982aa093 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d135c579-98fc-584f-b62b-c6e796a922f5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N9 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Add Signature
749ae2e5-1c3b-4d93-9d33-ba7f5da6adb5 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | N10
80ab2141-358c-43eb-b1d8-e5bc218c17f0 |  | work-in-progress | 3b532488d0e180cc0df3a2eeb59650f5bb5fe5eaa44efa8af14b5b55b90b0add | checklist | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater
0ff5a2de-b503-5883-af76-6b9350611464 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment
7d47205d-1871-5c6c-859e-0bd6a38dd4b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.1 - Extent of Line Setout
7c164b09-bd60-572c-b7d8-1879e2e2b73e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.2 - Environmental Protection
031edc22-c42f-571a-9444-0b35b18c6eb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.3 - Stakeholder
8e2b0828-cb52-5348-b4b6-7eb674f49f73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | 1.4 - Permits
2913af99-47e4-5843-8baf-59e0b970d5dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 1. Pre-construction (P&G / EStablishment | AUTHORITY HOLDPOINT
803966b2-1bf3-520f-8c65-57ed20279675 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater | 2. Material, Personnel & third party approval
c93d3278-b6db-5e4d-a408-090e6f266af6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.1 - Pipes, Fittings and Pre-cast Structures
2dbf1f61-653a-58e6-9bcc-425589601f26 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
176d1253-2c0b-5ee5-91f5-9f85120116d0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
4ab03925-98c8-508f-813d-c2bb4178f727 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.3 - Undercut Backfill Material
58e8c4eb-148a-5aa0-a5c2-3f2c8c45b968 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
a554c9c0-fc41-55e7-88f7-668b46eb946b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 2. Material, Personnel & third party approval | 2.4 - Geotextile/Geogrid
29ef740d-7794-5962-94ca-150315ac3501 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction
c99db046-0355-5161-85e2-41a2ae65e62e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.1 - Foundation Compliance
17eee124-6bfb-5989-b90a-a4bb58d78530 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
f4478e54-1720-58a1-b2ce-14bc458ed65f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.2 - Undercut Backfill Compliance
42574626-30e4-5342-be18-766e2fac909e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
1c7d6f44-3844-52f0-94e1-2d2d0424a6a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.3 - Bedding Compaction Testing
f3ff0ddc-5f4b-5541-bf50-f8d9bb913f0a |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
c3307d4b-4c24-5263-8766-b8a434e40073 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
9740c6a5-70f9-537a-add1-1cc3ab9483fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
d5df7899-7718-5f85-94d7-c55114da42f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
f3693ad2-12a4-5078-8784-1bc25d2bb597 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
ad346690-637b-5b73-b2f8-691cedca244d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
ab226876-a463-548d-b57a-1a8d9bd1b5d1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
c530c201-6e2c-5b36-a8a6-bf2a9aab68cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.7 - Backfill Inspection
253315d7-ec6a-5a11-a305-02dc5525e95d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.8 - Survey
e45fa24d-0c9c-5e9d-b804-09850be3c606 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | 3.1.9 - Backfill Compaction Testing
693539e1-0be7-5207-b3f5-d7a6ef074ffa |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.1 SW Pipeline Construction | AUTHORITY HOLDPOINT
92c3c7f7-6157-5761-ba03-e36625ae481d |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction
b857588a-4bff-512e-967b-024b669e9fd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.1 - Foundation Compliance
60609c3b-b3ff-598c-a2f6-1c3f3feef24c |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
00cc180b-9729-5d06-9522-c41a2406672a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.2 - Undercut Backfill Compliance
402e3b9d-0864-5302-a4e6-60edfa9c02fa |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
663f5cd6-2c1d-5f5b-8266-56e9fa991576 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.3 - Bedding Compaction Testing
5a18c263-78b9-5e69-80bf-4d561219df7e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
b54cd810-e4ae-5b18-af75-c2fa3bd7d18b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.4 - Backfill Inspection
4f979a90-69c3-501b-8144-d8f35ff29629 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.5 - Survey
b4177480-fb06-5d26-b1c9-92875d10291d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.6 - Backfill Compaction Testing
989cefb8-0b01-51c1-8b9a-ecb50fac1942 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | AUTHORITY HOLDPOINT
08cd3fc0-2939-59e0-8748-6bea9afd5d29 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.2 SW Manhole Construction | 3.2.7 - Haunching
08ddb70e-9df1-5300-a6cc-a749510c8f02 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction
c1c6b90a-9860-58bc-b9ed-cd09c8b27cdd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.1 - Foundation Compliance
f578ee04-1823-5f6f-bca9-7efc3c0e8eb6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
d9026508-a766-5411-b84d-fd01ad6fb259 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.2 - Undercut Backfill Compliance
ae7e5b62-40c0-511d-a05b-74d604605c4d |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
434b7135-f31c-5848-a34e-1ec8db291013 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.3 - Bedding Compaction Testing
a1b20b0f-2adc-5bcd-9dd6-3240afc61126 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
fca9f15a-08ce-5c1b-bb3b-66d1108e5121 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.4 - Backfill Inspection
91677af6-fa25-5089-bddb-7ee757ad814d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.5 - Survey
10f8c4a4-e8ab-5999-bff5-b293b47f027d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | 3.3.6 - Backfill Compaction Testing
2d311517-d183-50e5-af28-073e5a5f5bf9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.3 SW Catchpit Construction | AUTHORITY HOLDPOINT
072cda58-4b55-5b2c-b51e-5349ba4ffc06 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation
836e292d-5b7b-5efe-bf71-f8e5ad34b815 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.1 - Rip-Rap Material
a1512dbf-c4cd-5671-a48e-c50498782a9d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
71ff21fe-4a3a-54d8-a4ab-512f7ffac229 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.2 - Soil Rip-Rap Material
1be52087-1886-5ad2-ac1b-72a5480cea43 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.3 - Void Filling Rip-Rap Material
b71222c3-118d-5d1b-9a77-5fa77fef304b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.4 - Grouted Boulder
b1a57f07-05bc-58a4-b261-bc3557dc87a9 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
f4a5da7d-8e8d-5ad5-9f81-0af5d0d219d2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | 3.4.5 - Achieving Required Depths
3c5dd19a-94cd-5e08-8d48-1b94dfea5357 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.4 Riprap & Boulders Installation | AUTHORITY HOLDPOINT
54356ddb-97f3-5576-bad6-39db33a3d4e3 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.5 CCTV & Reinstatement
fd9470b3-a3f9-55b2-92a5-f76ac7cd1e03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.1 - CCTV Inspection
6f3631c2-9b24-5bfc-a91f-e9ab9227e00e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 3.5 CCTV & Reinstatement | 3.5.2 - Reinstatement
5a3261af-c130-5258-a0f5-22baffea060c |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | N10 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover)
a712a050-9429-5f75-a31d-11ae1b671f49 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | 4.1 - Survey Redline Drawings
6ac2f0e3-c6b9-5366-bc71-44a233997eca |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | AUTHORITY HOLDPOINT
015c7826-a800-4712-94bb-b1cf1f82f31f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
69002c10-70cf-5b07-b5a1-43dcb4cf780d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | N10 | ITP - Stormwater | 4. Post-construction (Final Inspection & Handover) | Add Signature
ff62b009-c3fa-47b9-b4f1-cf441f1b5ca7 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | Stormwater Devices
800b8fcf-fde0-490b-ad40-009bd4ed8df8 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Stormwater | Stormwater Devices | SWD04
a2603d0c-4695-441d-97a7-1a99c0d27c78 |  | work-in-progress | ITP - 131 - SWD04 Eastern Gully Works Rev E | checklist | FALSE | FALSE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E
758b47db-4bc4-50d9-b25a-4d288f29f728 |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3ea678e5-db6c-56f7-8c98-8b8f4fc4e690 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
346d4a22-2a84-54ab-b73b-b15021621f9a |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
3d71f9e3-fbe6-5f64-8249-225f96a7a280 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
8392b367-d3c6-55d5-ba38-8bfeaf3f0c9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
c725f65a-67bb-5603-8572-04123b0924d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
c0981627-696a-5556-b7d2-b832160eb034 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
a61c0331-5872-5ddc-9f73-681a98f16488 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
21e71212-cb6f-5017-b1dd-45be5369c27a |  | pass |  | section | FALSE | FALSE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
7eda5177-9929-5ce8-99bb-3ec79a283d4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Fish Relocation
5a19be76-26bf-5890-bd84-a741127bda7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Tree Clearance
27b99a72-c768-56bc-a947-1a6b6859ac02 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Weir Clay Fill Material Testing
eecd1417-2205-52db-bf7f-fb636c3d88bb |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
1471b805-ea53-5bec-be82-4e06756b9a3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Grouted Boulders
e2990be5-8aae-5c8a-8afb-a0cf5f7893c3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
c3b25dc9-d00c-5c21-87bf-12cfe93e3422 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.05 - Riprap Material
deafd85d-8a99-5e46-aa26-0a9cb3dd37ea |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
2cc381e0-b732-5a0e-b9ad-c4a9972e4315 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.06 - Bulk Fill below Clay Fill
af8e60a1-394b-59f4-96c9-7d95fe663b1a |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
d7482269-ff85-5385-8780-d3765c1a410c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.07 - Grout
6987c52d-3ba5-542d-a2ea-3feba22db51e |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
ab7a5ae4-c6b2-528a-b85b-6f0e9603acd0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.08 - Geotextile (Base of Undercut)
6ecd84ff-9c02-5e76-85c7-15def5e94aa8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.09 - Geotextile (Top of Rockfill)
eee41e3e-86e6-5186-85da-3286850e35b9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
96183606-175c-5f0a-a8cc-860b257612f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.10 - Geosynthetic Clay Liner
7f7ad858-6a0d-537b-a14e-9d75f96fcb23 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
3474148f-e85c-5cfe-bdd8-9d69b1ab572d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.02.01 - Pipes, Fittings and Pre-cast Structures
13f8463b-a0be-5b5a-ba03-02f73de64a7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.02.02 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
838e7313-f09c-5162-9cfe-d2a9c8b67c6a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.02.03 - Quick Mix Concrete (Haunching)
46f8cd4f-2fc2-5fb1-9074-bf14d9a391e2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY
5bac4362-7b8b-5c85-9513-a648de146fc6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Erosion and Sediment Control
9751a1cd-219a-5994-8abb-7b93a6a94968 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Upstream and Downstream Bunds
b81428cb-be6b-5907-8925-c93cd5eecee3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Dewatering
15fa56de-e676-5a7d-a704-7001ccc9ccc3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.02.01 - Preparation for Filling
2440c21a-de67-5725-bb8f-aae6366bdbfb |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
5fb8b598-5bae-586e-b56d-4a60cdbeeb7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.02.06 - Rockfill Installation
2a6d5e05-6c63-50d2-b2b7-96c2e762ff8c |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
e398e67f-7982-558a-84a9-c0b44c08530c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.02.07 - Geotextile (Base of Undercut)
63ac369e-9120-5c08-bb91-a99b9e6d5a09 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
cf5a7a0c-f9d9-504b-8c4d-827df9780d47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.02.08 - Geotextile (Top of Rockfill)
b8910a33-949d-572c-a19c-6b8faa5305f7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
d2919c13-b776-5a60-ba83-f4292a5390f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.02.09 - GCL
fb8a1faf-d71e-5e84-867b-a4d925b69086 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
4a2f9448-931a-56b0-88e2-ee6c121a6f63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.02.10 - Topsoil
228af3a1-e096-52bb-851e-a4ba89c9718b |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
5f516006-5c5d-5b7d-9780-2ee8d8ed30c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.01 - Foundation Compliance
0af7a1c4-db6c-523b-a474-05f442d5c5cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.03 - Bedding Compaction Testing
9004b8b1-0b38-5627-8f99-6cfe60c7546c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.04 - Haunch Zone Compaction Testing - Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
70534cd6-51f9-5e56-a5b6-30cab434f98e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.05 - Side Zone Compaction Testing - Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
6595bf0f-f5ab-59a6-ba3e-32f6d71285d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.06 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
51fcfcbc-4e26-526f-b7d8-b6c8f4f5d7db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.07 - Backfill Inspection
7d2ef192-82a0-50e3-b12e-8400262fc10f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.08 - Survey
aee52af6-00be-5ef1-aeb7-cdffd2d52dcd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.09 - Backfill Compaction Testing
1255c497-da95-5ed9-b288-8935215fe6c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.10 - Riprap Mix
a2ae7678-69b5-523d-a212-e05eb8681df8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
516c8acf-b477-57d6-b7d7-c9ccfafa08f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.11 - Riprap Embedment (Fish Passage)
690ce461-9310-5eb2-9943-f886c19a0fb2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.12 - CCTV
02f65e88-247f-5ae0-9096-36c356215360 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.01 - Foundation Compliance
6ff9320b-493a-5b12-bc23-8aee958c6076 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.02 - Undercut Backfill Compliance
0fe680ad-44e6-59c6-9123-b0b22a66f76a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.03 - Bedding Compaction Testing
e1dd209a-57bb-54a0-b507-7998b3566593 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.04 - Backfill Inspection
c9610e9f-fedd-586c-92aa-76156506f144 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.05 - Survey
c68589f4-3421-5692-bc87-7b5319305d45 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.06 - Backfill Compaction Testing
8946f8df-dc90-506e-8ed3-3375d4470f88 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 5 – CONSTRUCTION ACTIVITY | 5.03.07 - Haunching
97dc302c-89e1-5332-8568-61b72634286a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
ffdd376c-88da-5c08-b622-645ab1defd24 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Redline Drawings Critical Elements
edd2d047-7222-5b18-97fb-69cea201e6e1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Red-line Markup
76946727-459a-45c2-9874-f58d80633b9a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9d074887-dda7-56c9-8e91-6a5c8eb4235a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Stormwater | Stormwater Devices | SWD04 | ITP - 131 - SWD04 Eastern Gully Works Rev E | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
048f4352-1f05-436a-b4b1-e5d939d80808 |  | fail |  | folder | TRUE | FALSE | Site QA | Wastewater
3217804c-8dd4-4c95-870f-a816ef8cca54 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Wastewater | Network Line K
bd508604-9b08-40ce-8072-068cd031b245 |  | work-in-progress | b67a79512a2ba2120f5b2a0cb2f11254494cce7488dd2b72557df60c04d7ec25 | checklist | FALSE | FALSE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F
557c5739-e23e-5a90-97c3-c602ff9a80d8 |  | pass |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
c85f2ba1-35f8-544d-9271-ccdfb785e203 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
f09c9d4f-b9bf-5c97-90f1-81a90b6e49e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
9b315686-3b9b-5949-ac2b-ab7170db532d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
71e74f04-76d2-51f3-bac0-e3d019930e06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
6bf8b880-afca-5324-8983-64a3b5187b35 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
d4a18929-835a-5844-b7b1-8e9d0dafd450 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes, Fittings and Pre-cast Structures
e762869a-ed8c-5b0f-834d-eff70bad845d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
7e980f2a-76e0-5124-98c3-c4c3eeb9ed7d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Undercut Backfill Material
1dec254a-5e2a-5b76-81fe-8c27778473bc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Geotextile/Geogrid
22677b31-3ad3-5e7d-bc15-418d6427138b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction
e121db64-e1e6-5b5b-9bc4-37c43ae6cb3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.1 - Foundation Compliance
eefb725d-6204-580c-9f19-f073e22b5b48 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.2 - Undercut Backfill Compliance
fdb98669-3231-5c6b-b114-ef16a2a28713 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.3 - Bedding Compaction Testing
1624d573-af79-567a-8a0c-73f6a9fd26af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.4 - Haunch/Side Zone Compaction Testing
4e8fd44f-982c-5822-9123-71a60573e984 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
b1c9c32e-7d25-54ab-9bd8-be89f9c58b1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.6 - Backfill Inspection
be64f098-f498-501a-b3bb-0580c08f5284 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.7 - Survey
da2e0c20-9b91-5c1a-a0b9-51c0affb4cf9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.8 - Backfill Compaction Testing
5e850769-3959-5fd1-8b0b-2d82bfc65bac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.9 - Manhole Foundation Compliance
43ac6d7a-6390-5e92-8f5c-dfddea6563ed |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.10 - Undercut Backfill Compliance
85ad50e6-3d2c-546d-b396-faaad73bfbff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.11 - Bedding Compaction Testing
c61431de-1ab8-5e6d-8544-902c93759822 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.12 - Backfill Inspection
afcb020e-792b-5941-83ba-5430b901e973 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.13 - Backfill Testing
9e212843-a123-5b69-a2ae-fc635ac3530b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.14 - Low Air pressure Test of Pipeline
66d5b990-510a-5668-a3d1-5746946c8b43 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.15 - Manhole Vacuum Test
81c3a5de-72e0-50f7-8e2b-109cda8c2563 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement
dfb94087-1882-5e16-8bf6-b50e861a2d6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement | 3.2.1 - CCTV Inspection
c0ad67b2-252e-5a51-8992-f5447582c17e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement | 3.2.2 - Reinstatement
5d9c7edb-b958-518d-bf18-6555b4719d3c |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
88ecb674-cc35-579e-b1b4-81507df9a8ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
81a2d7e8-714e-48d6-b534-4d3b92ff8f83 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
289da2ca-6d99-5124-9185-6b44248c9302 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Wastewater | Network Line K | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
8ce43742-1f17-4833-8a84-2aa08c167ff4 |  | fail |  | folder | TRUE | FALSE | Site QA | Wastewater | Network Line L
9f798756-4c2d-4c82-9a36-5fa5a37a864f |  | fail | ITP - Wastewater-PVC - Rev F | checklist | FALSE | FALSE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F
5896947e-ef10-5205-8530-c69a789cd194 |  | pass |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
b105428b-3a6d-55e7-b4aa-fbd61fd5049b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
c59bde29-7458-5352-8137-696c82a024ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
24681522-cbf9-5936-95e3-7ddf51bb0c75 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
bd8fd630-60a8-5cda-a2ca-423f3a99da5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
c876f892-d0dd-544b-93cb-0540fdddf879 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
80e04118-54e3-5c06-a620-b09feda0e382 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes, Fittings and Pre-cast Structures
b80eb9d2-3669-59f3-a93a-f9a3e476c43d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
fd945722-74f0-5368-9faa-af346788a69d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Undercut Backfill Material
6d30f5eb-1a07-5767-9434-bace87810e39 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Geotextile/Geogrid
5f394b55-e7d1-5aee-8fe7-51a13ae57ff2 |  | fail |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction
0c06fa0e-3051-528b-8e18-2c543fd3b0b9 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.1 - Foundation Compliance
0c7ff628-1dd3-5e96-af1c-4d4977ea2935 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.2 - Undercut Backfill Compliance
1d8c9d21-0c44-5d61-99d9-8a4a7b8423a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.3 - Bedding Compaction Testing
1a7dd3fc-3181-5b27-977a-b84481c791a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.4 - Haunch/Side Zone Compaction Testing
5d503ab1-f95d-5181-ba96-462f6014c4b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
ffddbb78-0c62-5514-affe-50a340fb0a4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.6 - Backfill Inspection
d0fd944f-4548-5291-9355-ed5b3d922327 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.7 - Survey
7edfb1db-f6bd-51f8-80a4-6518448ddfc0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.8 - Backfill Compaction Testing
e79d07a5-f014-55b7-9893-b6d0e82d2161 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.9 - Manhole Foundation Compliance
d0af11fb-e909-5947-86ff-5e31e91a57f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.10 - Undercut Backfill Compliance
c089325b-3238-5ae2-8d40-42eea49e0b97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.11 - Bedding Compaction Testing
995368b6-87bc-5f32-a38c-317727ac6ab2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.12 - Backfill Inspection
de50e6c4-2df9-54d3-9a58-b2e580e31140 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.13 - Backfill Testing
1e81d5d0-1fef-5496-b9e8-56ec6c7019d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.14 - Low Air pressure Test of Pipeline
cd340516-8144-5757-a8af-19a1e8446e3b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.15 - Manhole Vacuum Test
a0e30267-acd6-5378-967f-4a7b66fdfaed |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement
192b5fe9-25ec-5dca-85fc-06dd6a29748c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement | 3.2.1 - CCTV Inspection
1934f089-a3c5-5a55-be4c-1357bd6d242c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement | 3.2.2 - Reinstatement
d74f01aa-69b5-5a1e-81ef-bf0a615e4264 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
71e12a80-b4b6-562f-a574-d1811205930d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
fbfb8c4a-9c02-5ef1-b226-f199c1d024b2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
efff0618-f4ae-5a27-b49b-20eef8b117d2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Wastewater | Network Line L | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
1e3829e9-c74c-4673-9163-0504c071f0f6 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Wastewater | Network Line N
b6dd5f80-68bf-4e0c-a66e-a4522ee5c346 |  | work-in-progress | b67a79512a2ba2120f5b2a0cb2f11254494cce7488dd2b72557df60c04d7ec25 | checklist | FALSE | FALSE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F
bc81e569-c42e-59ee-a251-8ad8845ef15f |  | pass |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
ea78bded-5ec9-5c9c-9808-def895a904b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
231256e8-0be9-5b8a-b6a8-141900139e4f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
c3b3e5ba-c6e5-5ea0-84e5-64bb9380e17f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
9a3ac8cf-b38f-5f48-aa1c-ab0cf722adf8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
b3df4453-3fb1-51b5-b02d-2fe3b62b7d01 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
8c919d70-747c-53ad-8c36-1553ead4ce51 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes, Fittings and Pre-cast Structures
21d23767-f24a-5440-8d32-e8fbd1726a76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
796a1f84-e103-56c1-8ab8-1fd3e6125f52 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Undercut Backfill Material
bb7756bf-e077-59f2-95af-0e11d8cb0aef |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Geotextile/Geogrid
a19ba6c1-f28e-5872-82dc-4cdba19a4a67 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction
4e940317-e8f2-544e-95ee-dd8ccb3a1521 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.1 - Foundation Compliance
4160cc87-8d48-568f-9712-7ec1d868662a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.2 - Undercut Backfill Compliance
66e9f587-ad36-5538-ad0c-dd2752213f06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.3 - Bedding Compaction Testing
ae45024d-bc7e-5299-b452-82272568c1f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.4 - Haunch/Side Zone Compaction Testing
3ce2719c-b939-51c0-b602-3f915b66336a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
0005251d-b73d-5644-b237-003d77b535cc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.6 - Backfill Inspection
f0835d91-b855-5528-88aa-037e0bcdfa14 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.7 - Survey
89f49a2e-7d09-544a-b492-dae189678f35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.8 - Backfill Compaction Testing
d3c6f5a2-1b12-5f68-9f5b-d09a51e723cf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.9 - Manhole Foundation Compliance
37cbb2d1-e50b-5ca2-9f3f-3b4cf487009a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.10 - Undercut Backfill Compliance
adf4f431-07fe-524d-81b5-048cefc3e994 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.11 - Bedding Compaction Testing
5948fcaf-a71f-5577-a1bd-c1b76782db86 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.12 - Backfill Inspection
a6056a50-f507-5f6c-b7e4-cecf7b2acf74 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.13 - Backfill Testing
cd8224ef-9dee-54d9-8495-4c157f178288 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.14 - Low Air pressure Test of Pipeline
3f0117a5-b1ba-5c0e-9cad-df801b5bdceb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.15 - Manhole Vacuum Test
84f9fff9-330d-5bf0-8c6d-fe360c9ce624 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement
336ffba5-08d5-595b-a860-c0bea80b94bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement | 3.2.1 - CCTV Inspection
cb44e02d-bb77-52a8-992f-6a94b2774123 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement | 3.2.2 - Reinstatement
4c6e6296-05bc-528a-9993-7f04352793c5 |  | not-started |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
96f4d71c-4f3d-556e-bdcb-ab8ce9065455 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
cccd5e0a-3bea-47a9-9f91-ec49446ee66f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
de837951-13b3-5750-8a6e-d49d5c98fdb3 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Wastewater | Network Line N | ITP - Wastewater-PVC - Rev F | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
f4e0bd73-737a-4e41-a0d2-b7a5aeaed209 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Wastewater | Network Line M
c51225bd-68f6-42e4-993c-71c395dc035f |  | work-in-progress | b67a79512a2ba2120f5b2a0cb2f11254494cce7488dd2b72557df60c04d7ec25 | checklist | FALSE | FALSE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC
9cfdd0da-f3ba-5c4b-a8c3-7916beaa036b |  | pass |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
18a91d1a-221c-5602-88f5-8c6ba7af86b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
c7f406d4-3b1a-55e5-af54-69f7afd599fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
0bd87d30-0c3f-5ad1-a11a-03ab8ac2df44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
88180953-887c-5e6f-be5f-fba7906faa47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
35e7cd9f-540e-5b09-96b1-ff73fb218515 |  | pass |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
08b345eb-9f85-53ac-8916-693f65d1d315 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes, Fittings and Pre-cast Structures
c42eac01-1967-55f3-8e32-f8210eeaa4a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
cd0751f5-326d-56f4-b028-eb405f49860d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Undercut Backfill Material
b3505823-0e58-51df-89e1-f2e1a743c728 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Geotextile/Geogrid
cae60eef-a762-5b16-abd2-f1f46af80163 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction
e46af36d-6239-56f3-b967-29adc7ef8549 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.1 - Foundation Compliance
979f9f70-143b-5966-881c-09e8b4ea71e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.2 - Undercut Backfill Compliance
ad4e93a6-8cea-5b5d-b0cd-0afae3f64ecb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.3 - Bedding Compaction Testing
2eddc863-a38f-5610-a0cb-1bfcce88f0c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.4 - Haunch/Side Zone Compaction Testing
d7d614a7-4d8f-540a-89eb-08b32f42644f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
ddd35d70-f287-5eee-af17-bd2e105cb6c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.6 - Backfill Inspection
73cf908c-2da9-526a-af62-1f870e9c7b13 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.7 - Survey
4a705a7e-d35f-5856-94d2-506c9a92bd9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.8 - Backfill Compaction Testing
9a145968-0107-5531-a175-926072eba5a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.9 - Manhole Foundation Compliance
93869491-5f08-5bb7-959b-ba94ad469fee |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.10 - Undercut Backfill Compliance
cb456f26-dc64-54ac-af43-5ac79a541c30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.11 - Bedding Compaction Testing
18407d11-9a16-5025-9b61-42ca685bc1c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.12 - Backfill Inspection
7319c1f2-7baf-5522-8b92-96aec3e4cfc3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.13 - Backfill Testing
f77de788-1f27-5f31-81d7-2465074a4813 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.14 - Low Air pressure Test of Pipeline
b2d77ade-08ef-526a-95ef-dd760911645a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction | 3.1.15 - Manhole Vacuum Test
e64e3879-b24c-58e4-9199-500f1a8ce107 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement
0f207dbb-da17-57f5-b789-cab4c82863c5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement | 3.2.1 - CCTV Inspection
d6a0f2c0-a98a-59a4-8245-2d6f5e735a06 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement | 3.2.2 - Reinstatement
b6a76848-e24b-5325-a9fa-47fa5350d312 |  | not-started |  | section | FALSE | FALSE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
bd2b8d0d-1169-5b69-ad18-fc8923f13e6a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
adf81783-35c8-402c-9665-0a5371debcac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
2a10dbf8-5b8d-5bde-a59c-9cf0477b741c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Wastewater | Network Line M | ITP - Wastewater-PVC | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
c3616573-ba11-4098-85e7-b888a86c2062 |  | fail |  | folder | TRUE | FALSE | Site QA | Wastewater | Network Pressure Main 02
d8785ef9-8d7f-4dea-82d5-14bac533bec1 |  | fail | ITP - 111 - Wastewater PE Rev C | checklist | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02
049c68a7-7ed7-5b71-9dec-dcf91c862332 |  | pass | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
e374a099-8b7e-5eb9-bb8c-2b3a055ff011 |  | pass | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:08e8669c-e5b0-46ab-a310-d0b3ff3aea44 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
31d7a224-4169-5206-9faf-876e1abdb603 |  | pass | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:d25d3c93-d075-455e-9dc0-43d4af373de6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
c3069c4d-7609-599e-bb6d-1fda857513b1 |  | not-applicable | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:dd01c6c2-4558-4cd7-82ad-a54f9af241fc | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
86d13eaa-8f2f-5153-8351-4a930d67ebc6 |  | pass | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:652b07a0-288f-4b6c-83e7-b1142f207412 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
09368296-4cab-5b47-a081-114c03ef87c7 |  | pass | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
959e7e39-2e7a-5019-a095-2a13fe9f5b7c |  | pass | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b:ff08673a-8620-4836-8497-ae10c996fdd6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
36c26006-103e-5b69-849b-1e255dfd9d2b |  | pass | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b:276f5a4f-2bc2-4846-b718-223127fa92cd | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Undercut Backfill/Bedding/Side/Haunch/Overlay/Backfill Material Compliance
36e572b9-2b52-5080-a545-1ddbba3298b0 |  | fail | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY
ec1ea837-0997-5547-a44c-ddbc14881072 |  | fail | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:2fb04865-fa75-4b15-8eef-7bd73c7a0c90 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.1 - Foundation Compliance
48995ae7-c9d4-52d1-83d9-3f5701523fa8 |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:f735f248-55f1-458a-af08-8d9bbd9ce555 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.2 - Undercut Backfill Compliance
cb4225ed-a6f5-5d55-947e-2bc2c925b8b5 |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:7f95d084-870c-4eed-ba49-8faabc22b233 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.3 - Bedding Compaction Testing
eb13c31b-8fc2-53e2-a780-1f2e2ede8f11 |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:393f7353-164f-4cb7-a8cd-882d4162a024 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.5 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
9c40103e-7248-5d32-bec0-a2ce815cd4a4 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:b3f7eb01-ea80-4d95-8c01-853c65a1b69f | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.6 - Collection of Waipa ITPs
2a4ec728-f96c-5bc2-8ced-6c07046e16ad |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:b3f7eb01-ea80-4d95-8c01-853c65a1b69f:e19b7072-eec5-4898-9c84-7078bf1ebaeb | signoff | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
cb498e48-f881-5166-b323-81671de64378 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:70825302-71ce-4bfc-a84c-1813935e63ae | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.7 - Backfill Inspection
f772f319-c7f6-5ccd-be0c-9dfcb73d924c |  | work-in-progress | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:1f35e240-b1b0-44a0-b683-60b0a6ee7a17 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.8 - Survey
5c8e6057-a786-53cc-ab05-45c6eff05fe2 |  | not-applicable | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:61b0e0a1-7ef9-4c0e-acf4-a4ae73ae6dc0 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.9 - Backfill Compaction Testing
6f09a984-54d7-51ed-ba36-2ef461b2fe57 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:4bcb429c-a0e4-490b-b99c-b15c4c212648 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.10 - End Caps
9e2413c8-6dbe-5239-8989-ddf217aadc01 |  | fail | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:5df501e6-968c-4e32-b92f-a44d270299a6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.1 - Manhole Foundation Compliance
57e94d25-5937-5727-8c9c-bca7adb7be84 |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:a767cee1-7cf4-4832-b667-e5ea5d06eab1 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.2 - Undercut Backfill Compliance
61846271-57a6-57c6-8164-ef5999fba574 |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:a73f421d-933f-4ea3-9c33-cfdc1b4391bf | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.3 - Bedding Compaction Testing
ad8a24e5-3269-5262-be08-afedaf1493ae |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:8543d836-efca-47e0-92e9-c3423fda8213 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.4 - Backfill Inspection
2a6d2eb2-8e25-5eaa-aa50-f66d508cef75 |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:97b4c7a6-4649-43b7-a470-faa13f0ab737 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.5 - Backfill Testing
30c21ac2-3e92-52bc-9d36-bf9d588be4fd |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:dc41e3c3-68e2-4502-8b41-9bcf6b862e29 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.6 - Concrete Load Distribution Ring
591e30e6-87b8-51f4-8db4-612363e11c5e |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:5f43b102-b3e9-4e06-9de0-1213af0030d3 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.1 - Pressure Testing Methodology
e9db8fd4-ac2a-51ff-af89-842ec78e76b6 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:1ffae514-5118-45da-9df2-9002b9c66d64 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.2 - Pressure Testing Qualification
3eaf468a-8af6-544e-9a17-2b340b66183d |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:7215e341-906e-4cbf-98b3-0a6340a0da23 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.3 - PE Pipeline Pressure Test
3a730fb5-86d3-573d-a32f-ca4d05e6be4b |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:270cf86d-dcf6-4ae8-86bd-eb1f109b457c | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.4 - Romold Manhole
1439a29d-32ea-56ce-b30d-01596b888f5e |  | work-in-progress | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
56642d7d-602f-5ffc-b7ce-8da4552f70d0 |  | not-applicable | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:4c47f7de-04d6-4249-b634-0430ffd7d109 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Unforeseen Items
c25b2521-5b44-5a18-9202-62540044e3e6 |  | pass | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:2fae5bcd-e8a8-4c87-88b6-a1fdfd4a8042 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.2 - Survey As-Builts
f5f09e03-8005-5306-a48f-dbc79dfa59ef |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:33447f0c-a3d4-4aed-9206-29596a02942a | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
0d606b91-4ab8-5544-970f-fefcd17b7620 |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:33447f0c-a3d4-4aed-9206-29596a02942a:7cc7f1d9-f91e-4b6d-bb21-3cae62da66e4 | signoff | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 02 | ITP - 111 - Wastewater PE - Pressuremain 02 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
c63d08f3-d340-41a5-81c2-366b444d5738 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Wastewater | Network Pressure Main 03
82e87d15-77eb-44b1-8970-bc28e2e512c2 |  | work-in-progress | ITP - 111 - Wastewater PE Rev C | checklist | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03
bdc4c9f9-9b7f-5fd2-aa83-4f3b61b4b85f |  | work-in-progress | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
af6da944-39d5-5933-8746-7681e7ee8572 |  | not-started | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:08e8669c-e5b0-46ab-a310-d0b3ff3aea44 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
a6dcd6f9-3c40-5710-8c3e-94b2abbb3e99 |  | not-started | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:d25d3c93-d075-455e-9dc0-43d4af373de6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
e38cd73d-b7ad-56f7-a649-56300e47d07f |  | not-started | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:dd01c6c2-4558-4cd7-82ad-a54f9af241fc | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
15e25e7f-722c-51b0-b2bc-5bf9fc0718ad |  | pass | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:652b07a0-288f-4b6c-83e7-b1142f207412 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
fef5b59a-ee4e-51e6-ac3d-653cd85c1505 |  | not-started | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4c533584-225f-5f14-a2ff-f30e1804ff4d |  | not-started | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b:ff08673a-8620-4836-8497-ae10c996fdd6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
962348dc-9135-5ab3-9ebc-04b642cc8e8e |  | not-started | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b:276f5a4f-2bc2-4846-b718-223127fa92cd | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Undercut Backfill/Bedding/Side/Haunch/Overlay/Backfill Material Compliance
c043d01a-4478-5cc7-8ab5-39ee331ea28d |  | work-in-progress | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY
858735c4-1553-561d-be72-46d103f41447 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:2fb04865-fa75-4b15-8eef-7bd73c7a0c90 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.1 - Foundation Compliance
2510278a-ab63-5341-a19d-ff4a1dff9fa4 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:f735f248-55f1-458a-af08-8d9bbd9ce555 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.2 - Undercut Backfill Compliance
33e55c47-224c-5702-ad64-e5c7fcc02a46 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:7f95d084-870c-4eed-ba49-8faabc22b233 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.3 - Bedding Compaction Testing
df068c3b-6e16-5a64-815a-22b8f4a74383 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:393f7353-164f-4cb7-a8cd-882d4162a024 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.5 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
6fdf2e15-2383-53d0-80ff-ca37452917ab |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:b3f7eb01-ea80-4d95-8c01-853c65a1b69f | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.6 - Collection of Waipa ITPs
6457cce1-d721-504c-93c8-91e4568e4df5 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:b3f7eb01-ea80-4d95-8c01-853c65a1b69f:e19b7072-eec5-4898-9c84-7078bf1ebaeb | signoff | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
e3ed1e03-77a7-5803-9e1e-672d9d541a3d |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:70825302-71ce-4bfc-a84c-1813935e63ae | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.7 - Backfill Inspection
215b6316-da7a-5b15-8fcc-1283c77f8ef5 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:1f35e240-b1b0-44a0-b683-60b0a6ee7a17 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.8 - Survey
37f3e763-cf6e-5f30-95c7-1da9f61e893b |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:61b0e0a1-7ef9-4c0e-acf4-a4ae73ae6dc0 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.9 - Backfill Compaction Testing
268775ec-6bbf-5fdf-bdeb-a3c9868fe21b |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:4bcb429c-a0e4-490b-b99c-b15c4c212648 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.10 - End Caps
27af4d53-a1b5-5951-a3d1-68ed1c94eeb0 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:5df501e6-968c-4e32-b92f-a44d270299a6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.1 - Manhole Foundation Compliance
c8139487-6648-59ca-9b54-0c914729eae9 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:a767cee1-7cf4-4832-b667-e5ea5d06eab1 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.2 - Undercut Backfill Compliance
32a7e9fe-d6f5-53f7-9650-19edd90cb56f |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:a73f421d-933f-4ea3-9c33-cfdc1b4391bf | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.3 - Bedding Compaction Testing
d41eba5d-d3f6-5ca2-afdc-7653cfe3c0aa |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:8543d836-efca-47e0-92e9-c3423fda8213 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.4 - Backfill Inspection
4bf124f1-f0fa-5b79-91d1-b705c8192873 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:97b4c7a6-4649-43b7-a470-faa13f0ab737 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.5 - Backfill Testing
d5853d2e-a6f6-5077-8983-0d3c9fb0b489 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:dc41e3c3-68e2-4502-8b41-9bcf6b862e29 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.6 - Concrete Load Distribution Ring
ee3267d4-99d5-5a80-b22d-184c97083b6c |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:5f43b102-b3e9-4e06-9de0-1213af0030d3 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.1 - Pressure Testing Methodology
b1815727-341a-5bcc-9b7b-f3c34a9df0ea |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:1ffae514-5118-45da-9df2-9002b9c66d64 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.2 - Pressure Testing Qualification
237a5999-b17e-5f88-832d-e871d712f231 |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:7215e341-906e-4cbf-98b3-0a6340a0da23 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.3 - PE Pipeline Pressure Test
23e62dfb-8815-50fe-b8a2-894e0edc6c1f |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:270cf86d-dcf6-4ae8-86bd-eb1f109b457c | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.4 - Romold Manhole
df1c025f-726e-5e9f-8e4f-baec55796b33 |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c37e8cc4-1f6c-54d5-aa0a-ca91fe7af5e2 |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:4c47f7de-04d6-4249-b634-0430ffd7d109 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Unforeseen Items
0e72a049-e108-5df3-b6f8-eb1fff8afc89 |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:2fae5bcd-e8a8-4c87-88b6-a1fdfd4a8042 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.2 - Survey As-Builts
5749f703-ffc4-5430-8d95-4c6dc61baaed |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:33447f0c-a3d4-4aed-9206-29596a02942a | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7d07c0c1-11cc-5ae6-a29e-50f8c1a6070a |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:33447f0c-a3d4-4aed-9206-29596a02942a:7cc7f1d9-f91e-4b6d-bb21-3cae62da66e4 | signoff | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 03 | ITP - 111 - Wastewater PE - Pressuremain 03 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
c0f9987a-e7e2-48a4-a07c-a43a3feea198 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Wastewater | Network Pressure Main 04
2a9e9c08-b1bb-4e3d-b1ac-0e87c94f988f |  | work-in-progress | ITP - 111 - Wastewater PE Rev C | checklist | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04
f1d4244f-baa8-59b2-9b3a-c69c1af6f61a |  | not-started | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
ee2d4c4a-91de-5b79-8f63-446d4afa7f8f |  | not-started | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:08e8669c-e5b0-46ab-a310-d0b3ff3aea44 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
410ab6af-0268-5b36-a67d-30044c461dad |  | not-started | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:d25d3c93-d075-455e-9dc0-43d4af373de6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
c1708a84-8861-5d50-8c39-1ac7f12b55b9 |  | not-started | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:dd01c6c2-4558-4cd7-82ad-a54f9af241fc | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
6e8bc11d-f6f9-54b5-8ee3-54acf250947a |  | not-started | ITP - 111 - Wastewater PE Rev C:3b41d634-1d3d-43ef-8adb-d3a04dbe5dd6:652b07a0-288f-4b6c-83e7-b1142f207412 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
ed868913-e882-5113-a49f-7a3c149d0abe |  | not-started | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
37eed964-58ea-5758-9857-5559ab03c4ff |  | not-started | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b:ff08673a-8620-4836-8497-ae10c996fdd6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
90566960-4723-523e-9361-bee1da807c5e |  | not-started | ITP - 111 - Wastewater PE Rev C:d2ce9723-f0d7-4d8f-b99c-3e030396441b:276f5a4f-2bc2-4846-b718-223127fa92cd | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Undercut Backfill/Bedding/Side/Haunch/Overlay/Backfill Material Compliance
9003d5ee-02a0-56aa-939c-0dcfc89969fa |  | work-in-progress | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY
fb615e18-1513-5f49-ae71-87aae75238ca |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:2fb04865-fa75-4b15-8eef-7bd73c7a0c90 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.1 - Foundation Compliance
3c2d057e-51b2-5c60-87b1-64aeb6d24afc |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:f735f248-55f1-458a-af08-8d9bbd9ce555 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.2 - Undercut Backfill Compliance
26890398-ab6c-5d48-aced-8e4d4081cd2b |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:7f95d084-870c-4eed-ba49-8faabc22b233 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.3 - Bedding Compaction Testing
b2d03f12-f9b2-53e6-b65a-c02cfb9ff26f |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:393f7353-164f-4cb7-a8cd-882d4162a024 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.5 - Overlay Compaction Testing - Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
5abc10ea-43c1-58b6-932a-0ef95daeaba3 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:b3f7eb01-ea80-4d95-8c01-853c65a1b69f | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.6 - Collection of Waipa ITPs
91f8db24-ae2e-5620-b45a-fbff83eca0d1 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:b3f7eb01-ea80-4d95-8c01-853c65a1b69f:e19b7072-eec5-4898-9c84-7078bf1ebaeb | signoff | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
4b758b25-adfb-55fe-a4c0-edaa638ac04d |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:70825302-71ce-4bfc-a84c-1813935e63ae | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.7 - Backfill Inspection
681ed706-9356-595b-9493-86d71889a667 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:1f35e240-b1b0-44a0-b683-60b0a6ee7a17 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.8 - Survey
15aaa9e4-7e1c-533c-9d1c-ca06a083c413 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:61b0e0a1-7ef9-4c0e-acf4-a4ae73ae6dc0 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.9 - Backfill Compaction Testing
b527d5c0-ee92-5903-9c52-b8597c02aa6c |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:4bcb429c-a0e4-490b-b99c-b15c4c212648 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1.10 - End Caps
43123286-ff2e-5680-9d33-a683df265c3d |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:5df501e6-968c-4e32-b92f-a44d270299a6 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.1 - Manhole Foundation Compliance
867c5678-c922-537f-8499-7d49de79aba8 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:a767cee1-7cf4-4832-b667-e5ea5d06eab1 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.2 - Undercut Backfill Compliance
cb32b07d-086a-538d-ba10-2644c660db45 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:a73f421d-933f-4ea3-9c33-cfdc1b4391bf | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.3 - Bedding Compaction Testing
db0c469c-8958-5835-a57c-eca526434209 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:8543d836-efca-47e0-92e9-c3423fda8213 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.4 - Backfill Inspection
f666572f-d6b1-5c51-8a6e-fb555460f613 |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:97b4c7a6-4649-43b7-a470-faa13f0ab737 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.5 - Backfill Testing
12fd0b08-295a-5369-af3c-db1bdb70656d |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:dc41e3c3-68e2-4502-8b41-9bcf6b862e29 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2.6 - Concrete Load Distribution Ring
07f0b080-8d30-5b39-ab04-8df09682810c |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:5f43b102-b3e9-4e06-9de0-1213af0030d3 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.1 - Pressure Testing Methodology
3354cf3f-a113-5df4-875b-1fa8b6f1dafb |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:1ffae514-5118-45da-9df2-9002b9c66d64 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.2 - Pressure Testing Qualification
5c95811c-b80d-5687-b88f-5cc9b1f63950 |  | pass | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:7215e341-906e-4cbf-98b3-0a6340a0da23 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.3 - PE Pipeline Pressure Test
1fab9737-7cbb-521c-a61a-77be71fb112e |  | not-started | ITP - 111 - Wastewater PE Rev C:022bc2de-c3d0-4873-bd8a-f83194ec3224:270cf86d-dcf6-4ae8-86bd-eb1f109b457c | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3.4 - Romold Manhole
4acea077-120c-5abb-9728-eb5bb8c76f21 |  | work-in-progress | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382 | section | FALSE | FALSE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
687e6fa8-e713-5dc2-b308-6fa0e4828f7c |  | work-in-progress | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:4c47f7de-04d6-4249-b634-0430ffd7d109 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Unforeseen Items
918bfb16-e5f2-5761-bc86-2fba147c5c98 |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:2fae5bcd-e8a8-4c87-88b6-a1fdfd4a8042 | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.2 - Survey As-Builts
ce4d3360-4a8e-5480-834d-98ecb38b2ffb |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:33447f0c-a3d4-4aed-9206-29596a02942a | checkpoint | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
4064c709-89ca-5e63-a3e3-d3909176fd81 |  | not-started | ITP - 111 - Wastewater PE Rev C:bb7aaf0c-55fe-41fd-93c6-b260952a9382:33447f0c-a3d4-4aed-9206-29596a02942a:7cc7f1d9-f91e-4b6d-bb21-3cae62da66e4 | signoff | TRUE | TRUE | Site QA | Wastewater | Network Pressure Main 04 | ITP - 111 - Wastewater PE - Pressuremain 04 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
27b45eba-d513-4ffa-8035-d59d7d13238b |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain
6acd2cd0-1c19-418c-b390-bd44b7a7ddf0 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-560)
daf2349a-5dd7-45be-937e-05bb642bc8d7 |  | work-in-progress | beaaa9fa0abadbd7d31c89516602c7df95960c47ef789c24dc8406536442670a | checklist | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C
93963cd9-f6bb-56b1-a4ae-d9b0b3fc9245 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
e7af1b83-3fe1-5cab-bcb6-7a09046de0a8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
0e7d81e4-9d3e-5696-a755-c0cb2765824c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
829a5b78-bc56-5340-9385-4a42218ce130 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
b61f975f-25e4-5ec3-8cdd-6dfe8de28a6f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
f8da26e5-49e6-592d-888f-945b1faca7ec |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
0d13a807-de3c-59d4-b39d-a30c488a018e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
6e50b5a4-32ed-527d-aa00-75473f8f70a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
86d25573-dfd9-5164-83db-22b9ecab9ffe |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
0cf7040c-626c-5aea-a088-2df79273f1db |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
e0326996-77a0-5914-91d1-fa388c42373c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
f3b5cb6f-b4c7-5cb6-89c1-74078b8d1907 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
1344baf4-ae92-5a80-b6f3-222ecc055877 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
5a81c3e3-ea78-5396-9981-b6cd7880b9ce |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
1e448a4d-bc5c-5339-bbae-dbf536a12163 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
706a0b51-fb93-5fca-8034-227cd0a7b760 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
8075e1e6-217e-5776-98f5-2f793b74d0c8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
b1cbf317-7561-5c62-b6b0-1f05283add4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
d940549f-7a6e-540a-90bf-0e2252fd5e67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
2fb075fa-f961-5332-83eb-9b50e625d659 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
f4962183-92dc-5de2-b4bf-229d390d936b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
7f13ce9e-7b8e-5060-85de-49d73432e0cb |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
6e85de7f-854c-53a6-bda3-7994e390e1dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
de41604b-25c0-5b63-8298-8db269c8c33b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
7d2740a3-6565-57c7-bf42-08f00df09a2a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
b8929958-0221-5898-b846-c1cba54765bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
81ff601b-91bc-5847-a2c0-08c0864c81f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
c455dfdf-1a1e-5f2e-bf33-3776b8993da0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
a1134c2f-8e1b-5f13-a024-ccaeb4382de8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
8c4e9d79-fea3-5f3e-95f4-472ba453b1f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
d03dfafd-5337-5006-9042-16d6fa086270 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
86dbd100-91f8-5c58-a6bb-ab082e487ce8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
77e83b4e-3c90-56ca-af33-e7b6f7c33f1e |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
b85bc3dc-87f7-551c-b7b0-a0f0ef4a9908 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
0da61373-929b-4828-8831-d77a08450a98 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
3d7b3468-7078-5765-9674-279f9974b2b0 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-560) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
23556f1c-1055-4896-999c-ce2355990736 |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450)
1a410100-d8aa-4b82-b9b5-03aaf48a83f2 |  | work-in-progress | beaaa9fa0abadbd7d31c89516602c7df95960c47ef789c24dc8406536442670a | checklist | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450
37e8ade3-d5d3-5683-89ef-2dc012263c84 |  | pass |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
2c21c90c-50aa-5d59-a78d-97818df886df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
0c9433c6-097a-5cd2-a3cd-44287f848bad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
a3a1e63f-2b25-5a4b-b158-085a473a0fe3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
c8fe73d3-91c8-5d8d-bb33-124aab7a1217 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
aa4c45ae-c949-51d1-bb41-7cf301bdf688 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
760ad11c-dc9a-50af-8f51-747dc73e0f19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
39793d3d-3b07-5939-a856-bc0125109728 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
1765ebe6-da83-58f3-b7d0-b0e4de4824f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
98f1ab68-25df-57f0-939e-0374a8c75bd4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
ed775ede-c7c6-5717-aa45-2b077b542d3c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
3f1b80f8-8dd6-5b5f-96c1-b3984c4ea4d6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
5caa6d56-f976-5c44-82f6-078c7e311dcf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
0deca11a-a903-5b94-9e41-a37074f78727 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY
eb642135-234a-59ff-8aa0-273b96bf51ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
2f45dee1-4058-5b64-9d55-b740cf22e300 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
551f9a72-65b4-589a-98ee-2c58606baba9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
d7f55546-853e-53b9-8737-9d16bc468dfb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
96961b14-0cbf-59fe-a0a0-2f878200446a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
a0561fe9-a42a-5a89-9f8c-3505be72f095 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
6d2a2dc6-c721-5576-90f7-914d7c2aede8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
d484da6a-3c9f-5766-a4f9-e6f55fa5f198 |  | pass |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
6dc04e41-4979-5b15-9aeb-6d48447a92d9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
016780b3-688c-5220-a996-64ccf388b82b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
52bcfbbd-6391-5a90-88ff-11632669b945 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
749c21af-6772-5a79-90cd-01721b12307b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
f18bb357-c8d3-5b62-837b-3a2a461f8636 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
84042f24-482c-521f-b9d2-ca38d9ea6876 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
aeab2b6f-e2b0-567b-b585-74396968fbcf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
01d294fa-b483-5fa7-a8b3-0f64fe7087b9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
8468fb3c-933e-5da5-87cf-c4949ae8cc95 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
fd280069-2cdf-5dc2-b882-4007d42e7fd4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
cccd5f76-f5e9-5ae6-86bd-13fb7085d67f |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
10511fd0-a182-532c-ab8d-e45665d72f87 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
0da15a78-29b4-4ffa-bcdb-c86fc4408f9d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e93eed97-1ec5-5412-afb1-bf1b70ff1272 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | ITP - Watermain-PE450 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
3aeb8892-0527-410c-8ccf-33380802cb4d |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3
7874c1ac-339d-4b02-8bd0-a9b0cc020369 |  | fail | beaaa9fa0abadbd7d31c89516602c7df95960c47ef789c24dc8406536442670a | checklist | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C
c87d3553-aae8-59fa-a612-0703c42cbe55 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
97ebdefc-23b8-5620-9a79-4a3d02c2adbc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
782ee86a-fe17-50f7-9739-e927755cd4cc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
25ffd4bd-3010-529c-8d7f-67d89972fdf3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
854580e6-b233-5626-a673-16d69881b448 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
2fd1841c-392c-56c2-ade0-2a735cd774ec |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
aa126075-51fa-58c0-9e9a-02867e349ae5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
c28ed326-c3c8-5615-84f7-9a673ab7d43e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
0efd2a14-a575-5463-a369-ff0fe0ca8652 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
0562670b-1ff5-5fc8-84b5-3b0d1c90c3f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
3a27a742-d20b-5b8a-baa0-47c0dc91a026 |  | pass |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
474b0469-1954-5d51-9c09-2ea3ae351830 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
071095eb-3f50-57ab-ba5c-4348f164b161 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
44fe0126-9643-5919-a3cd-6e56fd1f901d |  | fail |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
1f07e95b-dd49-5490-8842-d30c91ca817c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
0c956bb1-eda3-5a9d-ba95-567fd9d5a5e1 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
614777c4-2cdb-578b-8b06-35d27083e9e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
ffb0a37e-3a52-5d78-a858-31d2f13346f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
0e2168b5-0831-55cf-8977-4df013059b24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
45f241d6-9a66-5b65-9d1f-01994a32476f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
df8ec881-be87-5c83-98a7-13c4bc952abe |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
30424245-2739-5851-99e6-93f2071c818a |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
27cfc8d6-35e4-5037-9a29-0c0acda3b1cc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
7274c2e4-7464-5af3-bd70-5041ef889c7e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
200433a5-f782-5c14-8e81-672049c83b3f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
71f39eb4-a5c6-5f8d-97ce-2d872d869e44 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
8ac0a9a9-34d1-5c8f-a27f-fd9a5f260316 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
13bac575-f7bd-5090-aec4-27b7d5b4ae3d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
ce0159dc-d575-5cdf-9299-c15c54126131 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
241d1b80-a132-5968-a647-288da0f113a2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
a4998da6-760a-5e26-9fc4-44fc4249b2dc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
70078074-6a29-58d7-bb68-03c8c4ba68fa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
052ba95d-ee69-5e92-ae26-83b157709e46 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
1961b2e6-bc07-55ee-bfc7-c19d5c2f68fd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
302ab5bb-284a-410f-a957-b0e1fbdac4b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
fd3e4908-d9a6-59ea-aace-bcaae3c700d0 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 3 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
42d74a10-8ece-45d9-8e44-c10da904d63d |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1
f1ac51d3-63ea-4ed3-9b65-7eb0c55b09a5 |  | fail | beaaa9fa0abadbd7d31c89516602c7df95960c47ef789c24dc8406536442670a | checklist | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C
884667b7-8161-5102-9475-625dae18f7e3 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
17516bd6-b361-5509-afb3-d1f27b41a601 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
a79f60e5-4982-572d-a7e8-b2de8cbae197 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
979d51f2-a2a1-56a7-9d5a-f14a161974b2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
7b26cb3f-93a5-5185-b69e-14313c4a6f3c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
82f1572b-5f6c-53d3-bc83-6f7fd7f63864 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
9e8f9c19-29e3-532b-8d92-d0e4bc50c5d0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
ccb1ec0d-5a74-57fb-956e-891651308633 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
51147656-c663-50e1-8145-3a183b3cb09a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
89c0120d-f652-5ff7-8373-8bb4660d49dd |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
0a776549-0021-5429-bcec-4d48501a8da5 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
61367c9d-9966-57b5-8d53-365a447fe3ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
e1583682-79c8-5dfc-8d93-b1a1fcb1d820 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
99a9d2d6-d08d-54f4-a91c-5cc34831867c |  | fail |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
b3401966-78cf-509f-9ab7-68849e496374 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
ed849706-5f5f-5b7a-91b9-cdc0ab867749 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
e35071c1-8818-5728-ba6d-1344e65dad8e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
77279df4-abdf-582a-a2d4-ec6dfc6db6a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
5a475c81-61c2-56bd-b2cd-8d601dc0e839 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
a1f3b69b-d17b-5091-98f6-0995ea7d3465 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
50f27036-c898-536a-9bd8-0250a2049969 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
d5c1bc23-970c-572c-87ab-7aa94cd15cda |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
e2c7458a-3845-503f-ae43-970d672d3ae6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
0f0785aa-b497-5271-80a8-7518969a4a4b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
ee20b91b-2efa-53e2-b479-c3fd39c6056b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
95ffc8cf-cd1d-5799-992e-34533751e717 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
2f759901-3a5e-5024-9670-acc905af6c21 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
872ff0f8-125d-541b-bf63-2b914ac28851 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
77c121d7-3678-5836-ae6c-85ec6f3b0608 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
b2621bd1-103f-5ee7-a076-4fc1d22cc20c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
32f32703-678c-58d2-a1e3-92240ecb516d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
541f628d-2cf1-5c4a-8af9-d0c57a68f73a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
e4f81e2b-352e-5aac-ad6f-abcf95072bc8 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
9b15dfb1-77ac-54af-b463-de48244235c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
f098914c-3196-4918-8657-2504ae064bcb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cdbd0cb7-54e7-52e9-a156-9b04f089280f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 1 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
f66d7264-38b5-4ad0-aeca-d81a4b53a963 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2
aeed8ed8-99c7-4e17-bc16-62f6e68c7bcf |  | work-in-progress | ITP - Watermain-PE - Rev C | checklist | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C
f9a89adb-6379-51f2-ada5-7679775f7790 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
a081e745-1344-516d-ad47-5faf60fedf9c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
ea2c20d4-8fcb-549a-9523-e0cf449abef5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
d8b191a5-b3c9-5e35-880a-00cf39dd1d99 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
447a0b5b-96ef-5c57-b3b7-ce827698f715 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
ee7d07f2-bfed-50bc-b34f-ca6a13b4a652 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
c65fe62e-fce5-5706-bb78-db4f2d590872 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
8bcbc349-f041-593a-9543-edc7880a75d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
8d472ba5-7e79-5c43-ae45-bc0c97420c3a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
c4bdfee9-7cb8-5569-ac8a-d6c88578558c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
487382cc-8d56-5fda-b456-8c7ca62c5126 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
8dab18fa-6a02-5bc2-980e-9ffde955a61d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
c935e241-cb30-57af-b825-573d4979be58 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
9830b9e0-4419-5b97-b93b-3aa4924c755e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
2dd65487-3e66-599d-8afd-2a875a655bfe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
3036cf35-f085-5e99-bc07-4029380a8b7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
1748a2ca-3b24-50b0-b28a-df4af44de6f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
b532b13a-4177-511b-891b-68e57af9858f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
10fe79ea-cc9c-5e45-b048-5a64fdd7712f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
fb685fd6-3da0-548a-bc46-2243329cdae0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
87ad851c-6aa5-5bdc-874f-e614715619cb |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
24e583b8-dace-5ea4-a274-299572641185 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
b7a24b1e-5db2-59bb-b278-1326d1ce4c0c |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
a224c537-e0c0-5221-8e89-c5c3dd858e62 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
b8aa9f66-7fdb-5571-ba4c-c7c3dbab66d9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
b1ac621c-bb0b-5371-af80-f683a7e43723 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
c2f97ac2-fe9b-53d7-99dd-ab4a24e86715 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
016ee66c-1e5c-5c0f-a90f-26c8a2189455 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
425d3a0f-3938-5eae-a884-3ab8e804cf68 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
56df6d12-3a3c-5ac7-9d4c-83da32319b17 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
f1e2050d-2b4d-5cdf-8437-554f7d5c4343 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
eafee372-ac0a-5722-8428-01463c00b7af |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
97275352-74de-5baa-97ce-cf1975d5c760 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
b8f67f89-7db5-5475-ac40-986a47b2f7fd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
789ad885-52ca-5725-8ef0-a101a99b7837 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
aefe4fad-1b10-540d-b13a-60b92b86e7b5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW001-450) | Area 2 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
8f1e002a-142e-4d47-b5b5-cf559cae98b5 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-560)
dd241d58-12d7-4310-9679-4a9a2f21ed7e |  | work-in-progress | beaaa9fa0abadbd7d31c89516602c7df95960c47ef789c24dc8406536442670a | checklist | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C
6ccbd230-269d-5efa-89c5-d0097c4d8292 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
159eca8d-a1c3-500a-a623-f67001696aa3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
353f0e58-899d-5ed0-96f3-b6ad29f7a2bb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
fdd4e7c4-2724-5458-a140-a4e8a9726165 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
6b5ad845-cb7f-5a64-bf9c-615e7d2e72d3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
11de7e67-83ce-5aa3-a746-4fc131e8a64b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
608330c8-473c-5cff-887c-2465546d4789 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
9917a172-c466-567f-b5ad-cdfa4e74072b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
ba668027-0095-5660-9bb8-9c6e26873aea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
b0030c32-5033-532d-9c8d-107eae003def |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
548f5d8f-d25d-5552-a032-cde38bddde89 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
450b97da-ed77-59c0-9d94-d34e676cbe69 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
2a422c61-7b84-5330-870e-8f7d9bc3daa8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
603baa99-300e-545f-a210-d395f51e027d |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
8d2ba667-3089-5c84-84ac-c1d9b976ab45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
ecba1340-0d7a-511b-b697-8fee7c264f14 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
b7fb400d-1247-5a74-841d-6d62afe47125 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
c139e893-c66c-5dde-8b62-4198805ef250 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
4d9fe8d2-eb46-58fc-9550-4e4d0921587e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
2c74349c-8b9f-5b78-a708-c3f66ae44ab6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
3d91079d-c1c3-5382-bf46-41036fceed9a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
24a42952-ad6c-512e-8ae8-7ac9ca3f9e9f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
3f73e00f-da20-532a-aee1-2bf7844f6f02 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
550edb69-2ccc-521c-b410-73e2c6e93431 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
1f12b209-8ab7-5806-bdc9-33ea9c018dd8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
55636df3-bc75-57aa-9d0b-c7f27cb186a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
55e99657-b0db-56f9-b7f3-a6762903e9d2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
51e861f7-fe5a-5f56-a1e7-a65cf4ac9ad4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
97403002-fa8e-54f4-9420-09a632380ab6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
ab548ec5-77e1-5364-a3b9-e9fd15f81138 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
d68893db-ecce-5bb4-afd1-abca0a8f280d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
64c41fc4-1b9f-5d62-b905-6f0e6fa4bb9b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
6c4d436b-10ec-5d32-86a7-5eecee4a59ab |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
766f75a2-3b1f-5a19-b3c9-9f978d5590b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
e0720baa-1f6a-4212-9a3c-efaa675494bd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
2213dfe8-372d-538b-9ae1-1b7cc4d2b3f9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-560) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
5c92e366-6bef-4e8d-b918-de56224bdc78 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-450)
573a190f-4750-41f7-89a2-c8c5406c17e2 |  | work-in-progress | ITP - Watermain-PE - Rev C | checklist | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C
728c61a7-07c7-57e6-ac33-1e51454d1d69 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
75468aba-b789-5b19-9af3-b8569b11ee66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
c94bc85c-55b2-586a-97f7-2ba354790f92 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
547023e5-d016-5445-bb08-8bff6949568a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
054ef059-c4c3-51ba-bd34-c296c30fd845 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
8d2d69d2-e70d-5337-9c45-ba1a2dc37c22 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
fe24a026-c8e3-5cee-8fce-27ed65757cb4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
c2647855-d398-5f4b-bfb3-d446e302156d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
f58c686e-92a0-53b9-a774-f335c6513541 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
50f7b2e6-e216-50db-92a5-acc0562f43a3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
aa985a45-e072-50b3-865c-faaf8154e2b1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
f19779d1-5850-5159-8d2d-f319007546e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
9ec6eed5-4ff0-5bcf-8076-d6200c2275f7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
88506c27-fb79-549a-99d1-e6a4a48fac15 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
805a9223-10f8-5251-8b7b-42cef3c72e21 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
c23eb323-ee27-51c0-a6a9-e9d077b6c7ec |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
b39e0962-1306-5119-8b04-89359d7e697a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
f82399a8-6f0a-5032-9b3a-c652f389bbfb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
8fffca33-3c18-5a16-951b-c8c16be85859 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
b369fedf-ba5f-5f15-99ab-0dd0e92be62c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
fea71d53-ab61-5177-b30a-4af8de37ad7d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
94fa0694-1ec4-538a-90e4-a071df3280a2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
978a324e-7682-5c70-a296-ad6c2b194180 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
8926e170-09b1-59d4-8575-144db81bb221 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
36c65c00-a934-541e-9ed6-c84db08dfcca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
77d06a2f-1a79-5abf-8c97-72673829a45b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
95492865-57c3-56f0-b097-f7ba80197326 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
9ca36d51-e08a-5871-919f-7dd0eff7a76b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
b6f27a5a-6ab1-5b35-8cdc-cdf19ac414ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
da264710-e680-566a-b328-3c25d726407d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
f933bfa3-32ac-5c14-8a92-0014224cb931 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
173dce61-0abc-59e8-8137-b58a77b35862 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
8b637458-53b2-5c41-b934-f1c4a2cfa583 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
f84b8d2f-6700-5878-827d-f1b31f58f563 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
f7828dd5-d718-5b4f-a125-851ce54c9df2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
f1aaaee1-d0d7-5fc1-8456-9fdac5134827 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Trunk Watermain (RSW002-450) | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
7de0af67-90ba-4b34-8b84-9a66e110ffee |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road)
6e94bf60-40d7-453f-9a0c-1282c8440cfd |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East
ef36b767-df5a-49f9-a9a3-ad6316b794d6 |  | fail | 93c975dd78d913f917e2e240ccd442fa6158029987ca7bdd0aa81cb8b4cd79a4 | checklist | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC
bffb9bd1-0090-5cd4-9ab9-6849433b652d |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
cdf116e2-4c7e-5b35-bb7b-091a1f133bca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
a03df6ed-ff6b-54e7-a3e7-5a5a1455370c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
6598bad6-0f05-5fa1-82ee-b2146c3ea231 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
3aad66c1-9faa-56a1-a4f3-cafbb31ce85b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
ee88a9e7-5f6a-55e1-8fe1-c7afcbe71e55 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 2. Material, Personnel & third party approval
7bd45543-fb7b-59a0-a188-ecbda984ec7d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
b2254023-c11a-5a38-99e3-3c148ffb0e29 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
0efc32eb-089e-5915-9bb6-e6a7dc02970b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
b9577582-a705-5dae-be8c-c886f58a9104 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
b0186962-47ba-5e9b-9f11-f6070587ce53 |  | pass |  | signoff | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
d0a19d48-9abe-5fd3-8637-b2d46a5f8da6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
f225dcb3-3a42-5508-9f6e-8f229f4ff06b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
96a6b23b-34f0-5a93-a018-a0dfcebd7f43 |  | fail |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity
aba640d6-af05-59ff-8f95-084cd72c3335 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
7676f1b2-b9ef-5a39-acea-ef21d5672179 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
0e1a1317-d97f-5983-a610-d30e13c98f3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
de6eb0c8-926f-597f-b9bb-f4582855b2db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
ce135971-e6f7-5e93-b251-9e2ab35239a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
7866dc22-2273-5b40-8bc0-5cb67513894f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
22fb2da6-6e7e-517e-97e2-c3bebee9b756 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
8bd45623-2fb0-5723-ab8b-4f7c31e945a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
01a587bc-1f07-55f6-b4d0-6dc2ed91f684 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
7c6beaf6-fd52-5e3b-beea-5a061b577f09 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
b5b9d8a2-a70e-5021-be0c-783f245fcd32 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
87d39caa-c050-5e68-9cc7-3ec00fad2973 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
93cba7b3-2da5-542b-b4c1-c6c5f77ede33 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
3d40ee0d-0fa9-50f0-beff-300998934540 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
72f0f352-1985-5ea4-bedc-b750c1ba1546 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
37a52c04-aa9b-42e7-bba1-213c28a5d488 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
60ed1eb2-f3cd-5602-9940-259d17651594 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes East | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
e96a839f-fae5-4aad-85f1-2ee289f3aabe |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West
e87237f8-84a8-4b68-a3dc-52614f43cb8c |  | work-in-progress | ITP - Watermain PVC | checklist | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC
aa01ee69-59f5-5439-9c2d-8fe3d5414807 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
dd4669c7-22bd-5ad8-9049-a0866a9b521d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
46317278-cdc4-50a0-9cc0-fbccb5dfe948 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
213107f7-99ae-5e84-a2c4-449ad302e6af |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
fc300b04-90cd-5dd9-ac40-7f5d4f9415e5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
0b0d38c4-8230-50a0-b380-0cb1e8e19519 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 2. Material, Personnel & third party approval
9ae81abd-6581-5e0b-8737-914199b73eed |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
ac02c351-f3e9-5a14-8f65-1c6983985067 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
94be920e-4d65-54b5-819b-08838ecf9a63 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
8f958f55-c159-5d01-8b03-45a662a721e6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
34a7badb-dd18-565f-9663-0ab3c837a0b2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
bf587696-9306-5243-8078-2cabc3029272 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
a79126c8-dc56-58b6-9148-d925cfb8c2b7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
16deed03-d6fa-5c16-91ab-c29281ad1f72 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity
9463d468-c579-58b2-b440-88233cecf1a3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
15dc6bb2-06f7-535d-b02d-a5cb83491d54 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
046ad005-b647-5848-be21-f1d1d94d0428 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
52181b45-889a-5548-802f-bcbc56d9b2d8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
ff5fafd9-2035-5ef4-8179-e532d77d4e9f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
154803ca-233b-5209-be2c-e20a6a6525bb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
f80fbf68-0c76-5824-befa-477ceefe09e4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
4a84c74b-fef8-56a9-bedb-1e6a28e2ab35 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
3e3b5a5a-f201-510f-852f-5ec5f90d4a14 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
a2ce8798-30b6-5bae-9cfe-b183db094536 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
6752ef3d-e2b4-53ee-ad80-fc6e494ed045 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
db1f11f6-d2c4-5492-9393-0ad7d4907575 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
4ac1ceff-03de-5a75-bef0-37ac5fb604c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
023e9ca4-64f2-5264-b015-712e603c3077 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
0b2cef35-e68b-5c08-a419-31e63e385ec9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
86ab8a2b-d8ff-5564-bb8a-db5566c1c41f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
16a28eb4-f3b5-52d2-b607-9727a739d201 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 250 Dia PVC Watermain (Peacockes Road) | Peacockes West | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
e57f392b-6da3-47c4-a73f-c5a9693373c3 |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain
80f52519-7955-4f37-b61a-1a7a34204168 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3
c04d08c7-d044-4638-be14-ba7ef3d97434 |  | work-in-progress | 93c975dd78d913f917e2e240ccd442fa6158029987ca7bdd0aa81cb8b4cd79a4 | checklist | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC
9c2601a7-57b4-5615-8c98-146cd167109a |  | pass |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
9c4642d8-3b4f-52e0-b30b-2e6d9a9e1574 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
ea934be5-94ca-53bb-93eb-7b440a469959 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
e54990ab-b8f0-5a55-9e33-382d2b39f1b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
cc54257c-1e8d-5c62-8a8f-a71eae21d058 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
6fb403be-eeba-533a-a4a3-dfe9ea983bf3 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 2. Material, Personnel & third party approval
74258d4e-01aa-5a2d-8b86-de8decb6114b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
d9c27591-5847-5104-8d24-9499f120d9e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
2be423a7-15a8-50b6-93f1-3c7e55d9cd84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
4011a9e6-5d8a-577e-a12e-284297dde58c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
7a3978d3-7340-5957-bcee-567915fef370 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
e369127b-d6bd-5f6e-a95f-10a54b5668ab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
14add0e4-9749-5918-82af-24200df8351d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
0379f6b0-98fc-5ebf-9e6d-cf2d0f0d4435 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity
e7cb18fe-2929-5cc0-aa91-57f31eb904a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
012287a8-cfb0-54dd-86b5-12989f111d4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
e15d697d-5f02-5629-96cb-7d9d5359cce9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
83e61a7b-c17d-5958-86f2-6e8bb6f4a1a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
bfcd28cb-cde0-559b-8f56-3653b8d0cdf2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
f700e2fa-5e07-52c3-9040-e90b60120625 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
8426ffc4-5484-5493-bfca-2e9c3766f26a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
f063ba6a-3496-50a9-8bf7-e74e0dcd1f2f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
536b32ce-e8ea-58ef-974b-dffb505dd8a2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
445d9e41-f828-5f45-9d34-f376a3ca3953 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
0995bde5-afe7-537b-a6f7-fc78e438bb90 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
20176ccf-1b2e-5890-b7f4-c6e17549a12d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
3e72a249-cc64-5ae7-9b76-ab65aeb327a2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
a274cc63-5cc6-5115-952c-bdb70a5994af |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
034beb5a-0aa1-555f-87cb-55c1b78ff3f5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
1023df31-fda6-479f-a620-7e9709e300be |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c207f078-062c-570b-8fbc-cf2fb251b2c9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 3 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
ec363652-5b28-41c9-9ac5-73ef2b0eadea |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1
e576c76d-c3fd-4bc2-9140-b385fbde39b7 |  | fail | 93c975dd78d913f917e2e240ccd442fa6158029987ca7bdd0aa81cb8b4cd79a4 | checklist | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC
7d3e0b4e-531b-5d2e-a07e-f7630954c183 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
ae755b62-e1d2-5ff1-9905-73c75e9d313f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
03c580bb-e048-5865-99f6-26304fc68802 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
2f239dc1-145f-5243-8874-d3ce93323ad6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
6aeeb980-3a79-5ad0-a201-b97d9de5b0e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
addd8bfc-0ed3-542c-9721-bd98f91a6dda |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 2. Material, Personnel & third party approval
bdc35adf-fd98-5381-ab15-0b6957d3c40d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
0bb9efc5-be29-5ed9-bba6-18d2b1308d08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
10d06619-36b0-5f95-b32b-52b4f85e1a34 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
cf67c46e-4a7a-5f3c-acd9-3ef6fe180bee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
68d53920-f121-528e-8d3b-42f4f3f869cc |  | pass |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
8ae2136e-9f0d-532d-8065-08d86348e118 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
dee92f80-353b-5acf-81b7-10076c11c60d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
f5e23532-d22f-59da-80ed-b3854a820958 |  | fail |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity
faa4bab8-53b5-5735-b4a0-30eafe2fb108 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
5217fd27-d60b-57ba-a4b9-f3a44cb59f8f |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
fb285ef7-ee23-5746-b348-8b75280513cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
5c094315-1ed0-582c-8601-ab869de96340 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
38dfa651-974c-597e-a2fe-661d847b18f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
f1dd6777-695a-5232-badc-58e896b591e3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
1a2e96c3-425f-53a0-94b2-4b28f45bac12 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
41985e96-d4bf-5db7-9c75-a3fdb355c69e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
767c6f95-58ad-52ac-8798-3cd71334dc5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
9298ae6a-7ef9-5251-bf51-08f3432f7a38 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
d6496ff0-c18b-5abb-8157-11fe685486f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
e1513302-11e6-5fe1-8408-0f33b1a63c92 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
c8ac0062-6c39-50f6-81ee-75e1773ed9c3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
984e4ab7-5ade-59fb-a6bc-d592158c7dc2 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
1b8ab1ff-1619-5fb1-b89c-892f82778a82 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
009fe3ba-8650-414c-83ff-8efae6852073 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
18262703-402e-5eb5-9c2e-8a4b3eaa5c4b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Area 1 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
912335b4-c122-4b41-819b-ee827e819685 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West
b50abce4-92e9-4183-8abf-125c7fa36068 |  | work-in-progress | ITP - Watermain PVC | checklist | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC
c5367957-7342-59df-ab7c-2e1496e58963 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
d656fd46-9dca-5ff7-b940-2412faeb271c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
14c46243-61d2-5334-aabf-f687c18a515e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
3d817389-9f15-58ab-a459-64225342b71b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
c9205f0d-5a73-5c0f-83c3-6b7f585a94ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
e102b3a5-09be-51a6-9eae-1341a897d4b1 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 2. Material, Personnel & third party approval
6c697239-19ba-5531-b945-194ec79a610d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
b729b1dc-194f-500f-a0dc-2ea9f613303a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
47126607-f405-5460-9070-ab54f30a5daf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
c73887b1-f261-5527-a954-3364a537a040 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
d0ebd1e7-9d31-5eea-a456-13839dee43ed |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
cb9f2757-332e-5f0f-b07a-96ff8c0ea9c0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
db8c546d-4b23-5c24-a96f-144f0ea4351f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
849e324e-7694-5c8d-af40-38fe387c7fe4 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity
98a3ec96-16b0-5118-801e-aea55b53b399 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
c4b13979-5b8f-54b2-8312-6b31ab428aab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
397a0124-d9d1-57a7-a21d-5d5a1212f6a4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
a8b9e4e0-6608-50b9-b928-827139635455 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
97756ea8-b600-5683-badc-3081e7fe097e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
401990c6-bbc2-5adb-b2f9-a9d70344f8da |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
ffa0558a-f349-5547-ac42-9db08f2dd242 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
9cfc0632-11b0-590f-ac23-eb3566996e60 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
cf61d7df-0adb-50d8-bad0-b10345e64a46 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
51ed8717-8b1d-5ac2-9893-28e07e048357 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
360dd7ee-e96c-5daf-9b8a-d943c678221a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
67700d92-c535-5d24-9e6f-d767018474e2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
d3ae4f8a-0838-5ee6-b6bd-9e846ca0a060 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
efb2c88a-74be-58d2-a304-928876da721f |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
e615c101-1c6b-5001-b880-71868c1b2caa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
c375cf82-e310-5104-893f-1dd6fdce01fb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a253ca8d-c053-5fcb-8ef2-3f309060fc3b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | 150dia Road 6 West | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
bb8e6cd3-4661-4a67-84c1-750aeeafb20b |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC)
be2a9552-283f-4f05-8c04-c9a06f2653ad |  | work-in-progress | ITP - Watermain PVC | checklist | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC
de0dca05-6a19-56de-918c-e37490fac811 |  | pass |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
9d140440-33ea-51df-a7e3-c6f77248a066 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
aeba3e23-d97f-5871-8df8-f5e4bc464231 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
ffe7d5a5-6b61-5bc3-84ec-b7ab982c6b31 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
ab1d2926-1039-5141-af08-be25cd0a96ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
7fc4c24e-8fad-543f-b525-f8568f1d2ccd |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 2. Material, Personnel & third party approval
86330872-5b61-5a10-9555-978ba33db735 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
0e4f5693-693a-55de-82d3-ea2c41283685 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
3b2640c1-b39f-53fa-841d-648cac8499ce |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
dd79e2eb-7dbc-55dc-b665-507aa6e0f1f2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
42904841-23ab-56a0-8b8e-387f361cbf25 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
5323e9c0-7b03-55ea-b912-549d737cbb35 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
6131cd3f-82dd-54ce-98b8-5c972b18c035 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
03233152-c4ab-5a59-8068-8400b3c0c422 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity
2059bedd-3a98-5f0b-8bdc-50df2fa3e539 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
77827e92-e2ab-56ff-a999-11a49146331e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
61957c9b-3d8f-5d66-8f81-21546520c456 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
fc488715-d5ef-5def-8a00-e63765563ab3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
cf168334-14d5-5b72-88a6-1636d274fc02 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
7cbc5939-8adb-5fa0-8e25-685873eff900 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
2aeb6228-a698-59c3-9b4d-82e861f3e271 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
740cc0dc-14cc-5f03-ac12-be825d47c6b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
ac687947-148e-5195-a200-166417ac90a0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
c866d136-c577-56f8-b905-a229d62639fe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
9d29c905-03d3-5885-ba0e-f1b18d182120 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
90f7744e-d03e-5eb9-84a1-7bcf893b8832 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
e6e5a6cc-8cd9-5e12-abb3-bca2c92911a5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
99380758-a798-5182-8d91-7b89313bfcb2 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
fe351cd3-d5ed-54c8-8c47-7dd7dfe1e7a0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
e69985b5-13b3-53df-b769-84a3161fe410 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
96363198-7a83-5a0e-adff-b3abc0ffb342 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Crossing 05-01 (150 Dia PVC) | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
aa44aa76-5c71-4e38-b2a7-9afd00caa20f |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral
5d7be3d4-6a16-40a7-a4e2-5fdb5e2d9928 |  | work-in-progress | ITP - Watermain PVC | checklist | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC
5ed550ef-dddd-5ef1-bae2-348629d49fe5 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
127a89a8-c012-5bea-a731-0638f7ab2990 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
0877939e-04a6-5eb0-838c-f8c9f4929af0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
2163fb40-fe00-5eae-8860-a7dc35710722 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
3dc94181-9414-5294-a592-45c5a5c4348c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
8cf0dcd4-85d1-53ab-9eaf-bf0c936b58a3 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 2. Material, Personnel & third party approval
f6e6c8ae-ad50-5ead-8807-921856140578 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
a616ba43-986d-5866-abf6-d43ca2456c91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
f490c041-a1c7-5f9d-a584-55d30ab53e6b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
2ce26e4c-38a5-5606-abca-c259923608f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
20a85822-5ece-5a85-bbc0-6393ca6edb3c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
c54f26a4-8e50-5de3-85c1-eb1f07c58f41 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
e6dd0915-5519-56cd-9d35-8abdaa279d85 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
9b6eb7b3-83b0-5178-8d97-a8c13eb6becb |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity
7be533a2-4986-5871-9e4a-daa2790c3ca7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
1a23531a-05d7-5608-be81-656dcf810aa1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
2a1109b4-f03e-5eb7-b461-6fdd08106b6f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
3b733cd7-4682-5a2b-bea0-1066d153d488 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
15d721b8-9f11-5aec-8286-995caceea55c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
d8759e26-9e3c-5e84-908e-1407a9ff522b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
ed08a6de-2ca8-521e-95f9-cee18fa1b034 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
eb3a792a-5568-53fc-ad73-37457664cd1d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
4460e846-e78b-5577-8c7b-9d5d88e7e82e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
bd233ad4-7aa4-565a-8ead-afc4e20b9027 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
f366ec74-1f23-5ba0-b7f8-358a7ce03ef2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
ee062a0d-ed96-55de-a962-9edce232bb58 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
a0cf33b6-ac19-598c-bca5-82be0f7197b2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
46bb68ab-ab30-5232-ab4b-e03a8f0ac087 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
a55382be-b9f6-51a8-85c4-dab9de64e43a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
0415423c-1cf6-5a06-9e69-07572c450932 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9d919c54-e141-5782-85e8-22278b0224f1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 150 Dia PVC Watermain | Peacockes Stub Lateral | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
101fe4d4-03e6-4a46-b354-4125da728f0a |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6)
60f7511d-a907-441c-9212-b73cdeb8cac9 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02
1670592a-0474-400a-ac2a-833955d6f167 |  | work-in-progress | 93c975dd78d913f917e2e240ccd442fa6158029987ca7bdd0aa81cb8b4cd79a4 | checklist | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC
f8561cf1-2655-550a-bfeb-42a427ac9f31 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
abdf562e-98e6-5cd9-8836-7b3f12209278 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
b90163fe-81cc-5ed1-afba-2b41a837d016 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
03b4e5c2-d9b5-5238-9cd9-f954ac252c49 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
3bf2c92c-ab9a-54bb-9d2e-d2c848753468 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
5701323b-7833-5e1c-bb12-aad975794837 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 2. Material, Personnel & third party approval
78c125a0-8a2b-5c73-a1d8-d8ed127a17b3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
8311e299-f351-5009-829e-6025694175cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
bc9feee8-58b8-5876-b505-4a64a5bd752d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
46ea2dfa-f678-5e98-b312-295200fb5349 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
038209e5-6981-5048-8d1f-096d6bb4739e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
998dc8e2-3cba-508c-8925-298110b15791 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
12cdf8b3-0a4d-5b94-a2e6-8a5ad8061d46 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
00b8946b-e02a-50d5-8ced-034f0c52dc10 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity
fc98aa30-0b39-5d9e-9c14-7feceff451e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
27f43c84-3431-5edb-9c4c-2a04c59ca105 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
68d371c5-449c-5108-a9a8-0c26a990a5d0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
110026a9-5f22-5f6b-b56c-98256c25045d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
ab0ce930-6893-54a1-8f6e-f2b09bd51abf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
2762ca2c-b5f1-5530-9b9f-77d7452e8ddf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
675806ae-ca6e-5b5e-83c2-aabe7d3e522d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
084167bb-4078-5d4f-a29e-478f0b705848 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
0b79b00d-8696-5984-a37d-6b9c4d5176df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
21cbfde5-679d-5823-888c-479cb9993d9d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
a8c965db-bdb2-562d-92d7-74fdbced3b79 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
cb6b693f-32ec-525d-b845-003995e7a753 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
f9e1eb87-fd7a-59cb-9eb2-2c1ea2d8296e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
9e6d67fd-3c2e-5abf-8790-9e93396ae74e |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
bb2a71c8-31cd-5009-bb88-ec485d43576e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
8548bbc8-7e1f-4e33-bda9-e962deb44f72 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
009a87dc-c0c8-5fb3-b795-3a8f612096cc |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | Crossing 09-02 | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
16cc7889-6563-4b66-97d2-9c5d5580e9a5 |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East
28726c8a-8dec-4405-b107-0de445555831 |  | fail | ITP - Watermain PVC | checklist | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC
102dc444-c2c8-5621-a69a-eb3f3da31db3 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment)
d0379cef-7cf8-56e6-ba31-f5ee5158329f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.1 - Extent of Line Setout
a44f308b-ec06-53b2-a397-164c9559f9d3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.2 - Environmental Protection
c455f89a-5a44-5404-8ab4-85fb80777272 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.3 - Stakeholder
c93555e4-f1fc-5ebc-a614-47ba49f34103 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 1. Pre-construction (P&G / Establishment) | 1.4 - Permits
94c0074c-3c01-5c03-8309-1fbb97b7f0cf |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 2. Material, Personnel & third party approval
349dcab7-f44c-5f30-b2cf-39caa582886e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.1 - Pipes & Fittings
94124bdc-0437-5f38-8c5e-8458ce58bdd8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.2 - Bedding/Overlay
a9d4ac4b-1a2e-5e94-b8f9-a8c443cb7a57 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.3 - Backfill Material Compliance
1e2c3b89-aa6a-54ef-ac7f-910997d4b33c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.4 - Undercut Backfill Material
3b0533cd-295d-549d-bd3c-c770219d033f |  | pass |  | signoff | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | AUTHORITY HOLDPOINT
419dc6b9-4e8d-5a1d-bd7b-45b7ad7cc915 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.5 - Geotextile/Geogrid
b3699c07-f2ca-5726-8bea-e965aae48a48 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 2. Material, Personnel & third party approval | 2.6 - Warning Tape
8d47ccf7-727a-53ab-86ef-5d540208d135 |  | fail |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity
a596a809-b7d2-5e4c-bae6-6dee76cf8ee7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Trench Excavation
77adab6e-5bc7-5d06-9d58-efd12819633f |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.2 - Foundation Compliance
d3c96036-27c1-5fad-8a45-ffdf68b0b54f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.3 - Undercut Backfill Compliance
b98ff437-e716-5b5b-a73f-77493bf61f03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.4 - Bedding Compaction Testing
15fbd1e2-f480-530a-9c16-14bd4f0e5fda |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
42ffa2ac-9ac5-5a41-a4e2-b641a8562032 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.6 - Backfill Inspection
8a979e62-5be3-5940-af12-817a4cdc20cc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.7 - Install Warning Tape
407e72de-1283-581e-8791-69ec0f8626e0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.8 - Survey
38fa874c-2ea2-50d3-970f-97e76710bf70 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.9 - Backfill Compaction Testing
a0306929-7472-5275-b1fc-0b0e168d3bbf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.1 - Pressure Testing
e34ed835-013c-575e-9378-8743de2f764b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.11 - Disinfection & Flushing
fdc597c6-51d5-5f0a-8390-27cbf9494f8f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.12 - Bacteriological Test
b17ca91b-a2ec-570c-9603-695bed65c307 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 3. Construction Activity | 3.13 - Reinstatement
ea4de7d1-8321-558d-911d-46cedf6f7b6b |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover)
91112cfc-09c3-50c6-9b8c-dd2eb5c1d811 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | 4.01.01 - Survey Redline Drawings
df6e7fef-47e3-5f71-ae78-ece6da736a13 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8a441d90-d236-5240-8220-ddac30395c23 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 250 Dia Bulk Watermain (Road 6) | 250dia Road 6 East | ITP - Watermain PVC | 4. Post-construction (Final Inspection & Handover) | Add Signature
3b9af2f2-90df-49f1-a9ed-cc1c98dc2d1b |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE
ed3b3113-202e-4c18-a119-3d8b1c29cc34 |  | fail | ITP - Watermain-PE - Rev C | checklist | FALSE | FALSE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C
52b2699d-2b27-51b8-b4e7-ab3c4e59e53f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
8db19a27-8ef4-500d-b4a9-e88f3cebc15f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
e464db98-3289-5a24-a1b7-6fffb3179137 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
1649f243-1396-59b3-8863-080151cd42ec |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
403163c5-5c01-5d11-b45c-0fd0f264bf31 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
b8c57243-5671-582f-b2f7-e058c7f3a65a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
db458b42-3dbc-5caf-b4c3-cc7dbc0d61b9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
9f9eb895-9da7-5507-9643-64e9599ffdc8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
03a7a50f-026a-5eb0-affd-b083e7c1b49f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
c927f6e4-526e-56a8-8840-5edb91bd7678 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
5a2f1d79-5402-54a3-9249-1eb1f792c637 |  | pass |  | signoff | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
c6260288-981b-5da1-b2d9-27c1cdefbfaf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
d43c2455-d9a9-5cc9-9047-88f1c8127b94 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
3e76c6a1-4495-5d8e-8588-80185d37b7a8 |  | fail |  | section | FALSE | FALSE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
9bf8d3c1-b5ca-5889-9180-c53a6bc24852 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
10a576a1-6ba6-522f-94cc-240585398186 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
63ccd766-26ff-55d6-90cf-03f818313963 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
a7009300-7155-539d-b9af-310c0248e83a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
8135e1ca-48f2-5d1b-b004-9d163afed8b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
61d81688-2324-5180-8793-e72b71fc33c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
8dd84f59-255d-5ac8-a27f-79439b4c877c |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
6b81ded9-fce2-5bd2-bc68-bcfdff470ea3 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
6f097859-aad4-5016-a81f-600a70a0451a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
3dbfd24b-3361-5dd5-b22d-0d41aa3cdeae |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
40428a93-62db-5e31-ae47-bd1daa855ba9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
be3cf660-dbcc-5f8c-ae31-1d6ece182e3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
31cc53e1-a955-56a7-a09d-fa6531d2627d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
82c214e1-3db7-5dbb-8ef5-59b1c5feb9a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
6af79311-8f6d-59cf-95c7-e12705bf28af |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
508f8488-8dcf-519c-9949-530f44a1e811 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
de866481-71e8-5150-a679-fb5490a701a5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
61decd52-78f1-5e17-958e-ecbb4dd74060 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
a74886af-76a7-5382-bbf7-aefa14c10b45 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
49710a92-57f4-55bb-a5b1-1209cc410023 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
0d1cc3ad-35d2-5514-ad32-a76c7f2f3e71 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9fe5c41d-d56f-591f-a31d-07799d8b8aeb |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Area 2 Principal Watermain 180 OD PE | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
17abf3bd-5257-4169-837a-8ba27a844f29 |  | fail |  | folder | TRUE | FALSE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE
92be84be-0fbe-4cd3-aee0-56ab19d9356b |  | fail | ITP - Watermain-PE - Rev C | checklist | FALSE | FALSE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C
f622a55d-685a-59fa-97d9-980489ff49e9 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
30659e85-16ac-5ae0-abc8-5298df8166ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
6b4ac18f-b216-5fe5-9ed4-cd483927832a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
e1296dcd-f13c-5960-ac78-a8ca2da4c0da |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
a090ee6a-77f5-5c4d-810f-9b4846e60ac2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
4962dece-eca2-531f-b9c8-10990ff52a9f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
55f926a2-2da0-5299-b7e8-afd6ca989c7e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
a291e08b-b037-5883-91eb-e3a6f533c30e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
8f286d59-6e27-582e-9e5c-01038c641917 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
e3a0c955-8ecf-58b4-97ff-29bf63e3f0d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
15957e39-a45d-5e2b-ab21-480daca51afd |  | pass |  | signoff | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
775ef486-3725-54fa-9afe-5e766f539d2c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
4d935955-ee9d-57bf-9b86-48e96c168243 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
57288d2f-d963-5dfa-8884-130ad42b9104 |  | fail |  | section | FALSE | FALSE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
ba902e60-0d4a-52bd-8ca9-c0d3c778b856 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
31f44097-f334-5ade-b8f9-8052a0959405 |  | fail |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
dc0b137a-a94c-5aa8-9ff4-a55932af1554 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
e82d1a20-dc31-581e-b066-f0193b3636d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
07a9b041-e503-5992-8001-8101327f91ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
35695fce-bb25-5593-9871-b410ade4d4bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
b3c06255-fbc2-5eb7-8890-8dadf38ec9a7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
4d3f4705-9b64-53ae-8e97-89326aec04dc |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
bb8ceb81-1b41-5743-ba20-c07be4fc7513 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
3256e22e-37f5-5d60-a187-996105223c7f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
9cea9643-81a5-5afb-a142-483fafa9552c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
877b0ae2-53cd-5fbf-be3a-0a838a00d245 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
6801a5ea-80f6-59db-b1a7-9669556e5778 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
33cccf20-9d7d-58ba-a35b-f5024e1c0626 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
44a5bc86-79dd-57b4-8b5d-5ddee9f7b820 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
852d5339-3329-5cc7-b6bc-aa1c6dad49a1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
7fc5830b-e7fb-5d86-9156-ed7caf7735eb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
bb96b490-e6b7-582e-aa1a-a52588979221 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
c6071fb7-fa30-5324-ac52-75b2afc9e2db |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c421efab-1586-566d-9f31-c8c4d55edf85 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
e99c7dab-82ee-5f05-9dc0-5bbcd0e1d833 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
f0a2ba41-e4a6-5129-9675-0b1b2ba2caad |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | Area 2 Bulk Watermain 250 Dia PE | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
b8ba5fab-0726-42cb-ae0d-7fc2e8c2dbef |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | 180 OD PE
8c2ed6e6-89ea-40e5-84fb-b6d22f2d2130 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Watermain | 180 OD PE | Crossing 06-02
700be2d9-6b80-44a1-88ee-45dfd06eae0e |  | work-in-progress | ITP - Watermain-PE - Rev C | checklist | FALSE | FALSE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C
0b61df8a-431c-57df-9139-83b0756e0740 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1ecfcfe5-1ad0-5a3d-a49f-fcfb8e97e317 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
45ca5525-e240-57e4-8958-6dca2cfa0a37 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Environmental Protection
38426205-e5e9-5009-9e97-35279ff6697f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Stakeholder
8fb54fd1-cb5e-5697-913d-09f661266262 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Permits
c5c33d32-a421-58a2-831f-52c56dc8daef |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
8c76dd62-c301-51f7-be7b-2e8f7b66b407 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Pipes/Fittings/precast Units
052122d2-a100-5721-8763-15c70344031a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Bedding/Side/Haunch/Overlay
a7d89674-779f-55bf-b944-48552ab677da |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Backfill Material Compliance
6ef423cc-775d-591a-8e9a-8d6564e49655 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Undercut Backfill Material
2e99e9d3-e045-5490-ab8b-4de4223305ad |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
e8269946-27c5-5f04-b516-46277c30ad10 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.5 - Geotextile/Geogrid
3d6dabec-a92a-5abf-ab6d-3d635f79ebe1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.6 - Warning Tape
cfc1d012-2bd4-5a61-bcd8-a45bdf7ba92e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY
b053c4c4-26ea-5914-9962-1593d6b4e578 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Trench Excavation
1dba5f29-0a23-5ed0-a218-53fdc6ddc8fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Foundation Compliance
523c101f-de5c-5c86-8725-20a365578c7e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Undercut Backfill Compliance
43c0e5f6-e8e3-5734-869e-dbe046f1ab8e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Bedding Compaction Testing
50d74eb0-41f5-55f2-a2b9-acb69202475d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Haunch & Side Zone Compaction Testing
0cfe3087-b198-5602-bc43-0af803d9c940 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
40c74cf7-6bf7-5e48-8c59-fbc255f3a006 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Collection of Waipa ITPs
c87be6c8-35b6-589f-91d6-4a8d784d91d4 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
3828fefe-b67f-561f-9d43-595053f43540 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Backfill Inspection
74fa105a-353f-5f36-b432-5d7cd2bbad1d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Warning Tape
fee85c95-3bb2-5ab5-8629-69b703ad74d8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Survey
f339ec3d-5778-582a-ba7d-d025b28a84a9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.11 - Backfill Compaction Testing
3d5c5746-fd30-56b2-9d08-8e11722bba32 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.12 - Manhole Foundation Compliance
14a5f103-d167-5457-9812-f23562fa6a1c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.13 - Undercut Backfill Compliance
b6a30ce2-2630-5468-aa73-1fb69b214ce2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.14 - Bedding Compaction Testing
feeca822-3d67-5d77-9c51-4a5bb10032af |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.15 - Backfill Inspection
b9e7a025-63cf-5c3d-b033-8021337f1411 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.16 - Backfill Compaction Testing
be75f89b-4df7-5130-a17d-533a973f90e7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY | 3.17 - Reinstatement
26b8da12-88ed-5458-bf51-4290dfe26654 |  | not-started |  | section | FALSE | FALSE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
0d9c5493-516c-5835-bff2-dae2412ae09a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
385e56ee-9852-5328-8b4c-0861df90aef5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7442bf22-5d77-5fee-9b39-e0311d3bac9d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Watermain | 180 OD PE | Crossing 06-02 | ITP - Watermain-PE - Rev C | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
2414d114-f458-49e4-b23d-199a2ba10722 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Utility Services
152c75c4-0ba7-4157-abc8-e7bce5277b5f |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1
32b06139-2f6d-4eef-bc80-0fa53f2d72a3 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700
33600256-a377-4ac1-a7a6-4e67ec9a1cee |  | work-in-progress | 7633da16f5ea4e422f47e6bc1ef93646c8a4a2fb718aa86c7ba4fecb0d5362ab | checklist | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench
05fb8be5-4ef2-592f-b73a-9d494a0c4fd0 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1ea70b95-2dfb-5446-b67c-dea13e0b405c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
67c3a13c-17df-51bd-be37-42b0d17cd974 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
95ecf479-0025-5416-9709-edd3a1d00c52 |  | pass |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
89291f4f-e27a-5512-9b61-f531fdd10b92 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
46e9f2af-a3c9-5dd9-8481-79a7f4fa644a |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
1134545a-6b6a-5316-a718-fef7d143bc7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
3a6bef12-86de-56b1-a54d-ace8effdc186 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
56e9e3ac-4caa-50f4-b481-8906281f5388 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
0c7541e6-0018-53fe-bef3-1a0cf8140c35 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
96fb2524-b78f-58f7-80a6-7aeafa898535 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
a0344e16-fbc1-59bf-b9ad-33ca99d7207a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
01d0afc4-6221-5416-8ded-b60eee98ab9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
5bc238e1-0aee-5575-9685-d6ea7f319e13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
f68a5612-febb-57f9-98cc-7250ec72c088 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY
d33f8db1-973d-5150-973c-5eaf9c581cfe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
a74d7366-8b05-573a-8733-6a5038dcdf52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
25983516-ea6f-581b-a6a0-560d746d5d65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
5493f8f2-dc2d-5f1b-a901-b7d26005738a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
c94bbe2c-2596-5eab-94e7-64fc470ee4b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
dfba8239-81ba-500e-9614-b4f5f3b4bdb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
4fd341ec-ffbc-5419-acdb-b1d05e5d93da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
b84e43e7-cb16-587e-b841-10df2999c2cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
c0964eef-5658-5de8-950d-26b22f7ee7e2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
18a96c3e-9438-521b-9d5c-04df1023525b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
9573b754-adfa-5467-b9e4-cd0e084c1c93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
7c93f6b8-fc0e-5cbb-be24-88a8ec049713 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
9b845142-8f02-5133-b7c7-f75c998a0d32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
06a3dc72-1558-4d46-be6d-ae99b053c939 |  | pass |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710
50a72f10-0dae-4c7a-914b-95811dd9eed8 |  | pass | 7633da16f5ea4e422f47e6bc1ef93646c8a4a2fb718aa86c7ba4fecb0d5362ab | checklist | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench
d000b79f-7fac-5951-a33d-a2e486a3b9e6 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
b32c01d5-fb60-5d04-993b-81b1ef6633e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
2e8d05ad-c79c-5676-a290-cb2359ef0a44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
5aa81326-ef7d-5222-be68-6901181d6919 |  | pass |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
aeed4b8e-2efe-5b7f-beeb-186487de290f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
940e41c4-d3ff-58e3-a778-88ec2e1538a8 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
13d05bd9-3a12-5835-9369-75471f1fd556 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
538df8e0-59c6-5d9f-941e-5eb80b04f4f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
b925b8b9-1eeb-54dd-8e08-59aac6a1c301 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
8a1a2c8a-9b24-54eb-9b05-482952bfad11 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
04dadb3b-3943-5a56-b7bc-c36f16a4a267 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
a2503019-7a10-5f88-8e9f-16787a07350e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
14c65e02-6e32-5f68-8a36-abed49f5e9f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
26f675c0-33f7-5eec-9dfe-243f2f1e5a24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
a698fb71-c87d-5465-bd30-50872df330cb |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY
667fbdb6-967f-5730-8c6d-3fef16d4b40a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
2a0994f6-f441-5300-8e97-f008522332d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
0d6260c1-8b7b-53e4-a176-395ede853404 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
4511b8ec-69f8-50ee-b410-ed077c46b140 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
ad96f783-6558-5ebe-a9a0-99c718587629 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
9b3b7497-a6d8-520f-b239-0a6e91bfcbd5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
42b6dea2-f179-5c71-a87a-aa2a3e48a210 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
90ce1846-6513-54ca-a857-4e3b2e6494e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
7c656f4a-eea1-5fba-9da3-0beb69d636da |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
73f153b2-9a78-5820-83e0-2d83abf12545 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
c4ce8829-30b8-51b0-aa3a-2e52cac9a58c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
8cb4573e-2f58-5c7f-bd19-a1d245828bcb |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
2572a3e9-2e75-5d8b-823c-9378738a5fcf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1560 to CH 1710 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
aa0f9d61-e360-4d4d-8eec-3ea81ba9c195 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550
15c1ef74-2bd2-4b29-8fa1-85c8f1144c57 |  | work-in-progress | ITP - Utility Trench | checklist | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench
209db56c-db27-562a-a2f1-fd60af83cc53 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
97559f31-3ff8-592d-a7e1-91b39c88015e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
63312645-daf4-52ed-9561-79721d25349a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
a794ccc3-3951-50dd-9e53-742e3f6439aa |  | pass |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
b9616493-e848-51b0-abe7-ef99088827ba |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
60aca997-78ee-56c0-a620-d802ad1383e8 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
dd7f8e5c-08d2-51a1-a62b-a6b10c1952a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
fbb066f5-882f-5f39-a31c-421c4751a857 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
b6050a24-45af-5781-8311-ce09d0b7acdb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
9546b737-1442-5699-84d5-3221520c1937 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
edde900f-f278-5f24-952d-36a0fa4408a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
399dbf2a-90c6-5af8-845f-f617e76daf1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
a3d13408-5693-5847-8f04-4f41c375cd6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
1ff4f61d-521a-5be2-a032-82c2ca1a42ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
18eb91db-c788-5416-95ce-d9a24b8c819e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY
5ba31a15-0e2b-50d6-8f27-4ff4a7921e11 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
40c30280-85fb-56b7-9657-fc9206e29271 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
a5aeebe7-5a48-5268-9544-8a173ebe8db2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
824bafcd-6553-543e-9c77-90d50adda9b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
f7802abf-e6fe-5de7-84e0-0463aa64eba4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
6b023732-269f-5fa9-a3c6-ae5d3c4b87b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
b240ab5c-9e17-5fa0-bcf2-f9f46705c622 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
c6a66dc1-90a3-51ae-999d-8353ac96a409 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
b1c4c0a9-a9ca-59b5-8530-d8ce2326054c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
5900df82-a027-5680-b6ad-57115d630128 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
a5855c6e-4595-5cb5-978b-36df10eabb51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
8fe346b9-0744-54f1-a732-8d6278d5d2a6 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
d7e6ebd1-da85-5b23-96a9-b2cec0671780 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
45f4b7d4-b5fc-57f7-a6da-063f6578cbe6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
dc70061a-ef2b-5157-989b-b03623ecb721 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | RSU00L CH 1520 to CH 1560 + RSU00R CH 1520 to CH 1550 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
c474f322-f953-492a-be40-e47b6841f2eb |  | not-started |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1 | Road 6
862e0528-99cf-4dde-aba9-6a94c78285e4 |  | not-started | ITP - Utility Trench | checklist | FALSE | FALSE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench
c9390c0c-587a-5d2e-b794-7a343e54aa00 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
d4a17852-8403-56ad-90b6-0f14ae7aef46 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
b48d9037-a71a-56ed-8088-cf5bb9d41fcc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
7b27d4d5-96c6-5988-a02b-861b1580ae83 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
8d4f3ca6-4cff-5e9b-a612-6a4250a517cc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
f62223ca-b790-5493-992a-e419a0b469d8 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
af3f5c5a-94de-5819-a50b-6394a2bcc599 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
7e06c720-d929-5c33-a81b-060cb3d5f4f8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
a2f8de1e-7d38-5119-871e-d568356c2680 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
d04370dc-7ef5-5bdc-9139-4ea01b0ca78a |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
24e8f01e-cfcc-5620-adac-ed38edaad402 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
e968a407-b460-52d0-aa29-e22a8e50e3d8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
3d1cd1cc-ac50-529e-a1e0-b2beb41746ac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
49686b2c-2aa0-518f-9dff-5df25307a698 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
d5b56571-1a27-5f0b-a6e2-ab616df40f47 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY
56b05ae3-cf81-5a07-b085-468cad47922a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
112e632b-77c9-5b2f-b322-7796bab3f878 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
8c34f908-6d75-5ade-abda-6fc0d7279b97 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
82943a5a-8326-5f79-9f23-e0aa24e7b0ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
7cd1cc5f-3c5c-50e4-b1e7-4e95124637e1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
f56d3445-397a-5699-9445-19a1e443735d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
1b8c906a-98ab-5ac0-8953-34b73a3399dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
41cf6e16-3b55-5150-a7d5-846b7fc7630f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
a2519b80-6804-57e6-b6e4-6cb54fbdc4ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
aabd1b20-47d2-5264-a35b-b397d0ebb8f2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
9e4d6bd1-5547-5168-a55f-26f49c6e3cee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
041e2d67-d2fc-59b6-ae25-a6985072f471 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
0835ca11-f15f-5b48-85d9-5dbb3f3114da |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
947870d8-5ade-5a05-b159-39d2c6e387ce |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
4c93ebb2-111d-525d-9502-c24b53c36fc5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 1 | Road 6 | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
318e4c1f-807b-4c5a-a1cd-fb02fed31447 |  | no-status-not-started |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1 | RSU00R CH 1700 to CH2360
321d2906-f93d-4bcd-9f32-68b929b43f06 |  | no-status-not-started |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH1710 - CH1900
12b0ce46-e80c-4430-b872-2de7b051f7e8 |  | no-status-not-started |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH1900 to CH2240
59d2383d-ad4f-4d83-b48e-c7dc2f75d62c |  | no-status-not-started |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 1 | RSU00L CH2240 - CH2330
dc79a09a-7fcc-4792-be2d-38a8909e34d3 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 2
34e2d57f-14df-4eb7-b8be-ddf5c678e322 |  | work-in-progress | b0fadf059aaa1627f07427e377b51c920b85cb1a9cdb3702e2ffcceddfdb5f57 | checklist | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260)
bb0351b6-d4fc-54cb-8c73-36c65d3b8f31 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
28e6ff65-f18e-54e4-9e9b-83e371cb756c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
bd7c836b-7b55-5d07-8369-c5e32f81c9c1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
03716bf4-3719-5607-ba32-5d828e82aeac |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
639aeb62-cfa0-5849-bb3f-e731f0010c10 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
d50fb449-4eab-5013-a689-e89400659423 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
823fd79c-9c31-55c3-aed3-dffb899bd42f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
1dea47b2-91bc-5810-b983-42263fe94bbe |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
2dc8bb12-d148-530e-ad86-7d00fc05e2c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
e47eebc5-4f58-512f-928c-e89bfe311702 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
a7d67d3e-d75f-5906-9120-9c49af529e26 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
b7ec22ea-73f9-5ee4-8b71-c02340fce088 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
4413d760-c489-52cd-8342-59fabd04e466 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
f83a9cc6-7b50-5d38-a416-39d91e51d0d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
61fcafb7-d25e-5e65-ac31-4259ff4d0e41 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY
1113049a-cce7-5094-9b52-3b6abf0d627f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
3e3144f3-c31c-53cf-882a-e4afa751fe19 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
a3b4b71d-21dc-55b7-acb8-c1553e372af0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
8a6cbc5e-3ecc-5eab-83ca-5355d36bdb5a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
fac8e4f7-01de-5477-ac13-a0b16e115681 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
b32f9196-c11d-544e-bf63-a9f7212d1114 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
e8eb55cb-9dfd-5841-a471-859863f55bce |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
bd180e86-17e4-54bb-8c01-588b1c1e52d9 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
e2220894-ffde-5e9e-852c-59d701b181e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
8ef90a1f-e75d-5890-80c5-4a1da49772d6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
ecf85b19-6685-5b67-9174-1442a31f3e47 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
ed679c06-6ac3-5709-a04a-2290d8a706cf |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
57f977af-aa95-50e0-aec0-4290cba5575c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
a2792410-266c-41e6-89b6-bd8c5297905d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8f226ba1-52eb-5603-aff0-aec777b1492d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (LS RSP00L + LS RSP00R CH 150 - CH260) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
c4668c4c-e917-4c38-9203-d00d52aa6bdb |  | work-in-progress | ITP - Utility Trench | checklist | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366)
f003089d-6010-5b95-a0a4-389007ecf0ef |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
190eea4f-44e0-5ed9-bf71-2733f740d9e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
22b7de4c-10f3-582d-bbd6-6d0515b307ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
2fe6db03-443e-5f85-a196-3e1355490808 |  | pass |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
027c6fb9-c4fd-5ef5-8835-597d3951bb51 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
06eb0433-1d0c-5e24-a2c5-ae20cec25886 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
2f9f61ee-dd45-51f8-89f9-c24fd3ac17fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
37c6f040-12e4-5911-9fe0-60a41a40becd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
f35f1341-b89a-5b6a-8930-e2d3daaee660 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
797a6a8a-46e7-523c-bef7-7109f0db4b0a |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
8fd7ee77-1698-5ad8-9020-9fbac8ec4bb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
054c1698-8ede-5bab-95ae-f7f98c0b814a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
38630455-6231-5d3d-9aaf-d3e91ba27020 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
99c5dec2-8a69-5a32-93b3-683cac4b7179 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
dc9d365d-8cc7-5280-bc04-090ba51c8265 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY
7e0315b3-afba-5fa1-baae-f4a45f3fbf33 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
a4acf173-afd0-5d86-bc70-1e8b55acdf9e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
6d0e9bba-ab8d-5fa3-983d-54644fc0c3e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
44397354-5bb5-50e4-bf59-fa2a6156718f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
8673d9fe-c685-5012-9b7f-2b9d04a9b723 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
6442350b-5ddc-5750-afcf-b458fe40337e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
c8392422-d935-502b-b4b1-3d5da4dd7d6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
fd5179b3-5906-5754-a414-2aef2185b7a5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
c6449354-98b7-5877-b4d5-ab7e4bc8f716 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
1cedd5c8-6f08-5925-b526-aab982791080 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
830a4f54-3c7a-5f5f-88fd-d30b961ba084 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
a258c33f-f6f4-5d7a-a762-b797b59679dd |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
a99f1c98-da95-52ae-b8be-692423b641bd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
826b3c74-5ef4-5583-8ac9-3a868a92b8b9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
58528b6f-e2e5-50d0-902e-f383f630e433 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1322 - CH 1366) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
e1d879cc-432e-4b47-9bcc-0387d7a3f303 |  | work-in-progress | ITP - Utility Trench | checklist | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452)
f54d0478-54f4-5807-92d5-793cd8ce4949 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
6a6b862d-624f-5b15-9e44-ea0fb9cce365 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
ecd1cf09-4483-516f-97b4-d288307cb110 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
36e646e0-9be5-5e60-bbfb-421b5d6cab26 |  | pass |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
e503fe57-5013-5f4e-9274-027a8edeb1d3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
598f3cd8-772b-5adf-a239-7b4050a91191 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
2d732355-0ee8-5091-8656-6051b38000f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
6af54bf1-1157-57ff-b64b-d648d80ba005 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
05913b94-343a-5e4c-a8e7-890dfb67e2ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
e540b48f-334a-58b9-902c-7fdf439a0844 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2c1d7467-a54d-53c6-bfdf-59e5cf2c1529 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
ac8eed01-53f5-57e5-acbb-0e65b6037888 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
cad98ca5-15ba-5c07-936d-279a032c9bae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
fb7a2c8c-370b-59cb-8821-824656d48360 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
e2badecf-dc2d-5fe3-8fbb-a2ff9094f513 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY
a6a32905-8bfa-5eeb-8fbf-d248cb475813 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
21c1c8f7-51e1-5623-9246-812bf8024577 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
6a270b46-4345-5df7-baf6-5ae5b05fc3a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
ca76df35-cf3e-59a4-b760-ffdf46c41eda |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
bbde31db-c46d-5947-b26b-fdcfaf78f6e9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
aeb38c44-cde6-57ad-be4a-d84e1deffede |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
22f5ca55-4ae8-5034-a98f-bc89a94597a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
e33c6509-85be-54ea-8423-537c3f9300c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
c94ec525-0911-5754-8aed-e789bec5cf35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
37fe741e-73d7-5a33-99d5-2749a32d0f87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
c242ac63-353d-5927-8701-c9598f5ef912 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
750cc95c-fb24-583e-89c7-1582ecb55144 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
d325fa60-a99a-5f65-b12c-3b6349ac4091 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
6b2a7187-2c2b-5a65-91ac-dee2ae8b1f59 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a7b04299-6bcd-5c23-beb9-98c85a0cf4be |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 2 | ITP - Utility Trench (CH1432 - CH1452) | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
9d8d6285-e723-4ecf-95dd-993ec037a0fe |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 3
694f67f9-f158-421f-9134-7c1b42f2b228 |  | pass |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R
78a32a5e-0fbe-418a-ab2c-2d893dc88e09 |  | pass | b0fadf059aaa1627f07427e377b51c920b85cb1a9cdb3702e2ffcceddfdb5f57 | checklist | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench
089dc40c-7daf-5b25-955e-e1bb9622b7b9 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
28cd6656-bcf7-57a0-8a65-41f02b293cee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
849c38a0-c800-5ed8-bf87-586d9a84e516 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
a0c02960-70aa-5046-87a1-e321631955af |  | pass |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
a4e2580a-c682-592c-820b-0c2385196a62 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
e21431d5-5933-52c2-b151-9cc6a14471b5 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
f76a07c7-58f6-52d1-87ee-5c23ea3ac609 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
1240d554-5803-50d0-938c-10c93899dec3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
58f7dd2a-000c-54eb-a4b1-6ccb83810fe8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
8d6d2468-a558-5d1b-b3cf-38eeb7af4a60 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
a221e69b-f1ab-5ba3-80ab-76ea05ce380d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
c453622b-5c6d-5417-a4a1-fa8b9aec5fe1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
d60832ad-ed90-5ed1-9ec8-76b3420a706a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
6b315714-1627-5672-8ca6-fc99a0109036 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
da982ec9-3046-57c4-b129-9e0d14336a1a |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY
0c7b4a90-a38a-5173-aea7-2f4d5ca28a9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
323f3164-4c46-5897-8537-1fd854037d91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
62506553-d505-5432-b8aa-652fda92f79c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
a578372c-0051-5329-b05d-e6251d98239f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
94b2ae65-bead-5fc3-bcbf-b2b2d6f509b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
ed703b40-d828-594f-a315-5917739dc41e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
7e6e0b9c-00ff-5bc8-ad36-acf30c750c6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
f3b69c15-78a9-5af7-9eb5-0795f2a75b0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
63003809-e867-516c-a32c-286c398718e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
05d623d2-aa92-5c1c-8604-fb039f0b2b54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
a97f0a19-b1ec-5819-ab94-92ff49e19a45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
3e6d4f01-729e-5e1f-a9a1-304b3c202b69 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c720f825-d365-5f82-9fd1-afb63c15394e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
355e64ad-a7f8-4d52-824c-9861c917068e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c3ede00e-9def-5d28-849a-39aae5342dc9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH 1000 to CH 1200 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
67f3d56e-7546-45d4-9e33-56f394b9a4aa |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R
a2886d8e-2244-4e9e-95dd-9b42c4c60632 |  | work-in-progress | ITP - Utility Trench | checklist | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench
c05ebc35-50b7-5d91-a9ba-b3ce27a4ac7a |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
4051b947-bdd9-52d8-bc6f-a7495455ca09 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
e3c2c93a-96d0-5705-b58d-566a0a22dd2b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
7396646d-b49b-578c-8d84-2a0ce24933ce |  | pass |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
67d30017-7565-50c7-a4f1-6a7212e3cdb2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
0a89c532-83b6-539e-8975-7e901f6b006e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
a25348a9-5758-5c13-a9e1-0ee033268503 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
4361af5c-42db-573e-b0cc-b47a32f9ab61 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
6d4d9bea-fda0-54ae-9349-c06fe48dacbd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
6a2a49d1-9804-5fc2-bd2d-3fb823962fe4 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
b0cb2c8a-bb72-57ab-baff-d271c512b8d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
a0b81ec8-7a8f-583b-93af-79e5c907ccee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
b96b2bf9-d14f-5462-94b2-4843dd8fc450 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
37621aec-0744-579a-b709-080549dd1d44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
9bf589ef-e344-5bb2-82db-52b461aa0a48 |  | pass |  | section | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY
c13669ba-dfa1-5c0c-8d44-f804886870cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
2cd47077-858b-5d9c-a6ef-25aaba8ba193 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
b2c6fd27-732e-5ed9-953e-e89162848fc7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
24771877-1a3c-5b4f-946c-a3cdc751ede3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
e511f2db-6dc1-5ac7-b72b-ebbd37235292 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
f6de15e4-6531-50d5-9ee5-fab70ff19824 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
8c3dbc5e-fcfd-5234-8587-ecadf42d2769 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
9f7cbf61-d4c3-5f7b-af61-6157d32baaec |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
389332ad-c09b-565f-9150-7b794670a89f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
50fd5753-289d-5f66-afb6-9d686d975bcb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
fce68801-08fd-54b4-b616-e4a85b38fac9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
ec4facc5-9542-5aac-a98f-47da0f6fd3c2 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
87f52005-bd78-5137-b5d4-2c8b57b5aba0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
53bd547f-b114-599c-a862-05e5ddf1fb66 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d5291c03-530c-5190-87b5-f4f2807cbcbc |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Area 3 | CH1200 to CH 1255 - RSU00L & RSU00R | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
a8139eff-e416-415f-af83-fdfea80724a0 |  | not-started |  | folder | TRUE | FALSE | Site QA | Utility Services | Peacockes Road
84202cb2-9a68-4709-afcc-398f33b955a5 |  | not-started | ITP - Utility Trench | checklist | FALSE | FALSE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench
f5b6daa4-2398-53c4-807f-f09a70b26154 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3c5640be-7118-59b8-980d-1f369b36cfb6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.1 - Extent of Line Setout
dcca2015-db1b-5b70-b2e8-5b9f8e172068 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.2 - Construction Drawings- Berm
70152f72-d860-5d0c-ba13-0b5cde390124 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
c7ce4ac8-8e75-553a-9ab6-5b0c72d877ea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.3 - Construction Drawings-Road Crossings
e1783984-5cd4-5ffc-9367-99f49e36b487 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
4a3cb05c-df89-5b09-ba49-1cc16388ddc7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.4 - Environmental Protection
5dbffab7-c0b3-5ee5-83bf-28d6193bd3cf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.5 - Stakeholder
c7d7ed65-c566-50e9-a673-ec6751c9c046 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.6 - Permits
d71188a9-f148-5b1c-9d3f-5cc2b0702d19 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
e8565374-a3a4-5d43-86c5-20beacd2d461 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.1 - Duct Bedding
176c261f-a368-57c0-8584-68e76d4e3c27 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.2 - Trench Backfill
a5a5aa92-92e5-51af-abed-18e5c1fe1c11 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.3 - Duct / Pipe Material
73842ee6-9b43-58c3-811c-9ac4cecba25d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 2.4 - Warning Tape & Mag Slabs
0165bfe7-21f6-59a0-ba9e-505ce9913f20 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY
5dad490d-7346-52d2-9d71-9f0db7c6bd48 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Excavate trench
56a629a5-7f4a-5d6e-bd12-30fd36278489 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.2 - Install duct bedding
9202cb74-bac4-5641-bb39-2500660cc9d5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.3 - Install Ducts
267c5938-3709-592e-9236-cd12b14672cf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.4 - Install Draw Cord
eeb62f55-0a31-56a3-aabc-938d02e61a61 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.5 - Install End Caps
dbf26b5e-b80d-5f05-9742-5950dafd0db8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.6 - Backfill
9e2842ab-0dd1-5db9-944d-2a8e1cc6e23e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.7 - Install Warning Tape & Mag Slabs
744a848f-dcb7-59f0-96ee-399c257afaa6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Berm)
be9025ab-ebe7-5582-ade2-3aeb54900cc4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.8 - Trench Backfill (Road Crossings)
119c665e-83f1-5ca5-b49b-fd5cf010a2e4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.9 - Install Service
2568caf1-5493-583d-9bb9-ed32f6bb39dd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 3 – CONSTRUCTION ACTIVITY | 3.1 - Reinstate
a9dc57b8-5a08-56c5-a404-6d40ca14c8e0 |  | not-started |  | section | FALSE | FALSE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
f1c9fa33-76e4-5d8c-ba8b-018538f45c50 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.1 - Survey Redline Drawings
208ed8c8-4f2c-515a-867a-918f16f4507f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8a3c73dd-1500-5a34-a574-8b92b510d6f1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Utility Services | Peacockes Road | ITP - Utility Trench | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
e1bdbfca-d996-412e-a3ca-2cc2a8052fcf |  | fail |  | folder | TRUE | FALSE | Site QA | Earthworks
a54e6400-2fb8-4cf2-aa66-50b406b95e9e |  | fail |  | folder | TRUE | FALSE | Site QA | Earthworks | Area 1
80de5d68-8c13-419a-8a68-d17f4a7c7413 |  | fail |  | folder | TRUE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740)
6c970634-2962-4637-8e63-98e9510f4996 |  | fail | 2c7f82e493918989315b32fb6e08f2e0c04fb816461613049598363d5700b42c | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS
c26e940d-c6aa-5b1d-b27a-0b6cf776360c |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
0a5a7c03-3597-5f18-bbeb-d699ff5ee72f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.01 - Construction Pack
e9161ba1-7ba0-5c3a-b7fa-2abdb52ba801 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.02 - Survey Setout
b85c245c-934b-5242-bbde-b43fe10cc738 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.03 - Approved Construction Drawings
87450421-c2c0-5349-8d37-69385511fb91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.05 - Topographic surveys for measurement
0e8451c3-995f-5f4b-ae37-00b8e03a1d67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.06 - Permits
1f1e1255-bab1-546e-919b-5f89993025f5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.07 - Stakeholder Management
7b4c430f-9582-5eed-95c7-06cb17e5305b |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
a2847ddc-615b-5444-aec4-d6a98ffe5405 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.01 - Environmental Controls Inspection
b139df19-25f1-5b04-9f73-cda979f42518 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
be1d9422-7c51-5332-830e-92c0a2f7731b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.02 - Bulk Fill Inspection
98bc55e9-0f40-5563-9e18-b4fe6f060019 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
2bf178dd-5380-574a-971d-e482da3ad80e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.03 - Service Ducting Bedding Inspection
79f7f25a-805b-5e1f-8cb7-3d84b1b6d24a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.04 - Service Ducting Backfill Inspection
fbe47e32-de55-5f44-b303-fc3e5f69377a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.05 - Geotextile Inspection
8a0633ac-1c95-53af-a7cd-b77856efefa3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
4d6f90e8-2bad-50ba-aa24-3b573864c276 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.06 - Subgrade Inspection
8a53d181-94a6-5e00-9ac1-4bc0ed3485ac |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
a0c5cd58-1f1a-5a55-ab8c-c66296659651 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.07 - Undercut Inspection
ee7897ea-293c-5f21-bb23-1a42b1545e5f |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
bd382643-0333-50a2-a8de-05f4f4c019df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.08 - Settlement Monitoring
e71b1a10-bed1-56a8-88ce-575c8381d802 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
b8417063-9ea6-57f5-beae-938d44a283d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.09 - Subgrade Fill
247975f5-d176-50b3-b3d9-2fd7c8250bf4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
3891bffe-b6e5-5d56-81fd-25868ca293af |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
2174d0b3-7b61-57a7-b63b-9c91e561e210 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Imported Fill Approval
f41b1105-e030-5e24-ac97-dc6b25afe4f0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
b319d246-ef0d-50a9-b180-662114155982 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Re-Use Suitability Approval
66391130-59e8-5fab-9c19-c056ee45fe8a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
5e2b08e2-15e7-5e31-a74c-33e74ff53589 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
2dc846dc-8518-584c-b3cc-1ba9be173c7e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Cohesive Fill Material Testing
4abf23cd-1ac9-5784-bf59-a16bdafecc4c |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage
dd2b14d9-5700-5ac0-b5ef-c265df683470 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | Subsoil Pipes
5146e9bb-d8ee-5d6d-8830-f869d009c966 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | Subsoil Drainage Aggregate
44e1c446-29cd-5dce-9988-ad1a0ff4630d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | Filter Cloth
111dcd05-8951-5ed1-b74f-c32230c2b4b9 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid
737a5854-7a5f-5462-8161-b77597c51755 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid | Geotextile Approval
91ddded2-2fa9-513c-ab21-b8525cebe30e |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
02c6a4b3-3d76-5047-be31-1738505682c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid | Uniaxial, Biaxial and Triaxial Geogrid
1204827a-6702-5829-8c4a-98f58250ef86 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
01ccd740-4f5b-5825-80d5-dac0c78abba7 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Settlement Monitoring
4b3766e1-e860-538a-8de9-fcdda7887aa9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Settlement Monitoring | Settlement Baseplate Design
ab887e62-f3ba-5610-aa73-d81c93d39f5f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Design
703cc951-e271-5263-beee-a6636d0b181f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Bedding
6451a64f-843d-594c-ac60-54cfa0a388ce |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
5c75a4a8-9c13-5e40-b318-618cea2ea32b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.01 - Clearing
fa7eaa80-f9e0-519a-9a57-440f0951af68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.02 - Demolition
ba109c96-b112-5d8f-9f18-084f359513d4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.03 - Septic tanks
3f092185-cd2d-5792-8c28-7e1d12fba297 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.04 - Plant Clearance
8faf4707-e990-5137-b24f-a8d43f73f8dd |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
0b6051b2-84b9-5a83-ad8b-1a8160928d4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.1 - Groundwater Management
2b1bd787-ba2c-5a92-902b-3e849ca217a6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.2 - Cut to Waste Approval
f16dcfc2-f8bb-50df-b2a3-75970119d502 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
91d69ad9-4623-589a-a6e8-d938c14cda3a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.3 - Foundation Suitability
6a33fa0f-4ad7-5403-abfb-f147ff1075d8 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
b6f66994-888a-5ed8-bb24-47dd49c93f5c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.4 - Unsuitable ground
7cb268d6-0c2e-5531-9464-fe70b96d2d18 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.5 - Preparation for Filling
0ac68dcf-574a-595c-8141-93cd5bedb827 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.6 - Subgrade Conditioning and Proof Rolling
7c259ccd-d15d-5f2a-a511-d448ea4a4152 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.7 - Undercut Backill Compliance
a1024137-bc05-50ca-a565-907ccbfb6447 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.8 - Topographic Survey
e5e88bc7-e2b7-5797-9888-05c706254223 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Stockpiles
96dd35e8-7c6d-5f27-92da-7a28d559e9c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Stockpiles | 6.2.1 - Stockpiles
b9100c6c-6510-5213-bbe4-7a3161bd892b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Stockpiles | Hold Point (Engineer)
a9c75424-e87b-5953-8178-5be4388e25aa |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Earthfill
2d28936f-97b1-5e18-b91c-d00d8017113c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Earthfill | 6.3.1 - Earthfill Placement and Compaction
d709122c-7280-5e4f-9d0a-f2f41019def8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Earthfill | Hold Point (Engineer)
1e1634d2-9343-55da-aa36-0fbe9271a567 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
23954a38-417e-5876-bdd0-9ae488c4f515 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.1 - Proof roll Testing
964de0c3-0d8d-510b-8cb6-b152e39ccb80 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.2 - Compaction Testing
8b3b7bb6-4a24-51e6-8109-d532ccb1b1c7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.3 - Scala Penetrometer Testing
2299beb4-e090-5ed7-acc9-8bee97aba760 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
dbaeb221-f8aa-56a2-909e-e857a9193aeb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.1 - Vane Shear Strength Testing
71125594-8297-59b6-b558-97d9c660168e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.2 - Air Voids Testing
861ae295-be6b-586b-94e5-70a7878e3d1a |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
caa3936a-d260-5523-ae62-fc85e52aeeba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.1 - Proof roll Testing
8eb3befd-1c3e-5e16-ac00-326076ae2766 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.2 - Compaction Testing
88d242a0-fab8-5367-a1c5-1517ca7d2262 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.3 - Scala Penetrometer Testing
cde2fe5b-0f29-5112-9f55-4959bca957d7 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
da289eaa-00b0-5eb4-9b08-9cc2fc2c54ed |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.1 - Shear Vane Testing
7a59c433-aba4-57ca-829e-bfe458c88b1c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.2 - Air Voids Testing
396ae5b1-f272-5019-82e9-43dacdd958cc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.3 - Water Content Testing
750f1981-6f79-5daa-826e-3d5d077799cd |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Cut Batter
8df06d34-08b1-52b1-a740-dc221d7c82df |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Cut Batter | 6.8.1 - Cut Batter Inspections
c7cdb384-5fe2-5086-a87e-825209989a17 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Cut Batter | Cut Batters- temporary cut
d58a74ac-c08e-58f3-85ed-a311e8e1e1ef |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Surcharge Fill
145c2573-7e7c-5e8d-8d79-688fe2f0d007 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Surcharge Fill | 6.9.1 - Surcharge Fill Installation
d948e764-373a-5c20-a38f-254bf40790f9 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Respread Topsoil
29fe9bad-59d2-57e7-a75a-217af5c28f17 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Respread Topsoil | 6.10.1 - Topsoil Respread on Steep Ground
616ec85d-abee-5f31-96cc-23c667cda884 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Respread Topsoil | Hold Point (Engineer)
485b401e-f327-5f99-8af5-5f74aeacb347 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage
7f699930-8743-5210-9ad7-8a7d50cbc863 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | 6.11.1 - Filter Cloth Wrap Inspection
07846bf5-756c-58bd-986a-a29a4c37ebd1 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
3c591517-354f-5eda-8c3f-057ab2d74332 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | 6.11.2 - Trench Backfill
1ae328fb-046f-5469-9a47-b43fd91a5d72 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | 6.11.3 - Drainage Outlets and Inspection Points
8b96cec1-3301-5c65-b82b-a2b8defeddeb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | 6.11.4 - Subsoil Flushing
06b04fe5-6bcb-53ee-a1e6-92fef8e87217 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
fbad64e0-1e67-5026-acb0-2418762cb1a1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Subsoil Drainage | 6.11.5 - Survey
1e0ab240-b1a7-5197-bdd8-914b87cea6b3 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid
7ca2cfd7-8922-577c-b391-dab813b87ebf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.1 - Geotextile Installation and Lap Length
6b934368-f08a-5590-8df2-be12c3242f50 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.2 - Geotextile Inspection
4e0a906e-c923-5769-9f12-aedd5b266a5c |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
375d3622-36f4-518e-81db-3cf59ad2f7e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.3 - Geogrid Prep Inspection
1f4e9bbe-3c4f-5f60-b038-11e35863d97e |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Settlement Monitoring
2a6e3389-8a70-5ae6-a2e4-c3b054b9a84c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Settlement Monitoring | 6.13.1 - Settlement Pin Installation
6c14da59-a9d9-586a-a720-6f58623f3897 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Settlement Monitoring | 6.13.2 - Settlement Survey
8f24e305-f15a-5676-93a2-d69ae40ffd4e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | Settlement Monitoring | 6.13.3 - Retaining Wall Settlement Targets
4666bf93-e801-5b9a-b3da-de43a9299a20 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
a2e81f1d-d40e-5849-8ef0-ba81e4e23427 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.1 - Construction Record Compilation
79c96c70-a969-5be3-9041-6bb738db5f1b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.2 - Survey Records
6451b430-0e03-54ba-bbdc-b11cf6db0909 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.3 - Redline Drawings
a51a588e-82a4-53e0-b5cc-f5a6673e3f94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.5 - Photos
85007e69-6bbf-487e-8105-95bb1edf564c |  | pass | bac6fb00113e4149c0a3115ba5fd7868646f20422b1c36cf5407a24a943e2aa4 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL
7c888e4c-7ef3-586e-9bfe-b41666f36705 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
95fca570-f6e2-5234-9af7-023b9ad22707 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
1755bc11-d43a-5857-8f02-56b8d7bb72d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
8e13483f-b4e8-56d5-aa19-57bc76346be7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
d0eb3324-8f56-596e-ba65-768ee7ddc35c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
d381c0d9-33a9-5b4c-9153-c055e278b76f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
0d326929-1297-5808-a4d5-a05795c04135 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
25daedc2-fbf2-58f7-9080-8997f9c6c8a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Previous Layer QA Sign Off
e7a56450-ca9d-515c-a455-f5c5200703b7 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
f42dd4bd-d657-5ee2-a609-3fce38f993bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.01 - SIL Inspection
6fbebc9d-3104-5932-8c72-44913329e78d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
6f124933-64aa-58b0-9c0f-7b372482253e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.02 - Subgrade Inspection
532e5faa-3f87-59e1-8b02-955793990948 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
dac95b1b-19bc-56e5-9f6e-0cc09c2c49dd |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
42276e29-0e49-5632-b794-bdf037e30911 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | 5.01.01 - Pavement Subgrade CBR
d95d0cd0-0745-5fdb-b2aa-8b10c441997b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | AUTHORITY HOLDPOINT
48d8dd21-9b99-5932-9def-71405d43b84b |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand)
48923001-8541-5a41-af02-bbf2120e627e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.01 - SIL Conformance
08b5046b-0ee7-5544-b329-1b17fe75f1d5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
43f378fb-967a-5f73-be1c-06b164909c54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
639472aa-9848-5c0f-9502-9f0fb5673d61 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
fd340b0f-3c53-56c0-bcf4-d6f63fdcaad9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.03 - Plateau Density Test
9795fe60-9a52-5ef3-be9e-75d2b2eda2c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.04 - NDM
edbc4929-3c64-56af-894a-191c8518b502 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.05 - Benkelman Beam
ef9720a8-c3b9-5e03-af6f-429585244348 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.06 - Organic Material
0bea5c7c-6f82-532e-8e03-314d0d75cd19 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
e784c0c1-f116-5d52-81ad-ebfc83fde6f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | 6.01.01 - Subgrade Prep
e3ec65f0-5ec8-5c2e-928a-f3a0175609af |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | AUTHORITY HOLDPOINT
d514d884-828d-5afb-9458-c3e32b799af4 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand)
610685fb-07cf-5886-8f0a-41837ea1fd44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.01 - SIL Scala Testing
5911fedc-c902-5015-abfc-565524821091 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.02 - Layer thickness
6e81f68d-c4e8-56e3-9aa7-5aae34c5b2bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.03 - Plateau Density Test
996bc404-a61d-5dd9-9b27-18f58a39c2c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.04 - Sand SIL layer compaction
621afb81-bcb5-51dc-8d95-0bd4e2dd8f1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.05 - Proof roll
d4abc4b7-d43c-598f-aef1-bf77f4bf178b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
7a882d83-6e7f-5fe2-bcff-554407ad37d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.06 - SIL Benkelman Beam test
972a8d7f-52fa-57a4-a7e8-f1fe0942d3f8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
491b7b7d-2f8c-5b9c-908d-50b4583914ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.07 - SIL Inspection
230f9594-282f-5080-a627-458a9adde4be |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
846b4937-dece-59ee-825b-b175d14e03a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.08 - Topography
34362c0b-0b35-5316-be61-b6a93ba46e36 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
a6697bd3-3ce4-50c8-8efc-e4b1a6931bdd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.01 - Construction Record Compilation
ea92e7c7-5c0b-512f-bbe0-adc67e5d82cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.02 - Survey Records
9ee3cec4-047b-50f9-a220-877799bd6642 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.03 - Redline Drawings
b8b49ab7-b52e-4878-b579-feac86fc9545 |  | work-in-progress | c3fd7e996b01855f3d27b4cabfaaf193d7e7cca8b3f4586813e6ebe2296fd785 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER)
e81839b9-e1d3-5bd0-ac93-92f8994806a8 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
8daf6637-e4d7-575e-83ef-c15a06854f92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
53bd3a26-2d90-55e8-89e5-82e5057cf786 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
5690b1e5-564e-5a42-a52c-e168a242b08c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
85bbc483-a33f-5aa3-95d3-b1e2618711e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
e2594873-45b9-5cd8-9b35-3874173643ea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
98713897-57e1-5898-aa3a-e5609f10e4aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
8a14be1e-4b2d-547c-9337-2a47190f6a2f |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
6b277538-f88a-5948-b5d8-92bf713eef20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
59cd1a13-a73f-540e-b422-f50ea6a7bf92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
f93f03e3-9bf3-595f-95d5-36b657c769a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
784b1005-7ea2-5bf3-b92b-bc4e5bbe5bca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
2e59effe-90e5-5f69-915b-70a1bf978dc5 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY
05b10bdb-5406-5538-8bc5-76749fbffcf6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
c87554a7-a22d-5b0e-9d3e-bc76842382fd |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
c17afc22-610e-5dd1-931e-70e3cb9793fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
a172a56b-6952-5419-ad74-ac0348b03b5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
057cff8a-b4fa-5b3a-855f-4fcb38b637f1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
b95b94a5-efcc-5a28-9541-bafbd0da7fdb |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
313fd7a1-2c8f-56f0-bf5c-8e52ac3ddda2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
5527e5c3-9b95-5232-b145-ed69be5009a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
f8639a98-1d50-571b-91a6-16a9dec60a3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
fd960cf7-b440-5d0d-ace5-0aba3a792fa9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
1eaf4b68-190b-5250-9b2d-3f7c5af30b6a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
89751018-7ec5-59b8-aa51-f11ff370e328 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
e123b416-50b7-5a4a-900b-e352176d6335 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
c5403e9e-3b16-5403-8fcd-543190ebf135 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
e266b4c7-0e82-55c2-a5e1-deaaae1eb360 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
5a3dd6d7-98e1-4061-8ec2-da370407d699 |  | work-in-progress | c3fd7e996b01855f3d27b4cabfaaf193d7e7cca8b3f4586813e6ebe2296fd785 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE)
e63b490b-f03b-50c3-9654-a926b2dee588 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
04c41138-e639-5b92-bb18-dc2a291fc6a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
05aa1d76-5f7f-5cf6-8d69-d6c732a0e07f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
479b112e-9ac5-51f9-b213-14b4749ff269 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
792ee749-abe8-5d01-b9fe-3293761b9ba4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
deb527e0-f2fb-52b2-bd6a-e49e0baa6000 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
ce7a3fcc-e0b9-5310-968b-7cf363d42f65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
8c04a71c-a8c1-5c62-b808-326344827b57 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
a86cc64a-d1ec-5a98-bff0-65631cf66abd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
fb5be342-3ed2-5a16-95b7-bdbba5012c07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
5927603e-0ef1-5899-80b6-053358ead959 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
d6e44efd-9567-572f-a28e-74ab2ff608d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
db8667a1-db81-5283-8ce4-0211e5f80034 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY
eb7a80ae-1f08-589e-aa08-e2b8180b107f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
e326d929-1e8b-5bc4-acc5-93025847360c |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
d0c30f5c-cb3e-5292-9b2e-8d83d888124f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
10edf0f9-5020-58e8-b148-c46f31343bf5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
976444c2-c64b-5f5d-9805-bda760cb534e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
6412a283-31c5-5908-8531-823de5eb91ce |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
234c57bc-f1ef-5675-90d2-e8c0e08d47d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
d7846ede-a757-5383-93c7-994aed270e2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
33f0c668-d3d1-52f8-aed8-f6cd576fa25a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
9a25e777-23ea-512a-8fd7-08e73a5c9989 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
8003a1c6-f091-5dc2-97c5-c5f2ff2bc1c1 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
52523024-86b8-5f01-a873-43d56054dc50 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
d09def3c-a794-5dec-ba8c-82332d323ccd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
f3b9b193-3574-5494-b448-06d296662d70 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
a86c1aa1-1a6b-5c5d-9a06-1a29db2cfcbd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
63bbc978-7687-4f04-a315-6eb0d032143f |  | work-in-progress | b64c69fb4abef48fbce438b985333fe7e1c3b427fc12a68194aa5cf437db7b95 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS
788916e1-31cb-5b13-97d5-aed77dcd569a |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
2b5b1cbc-814c-5354-9462-52f3c67ffc7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
bcfa2fad-3e03-531b-b1e0-e937ac1018cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
cc9f96c3-a4b5-5233-b849-4418920ee8a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
a1331b61-803c-50b2-9211-7caeedeca169 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
562b9ee1-f4cd-58be-8ef6-1bc642890490 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
505505ef-cffe-5859-950b-36939165d603 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
007d1e93-b68c-5197-95ee-e0df46eb1659 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
12e64e4e-ff31-504b-a0f7-f14b9e782901 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Pavement Pipes
6485d9ef-7f94-5149-beae-f3af51bcb606 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Pavement Drainage Aggregate
f17a936a-448a-58c8-abf0-acd79e92de5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
2176c0db-e1c4-5471-9ec2-55df5093f60c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
348d5679-91a4-5323-83f7-bd5fdbd58827 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY
49ce3b56-094e-5d64-ba97-461c3a9edb4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
77a137e6-db02-5f9e-8897-bce7b512f36a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
c91ee646-4fc8-51ad-aa4b-b5cf5b66d97f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
64da41e8-26cb-5377-869e-a9cb00a36550 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
b7928503-2079-5f37-b6de-87e723b370a8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Pavement Flushing
8fdd47f2-ae1b-5aad-ae06-b4bd5db4fb37 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
c818f3c2-5ca3-5e7c-b5e3-cc21b9ba574f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
e671eb2f-44bb-5ae9-9b2f-8134336e70cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
cf614cf0-a6d7-5545-b114-4914d9ab79b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
2cf12c46-d0c3-5711-a7eb-9344bbac5c4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
57b90e8b-2fbb-576e-acb1-8e316b3bca1c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
005829ba-ab68-5866-b603-5f3e7df2cae6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
37953a00-5d7d-5a8e-bfe6-8723f0839867 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
99109cec-80ad-573f-a458-7b53e89e8ff2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
74afaa8d-a1af-54d9-b051-6e9301d1f7f8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
c052ad69-d061-5e6d-98d0-dfd2421b9820 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
0c7f58c2-91d6-5a76-9c40-436dd349d37e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
105b9c7d-717b-4459-8680-b9326e1d8e70 |  | fail |  | folder | TRUE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990)
32baeb54-805d-4061-a8ae-3636ad6e2b16 |  | fail | 2c7f82e493918989315b32fb6e08f2e0c04fb816461613049598363d5700b42c | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS
aaca74ef-4262-5ab8-92c8-8dbf5eac4ca7 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
8dcfeea2-3244-5b1b-8e58-59548cc6a613 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.01 - Construction Pack
1907aaab-fedf-55d0-ab9e-86adf7e65f25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.02 - Survey Setout
6dce32d8-a974-55af-8f02-eb0157f0cea9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.03 - Approved Construction Drawings
8ab5fa6b-8369-5e25-88e6-a980ed6a58de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.05 - Topographic surveys for measurement
ae699853-7c95-5b55-8791-441b07cdd598 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.06 - Permits
47ccdb8b-fb20-59b5-9116-056322e0d1f2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.07 - Stakeholder Management
f919a2b4-7ba3-552a-9c1c-2505038932ba |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
74bc9781-8bda-5533-930d-793d7c440d7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.01 - Environmental Controls Inspection
b3d76dcd-7d5e-5fc2-a3f7-4d98d4c7f145 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
7bc43247-a384-5962-901c-4ebd92569adc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.02 - Bulk Fill Inspection
0d2c0643-8822-5660-881d-ccb36e17527a |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
902a799c-0657-598e-b93c-79dfa1f946b4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.03 - Service Ducting Bedding Inspection
6f4fb112-6cc7-58d5-a508-d7429861de60 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.04 - Service Ducting Backfill Inspection
85f462b9-1535-535a-b188-ca26ef79e688 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.05 - Geotextile Inspection
6915dc3a-f88f-5f7c-9306-47b99583e2e0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
232331cd-a68a-5304-9051-eaecf65ccffa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.06 - Subgrade Inspection
1c0bf7a2-2215-5d7e-b1b3-5accfdf8ce2a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
2d223638-663d-540e-9ec1-8b2b3dfb3408 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.07 - Undercut Inspection
16a00496-b69d-582d-9a2a-c8865c672e85 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
14eeab28-2ebd-5eda-b461-a0f789f1d8a6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.08 - Settlement Monitoring
246e3cd0-53d8-574d-84da-0fba98905dde |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
297a74c8-6598-5fd2-804f-b0187d476ba7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.09 - Subgrade Fill
a3d3df66-5ff4-57a4-9ca5-1d18df2a4f5d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
587b8b10-72b4-50d7-b1a2-5fa1108db477 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
41baabbc-005c-50f1-a762-325584f50877 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Imported Fill Approval
540b213c-8431-5bdc-b509-944b27a53bab |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
8f0811c4-bca2-58d1-9aed-6439fb71266b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Re-Use Suitability Approval
38b40516-cb4f-5034-8f97-e600b4aed6a1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
ba703321-c4bb-5b39-8760-ce693eee4a7a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
26cf5d27-7060-5c19-a4bc-2ec6d2581557 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Cohesive Fill Material Testing
95ea05b6-ac80-5e4b-800b-f6d5e141a432 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage
ff9898d2-dcf0-59e0-af25-def69b6d3b80 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | Subsoil Pipes
ea7f92d7-c66f-5631-af7c-f5f379f182fd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | Subsoil Drainage Aggregate
6b526193-1813-5869-aa45-49e8468b5e54 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | Filter Cloth
178f2adc-31fb-5465-9256-6fe8710acae2 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid
67c1907a-87cd-55ee-abd4-177080e94878 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid | Geotextile Approval
16fc233e-5aa3-542c-860e-0912075ee8b7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
b8de871c-d954-579e-b1e3-bd880c12e306 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid | Uniaxial, Biaxial and Triaxial Geogrid
20ea8296-2ab4-50ea-a4a2-904ca51d86a8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
d0b9de63-71a6-571f-8d73-b5b93562e08c |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Settlement Monitoring
d8968357-80bd-53a5-b93c-ac82c3172404 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Settlement Monitoring | Settlement Baseplate Design
0fc95f3d-916c-5619-a1d8-ac2cddf88794 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Design
acabd664-efca-5bc6-a9f3-910d7f7050e1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Bedding
c20d394e-9436-5f8d-a70c-5b938e20bd77 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
a33c10a6-7c75-5b4e-9344-85d808a40d03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.01 - Clearing
dcc30ff9-8f71-531a-9e57-376d1999fd7f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.02 - Demolition
53db2fb2-66dd-51b6-93d0-0f4cd3d067a4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.03 - Septic tanks
00e0243b-92b7-577c-8c95-807883e6af61 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.04 - Plant Clearance
b6106f2d-d091-50d9-b5a9-ffe45d1ba021 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
e73211b6-10a6-5f9f-abfa-141cec4d661a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.1 - Groundwater Management
40de6103-f112-5b5a-b75b-b8345d3a48b7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.2 - Cut to Waste Approval
547504f6-4b5e-5f7f-9e18-19523e329fa9 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
7fc2c0e3-e674-5c0c-9881-e021a23720bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.3 - Foundation Suitability
2612ede5-529f-5d16-95e2-a033cd3610b5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
237b59a0-7c7e-59ed-9205-5326dff02a54 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.4 - Unsuitable ground
17811265-14c8-551b-80ae-0ba5ea27c2ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.5 - Preparation for Filling
7ff62a0e-89dd-5cdf-9bc6-4e8598dbc656 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.6 - Subgrade Conditioning and Proof Rolling
07db053d-fc0a-567e-bf75-35016a2b163d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.7 - Undercut Backill Compliance
eab404a3-a3ab-5b80-be05-0873851bd104 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.8 - Topographic Survey
5e064bd8-c540-5a02-8611-33d5c90e2bef |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Stockpiles
91830bcd-1a7a-5fb7-93ce-1deeb68bb751 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Stockpiles | 6.2.1 - Stockpiles
c370f1b3-26c5-5318-8ec6-d43476a56de0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Stockpiles | Hold Point (Engineer)
a9eb22b1-7464-55ed-b379-95b78411f869 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Earthfill
5000b4f2-162d-52b2-9248-385d229154e2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Earthfill | 6.3.1 - Earthfill Placement and Compaction
7f35073c-b6d4-51e5-9e80-869a3e244ba1 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Earthfill | Hold Point (Engineer)
55160775-cdc5-50f2-8b56-69b3955c5c78 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
45a60936-19c8-5188-bb31-4d0f0fd8eae1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.1 - Proof roll Testing
f221ca42-7e35-5bca-86af-683679593fbd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.2 - Compaction Testing
fe00355c-156d-56ab-b1ec-1b6516d52ec0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.3 - Scala Penetrometer Testing
1c7f7115-87b8-5ddf-8e18-053e68b9f1bf |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
59125544-15da-5b26-bb41-5c8a121be49d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.1 - Vane Shear Strength Testing
89fbae61-3790-512f-ac37-2c5167019dcf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.2 - Air Voids Testing
d1c783bc-f7ea-5e17-ac59-2cfb72c7e7e6 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
9a25e8fd-51dd-5d08-ba71-65384c467e56 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.1 - Proof roll Testing
06aac816-6079-59d7-b996-6edca731c3b7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.2 - Compaction Testing
2045b308-6622-5efb-9042-f58e22e20f80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.3 - Scala Penetrometer Testing
2d0cedf5-c969-507b-83d0-a9471ad5c2d5 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
865d4133-965d-5e07-8a36-a21ecaeed1a0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.1 - Shear Vane Testing
48b6cb13-5aa1-5c0c-879c-fd18ce33d2f1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.2 - Air Voids Testing
fab129ac-2772-5823-aba4-03d9ef8bc960 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.3 - Water Content Testing
429dcd41-b483-5914-8b51-798cae801633 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Cut Batter
78000214-a856-5a7c-b02c-b7886ce7e459 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Cut Batter | 6.8.1 - Cut Batter Inspections
2d6cb92d-daee-5c92-be03-449bb7579e26 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Cut Batter | Cut Batters- temporary cut
a1c86b4f-bc08-535b-a69b-f6ddf2db081b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Surcharge Fill
d1886f21-47b4-52ed-867b-29a8946e1511 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Surcharge Fill | 6.9.1 - Surcharge Fill Installation
b55441e1-2b5c-5b13-a59a-560da02ca310 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Respread Topsoil
8890c74b-ffbf-5e8e-8abb-107ea6986d07 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Respread Topsoil | 6.10.1 - Topsoil Respread on Steep Ground
6f2f9514-8421-51a0-86d7-ef647d650745 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Respread Topsoil | Hold Point (Engineer)
3088dd1a-8fbb-5ffe-bddf-538eac474ce8 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage
d19add95-fdcd-5e7b-8269-4c37f9de463f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | 6.11.1 - Filter Cloth Wrap Inspection
e87bb8d7-96b4-57e8-9e6a-60be88d62b47 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
f4966011-af99-55d6-8f0b-518fd4bc1461 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | 6.11.2 - Trench Backfill
8f69b2d9-5dd3-57be-aa81-339345580aa1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | 6.11.3 - Drainage Outlets and Inspection Points
3c46391d-5fba-5d77-97b2-c9d1d34c587e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | 6.11.4 - Subsoil Flushing
bb9c8ae4-391d-5d16-a2c7-8eb651f4c1cb |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
ff16155c-5d6a-5de5-be16-f5124482ad95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Subsoil Drainage | 6.11.5 - Survey
56d2210e-dff8-5856-84a1-e02bd6120331 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid
594a4f20-de91-54c9-9f57-42ff8900e880 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.1 - Geotextile Installation and Lap Length
adbc5e18-777a-58a5-9e6e-56272d2ba820 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.2 - Geotextile Inspection
8feef573-ac0d-50eb-b0d7-a2604e0b36e7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
6bd8f24b-9310-5759-a044-9106e9432bc3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.3 - Geogrid Prep Inspection
669c8e53-558f-5702-b9a0-43d221984cd0 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Settlement Monitoring
974e7415-03ff-594e-a6f9-7206abf8741f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Settlement Monitoring | 6.13.1 - Settlement Pin Installation
9b8a71d7-8e37-5d29-a751-666ce5ee29a6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Settlement Monitoring | 6.13.2 - Settlement Survey
2b86ffff-0a26-53c0-bb4a-45fcbee4fab1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | Settlement Monitoring | 6.13.3 - Retaining Wall Settlement Targets
4d4b8e3a-ffa5-56b2-8e00-3ee55360fbff |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
77106778-552e-5d2f-934b-ea77d1e50c72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.1 - Construction Record Compilation
ce88d404-e542-5c63-b02d-a874f1e23053 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.2 - Survey Records
02a9379d-48de-56d2-99e3-b6f001ded870 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.3 - Redline Drawings
b2494e9a-5272-5708-b033-e6c1188fa76e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.5 - Photos
8c0bd824-2790-4d1c-ae00-cc7475ef6001 |  | work-in-progress | bac6fb00113e4149c0a3115ba5fd7868646f20422b1c36cf5407a24a943e2aa4 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL
37619d57-f6fc-5b78-a90d-d5093add53b6 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9e42c248-8f68-5c19-bf1c-ea4fd29b7932 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
1f6bfdb1-d95c-58da-b8d2-0dccd08869f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
bb54e1ca-bdf0-52d8-864e-a2c41eda0c01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
ca552551-3f0d-5e09-95be-39daa9cf4145 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
8571eb4f-c372-5fde-8ab0-e01cb4c8c48c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
fd43f2d4-59bf-5c95-9d8a-89fdc07a4eba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
fa694f61-1979-5e45-8996-efadccefc150 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Previous Layer QA Sign Off
1b38ef82-ade0-502b-855b-cf937a505452 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
b4348f30-a26f-5875-b949-8b82ce598573 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.01 - SIL Inspection
857a4237-824a-52d5-b236-b0c338e191a1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
2a06cd4e-9a20-5c47-b1c4-8077db263865 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.02 - Subgrade Inspection
465b3dec-7a0c-5a27-a12d-78af8be74134 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
896db47a-aaad-5639-b110-6976018056ff |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
c72bb604-81d0-5962-a632-0d49752ee1dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | 5.01.01 - Pavement Subgrade CBR
c7eebf29-934c-5a1f-a38a-0ad33d91452f |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | AUTHORITY HOLDPOINT
78cb8b70-51ae-520e-84a9-265a6af2e35e |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand)
49db1870-ea8a-5e49-ac30-fe71ca9ba958 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.01 - SIL Conformance
71b39832-b33f-577f-9fcf-a52b3418ae1b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
8953aaaa-8aa7-5a94-8b8a-a7af14db80c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
bd14e9da-32c7-5f80-b789-d5590faf137e |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
37a5a761-83a6-5abe-95ae-59061678fae9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.03 - Plateau Density Test
f88f9e4c-3d72-581a-b6f9-21ee038ff565 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.04 - NDM
fbf8efb5-ad52-55bd-92af-721f98668cea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.05 - Benkelman Beam
2c9088ca-db93-51b8-8a6f-96e37f5ffddc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.06 - Organic Material
ade57961-4716-5b6a-b7a6-d7cce4f56b11 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
1ef74443-78f7-5335-8122-718398748e17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | 6.01.01 - Subgrade Prep
766b1674-b18c-5117-bb0d-618fde82d2b0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | AUTHORITY HOLDPOINT
f99e5c6f-86da-5c49-8071-154397844143 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand)
41b19507-7388-53c1-87d7-42824ef77488 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.01 - SIL Scala Testing
1d3c0c72-cec7-5560-8769-c2eaa730e0a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.02 - Layer thickness
0daddd83-4ef5-5d57-b483-5cfd768d7165 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.03 - Plateau Density Test
bdbab5af-fa02-590a-92df-a80573286385 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.04 - Sand SIL layer compaction
96c3e4e1-79df-5394-96c9-59b309961efe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.05 - Proof roll
7a86a7d9-a8cf-5f54-80d2-e02e0f3e9d07 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
e79558c6-7580-56eb-a387-e871c46f0048 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.06 - SIL Benkelman Beam test
18958734-6ef7-5274-982a-de088636e14d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
ba8cb391-6d94-5638-8180-a1b6aef7fa3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.07 - SIL Inspection
8e1d0a42-1989-53e9-a921-a352322e1a2d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
43f704e9-c240-5f4a-a273-162c0623512f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.08 - Topography
11167a23-063e-56cb-9666-9f61eeac9038 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
60413bdc-e7ab-5920-9c27-1a035d63c4cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.01 - Construction Record Compilation
111584d3-ecf7-56b2-9543-e80aabc330cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.02 - Survey Records
057c865a-6d0d-5993-8485-7a420e38ae7b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.03 - Redline Drawings
5cadb1eb-a78c-46cb-bc4d-7041fd14843d |  | work-in-progress | c3fd7e996b01855f3d27b4cabfaaf193d7e7cca8b3f4586813e6ebe2296fd785 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER)
14395f8f-c1d1-5b32-8cae-6acc8da3ce95 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
e0ae6078-1412-550b-a63e-1690e30b0746 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
ff9e71d9-45d9-5288-8c5a-e202bafcabef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
8cd3c51f-7fe9-51b4-96bc-8cb5b7445eb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
5c3d5cee-18bf-591e-b5cc-e692527758ea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
b9536250-313a-5b0f-a037-075e2019e76e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
2979c524-303c-5d6c-b8fc-0362837fc349 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
f80302f2-a068-58e1-b828-6bcfef94308e |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
5fdc0df8-5931-5d6d-a437-e7b06272db85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
7e64c4f3-4aec-5e58-acb8-9172c0161123 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
fd5d8384-43aa-5b6e-aef5-836ef5f5c5cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
3a4bf76e-e07e-510f-9e1d-c7bb8cc71eb2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
0be63543-23f5-5c69-916f-7b1bad52487c |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY
7d7c2b3a-f4a1-5974-960f-e495c45e7595 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
d29ae41c-2d46-5cac-a993-9cdaf45d0da7 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
7d12c998-041a-5af6-9e45-b982cc1459d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
51bbbc92-578c-558a-925e-5105fdb33a71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
a04274bc-c0cd-5ff9-99c9-71a48d0712bb |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
c642bf92-8eef-58bb-b036-a85fbdec8af5 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
d28f3d80-85dd-55ed-b9f0-bea9884e65d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
923cddf5-05eb-5fb4-b4bb-16782280014e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
a9f6db1f-e5c0-5c3e-ac28-e196fe67f5c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
9b429088-ddf4-5877-bb71-15c3b3c5301f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
9650acf5-a902-54f1-9272-02b5432fe9d9 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c20822b7-5aa2-5070-b42a-4c3cfeb80ebf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
9d4be387-1d90-5a54-a050-aca2df85abe4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
d010cf76-2345-58c6-971b-bd85db307407 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
1c3407d5-0aa0-5d35-a0d2-086034e19e44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
643d6d9b-f59b-4b39-ae4d-8a7a1e1c62d5 |  | work-in-progress | f83ef6deb4c7d27ec034767dc763d443325ffeef7328425a4a1ea22471b2f244 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS
7063e6cb-493d-5b4c-b0b7-bb5785fe7a85 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
fda817f9-a1b0-5f86-964c-b9d820942c79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
50144128-e41d-5cbf-8066-74882372d5d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
47624be4-27c9-5d0f-9f02-d000fd7b6fcf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
9335569b-3c19-5c1c-b891-d8ce38eead9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
42ed3ad9-9ae4-5291-a0ed-3acef262b55f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
22154357-8099-51d1-a2a2-2fa8f06b3b9a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
9beed154-27bb-50ea-ad56-622349dedb84 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
cabd54e9-ae2d-52c2-a1ec-30d91ffe5358 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
cac54bff-8b1b-535f-84eb-43c842b8d420 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
fd7a2f4d-e9df-5b18-9257-b3efc152edcf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
7ac31d02-cca1-5217-a162-1c1d5ec274ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
e892c2b0-c187-5f4f-9bef-93c29c534191 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY
e4db4066-d0c9-5c17-bec3-7df08e9a40c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
df34f3b1-0231-5626-97e4-f5db64edb2a9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
093b50a1-83ad-5c2f-9811-c16683e9af4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
a45f17dd-114c-5148-918e-2d3ec3ec959d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
7d6b3bf5-3d03-543d-9b10-5c31ff5226a2 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
b3cdba51-6f93-5d63-9e97-2c70ce249c93 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
402610e3-b042-5bb6-8c05-d1e20e04ab70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
7801cb6e-52fe-54b8-a520-32b93c68bfaa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
48f04dbe-368b-5f83-a47c-9b26f90e6656 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
e7cee00b-5177-5fef-bd1e-20ddd400a1e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
209453dd-d8fb-565e-9a51-a580cd6606cf |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
f5aa6f2f-6a8b-56a6-86e3-ff72fa0af2da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
f5cd09ca-4fd6-5d53-ae3b-a712f0e59075 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
922f0ad5-73b5-5558-8d93-d19897156f81 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
09650ac9-484b-5c15-918d-dda77751284c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
0c6d8b33-390f-4034-8b5b-90db466bce7d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
4d566f40-6ec2-52e1-aacf-17ffcfe401ec |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
b1978a64-1d40-4152-9abe-16dbd2acaf29 |  | work-in-progress | ITP - Subsoil Drainage - Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE)
205f0c20-738d-50a1-9cdb-79af4699d528 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
401aa37c-c262-5b68-a939-a338df221753 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
56650df5-e519-5f73-950f-6a66a546dc2c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
e3232054-3f69-5bec-a3cc-aaccb9714c79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
ddc5dcea-2125-5e23-8161-73e97fd66b03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
1bb11f8e-bb01-526c-a49d-42967a45170e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
cd8c928e-69c1-550d-b70f-e74e3270377b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
4eed89fa-6aef-503a-99cb-d0a0e5f6bb5a |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
63d575a0-96f5-5326-9014-a5b45a6192e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
1400d1ab-c3b8-5d1e-b05a-88a40965ab75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
c0fe7f99-d6d0-5119-b313-c4d1e9c88c40 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
3e7eff48-7fc2-532d-b2c6-2c6e60ee3c1e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
9c66f358-6cce-5521-8c36-a4a06f2caa56 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY
41955d22-2b84-5204-bc6a-b35a3d848b36 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
7bf2e626-137d-5f86-8d96-f4c918e401c2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
388f0771-eb2e-5385-b76e-547dd2b47139 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
67c3f08c-4497-54de-a23c-9aa1ca1b8647 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
70e2c3c5-0168-5200-9c66-ff4ba16daf42 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
4fd145e6-db5a-5101-afd6-5af03421f1bc |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
7675d7f2-fdc6-5e19-9594-3044a718a404 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
61c83a2c-da6d-5d65-a365-2565cb06c588 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
cc4d0726-f6d9-5988-843a-2e190ff891e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
aecd8bd5-6981-5422-bf1e-6b7bdce2e173 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
618798da-439f-5945-a43a-1ad51cd224e1 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
70156b2e-1d8c-511a-a54d-d7eee2a20ded |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
ab7ee5c1-3115-51b5-bd68-4784b0a0b4c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
12e2e48c-8c49-5896-841b-4ac7cb72561b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
f298612f-91c6-598a-9547-6ca2f7927636 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
1cbb2e0c-bc76-44a3-a505-c260a7961202 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8e944439-5e95-5b4a-9f99-a094026b7ed3 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH2030 SUBSOIL (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
2ecc6710-b52e-418b-b8f2-73802e65d8d9 |  | work-in-progress | ITP - 119 - Rain Garden Rev B | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A
ec5b2c49-ba40-5399-84ab-9ff97afdbcd1 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
f98cce7f-734b-51ee-bd4e-7dd916a467f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
291ffc55-30a0-50ca-b4af-2c63978b547a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
7e69fc87-be3d-5828-8ba4-e45c07baf0ea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
99c66004-a588-5459-936e-170fb979de79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
e48e696b-553e-5c72-bdf2-cb02d1c6d05f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
6cd8d795-63a9-53c0-bb23-19350245b485 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
dc4f3054-1822-5482-9a5a-d633857f5ea7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
f96bd06d-a31e-5f61-ba61-1e616ecab466 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
3300e4aa-a218-5ccd-a15b-54c28ab3344b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - GCL Liner
5347c531-3453-59a0-8b9d-0362191f032e |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
563ce4f7-0174-53f5-a7d5-50e975a200b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Geotextile
8ec4b53d-8795-5e2a-b4d3-482a359ee158 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Drainage Aggregate
c18318e7-65a1-5a8b-afcd-f2188783e26e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Pipes and fittings
920d9a24-a2b7-572b-bccc-7f5ae459d175 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.05 - Graded Sand
7deeabc6-fd70-5c24-be75-4ac795c1a114 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.06 - Filter Media
5bc9d751-d706-5ceb-902d-178cc3d2b1aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.07 - Scour Protection GAP 65 Rip Rap
bcf414df-36d8-5334-a012-03de2f454945 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.08 - Coconut (Coir) Matting
ea440436-5e6d-5a98-8874-3e89f846491e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY
882dea4e-09dc-50ae-907b-383088d4240f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Set-out
4f88dfdd-1002-5036-bcab-508a2558c532 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Excavation
dd5cf4cd-29ca-520a-b8b5-acf852498d4b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - GCL Liner Fixing to Kerb
5d5e10a1-4363-553d-86db-8155e421e0ac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - GCL Sealing (Pipes)
dcbb5afe-67cb-558c-bd92-ca9ac67dc0e0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - GCL Repair
94ad9c4f-fdbc-52bb-861d-9f3122e88767 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - GCL Inspection
372d93e3-4e68-5620-be9c-74f703ef3ba2 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
7cb853f2-60d8-502d-bf4d-ee18026c2bfd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Geotextile Installation
ffc6976f-b765-594c-b388-3eeb2b4e94a2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Bedding
093901b3-c8f2-52e0-841d-410071893898 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Joining Pipes
8ba3a55a-07bd-59ce-a508-be0cd1aeaf1a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Grade
196c20fa-41bc-546f-898d-779f6bccf496 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.11 - Pipe Cover
b9bc56a5-9886-5785-b12c-2bda34f73eb0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.12 - Sand Placement
5d83a927-e00e-54b4-9fa1-e3bc1d721dbb |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.13 - Filter Media
716fe4cc-e1e7-5b88-bbe1-3d10c7ca6673 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.14 - Coconut Matting
e24108b6-4a5f-5c82-9e45-54f6fc92c4ef |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.15 - Scour Protection GAP 65 Rip Rap
719ba1bc-58af-53d8-82b3-523eab10ac94 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
e6feca0b-828a-5e4b-ab66-dd50f9c02573 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
2cc8f5dd-702e-5f02-9346-7b3c1858ee60 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
529895ae-fdaa-5160-a6e9-245ff7099c6e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
1d97efc2-2f4d-509a-ad5c-05a2bba1c0b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
bff24fd4-f196-542b-a0bd-932c81f65423 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7d89ae68-66a7-50cb-9d6e-dfb7a45fd3d9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | ITP - 119 - Rain Garden Rev B Road A | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
a561e755-17cf-4e04-8043-c8e2b24e7576 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280)
b5dcd287-eabb-48f4-912c-f7d2db6005e8 |  | work-in-progress | fdfba5edaa3c12d619945ecba9bbbe48cd7668f5d4481b1470baa2cb0ef9edd3 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS
c0cd1cf5-22b4-59c0-9921-c002771a8414 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
40b3ed51-c6fe-536a-afc5-4cb55154d5c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.01 - Construction Pack
c431d474-708c-5e31-ab48-75fc08cff23e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.02 - Survey Setout
c7f442b0-7a3a-527f-bd09-962c6b52b41b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.03 - Approved Construction Drawings
a9940622-9a18-597c-b580-5cdd2a60601f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.05 - Topographic surveys for measurement
a415ace9-81ce-5e53-8dda-9022b2d2e15f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.06 - Permits
73ed6235-63ed-5a98-8955-49fdfeca2f28 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.07 - Stakeholder Management
df4979cc-6a1e-5903-b923-85d60c232615 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
6f57a2aa-926b-5df7-ad36-ea02e5b8667b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.01 - Environmental Controls Inspection
02e56e12-597c-54fb-b656-ec1ee25c0001 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
5e2046f7-43db-58db-b3d4-772210a853c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.02 - Bulk Fill Inspection
ac3d66c3-d86a-5d2e-9730-03168c962286 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
69dadfd6-aab4-5d73-aabe-6751cd648139 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.03 - Service Ducting Bedding Inspection
4d8b52af-710c-541b-acc1-cdf5dcf991c1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.04 - Service Ducting Backfill Inspection
c469cb17-c74e-52b9-b500-0ecc3e89dec6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.05 - Geotextile Inspection
9cebaa91-9501-58eb-8553-731e35e95e6f |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
6ea59bb9-5f8f-5729-8d0a-64cd8a772695 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.06 - Subgrade Inspection
4700dc3f-3fda-51e2-b6bf-c8e0fb731f64 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
5d43a4b7-8eae-5377-977b-e09a0ad27851 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.07 - Undercut Inspection
e04eaf54-1d9c-5796-8868-635be1fffaf1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
abf17a79-8673-55a3-8a5c-b975ffbe5bf8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.08 - Settlement Monitoring
387f14e0-c764-5780-84f0-b80543911f7f |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
ed3476ae-a9c1-541c-b64d-3597688919db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.09 - Subgrade Fill
faffa788-c992-5542-b727-467e308448e0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
12527eb8-0cdf-5033-866d-09c4e5432223 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
c0ee1ad6-30c2-52e6-9b8c-1ac6f535da4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Imported Fill Approval
896ee5db-932e-5d45-bd8d-1ac635291fe1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
2a448eda-6630-5188-b0a1-6a76d9b6d352 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Re-Use Suitability Approval
fbf17961-7204-57af-90e1-a37d01aec7f3 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
aca503d9-5444-525e-8c72-643ac1bd82b3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
5b6fda46-e6a0-562f-859e-7dfdfc5eda8b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Cohesive Fill Material Testing
09b7d327-2ff7-5395-aa7e-fa3a3f337843 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage
d10d3910-5983-5864-a28e-06c44cc487dc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | Subsoil Pipes
cb44e6b9-8606-5ff3-9c1e-38ccd3962fd8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | Subsoil Drainage Aggregate
9b02e202-7dee-5ee9-b77c-a49ec6fdfcc8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | Filter Cloth
451e5ed4-6c96-5be9-b392-945aad8359fb |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid
2fb541f5-70ab-56b2-8d2c-1df7f9f42f28 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid | Geotextile Approval
08346c52-7450-5352-8587-f46b744e30bd |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
640f834d-ba87-5c27-b365-a265763784d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid | Uniaxial, Biaxial and Triaxial Geogrid
c3e4e372-bec1-5f22-9d13-d360ed5f1f68 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
8b2545df-ba98-56d2-93df-09567564e473 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Settlement Monitoring
54cf953a-d254-52d9-be5d-c3fbb7951b01 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Settlement Monitoring | Settlement Baseplate Design
fac77332-760a-5989-a979-189403494334 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Design
92cfa61f-a96b-5681-92e3-9588762a9462 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Bedding
a68dffe5-dd1a-5838-b460-727fa369d6da |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
526e2501-e420-50ac-bfc0-b558f77ad80a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.01 - Clearing
a12bfda9-8086-5164-b791-c19267805f38 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.02 - Demolition
e59c545f-8939-56aa-a5b1-d0bf73a73d5a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.03 - Septic tanks
4a7cd5a9-98eb-5e15-8f83-6f1c93e6e114 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.04 - Plant Clearance
c8a0e447-e923-58fe-94ec-0554e7fbc3fe |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
c9c4b651-3517-5d1a-bc9a-246815377132 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.1 - Groundwater Management
9d1555e6-d503-58c1-8b11-81e54597f1ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.2 - Cut to Waste Approval
b28839d7-d06c-56f8-8d79-af2f013f113c |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
9faadec5-252e-57c9-86cf-075bcb8f8803 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.3 - Foundation Suitability
e17c5e7a-1127-53a2-ad5d-e322b49a53e4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
487eff5f-3db0-5c1e-9f0b-7a2d26eb01a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.4 - Unsuitable ground
3f0324dd-3561-592c-98cc-be533305ca71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.5 - Preparation for Filling
ca5fae54-7e8e-5f2e-a4ed-bba812598cd5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.6 - Subgrade Conditioning and Proof Rolling
d59557fc-1ba7-537e-8955-fec381e298b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.7 - Undercut Backill Compliance
2593aa97-b6f9-580d-8f85-fd93782a7512 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.8 - Topographic Survey
9a06fa31-8eb6-5bfd-96e7-0e99f07b1b9e |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Stockpiles
be001b46-8816-512f-9059-40f40404edfd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Stockpiles | 6.2.1 - Stockpiles
150bd289-eb84-5d62-b3e2-1cd64ca9228d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Stockpiles | Hold Point (Engineer)
88d43200-8d3f-541e-a25c-b9de11f84a2a |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Earthfill
80bed947-454e-5b9b-a4cc-8537489065a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Earthfill | 6.3.1 - Earthfill Placement and Compaction
f08735c0-d82e-5ffa-b639-6c950fbdf839 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Earthfill | Hold Point (Engineer)
e8728966-e835-5fb4-a1ff-d3b809631ed5 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
57b38f5f-12c0-5498-a699-ef64dd3baad8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.1 - Proof roll Testing
dcf591cf-04e6-599d-949f-dd9a1653d84e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.2 - Compaction Testing
a74cb07d-da21-524a-b7de-62bc69a5dc68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.3 - Scala Penetrometer Testing
eb28cd91-bada-55a6-a134-a3cb1433f848 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
67b7523b-d0bb-5a72-8027-f88a4163c9ca |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.1 - Vane Shear Strength Testing
20fe494c-62e5-562d-a7f2-9d2ceddbd854 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.2 - Air Voids Testing
6014f711-fd7b-5401-bff6-5933ad933865 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
203b3706-4226-5201-b088-27f0aefb976b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.1 - Proof roll Testing
6b6a808a-6d94-5afb-a683-639b721ce920 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.2 - Compaction Testing
3deabe02-ace6-5df0-a518-8480598d9d47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.3 - Scala Penetrometer Testing
03bd83a7-6e0f-5d5c-86d0-622c59e03343 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
8828ebcf-6885-5004-8e53-ebbabd4cd4be |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.1 - Shear Vane Testing
ba9e4f17-ce1c-575b-b8ad-2e2c1daf3569 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.2 - Air Voids Testing
cc5e67ca-55ee-5bd5-93c7-0bb48934734e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.3 - Water Content Testing
20a5b9cf-55af-5fd6-92f4-b71eaf697b96 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Cut Batter
d73ce0a0-195d-5c36-8c57-bbd204d378a4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Cut Batter | 6.8.1 - Cut Batter Inspections
f2a28ce7-7108-5333-a389-dd39663214da |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Cut Batter | Cut Batters- temporary cut
8af14f30-6e2b-574a-af0a-097e363ae515 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Surcharge Fill
c72749fa-4de8-5059-a58f-b35a2882756a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Surcharge Fill | 6.9.1 - Surcharge Fill Installation
e2e4728f-9f87-5428-82e7-7527730a6d68 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Respread Topsoil
18eecc3e-8aeb-5777-8c30-b02e3d62d7f3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Respread Topsoil | 6.10.1 - Topsoil Respread on Steep Ground
af795192-bfc5-5914-b638-5dcd82e07df5 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Respread Topsoil | Hold Point (Engineer)
fdb73ce4-7f47-5b08-abf2-618ef13988de |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage
3e4b2dbf-106d-517b-829d-3dad025074ce |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | 6.11.1 - Filter Cloth Wrap Inspection
4bfe8585-4939-5822-b640-caacb6b2c06c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
dd867c6a-f672-529e-b54e-dbf19b4f9c55 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | 6.11.2 - Trench Backfill
98d16494-5cf1-5dd0-b9ef-ed0d0d7eb3a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | 6.11.3 - Drainage Outlets and Inspection Points
9ed3c900-a325-5efe-bada-20c4e13cb92e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | 6.11.4 - Subsoil Flushing
93b8ec17-0306-5df7-b8f2-8b8150da7e62 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
69e9e8ed-4a05-5898-a2ce-8aea44205bab |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Subsoil Drainage | 6.11.5 - Survey
d3536001-ead0-59c4-b8db-1bb55a4eb409 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid
fb59523f-5f1e-51e3-9e95-0c74403009ff |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.1 - Geotextile Installation and Lap Length
add3904b-ed65-5921-a705-2a2831f615b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.2 - Geotextile Inspection
9f641f5f-494d-560e-87ee-e74d98aa0cfe |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
10bb2de5-d7c8-57f5-954a-32925be94040 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.3 - Geogrid Prep Inspection
cae6ec21-91c9-50e0-981b-01ac738197c8 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Settlement Monitoring
f666e7d3-b64d-5201-8a97-3d0cf9862e9a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Settlement Monitoring | 6.13.1 - Settlement Pin Installation
4436fdf5-2812-5924-a634-ec79a74bb15b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Settlement Monitoring | 6.13.2 - Settlement Survey
bac26bf3-84ce-51f3-be80-899c321902bf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | Settlement Monitoring | 6.13.3 - Retaining Wall Settlement Targets
429a8800-2b85-5702-a936-92acd8bacdf9 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
f9ff8453-e3b2-5ad0-a64e-c856b2e38669 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.1 - Construction Record Compilation
3ccc1a1a-4945-59a7-996a-4773b875f517 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.2 - Survey Records
f1029db5-eee7-5336-9414-42066afb510d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.3 - Redline Drawings
f03c65dd-adf6-5320-beff-b1793df41419 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.5 - Photos
0edad2fd-3b38-494d-9a1f-72b6deb8a8a8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
ab65836e-7963-57b5-a59b-55593a4754d1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Add Signature
b7dd858f-c2a9-4077-afd6-73ca73e6a78c |  | work-in-progress | d430f9cf7ed824575cdf540a6abc3a5975acb43723dc5aec746a2a55d155135c | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL
8bd3bb52-337e-5241-ad44-8aff53bc4fe2 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
cd2d6b78-6301-55f7-a095-aac01fb8503e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
9e001aeb-affb-52f1-809f-264d69d304ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
a3083b69-6c41-5822-a2b0-fd874998ed37 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
900deaed-8e33-548a-b6ee-07d077ce3562 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
e86c8f62-2311-5116-98f8-55e846452759 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
7423e7c1-1120-55b3-962c-638ea7bde30c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
c4bac6ab-c786-5ca4-aaf5-876a91f64b48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Previous Layer QA Sign Off
03ec07db-b1b0-54cf-9f7b-7aa059117bde |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
8a77563e-dea1-528b-8733-5fddee9abccf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.01 - SIL Inspection
2f59eec4-625d-54e6-9644-ba6bca2bfc32 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
339246a3-5ff0-59fb-b908-d968138029f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.02 - Subgrade Inspection
6473c9e6-ee42-51f2-be1b-38bcdc10e8df |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
500e6cd7-d0b3-5dff-97ff-c272c3358d60 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
953a56f9-874d-5047-8a4e-d3f2b5aa5c44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | 5.01.01 - Pavement Subgrade CBR
74df5eb8-3763-5f05-b9bb-3447f84c5552 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | AUTHORITY HOLDPOINT
a5add11e-9e22-58a5-a36d-349a0344477f |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand)
dc01102c-c801-59e9-9c74-6caa8136ac3a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.01 - SIL Conformance
8b111c25-3528-5228-b1fa-54cc90807e4a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
3be3de01-1ed1-51b4-acbe-5b7fd63808ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
88a4252d-0719-5497-a00d-c9048def9172 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
d1ef2500-0015-53ad-a415-77f63f4d6352 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.03 - Plateau Density Test
9f9aefc0-a18f-5255-858a-39ba0f96b0bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.04 - NDM
4b015694-e77f-5599-961f-bace63eda473 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.05 - Benkelman Beam
5fd1adeb-c50c-5294-9ad7-85dacfaf170d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.06 - Organic Material
5e91da34-6422-5edd-91d2-ba162b3898bf |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
ba30e542-c1ac-5554-a08f-b061eee3b40e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | 6.01.01 - Subgrade Prep
f630bbb1-0856-5f2f-8da2-e7fc20635f78 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | AUTHORITY HOLDPOINT
006128ab-5429-5098-8221-605bc8a20cf5 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand)
901a7dec-d972-5359-839a-4825269b8d10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | 6.02.01 - SIL Scala Testing
5bf44a2b-6820-5fc3-a980-e216148f33f5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | 6.02.02 - Layer thickness
04f53cc1-3053-5de7-ae8d-f1ee3fd83a14 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | 6.02.03 - Plateau Density Test
1a2d7967-6211-5b58-9ca6-aef5daca0ad7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | 6.02.04 - Sand SIL layer compaction
11c0bd6c-480e-5612-8358-ea45b2f38cdc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | 6.02.05 - Proof roll
1a51611f-7210-5f90-9ac4-f3964727cd51 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
def68f25-1bb2-56bd-baff-199f2c5601c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | 6.02.06 - SIL Benkelman Beam test
12c34dfd-30cd-5127-9f4f-aa8c89500639 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
ba9f278a-38b8-540e-935a-d14a15308eb1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | 6.02.07 - SIL Inspection
0623f37a-94c2-5b03-8d13-25f31775906d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
27484fbd-9982-53b9-8a97-8663ec59d27a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | 6.02 SIL (Clean Pit Sand) | 6.02.08 - Topography
5224aa58-a077-5693-8f42-d768165e0bf6 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
0f068260-0666-5f71-977d-fdbeb408a621 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.01 - Construction Record Compilation
6e37bcc0-cb9b-588e-a1d5-4bc45cd5659a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.02 - Survey Records
fcd0dbf7-69f9-5026-9eb5-6437eeca7828 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.03 - Redline Drawings
3bb5dbaf-6c04-4abc-a44b-985955ab5266 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d79686d1-58ea-5bb4-a979-cbece3bf43e6 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990 - CH2150 FULL WIDTH & CH2150 - CH2250 WEST BOUND SAND SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
c158b48c-7106-4bfe-8907-f6858c2a7109 |  | work-in-progress | ITP - Subsoil Drainage - Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES)
29853cd1-dc38-5c8e-bc51-65484326b999 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
2811ec8e-ebb7-5990-b0eb-28a880b9cd41 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
8d3e1cfa-a95d-5df8-9d79-83f42b4e44d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
dd9e0560-d117-5909-a4ad-8819de3743f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
e3c3d445-0588-5451-aa8b-2e55432f4893 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
c215a12e-8ade-55f9-8265-8a083ccb5ebf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
8baae319-251c-5cea-9a52-e9f81ac61a50 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
1e026856-b7d7-591d-8af6-31091928c3d7 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
ca61fb4a-5645-5988-91a1-7fdc1c484d6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
e0d8e50b-5b4e-52cf-b3e9-5cdc670209df |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
52409eb3-fe44-5647-92e2-e8e206e27fa7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
4137f5e7-ded2-5578-a7bf-9ee1b33e5bb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
3380d4f1-4e91-588e-b850-03aab447a5d2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY
d7036ab6-9f0c-5aaf-8978-8cff84eea9dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
e439f3dd-4ddb-50ca-94f6-89fa15222265 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
1caeec9f-6555-56f6-9092-937a6eda804c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
7f6e38a3-83e8-5096-b6d6-2e74bd2f8c8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
3e6fc39e-084d-5cde-a27d-3460aa54979f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
025e243a-1e60-50f5-a7d8-2141f32547e6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
a9ea89e9-d51d-55bb-a1aa-3efb2abb84e5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
00ce2830-368f-5b89-8040-cbc940ebe476 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
91c047f2-4813-5c4f-a0e5-8a6a00314f1a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
71e94892-7300-5d20-bf54-bb7a3839ee60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
29f25726-5d61-5661-a651-69560a3d4130 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
552fdb0f-b891-5117-9ea7-2717aaf08bf1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
09f4b888-4459-534a-b2ab-eb8acfbe728a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
46ac4ceb-ab62-5a09-956f-e6e0223c6daf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
af74f540-667a-56bc-93d1-a53835a0652e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
0e9feb10-4b8e-4253-bc34-cb46a9895ab1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c867a4cc-2b30-5153-99b1-763910514fd2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C SUBSOIL (GULLIES) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
0537ec56-aba7-4d99-b7d8-3c5390453686 |  | work-in-progress | ITP - 112 - Subsoil Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER)
e584ead2-7686-5321-a9ce-0a5781ff0b7b |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
cbbf397c-ab88-563e-924d-1f831b14c51f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
d1e4214f-7ce6-5222-b396-42a84061b903 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
f687e508-33b0-586e-8eb5-70c181cb3118 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
a489a8b5-6ec9-5a95-945b-71a69b6f05aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
3bef5041-a223-5da4-8db9-059819e56730 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
50daacca-3b1d-5397-a971-b2f234292bb2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
ac068303-6d27-5e2b-b662-ad52bd93eeca |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
64254c97-fbbc-508f-b6ff-fa17aed2973f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
1f789d99-b623-50f7-9919-c2a61364cda4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
7572b50a-cc6e-5d8c-8b97-06673538f6a7 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
7b4e2789-401d-572e-a258-76fc66ab3d39 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
4ac5e19a-af92-59ba-9ac8-5eec4e8d9e37 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY
79849b56-88aa-5547-920d-bba3f23dc794 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
e1f8189f-cd60-5288-9750-2d82c91ae9d6 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
334bddb4-9db7-586b-8c45-f37bd7416508 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
4a47d474-3a92-58b9-8da2-3c07572e3aaa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
e16852a7-94a4-568e-92d6-ac2c6fc10cd6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
afe9a402-9f7e-5156-a21f-64ae3fe68d2a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
8677775c-ff44-5402-b10f-fd163a430b68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
a19eb029-e380-5ee7-85ce-a99bb838e267 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
9b11d60c-ecb9-5ad3-934b-dc0dcf690caf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
70d3d2ba-ac60-55d9-9dc1-220e27eed176 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
242a37cd-57c8-555d-a1f7-3d2d801a5bb2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
7f8b6127-3edb-57ca-ba3c-278e26b2a39e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
bc6e45ec-7e08-5474-b844-17127ea4a74d |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
0b36fa1d-13af-577b-9236-becc31286a59 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
c9a9fb05-8f7e-50ef-8ead-14a21166e4cb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
ed415b94-f045-570a-a24e-8a3b45cc9ab4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
a4335554-fa11-5541-b53c-c91993e6d23c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
0e8bd38c-9a8c-4e4d-9988-c5b927be688c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
3dbbbd06-f3d5-50c9-889b-7fa3e723ec9c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 SUBSOIL DRAINAGE (CENTRE & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
da5cff0f-666c-4322-9d3e-45a733ecc3b5 |  | work-in-progress | ITP - 113 - Pavement Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS
322924e9-c5dc-5c91-bde3-9616e422fa4e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9528683e-cd5e-50f1-9b97-ec83453bcf46 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
60128c61-59f0-5373-8869-a40728864484 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
4c5ff76e-80a3-5c3b-9d66-0b8586445725 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
2bc95649-b4a2-58ca-821c-0b20aeab5fcd |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
4ac2ad3d-4b49-5149-a818-74a9d4b7183b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
cf4c0340-81fc-5194-af3f-a51fad8d70d2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
37fe036e-aa8c-5459-a6b6-233a681ebb97 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
6625c032-f33a-5f5b-92c0-e3e07f010ade |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Pavement Pipes
9e021e95-0213-5d2f-8970-50863a62182c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Pavement Drainage Aggregate
21583602-16b9-543c-b90b-96b6ccb1b027 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
d4dc7284-3273-50bb-9700-ca0d6f42944c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
33b053fb-0893-516f-b569-21f33f1bf5ab |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY
e14fdb57-a0ce-5321-bb0b-1cfe2f3e5834 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
a0bf688d-0097-5e3c-8b42-7649139e7f0e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
de530f17-411b-5bef-947a-16bc1c8900f7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
21bea183-4f7d-5bf9-9dd4-82df32357afc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
e8a456e8-7c28-526b-8f88-4e0e5552473a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Pavement Flushing
308fd276-fa2b-5a2a-9df7-9a1ab269aaf9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
e826c2f9-d25e-5998-95a2-635ad88d787e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
ea915c66-3ef6-5c27-be18-beef02e6ef8b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
0d79f3a5-03d0-5702-93d1-c88c3d772ca5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
daa492f3-ff4b-5d0c-a513-34d048862f8a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
7849a25d-caca-5689-a31e-9ffbc1c7e756 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
1262d54a-b952-5a5b-b235-7fe4f84d7a0b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
eb0d621c-316c-5fb3-8cea-52b8d6de670e |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
88036464-9dc0-55e9-8e05-68762bc222fd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
e21c8a49-7c93-5edd-abde-f8c82e1e3e2c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
74030ed2-ae51-5432-bc88-2ec264c0befa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
26a7f872-2c17-5e40-8423-9c53f2cda8f2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
29c87d82-1013-4a1d-804d-dbabd308f067 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
eae90eea-beb1-5d37-acc0-d089fa6f12f1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH1990-CH2280 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
b465ee99-ccf1-42cd-810f-d8280cbfba18 |  | work-in-progress | ITP - 116 - Pavement SIL Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL
9f0794af-4a58-5239-8d10-30d8bf53c626 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
866eeb04-ced5-5699-a834-1abb147ea5ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
fa105a54-df01-50bd-b410-371d246793e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
f8f26d19-28bc-5761-9295-9b84edda1fde |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
f7da62c8-c326-58c2-9e16-6ae3f2c59d1c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
220c41ec-9711-555b-b802-1e1117a299c3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
84af8ef0-26ac-5202-8898-6d0b4cca90ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
baaf5cf2-1a71-5fef-aaa0-d548296e9f3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.07 - Previous Layer QA Sign Off
8de883d4-3a8c-56f8-9afd-62a3d039e4ac |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 4 – ENGINEERS HOLD POINTS
429f5d36-83e0-56f9-8759-2a54edccce6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.01 - SIL Inspection
48defc24-43ce-5f1f-b809-e723158c5c6c |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
c6e59cb8-0093-5274-b427-7d112190679d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.02 - Subgrade Inspection
6ee7a016-9593-5ce6-bec9-47756c831acb |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
415b004d-ab9f-5e16-8888-8218a2a8b8d9 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
24fc121d-5b2e-5a08-811d-a17ab824e6e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.01.01 - Pavement Subgrade CBR
96b363d2-eb5e-5870-b916-4b970e2cfac4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
be5e4cc9-fbe8-5d19-a6ec-bcd3e4e98cb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.01 - SIL Conformance
4f5c4732-6b26-5584-9490-b93d2a0df133 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
2e83e4a6-3378-53a3-bedd-1ef5ada6cda9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
f06e9c52-4457-52b6-bebe-9ddf08902b94 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
3110b777-1b9c-57f2-a812-131ebe25460e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.03 - Plateau Density Test
9f34e05a-16a5-5ab9-9036-bb87e61a215f |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
bb16b4ba-4a98-59ea-b53a-7321e915c8b5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.01.01 - Subgrade Prep
79938a6d-ef7c-539e-93a2-9cda9b98947b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
85af3e73-0cdc-560d-85c9-deaf12c202db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.01 - Layer thickness
1237f30d-adfe-5412-8e26-2ec1efa505ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.02 - Services Protection
fd53bb29-9656-5eb6-9c67-07fc2c793881 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.03 - Plateau Density Test
d2fdaca0-2584-5c20-8964-4f10453f803c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.04 - AP200 SIL layer compaction
ae0ac76c-a79a-56af-b97c-3b1aeb2d177a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.05 - Proof roll
b18a8f27-0660-596d-bb84-757ccff0227b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
7ee93ac8-d114-52ef-83ad-486c84964b8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.06 - SIL Benkelman Beam test
aba584d1-2bfe-5f06-b0d6-b6df7110e05a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
79bfa146-7279-5591-abf0-fbcefe5c87b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.07 - SIL Inspection
606a3c89-cce2-5e64-8707-966ce665528f |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
e1277ae0-b1b9-5b5b-9bd6-9feb7db82dc9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.08 - Topography
a4cfca43-e2fe-508a-b0bc-da4bc47624ae |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
ee503bce-4865-5dd7-b12d-c643708e07c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.01 - Construction Record Compilation
771650f6-641b-5e4d-9a00-3f30ab6ddec5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.02 - Survey Records
10e0a034-8470-50a6-b785-c98ea591ec4b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.03 - Redline Drawings
8e1734dc-dfa2-4a5d-9f1e-47a731219d43 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
fff49c78-7aed-5204-be52-07a30cfc78ed |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 1 | Area 1C (CH1990-CH2280) | AREA 1C CH2150 - CH2250 EAST BOUND ROCK SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
5fcedea3-fd57-4a1b-a57e-c15dd63d2077 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Earthworks | Area 2
ba395a1c-db70-4743-acc3-c561826ea388 |  | work-in-progress | d430f9cf7ed824575cdf540a6abc3a5975acb43723dc5aec746a2a55d155135c | checklist | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL
e59d100c-382f-51ec-85e3-37d56c6f6cfc |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
9ef089da-ab85-5898-8e37-9771d15152cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
f8fd41da-f5ac-5766-a054-c0fedc368347 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
58e9c841-f591-5acf-8ce0-cb8c3cb6b462 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
393e1711-7118-551d-b562-f32b2a6eab5b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
7bafeb70-e922-5b46-aa49-a35f74f101f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
646dbd99-63a8-584c-bbb7-bc5d74441ee9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
676b48d7-bc77-580e-83af-1cfa63ca2665 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Previous Layer QA Sign Off
89c625a4-708c-57e3-be17-4f1a408a27df |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
ce53409d-4b0d-5da5-a881-0e26a1830426 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.01 - SIL Inspection
4e927454-c49d-5135-870d-c019b245aaf7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
8552b7f8-8c11-5dd2-8065-d0a5f0ed092f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.02 - Subgrade Inspection
5be4d297-6785-57a2-ac50-c9022f47fc53 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
17ee49b2-c405-52cb-afa1-56e9dbbd88e6 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
dd1e98fe-bd01-5795-8038-cda8f0d5d619 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | 5.01.01 - Pavement Subgrade CBR
9aef1bcf-6e59-5221-ab1e-733b213436ce |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | AUTHORITY HOLDPOINT
ba617a2f-dd88-5178-b0ee-59fed23d6e14 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand)
498f731c-e83b-54ea-b71b-fb0f52e16c12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.01 - SIL Conformance
c7da851a-9a16-59b5-8d4d-12213347826f |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
d1bc3826-651d-5d97-86d4-35b189d252ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
acfdece3-f104-5ae5-8d95-9657f1b3ae94 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
d3784134-b82f-5786-adb9-1da3f80b8236 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.03 - Plateau Density Test
32685af2-0947-5bfb-9ac7-8f7cc6d81571 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.04 - NDM
d5b3742f-2590-582e-b345-35e0e2304e7c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.05 - Benkelman Beam
03eed8d9-483e-5896-be86-d384d5267e42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.06 - Organic Material
c66e0233-1135-5c88-80d2-675225636be1 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
2e557342-51a7-56e9-a482-b4d791414c3a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | 6.01.01 - Subgrade Prep
dcbd46d3-8f28-51e3-bffa-7d19a5d93d72 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | AUTHORITY HOLDPOINT
7c08e838-9c9f-5082-9a6a-068cc2a2360b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand)
96b221a7-62b5-5d47-99e6-45bc89a107be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.01 - SIL Scala Testing
03343200-079b-576c-ab3c-455434e0501f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.02 - Layer thickness
ddfb6f84-d8c6-5355-b43c-5e8c2aec5823 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.03 - Plateau Density Test
0cab6156-2522-5363-974f-8b9dc5fb97d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.04 - Sand SIL layer compaction
4e0127f1-191c-5df2-887e-56087e49c851 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.05 - Proof roll
df83cd66-631d-543c-94bf-6c41c98a0360 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
e92cf4e2-c278-5ec5-a394-aff3191caf4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.06 - SIL Benkelman Beam test
3ddd4b25-d91d-5e52-89c9-a48c597c7401 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
b41c86cd-0250-543a-84ec-898fba6a928c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.07 - SIL Inspection
bf3544e2-45fe-5b77-9c50-5a6f9b95c075 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
f9cbbcdb-bc26-5b11-803a-ccd28b73792b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | 6.02 SIL (Clean Pit Sand) | 6.02.08 - Topography
0fea60ba-3067-5ce0-ae06-6b088b83b9ac |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
3c887b0d-6b2b-59a4-adf1-c5d0268275c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.01 - Construction Record Compilation
a8ecf20b-aea9-579e-b07f-22f087001c6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.02 - Survey Records
23ef2cbd-dc42-5a31-aae7-7f8084c14a3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.03 - Redline Drawings
2c275c66-561f-4c5c-9087-43aecd4255e3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8f38c9bf-99f1-50cf-a8df-51c850c500ef |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
ca2fd06a-19e5-49f3-8081-5f77ef2582fa |  | work-in-progress | fdfba5edaa3c12d619945ecba9bbbe48cd7668f5d4481b1470baa2cb0ef9edd3 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS
0cef4c88-8d4f-50ed-873b-b1be4828d832 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
257921ab-5b3c-581e-a28b-53dc5a3794a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.01 - Construction Pack
01e1622c-6546-5952-a26f-011decd993e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.02 - Survey Setout
794bfd6f-c476-51dd-946f-c99cfc5ee47a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.03 - Approved Construction Drawings
af393232-fdea-5f1f-b0b4-353fbe2f3438 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.05 - Topographic surveys for measurement
eacd58c3-3ca7-5c32-9086-665721df8e06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.06 - Permits
082b48db-ab21-50fe-b52c-7c0fabae255e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.07 - Stakeholder Management
7f498b9c-dd42-58e7-ad80-2e18e42288a0 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
ccfb338c-6a92-5141-ac48-e13a9984a31a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.01 - Environmental Controls Inspection
6e9d9f83-eb31-5e9e-a2a8-988d0acc16d2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
4427e176-e433-5e71-95b8-9f0d3d91e03d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.02 - Bulk Fill Inspection
87785d78-9c05-5241-9250-52e69987b198 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
43d00fbb-4f1d-5139-85b1-ad17910305bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.03 - Service Ducting Bedding Inspection
fb8725af-1db1-5590-b39b-c5a8a8b908a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.04 - Service Ducting Backfill Inspection
908fd6a6-0d95-5ee1-8e53-06ae966ba1e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.05 - Geotextile Inspection
1032f820-6d52-55f7-975b-1dbab42a85ec |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
718bdc69-0e89-5a44-b83b-0b2c470808f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.06 - Subgrade Inspection
d89a2ec1-feb4-5135-8691-0dda3e080dee |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
47bea37c-019a-5563-825f-103d73f047de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.07 - Undercut Inspection
6a172c69-1996-548b-85ee-ddd86ebdc85d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
3b123bdd-ca6d-5cca-adb0-590ec813bf0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.08 - Settlement Monitoring
3a83ffda-fa2e-552f-9a98-1fb8eacf62f5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
91d29550-5ebd-5a0e-8684-f2d28da3c1e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.09 - Subgrade Fill
43c34cad-5f5f-5976-a2ba-7a407db5d8bf |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
c7aaf08e-04f3-5b3b-9ccb-0abef506b93b |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
615722aa-0887-5786-abe9-c61e9db5470e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Imported Fill Approval
6eba0e45-e326-5ef3-9221-9339df50ea2c |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
b57d8b48-0a2e-5148-9700-59054bec9e4d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Re-Use Suitability Approval
2d8dd335-de21-597e-8ce0-76679fe0b3aa |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
b46fc9dc-e359-51cb-b025-26114495be79 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
edbadd59-7c07-5b20-9e46-7d404fb7c29e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Cohesive Fill Material Testing
516f655c-c662-5d50-a177-c0d74b86234a |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage
d60f15af-8305-5e7d-bbd3-c00a3bd47227 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | Subsoil Pipes
05172f7e-3ae5-504c-bfb4-653a154fadf1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | Subsoil Drainage Aggregate
c85f36b0-4060-53f9-bca7-5b8ef9726c25 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | Filter Cloth
fb162c6f-c03c-50a6-acdd-47b170e93bc7 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid
ef87d444-8957-528a-8bd9-0ac5efbce296 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid | Geotextile Approval
347ed04f-e6b7-5ab0-a294-6d9d9ed5953f |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
07b1a5d2-66ae-5329-ad0f-c15470afd115 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid | Uniaxial, Biaxial and Triaxial Geogrid
efe56c1a-7167-5995-9337-4b8a48c15cc9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
f7968b12-0f97-52fd-ade7-91bf7b0e8713 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Settlement Monitoring
9f8892f5-c451-5668-a3f6-5c2a9b9b96a1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Settlement Monitoring | Settlement Baseplate Design
4d0f4830-1f3f-5bea-9a31-e2c4dd382b9c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Design
71254ca0-f725-560e-8549-3a45a612c4f8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Bedding
4c1acf0c-d6bf-5b95-9efa-c5159abe65e3 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
ca3a5f06-f68f-5896-8b50-be10cac9998f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.01 - Clearing
0059cab9-899f-5eef-a9bb-273baddd8aa9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.02 - Demolition
d7cde1b7-fee2-517e-8f06-8bc56916d29d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.03 - Septic tanks
7c707581-5501-5a7b-8cd0-ee88570af670 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.04 - Plant Clearance
e9f6420c-c2ef-5019-8ec6-417527512f0f |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
d28f56cb-cc45-5b20-a9f6-a6c37b932c4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.1 - Groundwater Management
58d2fb7c-8242-5771-a3af-471f0cbd3a5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.2 - Cut to Waste Approval
642f369c-e83c-5b87-b5b5-30bd74bb1b3b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
b8d7a6ab-048c-56bc-aab6-b9d9a0b1f0b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.3 - Foundation Suitability
c4ad2b9b-94df-5c69-8d8b-77e691abeca8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
74aa7483-0ef6-5670-b029-3c30d969dc60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.4 - Unsuitable ground
325e4d17-b0a6-503b-be8d-1a0835bbc8f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.5 - Preparation for Filling
622531a0-e3ff-54dd-b3ad-e2eb20eb219b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.6 - Subgrade Conditioning and Proof Rolling
48c8cf29-ca0e-52d7-96cc-ca9e2c009bf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.7 - Undercut Backill Compliance
b8cf2180-6faf-52fe-9a6b-6d986d0553ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.8 - Topographic Survey
a758cd2d-5f2f-56e2-8beb-6f6aa51a24a9 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Stockpiles
d33b621e-ca27-54a5-b5ee-f4339583d20c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Stockpiles | 6.2.1 - Stockpiles
8a7bc9ab-2896-5d32-b541-0c05ad0dc8ca |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Stockpiles | Hold Point (Engineer)
8e68ac45-7082-5947-8697-2df31bfb57b6 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Earthfill
74e63ec5-8455-549b-890b-708098cc5045 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Earthfill | 6.3.1 - Earthfill Placement and Compaction
c47603ef-15d7-5e0b-a0f1-a906742306f4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Earthfill | Hold Point (Engineer)
c5da1f93-c160-539b-a166-dce9ee047e7c |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
af6e3081-d648-5a75-bf65-413ecc1273fa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.1 - Proof roll Testing
6d4a4a7b-18a8-5415-b418-aff92955e826 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.2 - Compaction Testing
674377ed-ac5a-507a-9d64-b1e184867290 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.3 - Scala Penetrometer Testing
f0811bcf-1adb-5c4b-bd14-e2bffddf1140 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
14c4c311-d8c2-5e0e-80a1-b5c29ebdf339 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.1 - Vane Shear Strength Testing
393bc90c-cd50-592b-9b2f-b24d5d2dcb32 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.2 - Air Voids Testing
34035693-5875-5ccc-b8ef-bdf0003d10d3 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
40929e9e-b016-54a5-b3af-dad00b85619d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.1 - Proof roll Testing
7e44634d-6fcf-5e2b-bdaa-617c9122e2f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.2 - Compaction Testing
c281b657-7bd9-5230-9f16-0a853c71881d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.3 - Scala Penetrometer Testing
600c3e4e-a732-5bfa-b27f-484895777e97 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
b3a14639-0811-5109-9fd7-2b380123c9c3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.1 - Shear Vane Testing
f5f3267e-a2e1-5fbf-96bb-195bf0f8d4bf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.2 - Air Voids Testing
bae6e863-1b0a-59f4-b5b5-81bdabeda143 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.3 - Water Content Testing
e1a22810-5d86-5588-9b55-c49c8c022d79 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Cut Batter
59aa3ef6-0103-5374-a132-75d2339088cd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Cut Batter | 6.8.1 - Cut Batter Inspections
687a198a-584c-52f6-b9df-9b9c8c5287e6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Cut Batter | Cut Batters- temporary cut
594ade53-3263-595f-9107-5bc0b4f53c64 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Surcharge Fill
06297858-f9b6-528e-a5b9-abfbe3769fe8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Surcharge Fill | 6.9.1 - Surcharge Fill Installation
0b1f93b3-79d7-556f-b8b8-d0c568718469 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Respread Topsoil
70cf2b87-5842-5ead-9f66-a9f94de1856c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Respread Topsoil | 6.10.1 - Topsoil Respread on Steep Ground
b8dd1ab7-80db-58a2-a993-f07a890b987d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Respread Topsoil | Hold Point (Engineer)
3ced7b33-3938-5554-8f7c-88ddc01b9ada |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage
7b947274-5e11-5ea8-bb39-674154a58180 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | 6.11.1 - Filter Cloth Wrap Inspection
77ab7018-4736-5d66-a676-f0779925ae4d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
4ba7c384-eada-5b9c-a49e-be1df08fdb8b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | 6.11.2 - Trench Backfill
aa244078-573d-5b7d-9fad-4c93f6172b1d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | 6.11.3 - Drainage Outlets and Inspection Points
f8a75c8d-8db0-5386-bb8f-969f1eeb723e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | 6.11.4 - Subsoil Flushing
6cd82c92-53f3-5935-b57d-78db15421018 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
c27e93ef-0365-511c-acb2-e59dcd8d5d97 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Subsoil Drainage | 6.11.5 - Survey
8f6266c4-f604-58d4-aa64-1d6342b7d640 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid
b239cea0-08f9-554c-a5fc-ca4fc5b1a47f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.1 - Geotextile Installation and Lap Length
94b6f656-ff3f-512f-b704-4ea89bcc9e00 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.2 - Geotextile Inspection
e87c7b82-73d2-52f9-acbe-c31fc52c71ab |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
0529fcd6-2bd1-5b11-9d96-70cec67f08c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.3 - Geogrid Prep Inspection
831027fc-9806-5a30-9395-c70ca19628a7 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Settlement Monitoring
1441635c-3b6d-5166-b255-17676cb219e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Settlement Monitoring | 6.13.1 - Settlement Pin Installation
22884a8e-4524-5fa9-a712-fb0614184542 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Settlement Monitoring | 6.13.2 - Settlement Survey
5af26f7c-0d8d-5fb6-9e0e-8605629de469 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | Settlement Monitoring | 6.13.3 - Retaining Wall Settlement Targets
f2d5ecf2-0e10-5454-9e79-a3c41ce0c6ef |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
87284954-290c-5c2e-ac54-950d9d252c6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.1 - Construction Record Compilation
c6d9e616-9540-59ba-a8f5-fe68def42fd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.2 - Survey Records
9296fdc6-6021-59e7-b020-4e420d86083b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.3 - Redline Drawings
47a833de-11b1-5ee8-80b9-5e31063bb6e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.5 - Photos
901fbc5b-e1a5-42d3-8f9e-3ccee000bbd1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
25fb3246-cc9c-5a99-8208-d3bd5dac1ca1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CH1340-CH1450 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Add Signature
8e80007c-c367-450e-8076-b3072f84858a |  | work-in-progress | ITP - 112 - Subsoil Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS
e9e3fa45-079a-52ce-a7d8-b133147f9599 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
7e30ecec-b895-5d8a-b20b-dc77aebc2e35 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
3eaa2ff8-9861-50ec-ba69-e102a2a9fb08 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
428a1d47-a6a2-5e31-b242-f6a9cb2ac864 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
5e3b54ed-af67-56e6-9915-c78daf2fecb5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
88867090-e7a5-51a1-8158-1776660ecb23 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
94f1e159-a793-5800-92f5-c32b4d59a6f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
634e2a6f-40c4-5c6f-aeb7-99551d71d6c2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
f2a44412-e5b9-5648-a9b5-05659cb8c86c |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
7bb57d7b-10ec-53d4-884f-7afc0239487a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
4c545051-c4e3-542c-83e6-85fca7f1ca9c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
fd65ed52-d026-5b8b-9c0e-6d3833bb717f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
6dc6a2c3-c20b-53af-92eb-7fe9a07015e2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY
b3feb5e5-b90e-59a7-8fd6-e1fba8055498 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
17ac80e0-ee7f-5fbb-84ab-4126df59e466 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
8afa25e9-c3f8-5a90-879c-672a13faa46b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
5d0b3712-75fd-5c80-be13-3c4bafd16fdc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
595eb005-9128-5d31-9732-197877020162 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
1eb11ceb-db6d-5d02-bf09-7a35b06e63ca |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
bb371a27-c1dc-5017-aeba-d388404a4805 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
baaca060-5d34-50db-a618-2268a20a23f5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
e6547c9e-7924-5d03-bea1-5186f97f39fb |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
8585a3f6-5b4a-53f4-bde8-f651011b2d22 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
470358d8-1dee-50d2-8576-83cc8e12a4f8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
314e9c1c-2bab-5ff1-a733-d9b1ea16fb46 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
7f12102e-963a-5169-bbea-cd4fcfafca61 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
dab3318a-067f-5664-bec8-82a89fe91e6e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
59848bf8-9256-574f-8be0-87b89c7e0907 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
f9e91508-ec80-5d71-bb83-33b665ffe88d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
64351ff6-58ef-57d9-ae59-a6dc6fd99404 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
2e22d124-3cb1-56e2-b108-f19af3a60fbb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
0b36ed3b-c174-59f2-a987-8a684eb7f744 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 CENTRE AND PERIMETER SUBSOILS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
248d1d61-ac11-420e-8f0e-9cb2bd8c2fe4 |  | work-in-progress | ITP - 113 - Pavement Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS
d6c004d4-a20a-51fb-b5dc-a4be1d0eebb8 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
d9fe85b3-6888-55eb-8350-879cfce7457a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
8cd78f77-94aa-5145-a99f-06e4f9f2ac4e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
8d2915c3-706b-54c5-a9ae-5d2d4832b341 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
df4d5114-c92b-5489-a00e-d7d6afcf4a5a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
13c2a488-e02d-5527-b6fd-3cd2c906fd89 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
1ff5959e-7671-5a62-ae8d-eee3cd4e8505 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
a6aeb3c4-eff7-55bd-bf84-568d03862b34 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
5bb925b2-269b-5fd5-90aa-4262b7567979 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Pavement Pipes
16de8d09-b90b-5315-8767-74e411039ca6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Pavement Drainage Aggregate
8cff50bf-3ff6-534d-bb6c-d1e1d79654ae |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
6a6b27c9-2bb5-5ce4-ba1f-e497e583679e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
0e119717-a4a1-5a2b-9393-d7de0fff582a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY
dbc5c7a8-36c7-595c-9c65-f5d6442cc716 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
f71ebcc3-3b0b-5e7a-93ed-c6d7d7acfe43 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
3facc7e9-1d49-54dd-84fc-ced736ffef55 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
29dc77ea-d641-548b-8c76-33a7934e3b36 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
fb35d5fa-403a-5272-82e2-d3508346972d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Pavement Flushing
5422a672-9517-5ae1-88ca-0a65bb51e7ff |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
d8f2b3a0-cbda-526c-a58a-156525abf2f9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
765d5466-3f9c-56c9-94f6-73f301e284b1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
bbbbba5d-339d-5340-86a2-3b0200f85e6f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
cc7e07da-45c3-5f28-9a96-5a0a8aea685c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
c3af6647-f2a9-587e-b8e0-56f978a27c9c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
d1d69f84-91ee-5309-a1e0-f51252b4014f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
0fab886c-2131-5f7f-a476-2518b5e63626 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7c55a15b-4a1f-50f7-9255-ccacebf1c110 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
4c9adfb1-992e-517c-aaf9-21a9de4e0fb2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
c2eea609-f283-55b9-b6d5-e4da67df8ccb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
51e2fbb4-69d5-52e7-9d2d-b1d4c04320e0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
6932237e-1a72-5156-b2c9-dab271913f7b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
2e607b16-26f8-589f-98d7-f712005170bc |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | AREA 2 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
a3f9efcf-a438-4c8e-99e7-2cb72a8d8f66 |  | work-in-progress | ITP - 119 - Rain Garden Rev B | checklist | FALSE | FALSE | Site QA | Earthworks | Area 2 | SWD03 POND
756a3478-036d-54d1-aca0-edfcc01a06e5 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
6b5ec4a1-9cbc-5379-ba94-465626a6ea8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
ff73a769-c7b4-5024-a2f7-aac2295ce15b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
d6b71fbb-96c6-5334-ad0b-db3caebfb579 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
d2836363-0a8f-538e-ac3e-5696ee58ced7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
a81a8a29-e05a-554d-83c3-402dd56cce8e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
8a3ad309-3a37-576e-a6c6-54bdaaf261f2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
029a8912-be7d-5333-9d65-318b86a72821 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
b47decff-f3ef-50db-bf0d-2041e1ea09a0 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
0570d547-a856-5dfd-b6bd-a0840612cae0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - GCL Liner
79c2a528-c43c-590e-8367-b187b2011b52 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
6792e453-a9ca-5d85-9ed5-e3d5dd3f22a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Geotextile
30f2ca56-5380-562f-bed4-114d49c462af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Drainage Aggregate
b8cfc8d2-f908-54ee-88a9-4cfb19c0f0e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Pipes and fittings
af7ff216-03c5-5d52-bb8d-67b6f73ba532 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.05 - Graded Sand
8670e1eb-cdcb-533d-8937-3d9ca5ca6c73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.06 - Filter Media
19ca3137-4bf6-5011-8c99-b5bef30d1c21 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.07 - Scour Protection GAP 65 Rip Rap
52201c91-e0d3-5ce3-bceb-464941df308c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.08 - Coconut (Coir) Matting
bae659f7-5e40-5937-8a3a-2de22e1175d0 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY
13a233d2-03d4-558f-9b9b-05ef40d14e16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Set-out
1f3fcf7c-96c7-51f9-a33c-8ac561d6bc61 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Excavation
553935e6-0fba-58d5-98d8-8abb13e500a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - GCL Liner Fixing to Kerb
c42143e1-cb06-5221-94b1-6af101c80ffc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - GCL Sealing (Pipes)
7709d800-fa62-5ebf-8014-17f9fb196b2d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - GCL Repair
227a0ce0-407b-597e-88d1-998b83d6b98a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - GCL Inspection
8b746d66-ab26-52f2-b6b8-3f05895dc3c5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
16b47322-99e4-5a39-8932-21346f58953d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Geotextile Installation
c1cdd6b2-9e92-5934-bc3e-706092fa8472 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Bedding
ef783441-09d0-53a1-8aa4-867b3e22f3b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Joining Pipes
054719ce-2946-5bed-be48-46bcfe4a0b9a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Grade
d760d4ff-3c18-5d81-ac96-c52210c3060c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.11 - Pipe Cover
fc44eb92-ad1c-5eae-87f6-303c59575ba1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.12 - Sand Placement
4c29e26d-eb5b-5c2b-9841-767369d61d57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.13 - Filter Media
b14826cc-eb7a-51f1-8090-4a80081e69c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.14 - Coconut Matting
794e944d-bbc8-54f2-bf5a-c14c0d6c1569 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.15 - Scour Protection GAP 65 Rip Rap
e03eb4f0-13f3-50af-a1de-a5dfa32a04ad |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
24c70abc-43ae-577e-b2c4-22de5b83447a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
69044f91-4860-566a-8a3c-787f1e43b8f2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
d67d1a01-5b49-5b3d-9912-ab645368ee18 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
58ab969b-298c-51a2-9d9b-12177036499e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
05896528-8c84-433d-b817-3163cfe9b100 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c7537432-6a8e-5f98-9481-364053d57a92 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | SWD03 POND | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
60e984b7-2f35-4d4e-b36d-4f9e50271abe |  | work-in-progress | ITP - 116 - Pavement SIL Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C
aaf22c3b-daf7-5a1b-8b7e-a9f37b2adb17 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
701576c6-a5bb-58d8-b6ec-40525b5c239f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
76323537-3bfe-5731-9fdf-4e8a28a95f92 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
4c578f2b-d107-5c9e-b5eb-46779e21dfac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
c060abfe-9795-5dcc-8610-38f285459a01 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
edd73b33-f568-555b-b33f-ab730727fa98 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
9f9c4e28-1445-540f-97d9-74c0541d1e98 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
8b2367dc-fdb4-5cd4-be36-5a72d946626d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.07 - Previous Layer QA Sign Off
b403c069-5b0b-5db3-9f7d-b44d2c636c32 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 4 – ENGINEERS HOLD POINTS
4b332c69-70f4-5638-9c8c-40df86110e37 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.01 - SIL Inspection
4c09f25e-08c6-5bfe-83e7-288aefcc44ef |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
4ecfd904-6dd4-5a52-a43d-8a3fbe3801c9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.02 - Subgrade Inspection
de753acc-18f4-589f-aa40-b1d5c2126afc |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
1e499525-c62e-5d2a-a7dc-4cc64942c7bb |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
4a8c80c1-0ed0-5f2d-9fa3-e47c87c45a5f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.01.01 - Pavement Subgrade CBR
102fc027-6e01-54f7-bf12-dcda52b8edbe |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
f6bbda34-c834-5f6c-801c-da8799c74898 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.01 - SIL Conformance
9a0fa58e-293f-50a5-a02e-38701d0aaf72 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
f028bb6f-b1e4-5b9c-9112-df59d0205800 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
80d38042-32ad-5579-a1e2-9522db7ba550 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
d0108566-1b64-568e-92d8-88360cc8a964 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.03 - Plateau Density Test
f79cfd19-c6e4-5517-9e6e-5d3b8c92a9d7 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
af701365-5729-54a5-b3b8-8d25c292a6df |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.01.01 - Subgrade Prep
ff907308-9f93-57dc-a06b-7361204b5ce1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
d371eca7-c967-53ee-bd8f-eae89295aea5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.01 - Layer thickness
7e2aa19c-5fd1-5140-b6c6-4896f2cf89b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.02 - Services Protection
82fb602a-149f-5f70-a156-f56cfae83d6f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.03 - Plateau Density Test
46689e99-6a52-56b0-b92f-e0e342857d62 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.04 - AP200 SIL layer compaction
e55c9606-1a28-5e1b-a3e4-0b71e8dc81b1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.05 - Proof roll
29eb9502-fce5-5d12-9444-d2b4642e8f6f |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
59145f19-12af-5bb7-a6d2-03e989670c1a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.06 - SIL Benkelman Beam test
3419c583-71f3-5de9-8358-a0fdf63f2426 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
96335fd6-36d2-526d-8318-b55bedb79026 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.07 - SIL Inspection
72c78804-1a53-5a86-8d3b-9665bea4644a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
c125140b-0253-51bd-bc57-7c598c4fe1fd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.08 - Topography
6cc638d6-6236-5202-84ff-1ac5859a0dff |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
f7daad60-016b-5ea2-b224-c9137a89be91 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.01 - Construction Record Compilation
9563c776-39b2-599c-b4f4-71185b5af807 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.02 - Survey Records
1c63e1df-3bdc-5fb4-ab87-6d27ee48e4da |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.03 - Redline Drawings
4858dc0a-972a-5835-9f25-941a6fab18f7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9893c873-d90a-513d-966c-1dd02bfc0dda |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 2 | ITP - 116 - Pavement SIL Rev C | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
149fef4f-92dd-494d-ab0c-ad61d8cbc369 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Earthworks | Area 3
978cef49-4d11-402c-af62-d798be75c49f |  | work-in-progress | fdfba5edaa3c12d619945ecba9bbbe48cd7668f5d4481b1470baa2cb0ef9edd3 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS
0167d59f-52ad-54c8-a69e-45d524edcdca |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
f85aaa1a-d9ea-57ed-8155-6c96064f530b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.01 - Construction Pack
a5450355-d388-56f5-80c6-70a84f09e855 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.02 - Survey Setout
e9500b92-bdf7-507f-bd88-a9b5518570d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.03 - Approved Construction Drawings
34d092bf-fddf-5d67-ad0c-4ef4605b1e4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.05 - Topographic surveys for measurement
4ba592e6-7cc5-50d3-a699-dd9a45b5b3a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.06 - Permits
aaa677b0-1305-5238-ae35-23580132d0b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.07 - Stakeholder Management
d19c2c87-b066-5e0e-af84-50636b8f68aa |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
616b3236-9dd9-5985-875a-13e46409c390 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.01 - Environmental Controls Inspection
1c7e12cc-e58e-535f-b170-849965f27413 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
f8475bc8-eaf6-5917-873b-e7f8f91949a0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.02 - Bulk Fill Inspection
c1f743d9-d46d-5fd8-b383-78b8d6457e72 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
57799b60-19ec-5bd2-8935-6c5716c23d73 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.03 - Service Ducting Bedding Inspection
c0c38256-14d6-5c23-98c5-6a74f65f3fb9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.04 - Service Ducting Backfill Inspection
8d5cca6d-0cba-506e-8735-db382c39b448 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.05 - Geotextile Inspection
7c87a98d-d82a-5200-aa81-3bbc7c9b4c0d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
037996d3-cc7c-5600-8520-74c8fad57e9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.06 - Subgrade Inspection
3b9daff4-df22-5678-8330-53f2e49eec27 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
7665b6c5-de76-5117-bf17-5c982634f39e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.07 - Undercut Inspection
f01552c2-7080-5037-bde7-388f1e6eb082 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
b73e0795-3c3a-5baa-8a75-0dcd9a3d062e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.08 - Settlement Monitoring
e0f5046a-8865-5aea-95ff-cb79157414cf |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
2410899c-92f8-5f2f-bd9f-3ac802032aa5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.09 - Subgrade Fill
7e380cef-b42b-50b5-b772-bee8baa39a0b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
d23564ce-0b5f-5c3d-8bc7-f417c260cd9a |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
53d6536b-99d4-5fdd-aa4e-ca573c9a2a3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Imported Fill Approval
16578483-e3b4-5e7e-8215-989db2353f15 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
1cc78228-0d0d-50bf-8c3a-d52b8906acc5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Re-Use Suitability Approval
aaf4100c-7846-58cd-ba3a-51c190fe9d54 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
fc5610da-401e-5ebe-962c-25570b808295 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
947d5979-b390-59db-9b43-10ba7f812736 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Cohesive Fill Material Testing
69d0b8b1-6f56-5454-8f3d-2a8aa84ab15b |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage
346af022-a005-5c86-bd03-8429965f88ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | Subsoil Pipes
0571ff9d-a369-5705-a542-e978ec315087 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | Subsoil Drainage Aggregate
652668e6-6119-55fd-a5b6-ffc1bbef6c50 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | Filter Cloth
779a6189-b116-5612-ae04-03b67d2df6af |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid
22e136e0-89bf-5eb7-bf34-cdd882698537 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid | Geotextile Approval
a3eb4edd-ad64-5b2c-aea7-c603ff7f077d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
ba6da29a-c2dc-5ff2-bd01-fca4024ccfe8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid | Uniaxial, Biaxial and Triaxial Geogrid
acf248a0-c1fc-5d43-8c67-1bd50e4ce0c9 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
b5aacfed-bc14-5354-9863-99aeb11a4d03 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Settlement Monitoring
30839ac6-f54a-5433-a66d-1ac88a75b6c1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Settlement Monitoring | Settlement Baseplate Design
878c59c3-e593-5cc3-b087-46018df0c886 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Design
2bd98922-7639-5daa-9435-49f66df411dc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Bedding
8fe41c9f-1dd7-5776-97b3-ebbf8824f4bf |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
f6661b4d-ed5f-5784-8786-b3e7d499b623 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.01 - Clearing
debad94f-bd18-5981-b74a-3a3847fb239e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.02 - Demolition
cfa47d69-737f-5af3-844c-dda9a899c49b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.03 - Septic tanks
b2035a08-e52b-5ecf-aa9b-1b36c3852a19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.04 - Plant Clearance
765a4286-6493-57b1-819a-3ac4e62e4fcb |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
35e76687-9dac-5561-af27-05259995c290 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.1 - Groundwater Management
efda02cb-de4e-5808-ba4d-d5d4160361ad |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.2 - Cut to Waste Approval
0b87d881-de04-51f1-a20b-53893ac2764f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
861057b4-3139-5d90-b820-31cc6f11cd14 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.3 - Foundation Suitability
72405a61-d06a-52f0-b4ed-25da460aa094 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
e1aeaced-f92b-5b1c-ad96-9dd35956a341 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.4 - Unsuitable ground
16370396-dd7c-5774-b482-7fa2298894ff |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.5 - Preparation for Filling
52525bc9-687c-5c50-83c3-895de2cc7020 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.6 - Subgrade Conditioning and Proof Rolling
e51394be-d8f8-50e8-acf2-f2ba099e86a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.7 - Undercut Backill Compliance
e82bf4fb-3337-5f77-8aa3-cdc8e16c744b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.8 - Topographic Survey
e2ffc157-642b-53c8-8149-d915368e5206 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Stockpiles
46fd77d3-16f7-53e8-b684-afa840119a95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Stockpiles | 6.2.1 - Stockpiles
90e46a24-81e9-546c-8282-7aab9ff1499e |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Stockpiles | Hold Point (Engineer)
38704907-c000-576a-a724-7f85215206a0 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Earthfill
66e904cd-e042-50f7-a140-761bc6392ed8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Earthfill | 6.3.1 - Earthfill Placement and Compaction
44441c02-1075-56e8-a555-31894cd787d9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Earthfill | Hold Point (Engineer)
4a7f3659-689e-504f-a8c8-b7ad11271dfc |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
bd9ca91e-2ab3-5fbc-a7df-319a6df72e89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.1 - Proof roll Testing
09998646-a17f-5c22-82be-754fc6416723 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.2 - Compaction Testing
e1c4f6b7-96c3-5f4b-b8ec-771768a4a0ca |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.3 - Scala Penetrometer Testing
e2ae1e1d-3b7b-5f66-b602-88ae20d2bc64 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
a8dc8d2f-cb12-52d6-9779-9031ef19cae2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.1 - Vane Shear Strength Testing
b57da939-3c0e-51b3-8474-1b2a1a38e488 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.2 - Air Voids Testing
8cf5604c-ef0a-54e5-b0f7-e92b6838e786 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
08ef664f-7468-53fb-9251-5908c929de30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.1 - Proof roll Testing
48d85be5-2dca-5251-a158-a968ef7efcca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.2 - Compaction Testing
e11e714b-d0c1-5d06-baf2-bc41f948c6dc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.3 - Scala Penetrometer Testing
1841947d-82c4-5ea0-9281-a61ca570193b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
dfe887da-fdc7-585e-b6a4-903be32f67b8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.1 - Shear Vane Testing
78956039-4626-5ab4-af35-f4381fdf5b83 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.2 - Air Voids Testing
d4681c4d-0182-5278-b0ea-797e710fa38b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.3 - Water Content Testing
9de88a19-9dc6-5a76-866c-34681da7999b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Cut Batter
63c2c627-e178-592b-95ac-7712f61a6ab9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Cut Batter | 6.8.1 - Cut Batter Inspections
d0f7ede2-cd9e-521c-8139-bf33ecb79239 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Cut Batter | Cut Batters- temporary cut
01fc1e18-c9e8-5732-960d-e7b19181c8c0 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Surcharge Fill
d2700042-1058-5349-ba4f-44442e2c59f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Surcharge Fill | 6.9.1 - Surcharge Fill Installation
50d2f870-bb85-5953-be62-230c4ede4bd8 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Respread Topsoil
e7ac7d2b-63b4-54db-b0c6-d0288825d817 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Respread Topsoil | 6.10.1 - Topsoil Respread on Steep Ground
3a001159-3d3a-563f-b1c5-d3f655b36593 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Respread Topsoil | Hold Point (Engineer)
fd89dcc8-df56-5702-96bb-f44e49e74faf |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage
46d22d9f-f2b5-5a97-9bf5-267fff958260 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | 6.11.1 - Filter Cloth Wrap Inspection
a51e1441-dcd2-56d3-bf8d-516658bb2ab7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
89126b2f-a0bc-5348-b3f6-30947712ff03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | 6.11.2 - Trench Backfill
843a8211-8a91-523a-926f-480c86600966 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | 6.11.3 - Drainage Outlets and Inspection Points
3b62f163-2f52-5d1a-910a-eb1c2ff6f07f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | 6.11.4 - Subsoil Flushing
48907bef-5d76-5e60-a777-d5327a695827 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
428b77af-28d5-526a-a1d1-27a3a102d71d |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Subsoil Drainage | 6.11.5 - Survey
2de7956d-b868-516a-ab2f-5c4416792edc |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid
a3dec70d-9e5e-51c3-9ed8-52dfb3d7ede1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.1 - Geotextile Installation and Lap Length
30d16308-45c6-5036-9218-44501bce03ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.2 - Geotextile Inspection
cd2ea704-3bae-561a-88a2-209dff78cdfe |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
82ef0b58-d8c1-5efa-9692-2d9ab9490532 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.3 - Geogrid Prep Inspection
43a53e73-fcf8-59ca-b2cd-75ad91ead8d9 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Settlement Monitoring
5e1a1767-b6d8-5060-918c-6742e9805a0e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Settlement Monitoring | 6.13.1 - Settlement Pin Installation
7493b5d7-3672-5a51-b5e3-5ae3252bac05 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Settlement Monitoring | 6.13.2 - Settlement Survey
77656b79-9728-59a2-9971-70a46887e2b3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | Settlement Monitoring | 6.13.3 - Retaining Wall Settlement Targets
072b5b02-7cc0-5dd2-9060-31b591bd036f |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
1d580065-6263-5616-b7bb-6c8da93f92c0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.1 - Construction Record Compilation
fd970530-20f8-56cb-87ec-9db9ad2ea80b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.2 - Survey Records
0cf102a9-9b71-5978-beff-e6f1f3e35e37 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.3 - Redline Drawings
87d7f78c-2803-5da6-86e3-e684151fe6c8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.5 - Photos
85a3a88e-2afa-4465-ae8c-aa6e0ecfa2fe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
5f6a8e78-a3c4-5400-b6fc-269fcaf511a2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | AREA 3 CH995-CH1255 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Add Signature
bde0d9fe-1232-4ce7-802c-82e557b65280 |  | work-in-progress | d430f9cf7ed824575cdf540a6abc3a5975acb43723dc5aec746a2a55d155135c | checklist | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL
af3ca908-4811-546b-ad62-afcbe2aa89aa |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
d41cf1da-2efd-5ab0-966a-eee1bf6d8347 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
25dbef3f-58ab-51a2-9a67-94e5310d8aed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
da850d22-40d7-5374-afc0-ed1f80ff2bfa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
dcfeb43f-0215-5aec-a00f-e95d463563b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
b7b68a8d-ea08-5a9e-826e-a1a028fb1d96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
87859594-c73f-53bf-a2d4-270e365072cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
83189796-bf3c-50e3-87af-9d50303c07b7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Previous Layer QA Sign Off
465cb4f6-3c39-5bfc-8d5a-a88b216bc49d |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
440bf7a9-f5fc-5188-9898-c2e80d75ae9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.01 - SIL Inspection
5c9695de-465e-508c-85f5-9084ae0a6f70 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
a9cdb364-c4cd-58a9-a7b8-59aee0f51f3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.02 - Subgrade Inspection
b7080e7b-be5d-5b22-b18e-8c1f58c87329 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
0e7cb263-aa64-56b8-93d4-7839a98978b9 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
c6a85076-aae0-54f0-b46b-8e9ca33a0fed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | 5.01.01 - Pavement Subgrade CBR
83902281-792a-586b-b60f-2604d266d488 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | AUTHORITY HOLDPOINT
4d39ab70-c026-5dec-ae29-06fb22a0ca42 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand)
b8ee60ce-ba37-578d-8013-a0297f22cba1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.01 - SIL Conformance
c437bd18-36b0-51eb-8db7-89e1931ef046 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
b426bf51-dcc2-5141-a3ae-fece58e3f205 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
7ea448ea-6f7c-5920-9f8b-4c81b131268a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
0c61e947-0ffa-5b13-a014-354126fc60bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.03 - Plateau Density Test
4bad383c-ea52-571b-bf3e-75efca3a6052 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.04 - NDM
87614320-013a-5a91-91ef-edc34b2dfb9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.05 - Benkelman Beam
2b82bc91-80d1-5224-8e72-2b55cba65eed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 5.02 - SIL (Clean Pit Sand) | 5.02.06 - Organic Material
5738bac9-6bdc-5f63-8e04-a6bab360f3d5 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
4c75af28-7d00-5227-aec9-7e39d811299b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | 6.01.01 - Subgrade Prep
0150a044-8239-5a9e-9aae-b695771dfc2f |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | AUTHORITY HOLDPOINT
a27e4508-d77d-5f7b-a390-2370933a2b2f |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand)
1f5b56b6-51df-5938-8ad5-0976d844d778 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | 6.02.01 - SIL Scala Testing
e883d580-0cbd-58cb-84db-6b69bc8b2f3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | 6.02.02 - Layer thickness
d88a8a49-f8fc-5898-b9d5-669edb942d1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | 6.02.03 - Plateau Density Test
4c2259fc-df18-5e01-ac11-39b51b8b130d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | 6.02.04 - Sand SIL layer compaction
0607edff-2cc9-5d59-9c59-8c0e23902434 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | 6.02.05 - Proof roll
b7b8322f-33e8-5adb-9869-ca650813f7b4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
d65904cd-86a8-534b-a042-13e09b27c360 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | 6.02.06 - SIL Benkelman Beam test
24830f36-1cce-5452-8c13-bb52686d4124 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
c9e24e0a-e8d2-505f-8f25-780d20cdcedd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | 6.02.07 - SIL Inspection
f4227982-a23e-5f76-9257-c12157612568 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
df390f60-49e9-59c4-9a62-82a513168c1a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | 6.02 SIL (Clean Pit Sand) | 6.02.08 - Topography
999a9bc0-8017-54b0-bbd2-c1984c019eef |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
85ed9168-6fe3-5ae8-98e3-1ad46408cdca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.01 - Construction Record Compilation
b80a72e9-8b17-58a2-b7b5-b882d010d435 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.02 - Survey Records
680fd960-029b-5c5d-b8b8-819c44fece29 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.03 - Redline Drawings
842acbff-c53a-4897-97ae-1e32a3ef216a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
4e77d570-1af3-51cd-b512-4fbfd26bcd26 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
e00be842-188a-4b60-a77c-3c8909ebe74d |  | work-in-progress | ITP - Subsoil Drainage - Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C
da729c33-4a68-56d9-80a3-aaeb24004aea |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
772bb85a-3278-5163-927b-c988908d0a87 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
225b19fb-1b54-5c84-bb32-91a17847e3c1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
1a1160ea-4fea-50e6-9d16-e544a142f45c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
4b4de35d-f1bc-5154-9b30-16161d652647 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
623713f6-c9e7-5a13-a92d-1772e98d5e3f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
e097a32a-4616-5286-ae4e-1ccc181b1ba7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
34623e24-ab9b-5dd5-a2b4-a405f31eaf5c |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
88309fad-3c87-5c23-b141-936bc87f6085 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
6925b66d-2238-5e11-ab94-25c5a2375038 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
978c2095-c50c-5cda-97e8-e4dd1017332b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
6e4f4866-97a4-5a25-b231-d18fcb19d9ab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
4b9bb8f7-5969-535e-8773-66e249c0e94a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY
39ff26cd-7a4f-55fc-8000-f811e55cbcc3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
44ee1f39-b8c3-54f3-bb8b-02e2fa560aa6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
a96c7e47-8eba-54e1-a6f8-8bbb3ea56105 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
7aa50acd-1410-542b-bff7-3bba861b64c4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
23dfe58e-1dec-5ddd-a4c5-bef88dc2fff5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
d9676bc4-0669-57ec-88a8-68607d04201d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
a13a5e2a-a472-52ef-8c1c-6f4ab105b0d4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
39c01d28-0b06-590a-9bfe-e1f9966610e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
f5725f43-da0e-5b55-b130-fe526aad74e9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
58f235d4-6dc4-5b12-9b80-e0309e13d71a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
2d87277c-4b95-5b1d-a4e3-8e5c72674f9a |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
5d2d608b-b06b-5ead-be2b-c85b9378cc1f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
0e4d0bfd-e339-511a-998a-6d971abd3455 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
86512444-a8ed-5914-ac5c-b8875ff1e46d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
af29a4d3-c23f-5ee1-ac52-15c7cd3c3672 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
9b439811-e2b0-4b3b-9be6-d6def16df399 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
855b00b3-46a7-52fb-8af5-7da8b4006e89 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Subsoil Drainage - Rev C | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
5fba8c19-d916-48eb-94d7-ed627719ac00 |  | not-started | ITP - Pavement Drains - Rev B | checklist | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B
e8daa8d9-656b-58b0-83e8-03482942d24c |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
34ab5376-4537-59d3-b927-47bbd1c61abf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
947b7fe4-649e-58f9-bd8f-556258d9ba93 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
c8719270-0689-5a47-9981-ff5bb08a6525 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
800103bf-b9d8-5e7d-a96f-298709c371c3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
bec62171-4106-544f-bf79-d2fac7ab9bbe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
b789c670-9bc0-553e-90ff-fb7b6b768239 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
08316079-31e5-5fab-929c-23cbf07c0a00 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
eb2c1472-7ea5-558b-968c-7e01e1b8bbcc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Pavement Pipes
1b236e17-b655-5008-ad3a-a7813f90e04a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Pavement Drainage Aggregate (20/40)
ca63ce83-b5f9-5412-99ea-ceac16d97994 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
55914b81-8390-5fbd-b600-611c53ac455c |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 5 – CONSTRUCTION ACTIVITY
a89ed6d0-46e3-50be-ae9f-bbc8a737511e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
7a3082ba-6e2a-5683-b818-529ba4f9ed16 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
9eca37b1-be8b-5913-a48e-7ef0f29be260 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
898bb0a3-c89b-5b75-bf42-399be9c4d7d2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
53b74ae2-b6c7-5f4f-8932-1ef0fc1e7728 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
9e03511f-64f0-54bc-8c60-0702b07e8a3b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
ad7e6f92-0b71-5d6b-afed-490f0ec38841 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
4cc5dfe9-7c34-57a4-acef-d2c28ffd4284 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
b975fa55-0f49-5338-bf27-e6fff4e75960 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
e7ae4e61-8186-513c-b71b-1b84881aec20 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
a189e5c5-f448-5c95-a56c-a4b5f1e2b466 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
2c838a4d-d02a-5ba9-bf19-cd9f97b6e0db |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
e47a5e08-498c-41be-b024-9f83412539c9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
1f4999b5-a19f-5f4c-bdc3-c75c8a594cd2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Area 3 | ITP - Pavement Drains - Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
40d4a1e6-bf52-48c6-a4b2-16270c54bf4e |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In)
df15dd61-47b2-499e-a1ce-2d1e32ed7fa8 |  | work-in-progress | fdfba5edaa3c12d619945ecba9bbbe48cd7668f5d4481b1470baa2cb0ef9edd3 | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS
484defc2-6e1f-570e-a8cc-3498f949786d |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
d315e6ef-896c-5c72-a505-3c1ba373869d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.01 - Construction Pack
610a6930-4da5-5e5b-aac0-65271649bc22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.02 - Survey Setout
98f0c52f-2baf-5d18-ad93-d4f04ba18c2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.03 - Approved Construction Drawings
68dac87f-43ce-51ee-a4ae-587c953002c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.05 - Topographic surveys for measurement
5ee4ced8-2001-5b21-bd61-b60f9a626dc4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.06 - Permits
26d4001a-2965-58d6-82c1-c3c1c7769231 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.07 - Stakeholder Management
6b98b63e-680d-54f6-8095-7d92b4a96f31 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
27c2ca1c-8088-54b0-a50b-67634d6ca60b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.01 - Environmental Controls Inspection
ddf21fea-fa60-5ae4-8c02-591e4c9754ca |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
a17c27e5-a63e-561b-9ceb-db4c6aaf4498 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.02 - Bulk Fill Inspection
dc983811-e632-5bb9-a101-22b90f17c348 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
74603cd6-95a4-5025-b2c7-57c1be2e9534 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.03 - Service Ducting Bedding Inspection
2a0a90e4-b51f-5170-b252-49d966db0513 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.04 - Service Ducting Backfill Inspection
3366a995-5ee9-5f3b-a0df-64b1e77915f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.05 - Geotextile Inspection
8453db78-9733-5438-8196-985dff0d5d76 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
0564c9d1-8a9f-528e-b9ee-1383e54f2a2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.06 - Subgrade Inspection
e83b1c0b-7542-542c-a3c8-e754145d3b2c |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
6417ed0e-2240-5172-9ebe-b097f381a15d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.07 - Undercut Inspection
3d050c07-20f3-5cf6-a9e8-b8ad585a1e17 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
e8c3121b-bf5a-55e0-ac94-f8fb3092c6db |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.08 - Settlement Monitoring
bcad53ae-e6ab-569c-b4fa-39975ea82b37 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
7b2e9efe-a862-5e6d-90d7-45c5462ebfa1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.09 - Subgrade Fill
19479e44-5af0-59d6-923f-2a4829d40f15 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
eec3d7d0-4c9a-52af-9b52-59fba7fbb4ff |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
8d6ffe57-7cb4-5fe2-9401-ee1998ee4d77 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Imported Fill Approval
181b5e7b-d6fc-59f4-92a9-95657ffa0d17 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
d371a3c7-4610-581e-9058-1dc25b850f16 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Re-Use Suitability Approval
57e1e9d1-307b-51dd-a2fe-2b6f16e94a4f |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
a94d5ab6-b0f5-5c28-b69f-8cafdece3605 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
b5dbd67f-8470-577a-8fdc-b55bebcdfbd6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Cohesive Fill Material Testing
5444b616-87ad-51fb-a562-c3edcfc09589 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage
b0d0d72e-a946-5cbe-86b5-d97716285af1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | Subsoil Pipes
6e639c8b-bb92-53ed-a563-a8c0bf5ec58c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | Subsoil Drainage Aggregate
b18f88cb-5869-5ca7-a78b-f824e87f9e3b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | Filter Cloth
8a726432-81ec-59db-a98c-4abb30206078 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid
3c766148-ba13-58be-aa18-ddbf05855a0d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid | Geotextile Approval
67c82b3f-f4c6-58b0-b7a3-69a9105c94b4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
54429fb6-cd92-551e-9193-b6d63531ffe0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid | Uniaxial, Biaxial and Triaxial Geogrid
61d2f49c-562a-5689-94d9-72c700531058 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
f65b31e5-021a-560e-9189-f41642fa07f0 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Settlement Monitoring
9055be0d-532f-5764-b24c-1e6d0b0e9071 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Settlement Monitoring | Settlement Baseplate Design
d9774ad4-4235-5c6d-b6fd-48f48bca66c2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Design
07b214af-7573-5934-8c16-0cb0faa9455f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Bedding
5400e8fd-69ea-5b34-b324-b019207bd4d4 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
e6de9335-1db3-54c4-bf8b-b0292a5cc9cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.01 - Clearing
6eaa48c6-393c-5cc3-b9b9-37d4e68d4b76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.02 - Demolition
895aba01-5891-55b2-bb5f-186147a11a35 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.03 - Septic tanks
65adcc09-e2a6-5431-bcfe-3504ac28e502 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.04 - Plant Clearance
1da5b406-bd1a-5699-95be-66ea8329d132 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
a5a39ebc-2733-5bc0-876b-f436b340b5c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.1 - Groundwater Management
2749ea07-4dff-5136-a4e3-3e9da7857640 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.2 - Cut to Waste Approval
94a6ab36-43aa-556d-a40a-f002edc3ecad |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
e2ca1d26-141e-5358-9fa4-1af0147dbf93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.3 - Foundation Suitability
56bed382-2018-57f4-95f8-c5ba5f3d6042 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
92b83898-a736-53f8-9a82-30b69217c26a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.4 - Unsuitable ground
fbb0f5c7-8fc8-5add-977b-c8ad2bba5a7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.5 - Preparation for Filling
afe8ee4c-6a4b-5cc0-a4e6-35ad147b44f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.6 - Subgrade Conditioning and Proof Rolling
18a93dfc-613a-5d21-8372-3c0c7f850bab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.7 - Undercut Backill Compliance
8a12b686-047f-5263-8299-c8d5242068ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.8 - Topographic Survey
a8b7c6af-098f-51e3-ab38-1acf6e7640c6 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Stockpiles
cf5532a6-9cca-5434-b39e-b2f5017c2ba7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Stockpiles | 6.2.1 - Stockpiles
f6137f10-7f0b-55fe-bb01-64aa4b83efc7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Stockpiles | Hold Point (Engineer)
5217e796-c0ca-5604-aec8-503fd856ca2a |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Earthfill
9bb90205-51fa-54ef-aa3a-4db3f767e916 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Earthfill | 6.3.1 - Earthfill Placement and Compaction
bfcea2b6-91b1-5d0a-b2b0-15af9444c4aa |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Earthfill | Hold Point (Engineer)
bec99313-edbd-583b-a6e1-9a440a9d159f |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
ddd0cb46-f7ee-5ee8-8a2d-fb2e331af365 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.1 - Proof roll Testing
edbd166b-c25a-5293-b1e9-0a31130e058d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.2 - Compaction Testing
2ce204ad-d9c4-568e-9051-29ed060f6b4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.3 - Scala Penetrometer Testing
9f6218f8-acc5-5d7b-9a46-4e309adbfe48 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
025d058b-6985-5c82-b070-099d6e362715 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.1 - Vane Shear Strength Testing
8933c1cd-6484-5865-b5b3-68a3e585b9bf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.2 - Air Voids Testing
4aa9ffa7-7497-59f5-803a-40b2c9d547ce |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
52aa2a97-cfe9-5dc4-9802-9be265207494 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.1 - Proof roll Testing
9f1994f5-a5e8-51b7-b413-d1b67fb8803f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.2 - Compaction Testing
c68005d4-dccd-5588-9dd3-a38b74a379e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.3 - Scala Penetrometer Testing
e2ae5ea1-a138-5ed2-9232-8de7ef172214 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
156c91fe-9966-5b07-bea1-c066e7c1cc03 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.1 - Shear Vane Testing
d78987ec-5887-5808-b416-68e3d358d8fe |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.2 - Air Voids Testing
93417580-8990-5dfc-bdb4-ccf701623303 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.3 - Water Content Testing
35e2fcc9-d3d5-59af-a908-f499d6a54e25 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Cut Batter
c2b4a133-1e9b-57e3-901b-f8475b65372e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Cut Batter | 6.8.1 - Cut Batter Inspections
e16adbe6-b3e3-5c67-8606-5fefab0a0d4a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Cut Batter | Cut Batters- temporary cut
b8f6ed29-d235-5472-b91b-fa7f6c4966a4 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Surcharge Fill
d5e3f05f-f416-54bc-988a-f0a4c82ce0ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Surcharge Fill | 6.9.1 - Surcharge Fill Installation
56a75856-b47c-56f0-becc-9a70ccbc0b6c |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Respread Topsoil
a12a3a85-c58d-5d4c-b3eb-67e22cb4a919 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Respread Topsoil | 6.10.1 - Topsoil Respread on Steep Ground
6464ee40-e8bd-5c62-b8ac-7adb1f8e08f3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Respread Topsoil | Hold Point (Engineer)
3d0eb42d-83a6-5d5e-962c-7d6125f241bc |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage
9cd2b135-dad3-54c2-a147-9659adea4596 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | 6.11.1 - Filter Cloth Wrap Inspection
75a0e757-6382-5364-868a-835cdc8f17ad |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
11c108e3-3538-5ada-b9b8-a569f56331f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | 6.11.2 - Trench Backfill
32e89489-9a80-5f3f-a11f-60d2ba1c56c3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | 6.11.3 - Drainage Outlets and Inspection Points
dfd92d8b-3282-50f5-b1b3-8940cf1d4538 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | 6.11.4 - Subsoil Flushing
407ecda9-38fb-5145-ae99-191316fd8061 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
79486456-04ac-52f7-a9b3-c83da998abd3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Subsoil Drainage | 6.11.5 - Survey
a188b289-6e7b-5c30-92be-9d93fe35ab17 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid
2e2a1215-0787-5050-84ad-37137c7132dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid | 6.12.1 - Geotextile Installation and Lap Length
eadb6d21-fef8-5f77-a317-83d66ed82fec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid | 6.12.2 - Geotextile Inspection
c78b28e8-f3d2-5426-880a-cbdbac66e7b2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
6f1a2630-70d0-5b22-964f-ee10910a9a7f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Geotextile and Geogrid | 6.12.3 - Geogrid Prep Inspection
22802a5d-c030-5720-8d67-02366fec75f9 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Settlement Monitoring
7f20d297-98a9-51ea-a000-e8805ff12b7e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Settlement Monitoring | 6.13.1 - Settlement Pin Installation
34691f29-e2b5-5c4d-8b39-154422271c6f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Settlement Monitoring | 6.13.2 - Settlement Survey
57f27cac-2f2c-5f81-98e0-70e2dff5100f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | Settlement Monitoring | 6.13.3 - Retaining Wall Settlement Targets
3a1d169a-384b-5b71-91ea-d32444c79ef7 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
f51a9348-2a22-55b3-8507-b831af93bc06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.1 - Construction Record Compilation
fdfeb37a-c453-5170-afdb-ab8d97815ee7 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.2 - Survey Records
6525c398-31cb-565c-bbd6-496148ebefec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.3 - Redline Drawings
6a377d52-36a6-5254-8c19-4b2185bb2fc3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.5 - Photos
f2be8c20-43e7-4741-9c16-1be68be31c4f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d02f2e40-f556-5dc6-ad73-a8db731b6204 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270 - CH1860 & South Diversion Road Tie-In BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Add Signature
e67f50cb-e614-4d18-bf77-dd71c51d9622 |  | work-in-progress | ITP - Subsoil Drainage - Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430)
5dadd966-6a3f-5f7c-a8ca-fbc243bbf2e7 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
c3ee433f-05ec-58dc-9dc1-02c757593451 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
82982796-6f24-56d1-a0e1-085e590e4bd1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
9a51df05-7522-56df-a01e-f9645d323071 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
91fe5e3f-b704-5eb6-9d9d-61affce6f7c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
06f422c9-fdab-532c-a142-e126f14a3759 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
256d38f0-5def-5f80-9668-895152dd4c43 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
6dfd4588-2c91-5323-b895-f0e3c990111d |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
f2eda71d-c681-5bcd-a1a4-30cbc3d1fcb6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
30778d3f-5b29-5eca-8794-1b16c1a2738f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
03a084e2-6ba8-51fb-a2fd-cfc428418de0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
f65b1906-242b-53c0-8814-58c15dfb2817 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
ace89a80-b8c8-504e-a8ac-7a50befe9fc6 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY
633cd781-0709-5ce4-a690-5c0b9b4f7c8b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
8327f9e9-5bc7-51b7-914a-11608fd984d6 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
6ef73e74-7ab5-5a60-a965-e17bfbb024b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
f72ed687-c607-5040-b5dd-445471e5840c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
e3d5eb61-b2fa-53c3-a1db-f2504c7b3b70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
e05e5fdb-6044-585f-8f48-012fb73bc4a5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
e662a084-3328-55d9-b404-f1298a99d118 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
80db0e6d-03eb-5c03-981a-13f076f8a2d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
358c0726-001e-5026-b9ee-a4785a234d54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
e4ac17a9-0ccd-5091-9822-2b4f89ba3c8e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
5cf650e6-0e09-5ba9-a5f5-e86c91444032 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
2c81224f-2848-5416-b2f4-2161d4f36f19 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
4cbcc290-1d5d-5e90-83ad-982ef34868ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
635b2439-e7ee-575e-bf2f-f6feadfe6e87 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
df1367d5-6c13-5f74-bd8e-9c0bf9d64fd1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
e8ca6549-5faf-4dc9-9159-ba73a1ebd80e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
fcc4740f-c799-590f-85b0-ee1df0c29ff8 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - Subsoil Drainage - Rev C (Gully Drainage Blanket Ch1430) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
e6d6420e-3f8a-415f-bd73-8c0737d57e22 |  | work-in-progress | d430f9cf7ed824575cdf540a6abc3a5975acb43723dc5aec746a2a55d155135c | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND)
e0917fdd-fa64-59ab-94a5-20c584f9c37e |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
fab97b2b-307c-50cb-9961-06cbcdff5d7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
5009771a-b368-543c-803c-b863bca502fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
1caf6db3-1913-5d4a-9ea6-800f7b6c8233 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
0089af09-2b05-57eb-8b2b-3a2c7109a047 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
d11d7cf1-c201-56d8-acfa-a85947724abf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
bac77c7a-1c28-56f9-be98-d36ed7825d9e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
15994189-1a35-58bb-96d3-327a93205eb7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Previous Layer QA Sign Off
fd04be33-0084-5e91-bd94-1fc357259ed1 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
0a5eb04d-834c-51df-b950-67bfaa0a702b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.01 - SIL Inspection
0152f32e-e7c8-580c-a4d3-f3ac4edd275a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
67bc36e0-a1c3-5b1d-9b21-975a5a22db42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | 4.01.02 - Subgrade Inspection
41bd2b02-7520-5353-8a89-8f454a3913e4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections) | AUTHORITY HOLDPOINT
40127463-2b45-5af3-b5ae-cc48c6d8fe55 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
c64e9e0f-fb5f-5e5d-a07d-0de0abf7895d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | 5.01.01 - Pavement Subgrade CBR
87ad9d4f-feff-5ab2-8302-053298e0e4b8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials | AUTHORITY HOLDPOINT
b1eb4681-78df-5c1d-98d7-14b930dcb692 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand)
14dab72f-fbad-5f09-b559-d1f75046e5c0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand) | 5.02.01 - SIL Conformance
78f7e963-4024-5ee1-a03f-14c2c6426f27 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
36fa678e-57cc-5c14-ba02-d1caa1617b88 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand) | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
17a412c0-5cbc-5880-b82f-6f8bb8296bb1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
b3b4d295-2237-5ed0-9a5a-8dcc28e53d0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand) | 5.02.03 - Plateau Density Test
331eafaf-3010-54e8-a881-aaa1eab46d24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand) | 5.02.04 - NDM
c3fcd033-e779-5c7e-aca7-771669c02b17 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand) | 5.02.05 - Benkelman Beam
828f7d1e-4791-588d-8349-6b4105599aed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 5.02 - SIL (Clean Pit Sand) | 5.02.06 - Organic Material
4d70fff7-2d52-584f-92d3-f7f0aa219439 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
a45082ae-658d-5220-b626-6d9709c5a35b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | 6.01.01 - Subgrade Prep
3fd7d5ff-a241-5ee0-ba26-6f002f2b2236 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction | AUTHORITY HOLDPOINT
910e6acd-26d7-5a14-a3cd-119635b169a5 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand)
f115c807-a5ce-566e-8882-f553a4713225 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | 6.02.01 - SIL Scala Testing
ec343ae5-02b5-5faf-8847-1c1ecf7136c4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | 6.02.02 - Layer thickness
e2aa65ba-014a-50dd-83ed-1edcfd943eb1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | 6.02.03 - Plateau Density Test
3f3a7125-faa3-5cc2-92a1-97cffc917ed7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | 6.02.04 - Sand SIL layer compaction
9b60b856-dd35-5ab3-92b5-9e44b3bdfd60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | 6.02.05 - Proof roll
dbcb3b57-16b5-545a-966e-ca674e6fb86a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
8551f334-ba7a-59cd-b9f3-517c8f56b2e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | 6.02.06 - SIL Benkelman Beam test
e5667aeb-d053-5b18-9c5f-d0f06e7a3454 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
9e864ec7-deac-5cc6-89fd-b740dace9077 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | 6.02.07 - SIL Inspection
aa2d4d5e-b443-5149-b5bf-8e4bc13bfebd |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | AUTHORITY HOLDPOINT
5567686b-a656-58b3-8762-d918dec7ffaf |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | 6.02 SIL (Clean Pit Sand) | 6.02.08 - Topography
509e037b-24c5-58b0-b35d-444a0f8ff0ba |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
61b653ab-8c1c-5a11-b7ab-9fa251f1a2e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.01 - Construction Record Compilation
4f966d24-d5e4-53eb-bd55-9252cee55b44 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.02 - Survey Records
c491fc5a-190b-5682-8d0e-594155edca29 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.01.03 - Redline Drawings
9dae400d-6339-4a49-bd15-d46a45e98759 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8c930bf4-89f4-5cbb-8b3d-f2c83bc56ec0 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1360-CH1860 SIL (COOMBES SAND) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
20af3118-fee3-4af4-a2f1-2caed2aa7275 |  | work-in-progress | ITP - 116 - Pavement SIL Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK)
9839f24c-b6b0-5206-8fd6-67250facc889 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
4e07454a-5b6c-5a3a-b72b-a1224b399f76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
cd2d5c3f-0f09-5866-999d-3eb2845a2856 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
4f141529-6f38-5a8d-a6ae-15254548b35a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
4dd529e5-6a4b-5495-bc27-e8786c20648f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
5cf39e1e-fc5d-5db1-bec0-8536ab1fe0ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
cbbf4568-2e64-50f0-a1d4-fb172fdb224c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
6a8d92ba-7ce5-5bed-8c63-0ddf848e06b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.07 - Previous Layer QA Sign Off
909157f8-6795-5792-8f30-577a2ccb75d5 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS
2193321b-323a-5654-a8dd-69c8a22e1127 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.01 - SIL Inspection
96ba4c74-9d03-5e36-9bd4-3cf7ba1f2e92 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
386eda5b-280d-50db-b82f-d15dae87f18c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.02 - Subgrade Inspection
df47b257-7aa9-5d92-8d61-4c260cfdf0ea |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
34b9d4f3-0de3-52b6-b9f1-f20ad9a6eb7e |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
38376ce7-4da9-5eee-8a41-eca18e73ba1a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.01.01 - Pavement Subgrade CBR
0c476994-03e9-5e36-a540-26c7d1e51865 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
db2cb6af-8dbe-530a-ab9c-2e033bbf4b26 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.01 - SIL Conformance
cbff751f-e0b9-50d2-8913-b82b3659184e |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
cc5ed3ba-c95d-5f95-9753-dc5a2814d496 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
a21d0635-7a05-58d4-aea7-6d13ffd6ac79 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
84c2298b-3e81-5ec1-afb7-d8d679df2c73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.03 - Plateau Density Test
99eb19ac-74a7-541c-8c33-6b200328e9c9 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
2eff0964-4f2d-58d9-8183-7b39af0b13f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.01.01 - Subgrade Prep
4ba1f9e1-425e-5b58-ac72-1610a7023955 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
0fdd73e9-ecc0-5a25-99ab-3e2c8bd379ef |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.01 - Layer thickness
8e105b4b-2e8d-5c02-86e9-37da135d9fab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.02 - Services Protection
4b1da0c7-0728-5dea-bdd7-404b86b32719 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.03 - Plateau Density Test
c9f0c12d-19ca-5fdb-b9e0-9680dc2005e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.04 - AP200 SIL layer compaction
f7d253c0-f318-5999-a357-26ea9881dd40 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.05 - Proof roll
b2650755-15e9-5b4d-bd0c-862e0fe33ed5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
216d9aca-ea8d-5d4d-aac4-a7996b353985 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.06 - SIL Benkelman Beam test
b29c2dd0-3ac1-5141-8e2b-bb87fa445ffc |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
88cddfc4-77fb-50ce-8780-3044adda68da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.07 - SIL Inspection
7cc6e75e-9ee1-5522-9d00-a855ad63e715 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
8d4d2edc-59a7-5fd2-abba-baec47c50e36 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.08 - Topography
53efed59-dccd-5b36-bfea-57d8ced68fe5 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
ae61afbf-c6b8-5b12-921f-9ea5ea411451 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.01 - Construction Record Compilation
cefd3e75-7a14-5755-a00f-e25229d28ebb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.02 - Survey Records
27cee122-f462-58f4-ae51-ca7d75381f41 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.03 - Redline Drawings
f26c7db0-10e1-436b-adc7-ae1a8611bb42 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
53ef9d72-97ff-5082-b328-a9b9867b159d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | PE CH1270-CH1360 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
fed115be-3182-469c-a2ad-04882222ff71 |  | work-in-progress | ITP - 113 - Pavement Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D
73db789b-0372-5aae-beb0-7ab3ae844bc1 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
4cc815bf-b5b7-5771-880e-f8a804a25803 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
8aeab85c-2f21-5797-8929-fb0fffc62e43 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
48e8d1c9-d8ca-518b-acaa-ed15cb0db8e6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
4fb1e0c2-c986-5fa6-9d68-8c8a90460dea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
6e1dfc38-1d22-5475-9420-0df0a46c1d86 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
e630a93a-1cad-531f-b1b4-c2e168c8a89b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
f7731084-e1d8-5617-be92-145c6070c312 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
1c4d92e2-9b4b-5acb-8c01-fd329ae0b4fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Pavement Pipes
ae6a8f4a-b10d-5055-a09e-c9af95270044 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Pavement Drainage Aggregate
db4863f0-fc20-5bbf-8af4-a334c5de09cb |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
8e6abef7-7dc9-58d0-a150-959fa537f63c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
995719d5-ca38-5dfc-8e02-b48e5166d5af |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY
eb23f867-0c85-51a6-87b0-a7edb44d418e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
de4917c2-d9d1-5f8c-88e0-c201add3c0de |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
fbda9ba6-5628-589e-a198-9d6b35e8e729 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
96118389-e101-5894-b8c9-a1a5d76f163e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
639a6da8-869f-5547-9441-6625b407d4a5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Pavement Flushing
83876b0c-692f-5309-8587-444618c981e1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
64c203e8-9942-593c-823d-9228c840a272 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
f092bfa4-271e-5abc-a494-1d924529ce55 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
a7ed2236-dbad-54b2-80c8-8911bc2ace7a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
d4bb6be9-463d-5e07-9ec5-746deb030842 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
a4dff071-8e6d-588f-a38e-cfb3e8fc3de6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
e5bf9799-cfc0-5fd3-bf5d-1559207c3541 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
0ccfaed9-c1df-5eb0-903e-13c464681f70 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
43d33afc-782b-5c87-a577-9ea9af6b5f7d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
16ca4482-d67a-5ef0-8678-c6a8c7a4e33d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
f3721504-ec57-5688-b904-566a4ce5f108 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
9260aaa4-5bc4-56d7-a350-9822352585a2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
9c6fa01c-4ed3-4476-be16-720360774605 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7d77a486-f81d-588b-8877-c1b1a35ff5ae |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
75456b31-9d50-4f4e-8d9d-de46186126ee |  | work-in-progress | ITP - 112 - Subsoil Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE)
8cd5835d-c4be-5c28-b274-cbc433e8193b |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
16b321a2-2b31-5879-aa3d-df031fa74b39 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
8b31a96e-e4ec-5d5f-a463-fe67c1031c56 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
0329d201-444e-5c3e-b109-35f5d0381b2c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
7f01434b-a913-52f9-b903-e768590bfb74 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
53288357-a719-5950-b541-702d0db95ccb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
ad40f005-467b-5d82-9145-8fef5828321f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
b6f8abd9-42de-5d53-af43-5bb1d6780aaa |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
5444e34b-d36c-5010-b25b-fb9b0dfc1fc6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
2649c540-824d-5422-8bca-8ac23b8de5dd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
d7351e97-4a9d-5d2d-a199-cd17a661c2a6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
141bc142-f676-533f-a2da-9e6e90d5e72f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
fae53d6b-14df-5ac8-b300-aa28c4a604b4 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY
8222b734-ca47-58ab-8fc6-0a9789454ca5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
8a7077d6-2f5d-570c-8140-bcb46a916ff5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
d0a37469-c054-57fd-80fb-297e93499ccf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
539fe2b6-173e-54f2-affc-5ad0b93e0515 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
e88b95c4-2ad5-5b91-baa4-e1b8d21372e9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
d6cec9a3-1284-5c9a-861e-9dbf26ad6ef8 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
8c8c90a0-4952-50c8-96b4-4557b24ff819 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
614277c6-786b-5bd0-83d6-eb5a3df10ee4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
3ce1ed99-2e7d-5136-abea-d4ab6e3ff1b7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
913781a3-f79e-5de8-bfdf-bc5f19a2376f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
8ad276a4-b034-5cfb-ae9d-c111e640e573 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
fabce5ac-9bf2-5ede-b25f-3a10d22cf6c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
c45bde0e-46da-56d6-8fe1-d0d053dd63b9 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
f8391db2-9279-5d4d-9d5f-f30c0372f903 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
10b25c12-267b-5912-a60d-dfcfbfa5254e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
dd2d6844-93c9-58d5-8f14-ca79d1ec7f6e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
3d5a8f11-8941-54cf-94df-4e5ab1532d30 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
f5abc29c-eb47-4aaa-be92-ee448890ed92 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
ff759bf2-5175-5788-8816-0f10be894f1f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 112 - Subsoil Drains Rev D (SWALE) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
bf21a266-4ddd-4349-be6b-9e59a8de9705 |  | work-in-progress | ITP - 119 - Rain Garden Rev B | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B
3612bcf9-8a09-54ed-84c2-b1068c6c1b42 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
7f9c2528-fb1d-508d-89ea-5c96e41dfd89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
5dfc2fe1-2cbc-5010-b104-e17c80b3e7a0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
d43b6815-144a-5c0b-9980-0197d76e55c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
3159ee0f-ee68-5be9-8fbe-cd3ca73ea3ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
369b11db-6131-57ca-85d1-40ae9f68dac0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
b9e98a63-f22c-5ca6-b361-403262d8b878 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
fbc46e7e-27a4-5363-8b90-f9513c24686e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
6c43cb8c-c7a3-577f-8a7d-9765050f6efa |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
84e53b43-3074-587b-86c8-e3d67f3c836b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - GCL Liner
7d0c0bb9-febf-5d88-bdc1-904a29ccfb32 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
3ac439ed-3a73-5632-b971-7e7ad01f8c62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Geotextile
ae136ecb-3f6b-56cd-8736-1eccf3296639 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Drainage Aggregate
cd48a5b5-4809-57da-a86f-5beb103389db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Pipes and fittings
862f3ab0-ba25-574c-9ad6-7de964e9a6da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.05 - Graded Sand
120feab2-d61c-59e7-905d-a6d830da29c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.06 - Filter Media
6cb4caad-3f53-59d5-b66e-b4d4bab0ddae |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.07 - Scour Protection GAP 65 Rip Rap
6cb36ea1-0bbb-5f35-a9bd-77e26e888ecc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.08 - Coconut (Coir) Matting
c8082be0-48a1-5b06-97a1-4c1dbf085f81 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY
affaf51c-2cca-5ede-975f-c086519cc56a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Set-out
bfa3a444-566a-54c0-92dd-eeae11ac6206 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Excavation
9c450e8e-17b7-598a-aee6-aa188ff92a06 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - GCL Liner Fixing to Kerb
649874b2-f89d-529b-a3b2-6e7f292d3a8e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - GCL Sealing (Pipes)
65a6c8df-d98a-5278-abbd-961329d788ff |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - GCL Repair
17d4eda3-45a8-5cad-9c6d-e29edc0c8252 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - GCL Inspection
b0b865be-3ed0-5092-a965-d001e4ce9c94 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
f7d4a2fb-19d6-52b9-a3b3-85705083af30 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Geotextile Installation
a4071252-9de6-5717-aa52-e4e58824c217 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Bedding
145d893e-5a49-5fe8-b6a7-775fa02720d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Joining Pipes
f61bfb1d-ce24-576c-911f-af8c8227feda |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Grade
1dc63a28-5b55-5fed-83a4-d6d4d7815400 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.11 - Pipe Cover
744f2a25-e586-5caf-bd94-4571505d5c86 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.12 - Sand Placement
af093e73-b0b8-5ffc-b3fb-0df99938a341 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.13 - Filter Media
1e4a39ca-c96f-5311-b5a8-fb611b027e4a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.14 - Coconut Matting
09b0caa1-c43f-5a3f-b4b7-d0206ab44565 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.15 - Scour Protection GAP 65 Rip Rap
25c0522f-beb2-5fde-988d-695375c539dd |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
665de00b-8ecd-56e6-b4a8-52de66b2de89 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
abe73996-6bd8-5142-aa7c-1a73b82cf0bd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
b060a3fa-2ab3-5f48-9b13-5494dd0552d0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
5a18dc22-f478-5cbd-b4ed-b70222ed970e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
c8609004-427f-4e40-9a38-b7b5bf94c4e0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a16533d0-c5e2-5921-a573-9df68b27a337 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes East (CH1270 - CH1860 & South Diversion Road Tie-In) | ITP - 119 - Rain Garden Rev B | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
ae23c02b-a093-4add-a3a0-ffd1daf831c1 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South
11921a82-9a5a-4362-8f1b-53b2acf6b5c6 |  | work-in-progress | fdfba5edaa3c12d619945ecba9bbbe48cd7668f5d4481b1470baa2cb0ef9edd3 | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS
3658247f-20f6-509c-a3bf-97108bf9a7cf |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
ae1204e1-f263-5db6-b181-f42db300d490 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.01 - Construction Pack
30ff60b3-e6b0-50c4-874b-e08c8031cd78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.02 - Survey Setout
e3917335-1aed-5a27-aa3d-6b4a17d88d29 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.03 - Approved Construction Drawings
5eeb9718-6ea0-573e-97ac-f43abddc4300 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.05 - Topographic surveys for measurement
0d6dbb51-602e-5ff3-8ff7-2fe328757f0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.06 - Permits
d345f8b5-b8ad-5ee8-b797-c7692e68b100 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.07 - Stakeholder Management
37a2e010-ac70-50c4-9c58-7714716a6313 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
1adbedd6-75a3-589e-9369-b4ad791d6c67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.01 - Environmental Controls Inspection
682b9355-ffc7-5424-9b63-b7502e91750a |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
bb801dbb-6fda-586d-b827-0af128474aa2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.02 - Bulk Fill Inspection
103b5757-6206-59e3-8040-68e4ef8f888c |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
7763e866-ee41-59a2-865e-75c42848a019 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.03 - Service Ducting Bedding Inspection
877b11c6-c962-5bd4-ab27-9bcad23f7597 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.04 - Service Ducting Backfill Inspection
2e38110f-41a9-5093-bc78-4586a95ae5e7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.05 - Geotextile Inspection
74f7326b-5c62-59e1-ba63-a2eed16aac22 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
b56112b0-627b-55f4-be9e-bc7c83f26f25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.06 - Subgrade Inspection
b4f51441-7f8b-57fc-b7ed-ac28b55cf384 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
613aa8d4-dfd8-54db-a681-b4a45908cfec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.07 - Undercut Inspection
86b0f18c-3204-596c-97ab-a61b799170c7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
5188ea2c-b93b-5c3f-877e-6f93988009a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.08 - Settlement Monitoring
d0714ca8-3b8d-5660-886c-ca7413d9dad0 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
bbcb17bc-7cd0-57cf-888c-ae78a1aa4e7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.09 - Subgrade Fill
e995df6c-229f-54db-9632-9ee3e121fca1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
833ee26a-037c-51ea-a06d-6697bffe0b0a |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
1bd24185-c1d3-5e40-ac17-962616a85926 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Imported Fill Approval
7ac8d057-6b49-537c-a511-7d9327d0988d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
6a024448-bf1b-55d2-aa00-2cada2de668a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Re-Use Suitability Approval
361f22ee-edec-5454-b230-5b46c32f5b8d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
7200009d-bc0b-511a-a0ca-6546a4be6466 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
3277ca8b-041c-5e8d-8647-33e0b840221a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Cohesive Fill Material Testing
1881834c-e1d1-595e-8ead-f1769540c0d4 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage
7b63c873-03b3-51e1-81ad-337f94145359 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | Subsoil Pipes
57b558db-2315-5bde-a710-ca5b772223b7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | Subsoil Drainage Aggregate
d40024b9-252c-5703-8369-65ee22d0c610 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | Filter Cloth
0daae540-a18e-536d-b42f-08b0674dbb78 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid
669d8e5b-a12b-5108-ae62-270eb868a6bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid | Geotextile Approval
859ca8c5-d84e-5b0f-b554-e46c352b4056 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
238e1ec8-266a-550f-b3a7-7e53cf401ea8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid | Uniaxial, Biaxial and Triaxial Geogrid
2eb421fd-2e84-5c1f-82a3-e6f99c437cff |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
915b5fb2-3a7a-5595-8208-6885c75d50f1 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Settlement Monitoring
8cea97e8-4a25-5ad8-bb99-10c399f5f6fb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Settlement Monitoring | Settlement Baseplate Design
9ea49fde-8f13-55e3-a89b-2eef64a00922 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Design
3d22ebd1-eee1-5dff-8e83-23b9b093d198 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Bedding
e32a8560-7cc1-588b-9f36-78ed579e9768 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
45ecd607-95c3-5b60-8fb7-7087814ea6c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.01 - Clearing
19501e40-9f05-5009-a9b9-819ed01007ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.02 - Demolition
671dccb4-ab2d-5a8e-9a9a-99e8321af9b2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.03 - Septic tanks
6a3c3d95-21df-5d31-aa37-85cf57356ad6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.04 - Plant Clearance
98e56b54-1bac-56d6-91d1-7effc90090e8 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
1c3f6c48-ef2c-5b6a-9d57-129029a1173c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.1 - Groundwater Management
5026f90e-b0ab-58a7-88bd-b9c7107d3752 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.2 - Cut to Waste Approval
1106309e-31da-5476-8a7d-4a565ad14501 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
3aeed6c2-0141-563e-899a-9e717f2c67dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.3 - Foundation Suitability
db6131b9-ecc9-54ee-bffe-48b6784446c7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
7e1e9442-8447-5981-bcc4-8ae2e709fa3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.4 - Unsuitable ground
025f22c9-9801-5d91-acb5-1344668ade09 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.5 - Preparation for Filling
e0201689-7274-5761-b5e1-35554efc6a99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.6 - Subgrade Conditioning and Proof Rolling
ac41ca8c-d86d-5982-9d35-9710c0d7a2a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.7 - Undercut Backill Compliance
b8d95541-8975-5e7d-8f3b-ae50fac2f36f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.8 - Topographic Survey
5610ba74-6058-5d75-b852-3d2256042304 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Stockpiles
fd488bf2-d30f-52fd-bc9e-dfcc6197e07b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Stockpiles | 6.2.1 - Stockpiles
b05a5725-2d20-5e76-9a08-271fc80f3a69 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Stockpiles | Hold Point (Engineer)
54a6fc95-7dff-5aec-82b5-b326053d0aed |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Earthfill
6cce6be2-58a7-5368-aeba-726cb05ef94a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Earthfill | 6.3.1 - Earthfill Placement and Compaction
078959a9-16f7-56bd-b6dd-87e358ac548b |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Earthfill | Hold Point (Engineer)
4d4e0f0a-b078-527c-9eb0-4414284d21b2 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
a45d2f57-ff07-5302-a7a2-49aab2463c9f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.1 - Proof roll Testing
8a5cd602-5fba-5dbc-8ee4-30d496242e97 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.2 - Compaction Testing
24e8503f-98c6-5133-b316-6f70e70be768 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.3 - Scala Penetrometer Testing
de6c8477-78c6-5f9f-b7f5-001c7ae53f03 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
2b58beb1-8781-5aa6-ba43-4348d847d7b1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.1 - Vane Shear Strength Testing
83391be5-c5c6-5559-aa59-486949cda87f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.2 - Air Voids Testing
527a5786-6205-555c-9050-730d52a7deee |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
e44d2cbc-549b-5617-9f8d-641c6f119ea5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.1 - Proof roll Testing
ede6b227-5599-5b7b-9bb1-1405cbdc6b54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.2 - Compaction Testing
22d95401-3aee-511d-9b48-bbdae9029713 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.3 - Scala Penetrometer Testing
9edfb32d-9ba7-56a6-8452-a3413088c101 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
68d9613c-d383-5b13-88d0-98fee25cc97e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.1 - Shear Vane Testing
72e079f8-294e-53d3-b824-99647d609207 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.2 - Air Voids Testing
073131f2-22a4-5e41-83a0-a41e4c393d57 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.3 - Water Content Testing
2b33c4b1-f48c-5700-b9cf-205d7ba57085 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Cut Batter
84320fea-fbad-5307-8839-7c5bb9dd443a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Cut Batter | 6.8.1 - Cut Batter Inspections
f3c642e4-79a5-5fc5-83ae-feaa0d8414e8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Cut Batter | Cut Batters- temporary cut
d3b5c885-39b7-59f0-86b0-1fd38dec89bc |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Surcharge Fill
e5a9dfa9-3e97-5f07-bbaa-aeff33a87810 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Surcharge Fill | 6.9.1 - Surcharge Fill Installation
4b5ea54d-4e0f-572b-860c-055a767067d1 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Respread Topsoil
142daf54-44c4-5486-8b10-dbe7d43d6a63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Respread Topsoil | 6.10.1 - Topsoil Respread on Steep Ground
e2f62dc4-02ab-56b6-af52-1a2af0e734ab |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Respread Topsoil | Hold Point (Engineer)
6d4eabdf-e5c1-5b8a-8959-f73c5e56757b |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage
45688485-64de-5628-a56b-a4cd57de72aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | 6.11.1 - Filter Cloth Wrap Inspection
76dbc5e0-3678-58a1-94ee-580cf103bdb2 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
4b8ad0eb-e7d3-595b-a5e9-149e2e6219ef |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | 6.11.2 - Trench Backfill
4b77cd80-a1f2-585b-bef9-123af910807c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | 6.11.3 - Drainage Outlets and Inspection Points
2bf59152-892f-57a9-abe7-39d2c51edf2e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | 6.11.4 - Subsoil Flushing
3dd9c34e-e7df-566f-ac64-c7fa507dfd48 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
a72b0782-f098-52f8-958e-69c5f528b67a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Subsoil Drainage | 6.11.5 - Survey
af0afdd4-cf7e-50bf-bb2c-effde9005a8e |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid
0d1a09c0-606a-5288-abf1-07a988b2b7b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.1 - Geotextile Installation and Lap Length
d2eec816-1b08-5427-a33e-ba23e61dcd68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.2 - Geotextile Inspection
efe01119-d0ae-538e-994b-d3ed00e86361 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
a932cc85-86d6-5b84-a1f8-05e72d436860 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.3 - Geogrid Prep Inspection
b92fb751-1cd4-52dd-852e-3dcc52f7c840 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Settlement Monitoring
afa44a16-b276-5b59-bc2f-ba572c36f79b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Settlement Monitoring | 6.13.1 - Settlement Pin Installation
9f98e782-67c4-525f-8d39-314ba5ee7ae7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Settlement Monitoring | 6.13.2 - Settlement Survey
bce9037a-9089-5d38-8bcd-9a66c0f5a12f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | Settlement Monitoring | 6.13.3 - Retaining Wall Settlement Targets
b055ae89-48ca-52fa-8528-27684da37b94 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
36eb8c92-4947-5828-8be6-700878a671f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.1 - Construction Record Compilation
a133325a-194c-54d8-ab8c-d618fc3c0397 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.2 - Survey Records
f9b77722-4073-57e4-bb6f-9f88c7b762b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.3 - Redline Drawings
d176e453-0bc3-5fee-a853-c2057a2b46fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.5 - Photos
e35e8f1b-8362-4982-bd7f-d45536a31a59 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
90374442-b723-54ee-a032-f5159b4714d1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Add Signature
52132443-d22c-49bc-a873-c0ad281eed2a |  | work-in-progress | ITP - 116 - Pavement SIL Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK)
2cbba439-eca5-5364-8dff-1fef49a59198 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
2f9ba4e9-138c-545f-8790-50fd6c379980 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
0269fd33-84f2-587c-ac84-42afe3215180 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
8659c5cf-6485-5c1d-ae76-b20a538fb00d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
c5342fe2-2734-5a3f-822e-c46b875413a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
39153238-4ca3-5db9-9b04-e088fa128a15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
3aea24de-521f-5ff1-8099-a8014c1f7eaf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
a0ab2778-6849-50bc-8afd-eb3102b7890f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.07 - Previous Layer QA Sign Off
a24ce165-b90b-513a-b77a-2fe06d4e1e48 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS
610cbdb0-eb89-58bc-a03a-ef9dabfbbc60 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.01 - SIL Inspection
f94a3531-32cd-52d4-8b78-3b01df5112b7 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
280f953b-9bdc-597b-978e-e331c3d24834 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.02 - Subgrade Inspection
fd144d95-f9fa-57e1-bb93-3d7791c6e5e7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
1596e7ec-f20b-5f63-ab7a-fcc958e89fcc |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
4016b5ca-ffaa-5dec-ba85-59e5349ab18d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.01.01 - Pavement Subgrade CBR
a94e82dd-520a-50eb-b644-a08eb137ab8d |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
be04b8ac-c495-58b7-8806-54444bdb6723 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.01 - SIL Conformance
cb54fd27-b518-51d3-b318-b7ab42b3c1de |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
43ed0f3f-842f-5b98-aaee-14c8f96d0ecb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
17043a15-26ff-52cd-ae5b-e4cfecab4950 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
1cc6f141-601f-5754-8a94-52515d7296bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.03 - Plateau Density Test
cd982e1a-e959-5a62-a9b1-a2566cf52715 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
c383e686-98ad-53f8-8c4b-4e50061f7935 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.01.01 - Subgrade Prep
3f66dde7-8042-5cfa-a9c3-dba9564cc528 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
913c1bb2-2e18-5088-ba4f-53cfb0e65d3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.01 - Layer thickness
5f0e0349-3627-552d-84d3-9bc61736df84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.02 - Services Protection
afcfed50-7c1a-5f60-ad7a-8880d3bc5850 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.03 - Plateau Density Test
98be5f97-3523-564f-ab01-12f42f961a47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.04 - AP200 SIL layer compaction
6866f5a1-52f6-5453-9b3f-f89dc32d55b6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.05 - Proof roll
758ea3e4-2599-5d00-99b3-e6f8bbdf3c99 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
2ccf1a09-032d-5a80-9027-08a189f1ecd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.06 - SIL Benkelman Beam test
498a417f-370d-5034-80b3-aefaee7ab835 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
d37be7ec-358b-55eb-b5ba-2660cbc22dff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.07 - SIL Inspection
2d9211a5-f9f1-56d8-bb00-68789ba48474 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
60dab79e-f8f0-54f6-972c-f1e6a4d25e0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.08 - Topography
d47989ec-c117-58fc-801a-f93d0b607c8d |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
e7a2a609-7c0b-55b9-a4f4-8e76f8e332b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.01 - Construction Record Compilation
9e5fbe07-0b4a-5dc9-889f-34e71ab507fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.02 - Survey Records
06b1dc1d-6727-53a2-9cce-a37cdd794fb8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.03 - Redline Drawings
63e11d2a-a460-4ac8-b90c-6ad8187b2e23 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
2837dfcb-0aae-5670-9a3e-cec622cf2584 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PW CH1270-CH1860 & FULL WIDTH CH1860-CH2100 SIL (100mm BLUE BROWN ROCK) | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
c83a9d5e-73ce-4497-b8a0-537bea9b1cb3 |  | work-in-progress | ITP - 112 - Subsoil Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale)
b69e917e-3892-5244-af1b-e8a7c324af51 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
ede92729-e16f-530b-901c-5c535ede07b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
c90f1be5-0bfa-5d47-ae99-511b0599a355 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
74c41ad7-4b65-55a6-ba65-5817942b43e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
5493cd42-ebf6-56e6-a75d-5628310d3250 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
027e4260-35b5-5607-9f56-2a5608e62a01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
2607ca12-1f23-5a57-a4d3-83d9a1bca3c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
8cbbcb5a-3312-5eed-b09d-a44e92a76395 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
1db7132e-6cb0-58c6-9781-cabc1f2f9d0c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
34bef065-e1ed-5b05-a26d-baef581683e4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
61705a84-1337-5bba-bd18-aaba3691dcb6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
83940a55-3558-5184-9cbe-5f333d2087b5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
abb9cb28-a1f1-5849-b050-d660dfd7ff34 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY
1dce3404-824e-5b8d-a4db-61e85c728ae5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
6083880f-50a9-5939-8725-9bf5c6a5bf6a |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
3e97d045-bec9-5005-ac09-acbedc04e4de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
6e6ff4a0-0a42-5e56-9d77-aeb036fca0a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
710e0638-4e14-5d5d-ab27-a68ec3faea72 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
8f16bf7b-56de-5cce-b268-5d9485af2c61 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
9c18f6fd-c5d1-5c00-954b-27d46d079f43 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
7f99d924-8f44-59f1-a7a7-309f5b750d28 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
fdb656ce-8249-5d88-a151-0adf6f9d38df |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
6051bf62-a457-5744-8cfe-a0a48a438899 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
b84f706f-9ea3-5224-8a8e-b5d6d0c03173 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
f0c3caa9-b5f5-5c6d-b183-0c527df140ed |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
a9923f32-19b8-59ce-84b2-87480bfe8f28 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
4f9eb394-953f-5d60-a53a-7fb708ecdcda |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
1b9e359a-edf9-54ca-a23e-cf633c88c0e1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
066608a5-b920-5576-b7f7-23946e621ca8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
ef62e34e-6fcf-501d-945e-cc6dd011d534 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
1959928b-91b9-44d0-8a67-644f1d2b0113 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a31dbf00-bb96-51d3-9980-a08450fee0ae |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 112 - Subsoil Drains Rev D (Swale) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
fdc7a75c-f442-4f54-b361-99e971f5a1bb |  | work-in-progress | ITP - 113 - Pavement Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D
7e0db3fc-616d-526a-bdc0-060e81c4e3f2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
03a72bd4-1e19-50c4-8699-ae3d5db818aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
66725c23-3e81-5682-ab49-50811a863229 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
2a4c2a57-cd5d-59b7-bf3f-5060255b2b0d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
26eda15d-3f03-5e20-83e1-cb104ada3158 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
bbe1e9a8-9f00-5704-8ff9-84df0b53e9b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
4ac1e3db-6861-56f5-ba6a-cc1709f7dfc8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
af149467-64aa-5f76-968a-6aa28b59b6ec |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
45adae29-205f-51e8-a0e3-330525e6864b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Pavement Pipes
3029855e-c9f7-545c-97de-54411c700aa8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Pavement Drainage Aggregate
8f90cfbe-a6a5-5f7a-a980-b225e86d1759 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
61c8f9d3-1826-58d6-b8e7-93678ee04d81 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
69b0f886-a300-50fe-aa6d-6704a0e6f451 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY
51c6f580-9b32-5cd9-8c17-5828e5d937d2 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
7cdbc7e5-a7fc-563c-984a-6f3bf0c02247 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
9655b6be-dd9a-5280-8c5d-b46a60ce877d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
4dab2751-9cfe-5f4f-a21d-8a54f83c3a7d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
1cbe73c4-f894-511d-80d8-94eaeb244e36 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Pavement Flushing
e4802e70-a6b4-5e3f-9a4f-e8f2b7957825 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
6dbf900a-94e1-57cd-9490-650aa1da3ab7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
e877cb6c-c502-59f1-8524-ca2de2133e8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
316d9990-e394-5300-983f-2486e9b272e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
722a2bf2-9eac-5727-adc3-c757aa122914 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
9585386c-3a10-5788-a247-4ea57560b9b8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
f22fa86e-085a-5e0f-9603-a6d17fbc8e5c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
ee4a3d66-99b2-52e5-ae43-6c7abb216810 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
98bccfaa-4e0e-59f3-adce-f202bdca5486 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
4b71429c-ed81-5cbf-9fde-540c1d4dd286 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
9cd68888-2f2f-5f0f-967c-da2e3487c154 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
97ecf403-8620-5e04-ab27-3eacf8f8a9c8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
1269e452-5cb3-4740-810d-138a69015585 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
49e825d3-dadc-5183-b556-d2b5c162d445 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains/ Perimeter and Centre Subsoil Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
976faec4-313b-47f9-8311-2408b7d5811e |  | not-started | ITP - 113 - Pavement Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D
5f5a2238-a1c4-594a-83d8-0ce3b8b0457a |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
f1def8d4-1b00-5379-b615-f43442866a85 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
99068289-3dab-5a40-ae81-73b9f13b7d05 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
b709a299-c450-57ba-a1b4-54e611ce29b2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
e4724d6c-12a3-532b-ac1c-85c443fb9073 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
3981e591-4735-5774-999b-7ba295b7ab54 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
cad3b427-8b0a-5537-b9e0-7804f69cb456 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
32a6a551-b054-548a-9619-80211880d41d |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
630f52e3-be88-502b-ae03-1903e7549461 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Pavement Pipes
c73f7ca0-3ccc-593f-9bdc-7b03dac9bdeb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Pavement Drainage Aggregate
a59abc72-a2a4-5512-a985-1de998a88c2d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
729abff8-b964-522b-8ab3-cd20bade73f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
47c44773-8bb7-55aa-a64c-23df6d78fa79 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY
e4a3a480-eb0c-5a68-9a8e-a933fe8a74b4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
dc299fc2-a64d-5267-ab8b-c4e121b0e323 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
9c323188-c31d-5ed5-b6b5-9cbd2bf5c9e9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
4f43a777-125e-555d-8989-58dfe02d9827 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
6c4c5499-9c3f-5321-a4a0-9a535bdeb860 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Pavement Flushing
72315230-d748-5892-93f0-656f0425b146 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
a1f63906-96cf-5646-b76b-38e12d5a4839 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
65bc8c4d-4bb7-53d0-9c91-60af9e437eaa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
a5dce6d6-4739-57c1-a05c-7ad334a2a210 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
e77a36ad-547b-503b-94cd-dddb86d920ce |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
8e7afbf6-e7b6-5fd7-972e-f6abc09256d1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
fbed0935-de82-5738-8ebf-8879459b0988 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
5648837f-3472-5482-b69b-b613e1545b97 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
1c25279a-b69d-53c9-8ae8-4b710d0f3421 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
b4f48231-cbab-527a-851d-8dce8c16458b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
0371c621-69bd-56ac-901a-66de29867097 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
9d032729-b2b7-5207-86d4-32e86fe2583a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
9023b2e9-ede7-5a50-bc23-e137d1720244 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
3c624c2b-516c-56d7-9532-1f34ad2d46d3 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | ITP - 113 - Pavement Drains Rev D | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
a5c6b203-0f45-481f-a097-54fb11b8f6e9 |  | work-in-progress | ITP - 119 - Rain Garden Rev B | checklist | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS
f4b7072d-42db-50c0-9b91-929aa73b23ec |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1e3806e2-ad3e-597a-ad75-0fc3714ea8d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
05717cc3-6561-5fad-be6e-4adb64b1537b |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
4c939f42-dedc-56a9-9cab-b23eee318e25 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
a9e16926-2c35-54f6-8b5d-b72b0038e099 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
b07fa27e-f2b7-5b76-adb8-a596ef0f31e3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
36c41364-8845-596c-91df-4802461517c3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
3bfb9d2c-cd11-52c7-8c27-5f95564a1474 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
faae9502-584f-5019-9fea-33d8bcf665ef |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2b71a44c-2775-58e2-9e66-6ea0bedcac6a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - GCL Liner
dfad979f-0f6d-5170-b6ff-9c3f6aa6ec2d |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | AUTHORITY HOLDPOINT
86df8136-d7b8-50f3-80a9-53c34e513d77 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Geotextile
c56f5840-159e-59bc-968d-d1659d8ab4ef |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Drainage Aggregate
9afbad37-45c3-5f57-854d-703683537ffc |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Pipes and fittings
f76b821d-a5f6-5868-a101-effabbb08f30 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.05 - Graded Sand
fe6b0707-0c6d-55b7-80ac-8294bceef9f8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.06 - Filter Media
a839bc29-9270-5293-a4cd-08ba8488fa24 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.07 - Scour Protection GAP 65 Rip Rap
555873f8-8468-55bc-a999-443b7878c2c2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.08 - Coconut (Coir) Matting
29fef824-2017-527a-9b28-632f0ad936bf |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY
93f9aa85-ba39-5bdc-9ff3-3cd2e180a3ef |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Set-out
be2377ac-90ee-505e-873f-9cf435ec0420 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Excavation
e95ae669-c125-584e-95b1-d56f082effdb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - GCL Liner Fixing to Kerb
75a09216-a855-55ad-8f72-c78cb35b24d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - GCL Sealing (Pipes)
e3796cda-4e8e-5868-b13c-979d5037c2ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - GCL Repair
30a4e32e-5b02-5c52-8f99-4c78a3a5773c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - GCL Inspection
9c96a3e2-8f16-5676-9517-d8ca87c37dc8 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
d7a68625-a7f5-50c4-8eb4-394a22338ca3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Geotextile Installation
3542b58b-b6e3-54bb-9535-5a2593024037 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Bedding
beaebe43-8ec7-57eb-90e0-e4170f033248 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Joining Pipes
e7e7ff88-30b2-5ea3-9068-6605398d642d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Grade
8a19f821-507e-5b55-872a-125f04091750 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.11 - Pipe Cover
5686feb0-31b8-56a2-83ae-4efef9841470 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.12 - Sand Placement
4df94bb3-05cb-5052-b36c-e64b6920d2e5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.13 - Filter Media
a2c914e1-6f5a-5e11-9c9f-3a033955beac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.14 - Coconut Matting
7bd6c2fd-8f2e-5e73-8271-dfb8d52b2091 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.15 - Scour Protection GAP 65 Rip Rap
e7e3e976-77aa-54d5-b857-a0109d335b86 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c4742c68-9c02-50ed-8372-f9bc5acc8390 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
b49dc345-7641-5846-82ce-ccc8efcb98c7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
3e819cdd-bb51-5cf9-8bc4-df532adc4bb7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
888fb8a1-5db7-50e7-8674-4c54d05d5ea1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
60d0c6c3-5757-5a5a-9af5-052ff870b697 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
43b28a03-0e0a-5637-b255-5ea78d74142a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Peacockes West, Intersection and South | PEACOCKES WEST RAIN GARDENS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
a6fd2ad9-9f77-4bee-aaee-4f2dd94e5386 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Earthworks | Road 6
d5e90d05-f96d-4f1b-961b-21d6d08b6917 |  | work-in-progress | fdfba5edaa3c12d619945ecba9bbbe48cd7668f5d4481b1470baa2cb0ef9edd3 | checklist | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS
5ca373bf-9cf8-59fa-bd85-1ac0d7357b41 |  | pass |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
b3db9ad4-0d83-57d3-b116-b49975eb299f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.01 - Construction Pack
815ad0be-e742-5055-870a-3d464ae09184 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.02 - Survey Setout
2a4f0d66-0c7f-53ba-98b1-e141ace35b41 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.03 - Approved Construction Drawings
4e6859ec-3aa3-58e9-8db2-e1c6aa0b0333 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.05 - Topographic surveys for measurement
a72d3b80-5290-5734-a4c2-997e7c0274fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.06 - Permits
a356bf24-c496-558c-b8eb-a741092a5afa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements | 3.04.07 - Stakeholder Management
cb158b41-cb38-5b22-a205-65496b1c61bd |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
fe30c784-1d99-5ead-b25d-c2ff8a86025f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.01 - Environmental Controls Inspection
90666859-bd1f-5859-bcd5-fc6ddd2fbed4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
bf53d58c-00e5-571a-bfd4-154a4dff2ac2 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.02 - Bulk Fill Inspection
7b9d201c-26f1-59de-ae91-61f281883fb4 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
07b8e045-493c-50c7-a4cd-8ec9e1db4848 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.03 - Service Ducting Bedding Inspection
a510dff2-27db-521a-9292-efd6e0bdfca2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.04 - Service Ducting Backfill Inspection
7c455239-bcd1-5828-a96f-3382e57d736e |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.05 - Geotextile Inspection
f9f2745c-b481-5d09-b71f-1f374887c6cb |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
9ff0b964-6905-5136-902f-96e683ab80ba |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.06 - Subgrade Inspection
ab90fb59-6670-54e8-8577-8a766c01b25a |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
0129a9cd-641f-51a6-af46-cd1cbf9fde8f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.07 - Undercut Inspection
b0e40050-c6a4-5918-b161-f56bc6c29d6b |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
3012e60b-eba3-5ff5-94ba-91012f6b0f97 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.08 - Settlement Monitoring
888ed40b-7f7b-5cb8-b052-d34d389f9807 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
4251d428-38d9-59b5-b799-a3e41eb91601 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | 3.05.09 - Subgrade Fill
6aad351d-4652-56c8-a048-5ec85c78a3a7 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | 3.05 Engineer Nominated Hold Points (Engineer’s inspections) | Hold Point (Engineer)
1f172298-6ded-52c2-88ef-18b4dd5917f6 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
d4f9452d-f107-5443-b95a-2757f8880698 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Imported Fill Approval
9bd46f5b-ca5e-54f8-b183-528da62e7c98 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
1b6ca824-a113-5f36-8c9f-7e91a1e394fe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Re-Use Suitability Approval
03e98e78-47c4-5054-bdeb-e0acd1012e21 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Hold Point (Engineer)
22368b4e-83a0-5c0f-a4ae-182865ed900c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
18084ec0-b7f9-5ce4-91a6-a04bf3875a97 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials | Eastern Gully Weir Cohesive Fill Material Testing
13d8f383-d80e-596c-b6f3-f47651d4b1d9 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage
9a5d38ca-6943-58e2-a9d8-7f3e0d38799d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | Subsoil Pipes
1187d5c5-f4fe-5997-91a5-2764ed78b9ae |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | Subsoil Drainage Aggregate
49e4b2a0-5a42-5dce-b023-a4adaa00059e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | Filter Cloth
b4615d88-f226-5268-a0db-0b33f336b307 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid
167cd27d-8964-51a8-a5a5-ae62a18c2a7a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid | Geotextile Approval
04919376-34d2-5065-85c7-583e0a8f8ad7 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
c277408c-ab2c-57d4-af9b-68bbeddfbd58 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid | Uniaxial, Biaxial and Triaxial Geogrid
cca846e5-4d24-5b43-abaa-f449dcd0b101 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
fc2a1f57-84bd-5132-a3e0-55c889aeb992 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Settlement Monitoring
2a19691d-7d1a-53ad-87d8-524afa997edf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Settlement Monitoring | Settlement Baseplate Design
21c83a7d-16c9-5b32-ac09-7a4070fe23eb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Design
f9df0686-398e-5bcf-b896-255b50a822e7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Settlement Monitoring | Settlement Pin Bedding
e84c1ad5-cf41-55e5-92d1-d4b839f8e35f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
1b72403d-2950-52d7-9dba-59e3479b79b1 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.01 - Clearing
3be2664c-ac93-5685-9341-3713d9bad8ab |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.02 - Demolition
a2f03d1d-b491-5ff1-85df-3bdfc98b3a5d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.03 - Septic tanks
2247ea26-deb9-5401-9a2d-02bbb6ce3f79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance | 5.01.04 - Plant Clearance
7cbd6bc9-b578-5331-ac7c-d433e4b02a75 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
303b69c8-d517-5488-b5ef-d0cbc5d57153 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.1 - Groundwater Management
64381bd9-f808-55b1-8293-0ac15532d70b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.2 - Cut to Waste Approval
903f93c2-2f41-582b-80d2-f4705f90179b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
212d7643-7c9a-5745-8c35-db779ad20c1b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.3 - Foundation Suitability
9f8c4960-61aa-56d0-8ccd-7c28575506c1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | Hold Point (Engineer)
0ced00ff-c015-5353-9140-8f20e9a95107 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.4 - Unsuitable ground
ac8bc9be-e8fa-5da8-9d5f-8d168a8059f3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.5 - Preparation for Filling
e10058e3-2f05-5111-8b35-27351e547c1d |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.6 - Subgrade Conditioning and Proof Rolling
a0648f11-bd83-5bc7-a842-e07c76456fa7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.7 - Undercut Backill Compliance
0d0cccbc-0b9e-5202-8693-a09524746d9d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General | 6.1.8 - Topographic Survey
36764d6d-d042-55b8-b8e7-e4f0cd25b5cc |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Stockpiles
29f9c6a3-f0b1-56b0-b3b6-dd1ec5d6ea69 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Stockpiles | 6.2.1 - Stockpiles
ec22a994-5a54-5b25-8329-753b937015b1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Stockpiles | Hold Point (Engineer)
a0444b24-11cb-58aa-a54a-43ef422c670d |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Earthfill
7dc5b2f2-f6db-5c3f-b8ac-23d1ec91680f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Earthfill | 6.3.1 - Earthfill Placement and Compaction
a8f11396-9a53-5e5e-b6c8-957e63a14055 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Earthfill | Hold Point (Engineer)
8cd3aabc-b80e-5ddb-8e07-0b6229102204 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
05705d57-477f-5036-90df-85a3ce16de73 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.1 - Proof roll Testing
51ecd1d8-9d26-5f2d-9824-9d59896a3579 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.2 - Compaction Testing
cf28d8a2-7712-590a-98bc-a412dd492f5a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.4.3 - Scala Penetrometer Testing
2ef2e6ed-4019-5408-a352-afd6496e94bc |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
e2595792-a8ee-5ad6-84bc-6b294c3af23d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.1 - Vane Shear Strength Testing
99aac4ca-0311-5dc2-bcd3-b45ba650f13b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend) | 6.5.2 - Air Voids Testing
2afb475a-9e2c-5836-a491-aa1e0de4dd06 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
e4a8629b-6599-5a31-89c1-0c083cbc1393 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.1 - Proof roll Testing
d7d3e0c4-1ae5-5295-8855-fbbf39fa1ec9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.2 - Compaction Testing
8ef64892-8a0c-5793-9793-cefb04de1a00 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel) | 6.6.3 - Scala Penetrometer Testing
27096d06-daae-5dad-86fa-307027b63ae4 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
533b8fcc-680c-56bc-8e90-8353723466fc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.1 - Shear Vane Testing
e5a8bedc-a4ae-563b-a9a6-665e056ab321 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.2 - Air Voids Testing
858737f0-70f9-5cf3-979a-124bb49a0495 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Eastern Gully Weir Fill - Cohesive (Imported silt/clay) | 6.7.3 - Water Content Testing
535e598d-ad70-542e-8e0d-2bc348f63195 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Cut Batter
59a65a44-68d2-59b4-8921-ad3575bfbc42 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Cut Batter | 6.8.1 - Cut Batter Inspections
e157f606-2613-5909-bcdf-72401cadc821 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Cut Batter | Cut Batters- temporary cut
aa87df4f-c3b9-5f1d-b21a-0bdcb82bbfa0 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Surcharge Fill
3ccf19a9-1832-5f9a-9152-cf77b1af985b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Surcharge Fill | 6.9.1 - Surcharge Fill Installation
70fe7ac9-027a-5244-8314-2dd43105107b |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Respread Topsoil
292c92db-e335-5c41-803a-71ecbe1e32f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Respread Topsoil | 6.10.1 - Topsoil Respread on Steep Ground
cccb994e-6979-5682-bac2-aace6baa1b9e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Respread Topsoil | Hold Point (Engineer)
99dc39f3-4f72-5bd9-a2dd-7e8cbb126dcc |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage
cfcaf034-f165-56a9-874c-a98fcc303ab4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | 6.11.1 - Filter Cloth Wrap Inspection
7d4bd7f8-eaf6-5288-b499-104e17dddd69 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
1f625896-76c8-5289-890d-f734d6709f7b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | 6.11.2 - Trench Backfill
a10dd970-49ed-5e5f-ba6c-0b4524a7eadd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | 6.11.3 - Drainage Outlets and Inspection Points
a47addcf-b3f1-5ce4-8563-2fec1f24ad66 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | 6.11.4 - Subsoil Flushing
4007c693-da07-511a-8d25-a290e618a389 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | Hold Point (Engineer)
0ce06443-e72b-5176-9cd0-13af6bfc8b79 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Subsoil Drainage | 6.11.5 - Survey
a78efd93-a1d5-5eb0-b1c8-4596e7e16cff |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid
dffc4d26-d42e-5438-85c3-ca4a9675e4e4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.1 - Geotextile Installation and Lap Length
02ddc330-3853-5703-988c-ccfd08db4981 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.2 - Geotextile Inspection
7b13bedd-64d5-5cb8-a934-f07fe1cac35c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid | Hold Point (Engineer)
fe83d266-a132-5bdd-aad2-9cd60067de1e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Geotextile and Geogrid | 6.12.3 - Geogrid Prep Inspection
dd9d3f52-968d-5e49-a6f6-8bf949ae54b3 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Settlement Monitoring
62ee5049-c3ed-5bd6-88a4-7d9eb02400e5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Settlement Monitoring | 6.13.1 - Settlement Pin Installation
f274cc6a-7189-5f7d-aa5d-4eb849a31816 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Settlement Monitoring | 6.13.2 - Settlement Survey
8b23b3ff-7e5c-5c30-b7cc-319b4f837ac0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | Settlement Monitoring | 6.13.3 - Retaining Wall Settlement Targets
d5aced91-7373-5f51-9365-e1767869ab72 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
915b957c-d6ec-5d1e-91f6-648d549944d3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.1 - Construction Record Compilation
937b6cf4-a7da-55e2-8d40-b2f4b738dfb8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.2 - Survey Records
e534b68a-c831-5590-8388-d3ccc5d2ed16 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.3 - Redline Drawings
7e25dab7-eb29-5f60-9da8-09e2e88ad761 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | 8.1.5 - Photos
82b8a1a2-9e18-44e3-8e34-65c67e423e9c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
599c7057-61a1-52e7-8c88-01d8c2fe64fa |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 BULK EARTHWORKS | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities | Add Signature
2e1797cd-5000-4dcb-981f-b742a72e362f |  | work-in-progress | ITP - 116 - Pavement SIL Rev C | checklist | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SIL
8fd52184-6b95-513e-b0b9-bf96f970e891 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
ece78c49-2a56-5233-ba39-946810be4ba7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
990d2cb7-9ecb-5187-b10f-6e7b980868bf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
52abde26-f79d-5c61-925a-611b25e5f501 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
a11e2f75-9dd3-5d05-b969-42b65822a38c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
8c49645b-505e-5baa-9648-6b29022d7052 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
c75287b2-1ece-5295-9cca-12f9ce9c168d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
dad90d02-4ec4-5329-beac-f2b7335a48d2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.07 - Previous Layer QA Sign Off
5765c1da-c57a-53d0-878a-4a9c9417390b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 4 – ENGINEERS HOLD POINTS
2cb0aa34-8484-58b0-8ddb-278015337db3 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.01 - SIL Inspection
07745ae4-d487-514a-9297-9ca0243578f3 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
acacd4ff-7943-5144-949c-318d4580521d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 4 – ENGINEERS HOLD POINTS | 4.01.02 - Subgrade Inspection
b322a3c3-0d58-5ac5-94d1-81e637d7ad4d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 4 – ENGINEERS HOLD POINTS | AUTHORITY HOLDPOINT
6a083161-e40f-5a6d-9cc5-5252bf4940f7 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
fbbc4b70-3e74-5d6c-9324-50a44dd3cd4b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.01.01 - Pavement Subgrade CBR
6ff57ca7-8dab-5fa2-9f56-a987f8d02de2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
23d8e647-b0e3-56ad-b7d3-2a33763f5e23 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.01 - SIL Conformance
fc7cb60d-318f-5b33-b9a6-d2adde9d8690 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
b0672e3e-0a1c-511b-b7ac-134129c3b5cf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
e6bfb4fe-dfdc-5162-93ce-9d105e37bb1d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
8316c31e-416e-5b6f-a266-039e81c40229 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 5.02.03 - Plateau Density Test
275a60fa-8d9c-5bb6-8ef0-28b4978f17a0 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
5a4a5d2f-5cb7-561b-9cfd-be549d19f8d6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.01.01 - Subgrade Prep
1eba5a18-bf41-5e30-aaec-92946ca9e18a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
20f68422-1e47-5f9e-8271-a4023af3b3d8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.01 - Layer thickness
4885c7a4-33eb-5dbd-b881-fd35a2d3997e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.02 - Services Protection
91de1664-f7b4-579b-b8c7-4b4e274bd3b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.03 - Plateau Density Test
bcc294f8-dbbb-5d0f-99a8-76146a18f23b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.04 - AP200 SIL layer compaction
c9f56194-f4cf-542c-8f63-6c6fd7565859 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.05 - Proof roll
e64752d1-7461-5247-bbec-fd1ff0b13169 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
a4a70492-af31-550f-9bd2-bafc0b0603a3 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.06 - SIL Benkelman Beam test
07c0f99b-d0df-54ce-b64d-49f6210bb050 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
b19ff3d5-c45e-55e8-94a3-f456d9dc4430 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.07 - SIL Inspection
ddb5fe8e-f1bc-52fa-a2fc-c6c0c60919f7 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
6d8e69e4-7cd7-5bd9-8f60-80f8bf7f6a86 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 6.02.08 - Topography
073b9ca4-3469-5da4-9672-d09610460d53 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
d1757d09-7be4-5592-9d0e-842460e85cd2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.01 - Construction Record Compilation
22df1023-b6d5-5a2f-817c-9a6d33557fd6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.02 - Survey Records
03d69d80-e27a-5333-bf92-87da35621ec5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 7.01.03 - Redline Drawings
6ed8abac-7ee8-5045-9c0a-2133a0f185c7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
6a002c9e-be03-55ea-a223-35be032fac68 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SIL | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
eeb698d1-2c17-4586-a478-cc83d51615d0 |  | work-in-progress | ITP - 113 - Pavement Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS
5aed9e68-facb-523b-ba8f-8c58b75d1817 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
4a965bd2-28ea-5281-becf-f2c6edc9df98 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
18f7787a-cbd6-5de3-8320-2be8d3981e13 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
6a6d2206-e682-5bc9-84a5-4db37cee1992 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
261364f6-57af-5eaa-91e3-65acc98d6b71 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
18feac2e-857d-521c-aae8-c837823a46fe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
5ce7ee7f-7b06-500f-9b95-71f62632c57d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
eec23a8f-2280-56bc-8006-c8ab76f95e27 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
45f86fc5-f572-5bdc-b3bb-f62d69ee0d09 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Pavement Pipes
e3419086-e999-54f9-b98a-2c28179eaa4b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Pavement Drainage Aggregate
84810084-0276-5721-8545-48765e32f4be |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
a5f16d6a-4afb-502a-b8b0-cebdb86568c6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
09072bbd-834c-5ff1-88bb-ed8a78497496 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY
3413b7f2-e8b7-563a-a06e-0be6469609ad |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
f0e7281b-e58a-5dac-aeef-04ba3a5fe024 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
e03b697b-78cb-52a2-9e15-fb72ffab7822 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
5d820355-80c8-5754-a459-0c4831b93313 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
6e5167c9-8e5c-5b06-ae0b-97aa53cc1f5e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Pavement Flushing
a24034a5-bc87-5970-b62c-4c0f319df6a0 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
cfe0fd41-77e0-53c6-bd05-164922cb3815 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
f3aa43b2-c243-5d9b-ac35-08b40a5d758a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
2ecdbf6e-1d59-5e5b-a619-af1b4d9ccefa |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
96351173-329d-5a82-829b-79d07a738df1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
9b74627b-55fd-5065-9b63-18aecf535900 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
adc8f6c7-0a07-5707-bbb9-627dcd377239 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
d5134632-ace8-52e4-a5cb-47bc4f68f491 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
a9419aca-e307-5f81-8e12-49a78ccf9d3e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
46e03220-9136-595d-94d8-2221a48c17d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
d7414bd6-cb5c-52e9-880c-2793d8205870 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
de668b0a-d767-5ed3-ae0d-152392b68ed9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
ea26c650-c85c-5e48-91a8-6d6b99ebe5f5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
341523fc-2c9b-597d-b2fe-7f7a979d69be |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 PAVEMENT DRAINS | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
e8d0f468-67f5-4582-866a-800bc4d4665f |  | work-in-progress | ITP - 112 - Subsoil Drains Rev D | checklist | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER)
05865d9a-3a9b-59df-bbdd-3f09754243ec |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
9e391e3d-ed7f-591f-b4bc-94031357a037 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
2c11ed2b-01fe-5aea-a75d-c796bfb46251 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
083a4eb4-5fc3-5fab-951d-49c9fb2acf0c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Approved Construction Drawings
ff9ee8c3-75bf-501a-8ce2-08cd7a468902 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Topographic surveys for measurement
f924b6b5-a2b7-5e2f-803e-65ea49d82778 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - Permits
29d6eb95-e9d1-5355-a0f6-43d9621f2653 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Stakeholder Management
6b68e6ee-dfd5-58fb-b09c-f43f65bc2f70 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
6d9ba76f-b6c7-5b1f-a671-8036080164a8 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Subsoil Pipes
b98fe95b-f4cc-53e2-a795-b3162121c762 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Subsoil Drainage Aggregate
d216a3ed-8c12-5091-9959-624c7e2375a7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.03 - Filter Cloth
37f876d6-08ba-5f61-987f-96537c5ab3b3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.04 - Securing Pins
3aeeea98-9404-50ba-9601-8b4bd10e1ebf |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY
d089980b-5d1c-539b-aa98-16940e540b90 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Filter Cloth Wrap Inspection
c238c0ee-4e91-5db9-96fa-b6d6729c1590 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
66747ebd-c5af-5b58-bf33-38d4b0a4b311 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Trench Backfill
047da996-047c-5505-b470-8f1eba32bfd9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Drainage Outlets and Inspection Points
f0962cd4-db2c-5706-85ea-7313b446ea1c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.04 - Subsoil Flushing
f80f8403-2eb4-52fe-842e-67159254fe2a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
786ba11e-d103-5134-83fe-3b4c89865098 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.05 - Survey
eaa6d8a2-fe37-5803-ba4a-64d85c8d7d6d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.06 - Excavation
b824bd7f-6dd3-521b-958e-0380e858ab4d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.07 - Bedding
74ec4368-ad38-5900-82ac-98885796ea12 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.08 - Joining Pipes
447d3484-26dc-5021-a73c-90d794af9762 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.09 - Pipe Grade
1debac33-f8cd-5ef5-a1b2-357267ce9ca9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.10 - Pipe Cover
e36ba695-c62f-55ee-b7ae-02fbe24f1541 |  | not-started |  | section | FALSE | FALSE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
33301231-d126-5a80-83dc-9a4932c2f291 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Construction Record Compilation
3f733435-5f80-572e-8d36-8397b883b638 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Survey Records
3c9be36c-1619-5dd2-925d-ca38ac5078ad |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.03 - Redline Drawings
ff7952cf-5061-58f9-9066-7368d3b308a4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.05 - Photos
0a161048-70e3-517c-a04b-30d178708696 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
ba057817-3e86-5cae-b3b2-ee094a1badbd |  | not-started |  | signoff | TRUE | TRUE | Site QA | Earthworks | Road 6 | ROAD 6 SUBSOILS (CENTER & PERIMETER) | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
c7732be6-e52e-46f4-aacf-af7510f80f96 |  | fail |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2
20e04964-8326-481d-9586-6764430b5d64 |  | fail |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1
29bbdca9-e37e-4210-8373-b27a36e2cacf |  | fail |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730
73c995a1-61c0-4695-b164-93ebd25a3639 |  | pass | d19eeaa84687926eab71cf54cebaa826ad3d91a2f810c8df2789de9358c46668 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E
424aefbf-6643-5453-b8b5-5df40a16b479 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
ccf15857-b661-5dbf-9e12-e351522ed81c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
b7aa4bc9-f24a-591f-9403-f2f38de405b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
56ab1672-a683-5bee-a03f-1acf5523621e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
371bec80-ebd5-5cbb-96a1-cf47cdf3bdd9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
dc12a8d6-235f-5b81-a07f-d6e5b663ac88 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
84ff6859-da04-527f-8e66-25e080295f9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
6c79d1a2-6dab-5c7d-931e-f57ae99094e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
7de66e9a-fc91-5a9b-8bb4-fa74023e3ce6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
b794f6ca-3694-5d12-b842-bf9acde8ba70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
5d11dd2c-087d-502a-81ca-3e411bf7444a |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
811c1ddb-b860-5ef6-b4f1-7111a132b9e9 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
2e7ec3e7-fb74-545e-af20-0398306a4086 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
cde256d8-60e7-5857-95f4-897e6adb4ef9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
9c79a1e3-63e0-5f87-8e37-2856fe8d8f17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
c70d42cf-7139-5c6d-956c-a50c5a229576 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
225cafd5-8379-5ffb-ac24-a71f50d7d35c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
a196ced7-0023-5a89-9e54-74bf12ea0b19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
65f3e6cc-b8e5-531f-8796-b068d76cedf8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
ac665ce8-2784-5208-b4ea-0410d2ad8f76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
52809267-175b-5b63-88fe-0cbaef90e857 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
9b2c713c-af20-5d85-ad9d-2d60da23fa1e |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
3273d2e2-4b24-51df-a6fd-5b4ad055c718 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
bfa2fe80-7f05-5b24-9751-04096252129f |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
15792f39-fb55-537a-af17-949a9eb7d39e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
4b0e5ab9-46c6-5652-80b0-fc42d188f5ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
270a9888-7f71-55da-bdbb-7e6952ce372b |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
16c3de6e-a4c9-5862-8afd-851a8bb4befc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
7121c04b-ac73-5f93-a92b-028fd8e17b49 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
dcd1ca47-dad0-5928-98ee-4003160b624c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
e1249143-ee65-58ff-afd0-afa52ea48461 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
1036710d-a7a6-5ac4-9e03-ce1f7be9d7d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
18a783c9-4808-5c18-9750-b6cf21d6f6ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
81a63f09-46df-5122-ad01-81da1bb7ed95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
f9f4aa03-eb54-5eb2-8804-f56861822096 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
1daf5d75-dcac-5b91-9d62-e9d921b4e43d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
f4a6c04d-9005-5a9b-bf87-e6814adbce7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
d20c9bb7-6f48-5735-84d0-ea31d5401083 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
9833f018-1065-5cc9-bdfe-ba1ec96a307f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
de5e1939-c9f9-5821-9aa4-e5ece7611a91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
db0a45cd-486a-5059-b68d-42437f25be3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
7d738b47-584c-515e-a029-71887dbe296a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
226a26b9-af41-5c5a-a62e-35e6059c26be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
8f5e8c86-e932-5796-a9d9-f9e32b24ddf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
6f0544df-f808-5707-acd9-7777b53bc24a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
f7b15606-ff71-55ee-b683-065c5756725e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
9b901217-e56b-5072-9a8a-74549ccd0e6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
0ba2b6c0-53f6-5c1b-999d-3908ae8797ed |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
653e0cec-3d84-5a0a-a9e3-4950c064a134 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
4c3c359b-75f8-5b36-a3bf-fcc9d1332cc1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
ef79a9ad-e1d4-5a52-a08b-2d4bede33905 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
4760e3db-ee49-5aeb-8c14-6893e1c44d92 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
40f28c3b-9474-5ceb-b2c7-8032b254662d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
8ba8fafc-2d17-5bb9-a674-598cdcff3c17 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
fa1f6c75-9cad-5df3-80ef-5426999da512 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
6f95f120-5179-50dc-9126-357465dc1e6f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
336a020c-2b97-5f44-a053-d8d5ac467d57 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
98f284ab-c9cf-5e2f-a178-91b362821f9d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
77204df3-fa79-5aba-be63-1c595ee7f94a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
0de335a5-d546-5e32-8845-adb6c304c116 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
27192e70-02ba-50ba-a781-35b74ee3cfaf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
6720c1c2-4a90-5b67-88f0-b6ac1f956eca |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
07c0dcce-9964-53a5-bb24-3f5812fa1a00 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
722a6c03-26a9-57eb-ab80-11adf9620af8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
0a1febac-5e20-53b4-9117-43dd5484acf6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
57ddfea0-e6d0-5279-93e4-5373d42e6c1c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
68a7b1b8-29a9-531e-9b86-de8471897ec5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
0275d13f-6dee-5e9e-a09f-b42c03792025 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
8a1a4c7d-d284-5b67-b58d-4f3d8891d412 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
a0f42208-8d05-5dbc-b73a-98899b43d465 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
f0e3f00f-fd09-563e-a0ff-b19db2e87671 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
e3b37f88-e0a2-5c18-bd8a-07e2a3b7efcd |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
4f721e5e-a816-59f5-9f0d-2d345e0291a6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
04b6ad68-bcef-5339-9384-a11337d71379 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
96f29741-d4db-5c1a-8671-cc008f7fd866 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
003c6238-9e49-456f-8736-fadc7299b4f6 |  | fail | 1e583f8b70273eabf004fcc38eca8c02710d652e820a3ccc1f9a151f83465210 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C
b5846f00-e3c8-53c9-ac4e-825d19005a6b |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
56ba4985-7494-5ed6-a2c8-f3dcf0c355ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
cbce5515-ec99-5c1f-aa28-bc72d3a876f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
da8efc82-13c2-51e0-8a09-35ad613c05eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
75b568d2-e461-5c4c-adaa-9b85e605ea3e |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
03d0ebb9-f612-514f-9617-d9d9e4f92ebd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
853bea71-20d1-5362-910b-16fd72f649cd |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
9b02a226-2760-52f1-aaf5-6103e778fbfa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
7c5fec79-9147-5ba7-af97-e4ec3c7a27b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
9ac8eed2-4677-5e5d-9981-00995e93dc8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
f97ba87b-3b64-5268-8ac3-71764822ac13 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
a405453f-3af2-55d0-a231-864779aae659 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
f4955674-9a5a-51f7-b70b-6fea30eeefed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
1d925e46-7923-5b2b-8d5b-0ad73e77aab5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
716472ef-de9f-5e87-8265-4d22c83dba27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
2a418f76-ed22-590e-943a-e224b2a32d15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
337077ff-7d95-5e80-80bd-0ed022dde124 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
04c3e067-5071-527d-8ca4-3a335e4e5636 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
f464fb4c-2fd0-5ef7-9b1d-5942d6a136b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
aa09bcb3-0746-4dad-9c28-ba938c8dbc76 |  | pass | 47131c73108e41695a7b24afbce5dc5171ba536d54b8f4c0fbd189f3538b10c8 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A
187d0733-2deb-596e-a610-365deaf7777a |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
c82732dc-c680-50b9-9227-d2b9b90e3c9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
b3ede6f8-615a-5446-85fd-a5c3cf96b381 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
e9d43e11-2407-5910-b725-86a6654be8c0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
93b1779a-e9fc-58fb-a008-f663f4363ddf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
04e45e24-7209-5175-a03c-5850530f9268 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
3b90d75f-e376-5271-ba08-d82eb533aaa0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
c3d7913b-652a-5a96-bbe9-52bd17f73e07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
462ef6d8-d923-51ec-b952-7e3b9ee2100a |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
0aec76d4-9c25-59ed-a67d-4fe47b3d1ff5 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
f7f240bb-b287-5666-8659-66090d6424e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
781315f3-2dae-5b9e-b130-cd8aaf1df1e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
ef15fd5d-2953-5098-a8a0-8a5a2c5ecd93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
916d7bce-a1f6-57ea-a45f-8c729532357a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
3c924386-1b18-5ae7-b8f4-da71dbc74921 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
5c2b7a89-8e4e-57e9-9e3a-244ecd6d4962 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
86ce2418-59f8-580f-88df-a76642939d84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
faad3e0a-ecb3-5540-b357-cd7ae2a62214 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
d3c9b966-cd73-5e8f-bbb8-c8ccad66049f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
ec3ef844-cb07-5251-9d8c-6c7d0e9b625a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
0f799df4-48a6-5ec0-9a45-3853ec0a6d8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
f155b58d-37b2-5d35-a62c-7e2b1a1e78ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
62ba2cb6-e9be-5b57-8674-c4f8661822e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
94047231-c2d2-5383-8a3a-2d3a7a7eeed8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
ee2beaf8-1061-5f48-9f2e-55253124e047 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
b88a7698-b819-5eb7-a740-9a0008774668 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
384c0089-5be8-5200-8fc0-ad7b239322b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
6c2e113b-bc14-59f9-a225-e82de28cb028 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
1bc62435-9fef-59b3-9eef-f232a57ffb7f |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
7355c4f0-c527-5e29-bcbc-53c74765cbcc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
ba533614-c4ab-518b-976d-584ecb66c4de |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Basecourse Rev A | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
2d33bc6e-13d7-4f8d-b419-b439b5540fd9 |  | fail |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960
524252ad-4629-45c2-aa16-d5f9e975bb57 |  | work-in-progress | d19eeaa84687926eab71cf54cebaa826ad3d91a2f810c8df2789de9358c46668 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E
4a78e007-c6c5-55cd-83d9-fc56b290c1c2 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
c3031220-eb13-5382-a93a-0eae6613663b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
1efd7171-a92e-5209-8a25-a65768abda32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
56636cb2-8e9e-5fe7-a4f3-992eda99ff40 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
0d28a77f-e9cd-5e0a-96fc-a28b279bcf34 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
5e464309-64de-573e-b323-68ce96818c66 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
c6da017e-5bb4-55dc-8bb1-c944f2ddfe93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
50eba124-69b4-5b98-8363-820b3087b15d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
60bb9e1e-43ca-5c96-9a3e-2091a3a0ec32 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
e4bf9212-29fa-5465-8626-ff1cf5e226ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
2acd3b85-4399-539b-8e68-237297dc149a |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
8a5dedd1-aa54-5e64-904e-988c37a05edd |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
fcb64382-b4df-5902-b276-5cae3e77a3f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
39cfbbed-cf22-56c4-8d45-df29ab469d3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
4cd6fba6-e541-594e-ad13-81566af0c912 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
05abe473-50b4-58f5-832d-bd5ecc5be8ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
10bbe5b7-b607-5e6d-8053-aba60b58f15d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
0d8a0102-4d14-52f3-9963-901672a3e256 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
fb69c901-ff62-5354-a2e7-afb186544e4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
f2db6374-a54a-5de2-be46-0da6ad0a6ec0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
87a9ea8c-619a-5957-9cc0-64b33d172023 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
1ebf925c-b924-5f32-9f1a-0746299303b4 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
7c10c8ad-46c6-5830-aede-b9a1ad1676db |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
ea284104-a8a8-5027-a35a-53d40ce1a114 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
4131f545-9960-517c-a092-ca20b89cfbb4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
7a1bb16d-15e8-56ef-93f7-5a29cd438bf4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
e6c9e7e4-75c0-57f9-b474-2b142ddfe1fc |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
28666734-6311-5926-be3f-e13ccb99385f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
8c5ae9ab-6a60-5414-8590-98210bd9b9af |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
7b5f5c80-13ff-51b7-8589-91e2a4e7a785 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
a15f3575-8d9b-5163-b7c2-98db7f6f8e01 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
59e44a4e-191b-503f-9bda-43cc8640ac78 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
af16ad9f-d376-5b2a-8d75-eb4540485c49 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
15275597-fa20-5ad0-a9db-9cfc074caebe |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
447bb581-3060-5d45-bb3c-6a8c0920d191 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
486d8f00-b545-5d07-987f-a073cf430e3c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
7ffc574a-5712-5063-9402-9021d8589b77 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
8b82c238-ac0f-5fa1-a3f3-484861b945d7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
85a3e172-66cd-5cc1-ab2b-f87424d01f2a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
74f26d70-134c-572e-a124-ecb76d565cf9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
91cc7003-3434-53a5-905b-9abab57c85e9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
c6356443-893f-56dc-810f-a8a997250605 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
0c238abe-67bd-5a4a-aed9-875c2c1fa50f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
e0d419e4-d98a-5458-b796-40896fddc827 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
31b8042a-6eba-59de-aaaa-ce3eb16f0937 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
1537abab-c99c-545a-a1a9-12f91463662d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
d608af55-b9a0-5e46-a27c-da1ea080a4dd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
2193f5d7-49dc-5ccf-8149-3d5f734abc79 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
b9748857-d706-5a73-9070-73e429071de8 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
c5a94594-07ec-5691-a829-d60b935ebfcf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
f513e211-81cd-5cae-9545-40027c73024e |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
057f13aa-e447-5e5f-8c2d-dff7550d6ad8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
0dd2d18e-7b04-5542-bfc1-cf9704e37b45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
d196ccb0-473b-5224-81cc-d24309484cbf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
19f77df7-f425-5bf9-9a8a-9f77435253e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
4abe8c19-20f1-5dbb-8dba-c0396cb72600 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
489e1335-5d6a-52fa-96ea-d9336ef27f4f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
b14592b9-6119-5b5b-911f-df763e703bc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
1b9a7c89-3e24-5fb6-8294-3277f70387e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
4d22e0c0-dd79-5515-97d4-1644442ef96d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
4fb0f3b1-9dca-5cf0-9ba3-c4ef6bbd3590 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
64a0f4dd-c27b-5038-af2d-f2893c416151 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
46b0c402-aaa7-55be-8946-749093728709 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
4848c9fd-4257-5683-a8b4-fd8c5bf3a480 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
7a5c40bc-9df9-5965-8b08-ee3ff26c3077 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
77c17a39-e8dc-5b7d-af3d-a8952fae5bab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
7b7fdcd7-ac6b-51d1-94cb-2eb0fa14325e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
5979fddc-5e08-5cf6-b2b1-88d51360e90e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
440bd992-07cb-5cde-9401-2a553bb46e9e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
2ba6c463-4fe3-5701-8d0f-fdefece1cac0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
29218753-5bc2-5401-a169-fdf855391665 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
3a58156d-cb59-5adb-a7b5-17338679670a |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
2d4f5924-78ad-58b6-b5cf-4398071bf446 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
821cbb4d-bff7-5c17-8f24-d28ec8605187 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
f6a7bc15-58ed-5309-8a1a-cfd7529e47d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
54727cb8-3858-44cd-a976-44ac117b0b54 |  | pass | 63b1e491901cfe89030f9bfcf85c2fe0f9b00560a68517104fc1e1b1037eef12 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1
d82ee7f0-ecea-52f8-ad02-d83e0fc0e12f |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
dc8abba6-db7e-5faa-8827-8cf1982eac63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
2771fe2b-d6bb-5441-a2cc-13d91712562e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
bf5ce6fd-bb40-57ea-83dc-4c90065b1c1a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
7d097805-15f3-56a2-9d0f-ab71e95e2099 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
b627c71a-f070-51c5-b794-a04353b017d1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
e1800ae5-ea21-5b6f-9582-34a91ff1e0e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
222e94aa-7b68-508e-821d-8b2fba750f88 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
682db794-3f92-5a1f-ad21-e9f92d7b1869 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
87f6f6a2-f861-574a-88c2-37bef5bbd134 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
f7354634-580d-5c94-8a5e-d30d1bb07b80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
720e0300-c01f-566f-8c1b-a03f1ff81029 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
f889432c-b889-536a-ae4f-f49c0b8d708f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
ccbb277a-f3b9-59a0-ab56-78ee288275f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
cf848b4a-99c7-5c8f-a273-174995e73025 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
903ed84a-1fe8-51e7-83c5-f3baab57a759 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
68143ea5-4fe9-57d1-ad10-b58df1585864 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
064e67e9-6e54-5608-a9bb-9ed3856e3aa7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
5b514fae-0a18-5457-a196-e7fbef217a31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
fc96af2c-19f3-5b8b-bb33-2cd167be77e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
bf5ed39c-1633-5f90-bcc8-58fd2169f1b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
112a01e9-9621-5740-a023-65e5988ca396 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
799e1e6e-dbbe-51ef-b17d-56412fd98a21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
7e1ad255-5977-52be-8d45-55bc78a2c759 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
f1857cbc-ace2-5754-80f8-bc999e103a59 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
34da0ee3-280e-5fdb-9fbc-b0a9546d5d7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
fd612d10-b246-5f89-b982-6916831e4a1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
637af735-f7d9-539a-a17e-4e871527c264 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
86d388e1-4cdb-5342-be4b-01be8cfd38ab |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
574f016f-49cf-5c2d-a2a7-7b29d31467c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
bb82f1c7-89ca-51f9-98a6-4de527e68c8c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
a5469e71-9c58-43da-b65d-eb3f0d370c2b |  | fail | 1e583f8b70273eabf004fcc38eca8c02710d652e820a3ccc1f9a151f83465210 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C
e6d231ad-1d3c-5e19-9ab4-82b3c810b0af |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
b73ba2a9-fd10-5f26-b3b5-5cae05499ed3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
1eb9fcb0-4b48-5b03-b5df-e5ba385731ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
13e7d712-de6e-5a58-9f1d-fe396c4e5bc2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
d8052bde-832d-5559-8198-aa82d5265c37 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
75d92a1c-5687-5c91-bdfd-a1a8ea508a98 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
a6725748-a0c1-555f-8755-3cfb765b5764 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
143cba81-589e-57b4-9f0a-554f178b394b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
6e50d7a7-a4a4-5e40-90bb-d913146cdfe9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
15e139cc-65fd-5581-bcbc-7268d13c9337 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
8e7df873-2e62-5975-a175-eeb9c44c44c3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
49dfb96f-f5d3-5eef-b641-64a4fc0c736e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
a23c8c4f-7229-5329-bd20-cc41ae962bb7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
4fabde66-bfdf-503f-b54c-b1ba66d3a913 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
8f221d34-4b6f-5bee-acde-89e64caa1c35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
33e2d9a9-a46f-531b-b365-23f89784187b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
aaddff41-5a19-5e6d-a84d-88560ba580a8 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
ffd16464-fc29-5375-91fc-e8469733e297 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
2bf68a84-9304-58cb-8980-d72e943d980b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
7456d253-9c17-42c6-b924-81401341f439 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound
635ac6c2-895c-49f2-b624-f414207037b9 |  | pass | 063e740830527b1dbf72a9fae99d75366e0cb00c6ea1b12172a94088440b8882 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E
def744b6-330b-5f35-bd13-1c16637b731a |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
c4471180-fe4f-5b10-ad4a-53eb9e6bebbe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
0d724ee4-8033-5659-86da-c0950f0ac9d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
11c9d2f9-8060-5de3-8bcf-77577babfe52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
6aa808ce-3c68-53c6-bc91-ec95f0dd8379 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
c39b84d5-6b05-5f00-ad69-589d80c3ae98 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
f1bc311b-f592-5117-9062-47123e1ae7d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
0ced846c-6367-5f98-9d7c-06a7fd60a26f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
4fa7f344-f4ee-561b-9482-6f525891eae4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
8ae16d41-96a9-5596-93e6-29684ddb861e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
bf5321e3-b2e1-59a4-a831-9adbb68f4d15 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
47641970-d0ad-540e-8e7d-bc88d8792228 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
b7c89d95-abbf-594c-abb4-fc796387b86c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
9caba4f2-d593-5dee-b629-ba94953e790c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
1239e4b3-b629-56ba-9a1f-408785dfc588 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
067261a6-1d46-5b40-982b-badef61ad33d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
967c98f3-2ce4-59c1-a88c-7fc67ca1d69f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
a1040cb1-905c-5ae8-8f78-e995b73d7097 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
a7ef5f63-b60d-5af1-a86f-e3de73681246 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
d3c656b2-417f-5529-b738-3b85e5938764 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
d44f24c5-1a58-5ea4-b7d5-3a160ff36d62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
1f9f78c7-83f4-594d-984a-4fae58877653 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
c42317fb-0134-561c-badc-fb51c8011cd8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
54a25fac-9d7c-5b45-b27c-a38b551941ec |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
4fd0dae5-96b5-5fa4-9e84-567d2c703db1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
2803447d-4154-51f7-a1f5-8fce06f054f4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
fc486433-e8d4-55d6-931b-d47f43731498 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
c4446ce5-e353-5df1-a6ed-aa0d8ae9a586 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
d071f90f-bae5-5824-8f54-92e4438baccf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
e227ff55-754f-5379-a4a2-e03516f13ceb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
8976faa4-737c-5196-9ed3-6cb3c3fcd035 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
2db37da8-0df3-5dd1-a6d5-51078c6997f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
ed442d10-99b9-5a83-9c4f-6839fe36caf9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
dcb1aade-dd35-5702-af92-a1ec8fa9a2f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
516b2a41-2420-5bd0-bb3d-fd3f5f0a356c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
c5559ccc-1cdb-5584-90e0-ba9527a58708 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
e068ac55-8fb2-57de-b301-6d8bd07bcf63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
7fc24f1e-aa6b-54cc-9ef3-86e3047fd595 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
f63a9321-4cca-5266-a514-6a5f3c472f3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
ec69a559-c906-54d8-ae92-015c8096e2ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
5d8cda84-ba96-5381-92a4-8571bd7ec0f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
cdcf13ce-eae5-540b-b198-27f6947abfcb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
7ea55dbe-f3c9-5700-84a4-35f95696a9f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
ca51ebc6-69cf-5830-b3a5-376e1636912f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
5653ceb2-29f5-5c10-8c0b-cfdb74d190f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
f04278da-4507-59b9-8f57-d74918d61b2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
d380422f-0b4b-5039-9cde-0d0faf7c002d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
f7189a99-3006-59d2-b78b-49f46fa5c9b5 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
4453985c-4506-5398-8bfa-5dd1b9f8106a |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
b9b15d0f-7e60-595b-91fc-ae8682d8bbd0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
88b21f49-5241-5441-b5b7-f5b5f0d5c278 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
23dfda2c-3400-5179-ab34-35b8c4767a72 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
c1814c1a-07c3-5229-ae43-d5e40cd1659b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
05cda45a-1002-5f8e-ad76-2dfe31601ebd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
6ba710f7-bc48-508d-b80f-7ff31f335dd0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
5f4b7eb8-f513-5b0d-bd04-31e67c59db14 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
e09c595d-f697-54a5-8dcf-e8755a674f7a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
c85f1cfe-64d4-5265-b757-0bcf03bf8898 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
c4cd261e-1668-5e7a-9f9b-b248b3e32637 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
cce4dd8e-95d0-55fc-bfc1-c85573bd893c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
6d807b07-b64b-5d14-aed8-513970f43cb6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
82c305de-d4dc-53b5-8b7c-877679e6e9a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
705b7a4b-13e8-5bb4-8109-bc4b90f7371b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
52bc5be0-1b58-5bed-8cd2-c5fa9c18d067 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
ac3d4519-4082-5196-a752-8b03b7ea670c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
8964c6e6-27f4-5e05-98aa-11a511b62bad |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
eec5d3bf-5494-5d0b-b0dd-11cc09ab7d59 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
af6b13f0-a28c-52a1-acce-1fda0cd9924a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
37e5109f-bb7f-5471-a574-abf3dd33f271 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
f20bd9bb-a21d-5ea3-8e23-13db803d822b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
096e97ef-7db0-526a-b9f9-92b850f79f1b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
2d950c29-1c6b-5ea0-ac0f-939ac783c38a |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
bdf5371f-6a4f-548d-80b0-96a9fa936c52 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
0370215a-fa26-50d5-9d56-24c15b46bb5b |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
a6c673f3-edae-51a8-b55d-2e99e9863ead |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
033aa5af-e092-47c4-a191-747a80ddfba2 |  | pass | 1e583f8b70273eabf004fcc38eca8c02710d652e820a3ccc1f9a151f83465210 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C
1bf86c89-9789-580e-8a03-7b042faa8a3e |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
989a5f80-28e4-5ada-8b81-a11d58698f2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
7e1967a0-655a-5f1c-91ad-8172fb14f451 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
bbd176e2-8643-5303-b06f-07451d68df4f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
b11c8c7c-3927-5916-8833-b523bed3d09e |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
d3222f2f-038c-53d0-852c-1a928626f7b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
a9a320a0-f484-5668-99e4-adbe49885318 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
77eb876c-ecb7-5689-9554-4544a868f348 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
b5359fe4-09f0-5e8a-96be-1816082c5551 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
84725d76-0e8e-5e73-acd3-168005d4136b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
dd75f04c-b227-591b-9006-d4c28a11ae5c |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
afa7fd80-1423-55df-9d78-e41aa0d0d3a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
284552ab-1631-5443-a6f9-77b2640f46aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
0f3101db-f376-507d-963a-79e6488a5779 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
d8d0f136-b478-5e35-895f-3bac4162da3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
13808f50-c287-5dd8-8be3-a14100c9fed0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
279cf162-1d41-5fb2-8d9d-54d23b336503 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
17410865-3925-5551-befb-fae6434b7281 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
26f29f9a-3139-542e-a822-8d0f92068db6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
cf956475-fee7-47db-9fc6-e81ad50de683 |  | work-in-progress | ITP - Pavement & Surfacing - Basecourse - Rev 1 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1
dd334f53-1565-5893-90c2-9e16969015fb |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
0d64e5b3-5eec-53ce-b296-d917f54c5565 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
c3d2c283-814e-5bba-be7c-e3909574e571 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
48f633e0-21ff-5ffa-9499-1396bdd46065 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
6f482309-3089-5fe3-8f8f-a2c136628ee8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
8c8d20cf-e7a8-5131-b1c0-60db74f05622 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
594efcd8-e9f5-541f-ad6c-5a35c483a0d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
bf592b6b-ecc6-50dd-8290-4837f1a869c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
c8778876-375c-52df-82a6-de074f3dd7bf |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
323ab1a0-d84b-5f12-9dc6-1934a87c7ac5 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
99dca466-af82-57ba-98b1-cb74a7584e76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
4e6d6be5-e04a-5c17-b5e3-0d1a51a8ac89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
9d92c4b4-efe8-5c37-959f-8f1292001c28 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
55169b55-934b-5659-85e5-17dd1062e51d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
966b29ff-d9dd-523c-ae3e-d890676eb93d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
51bb1b4f-fd04-55bf-9dee-74aec8e757b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
672bd0db-0fc9-52ef-8d58-231d66eb3863 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
c63979f2-b184-5f49-8c41-294bc1c5a77d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
13ba0a2e-b79a-5db4-b78d-5359ee857551 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
f4f2f171-0933-5710-8689-0e50c8200cfb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
6e793e6c-f8fa-5e23-b8c5-28c1fef982ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
78fa170c-8e0e-50a7-9b9a-344d13447a2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
db622b2b-2654-5529-a324-6a8fcf704678 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
eb336499-e7bc-5536-8636-306913d06680 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
99f9cedf-9b87-517e-8c49-20604906f517 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
98c33dce-99f5-5660-9690-9f1274dfe97c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
30ffd3cf-fa89-5874-9b90-9e061800fb6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
ffb11cd8-db79-5b56-becd-e3e57e84cfe0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
b58fdb53-8518-5529-91f6-42e42e673c86 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
bdc51c0f-a2f4-589d-8af4-cec7668ff340 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
098f91ec-af57-50ef-b2d6-e3597b4d6a9e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
6915dbf5-d7d3-41d5-af8b-cec64e522153 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
793bdb7f-b34a-5070-a881-6a1b5f3a1992 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1 C - CH1960 to CH2100 Full width / CH2100 to CH2270 westbound | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
773d6161-945b-4574-ae34-48a84815e652 |  | not-started |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side
fd667131-dfa0-4ad0-a41d-666a49914c76 |  | not-started | ITP - Pavement & Surfacing - Subbase - Rev E | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E
1bae8b1c-7c9a-5d35-aa21-ce352b20b53b |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
59f0c3dd-4141-5d38-8197-5c8afb2e5a3e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
103a4fae-403b-5813-9a77-62bd06a2467a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
8ce344c7-ae03-5904-a727-c9fd2ada8f5e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
89cd08af-065e-5757-b081-da82a1774e47 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
0f0c232d-4676-5079-9ebd-8919d4f0e02c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
42ef446b-ad80-5a65-a320-b975b43d5d1a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
0dc2bb16-a199-5371-95d8-7e22a440dd96 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
5eec08f5-e44a-5d25-a743-1e8663a0e6fe |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
aa610bdb-5280-565b-bca1-3367fd4081d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
1103a100-1ae7-56e8-8b05-4754966b3ceb |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
cbec4967-4925-50f0-b919-01138b052b53 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
1ffacae0-42f8-5f1f-b34d-7bd7bd30ec8f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
31939ed8-8abf-538e-b120-ecaebc1e98f2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
b233e88e-e37a-549a-bfbc-6f522b2415e0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
f681e6aa-d41e-532e-8add-03b70e4df5f9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
ac4e2e3a-58ca-549c-8208-1e99e7b74c36 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
c43cb5f0-1270-514d-b8d1-c0c91619ff72 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
b887b770-d98e-5e2b-9cc8-1861a1e4b6a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
06ab29b3-75e8-5003-a118-f6336d359d84 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
6f62ed1d-9468-545f-bf52-4fabc92c4881 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
b578e7c9-a4d4-58e6-932f-23025eb62dc1 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
1f6438f1-e8e8-5fa4-bdf2-e4ae69383ffd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
96a11a67-d39a-5b58-a1ff-3a8d0bee0bdc |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
ced10d75-51f7-5fbe-b609-323b028df856 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
242ecc39-5f08-5908-bd68-e18603b82877 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
950a1d16-a0a7-5003-a578-f0869f2a55d9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
13a80fab-4672-5150-98a8-65c03ebbc164 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
fc7dde9e-17b1-5192-a7b9-9227370acffc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
9893319e-f541-50b6-9ed6-5f77436148f5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
68b83069-a44a-5207-913c-5ee9c7c0dfdb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
d0557b96-dc34-5faa-a7f1-dce02cf4e078 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
a0928032-32e4-521c-ac19-3cdd5705a2d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
576ae5bc-87bf-5b6f-81d0-b0e2beee6e15 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
97e09e1b-62ba-51c5-ac65-7e91ae5bb3f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
63c4e29b-62f9-5d99-836b-2bef6a02b15c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
9801f030-528b-5b3e-bfeb-65a8a1f24980 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
de9934fc-e4fb-5b41-a176-4944b9d9051c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
fba7e33f-82ae-59a4-bf7e-772fa6d8ba56 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
22d72a32-8eac-5ace-aa59-1bdab0781aae |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
5286a501-b908-5201-8179-a6aa07233ae1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
f2cfc6fc-d26d-50b0-ab8c-1423433c07bc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
60c5f90f-9b1d-5ca4-80b5-42d7e32d0dd4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
706d391a-18b1-5b50-96bf-e3e4fc0c6b96 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
31128a86-b28f-5f19-95f1-021a450c01e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
907abd9c-d4d4-5d12-aa20-18a68e8c6db1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
8564172e-2cdf-5a5b-a055-609f4744093d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
087beaad-7185-57f6-b7f3-007500cb358c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
3711e525-bf3e-543b-a2d4-0631f6544dcc |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
ed238eaa-1919-58e8-b152-d085c3e9ba94 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
c3e1dc38-785d-556e-aff2-9ded13aa6b49 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
a947f0fc-8299-5506-aef6-a569e79f068b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
3a964db2-f6a5-5b71-bb90-995718338fd3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
5339ed60-29b6-5b65-baee-6483c7d48994 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
ad79e0b3-63e3-5e43-9d3a-8f718066be23 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
42481edd-0d23-5fb1-8cbb-4ed35c9beb6d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
ad8277fa-884e-5310-b34d-4b4490bd140f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
de0ae608-1a44-5f0e-975e-4d303b9d0fca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
53a178fc-dc51-5f4a-8399-9338ef1aee9a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
280a4f32-5a68-5f23-af59-1d63af7f211f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
fe35e286-8ce6-5550-9120-05a571fc5fc6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
9e82f7c7-fb81-550d-b70b-93a435783974 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
54a0cb84-a373-51ab-97c1-bd4b604dcf1f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
f938f49f-9570-5267-94b7-a8f00b999f6e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
b6672944-6131-5d28-a009-18b5e97d85d2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
d29c35d4-2bd8-50f4-8a9b-0796fdfd78e3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
d9ecb116-8ed1-52b6-91fe-2337b56ad440 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
02041836-08df-5bf8-b9c4-889118156ea3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
e50ae40c-7593-505e-8033-25f39680ac8b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
137b3957-da44-5ee6-a0db-aed2e692c4ea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
8893fdea-6f33-593f-92c5-093e46517f9b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
b98c3f36-27eb-554b-905e-ba084c56d3cb |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
7dd2f1e9-b848-5afe-a384-e7d6012c8c84 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
3725a44a-f84a-5ac5-96bb-f8eb0865bbd1 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
0da0d319-6b2e-57ba-a189-41192b53b9cb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
34da3f53-60c8-546d-a9b3-5f96a3b3fd44 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7880b664-b035-5f1d-b9e7-671e63b8b416 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
e5d9211a-b08a-4e29-8aca-e9d70f7ba267 |  | not-started | ITP - Pavement & Surfacing - Basecourse - Rev 1 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1
ab1843a2-f815-58a3-a96b-58a72ab435e5 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
d8cc66e8-2c93-5f5f-abb3-57249180f3c8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
9179833c-76fe-567c-85b6-eebc1c99e985 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
9d0f5fb0-5301-5d27-8eec-4670a95771c3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
f029a39b-af9b-5641-881e-3cbb9a402404 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
6459eb33-521d-5bf8-91e7-fe708d388217 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
2ce4ff8c-0202-57e0-b25b-0511345fbef4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
f710bc1f-302c-5f54-b9f0-9e40a2f2a797 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
e1e360e0-4aec-586b-badb-4fa55c085986 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
bb02ccad-bc75-5a9d-b8fd-70ca585c2dbc |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
91e962f6-d187-5f9f-9acf-f93a55987b66 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
c7f46967-2297-5a9a-abc6-a901838aebea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
a154ad35-c67d-5100-9df5-bc7998d7b71f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
cfbfb2f7-f862-5bfb-b5e7-f282fe0518de |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
a0278115-f2ab-584e-854d-270af9054220 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
2703463f-2719-595f-a310-2efb87621ec2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
3e5b41e1-7345-572b-aa57-899c03d3acc1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
fb427323-3ebd-5c9f-a098-84ff892138b8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
9d07d095-f1be-5583-94e1-6f0bf4f4e016 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
2fc2b035-a44b-5693-ae6a-9e32f28a4578 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
0f62f1cc-2e6a-58af-ae13-47baf4868529 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
01c2357f-0105-5944-9f38-a7377ee3de7c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
b4d1b63f-8d61-5129-81ed-5a2b3febe743 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
812ae973-d84e-52a3-a8b2-373dab9864cc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
4f832f50-b8ae-5b12-a941-23a7a8fd4aa0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
7aae6285-2dd5-5852-a834-5e664f7671e7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
94444cae-0b65-5657-b7ff-df5f8387f83b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
29c7a7bd-d638-5d7b-b1e9-2f34360df613 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
0c566e92-ac23-5027-b66d-4864e2b813f8 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
05189ee0-411a-5b37-864a-9ce3c59f7fdd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
c49191bb-98ae-50b8-979c-7dffa5a9c732 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
ade1aa08-3acf-5e48-9aa3-897511307018 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
6f262a5a-7085-5cd4-a082-f43c3abd09b6 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
a3247745-617d-4823-8b74-b0a7428743b1 |  | not-started | ITP - Pavement & Surfacing - Kerb - Rev C | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C
58c008cf-5d80-5dbc-acf3-75ca7ae7e44b |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
a00d6261-ab54-5360-b0ac-26de2179544c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
2bf628ba-e6b5-5b9e-96ba-a3db17f7468d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
26d7bc98-f74d-588a-8d6a-b4823671108a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
4246fe40-d048-51b3-a6d4-f577036a7c2e |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
a3c1ba7c-6049-510e-8e8d-807912175697 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
3ddfe2ce-1771-5bd8-9ed9-570336de778d |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
0c4b336b-cedd-55d4-a788-d6cc449313a3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
74741690-9b42-5b97-9b59-23b0225c7281 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
1a438ac3-2235-59ef-b665-f40ca34d144c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
09d8c121-b4b9-5c7b-8f10-082809f31f87 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
5af21613-e3bc-5b09-a1d6-27c225f166b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
e715fff1-6198-50a4-8977-cd5a8361840d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
cdcb9778-5ff2-5b18-a959-ea343d2fd113 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
2b45fc19-0ea4-536d-9a71-ba6ee7960738 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
9e50432d-5d53-566e-b865-a47f6b7c3cc8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
71259eaf-1e9c-591f-826c-3d2d6104405e |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
fe5f0864-96c2-571d-b754-f1b2532cb66a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
f86abc3e-0311-5151-af04-1b0589299bbe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
3c303bf0-2c55-5c47-92e6-e945e8b1d0f2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
3b0a0950-3496-5848-810a-5e994c4d42d1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1C - CH2100-CH2280 - Area 6 Side | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
53013f14-d543-4424-b902-3d4fe3850a24 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB
ddfda00f-1964-4d65-a0cb-3acfa03cffe7 |  | work-in-progress | ITP - Pavement & Surfacing - Subbase - Rev E | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E
915a729c-902b-5040-a877-1f5aa19980c5 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
4bed3dd4-5658-5727-a2cb-2bd4b98fd873 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
611123f0-f729-5b16-b6ae-9d8b15faf157 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
81f52a48-cb42-5ad5-ac40-5826551606af |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
e226696c-7694-59a5-b7e2-298416a5e234 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
379cc046-73f8-5e1a-8ba1-93c8866d615a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
2ca576b5-a00f-595e-a58c-9c328945a122 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
2eb41846-a9f9-571d-8061-db07c31bfe78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
1006f822-cc0a-5a9d-90ad-7c08a61b7396 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
21831ae0-a286-5cd9-98f2-5e72d783aa43 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
7a2761f7-ca00-5c7a-9aad-7733bcbe40c8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
672f8921-eac0-52ef-99b0-a8e80ff3c22c |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
ed95bf89-721a-5c74-9c73-1c9ebfa34aed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
95593db9-c57c-5171-a86f-f6caab8c4f87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
82de99fe-1544-5300-bc2d-d0ee9ce25677 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
b76e230a-ae2d-52f4-86f4-3414852995a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
ceed56d0-a1c4-5b19-bb12-959b49ac92db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
acf7305e-6a83-54cd-b765-1b1aba73a1de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
4e42c4c4-395f-5f99-8f0d-7fb5d14aef3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
0910047a-93b2-5110-858e-455f17ffa8a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
a6cd2693-843c-5ab9-9c34-c9abb0175e5a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
a1611872-87e6-536c-a7cb-29ae9d67210e |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
6e5cb057-a0d2-566a-968c-322033e5018b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
6b0af090-7b82-5208-8f67-649fe984200f |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
683ab394-2abb-5d68-83ce-2684b9d3e58b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
e5a37c6b-4c0c-5fa4-b4f6-1a801e9b0ee8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
80af9e07-5196-562b-9106-0ab12d6078af |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
2a8ac952-8035-5006-ba31-56bc25ae5fa4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
c7acb0b3-76fe-559b-b45c-7f2234675bf3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
f03929d6-bc12-5b40-8f97-ecdd2de43138 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
d9ffd4db-1650-558a-b727-43c9a42223a4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
81a23370-61b4-50ae-a513-77a987009760 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
e54a910f-7ee9-54b2-9ba8-3b6b0cca7d83 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
d89d25b9-ff94-5846-9f81-a38f0bccd47d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
e56ead22-c41b-5335-891c-3fa3761329ea |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
e4f1aac3-0828-5eff-9464-8c94f1b726aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
63bce0d8-5977-5a9e-9f6c-efa8126f3672 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
e48d61b4-4242-5a7c-b18b-44488c070d01 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
e53c2795-0d08-5b11-ba7d-6ff5faa2c0b1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
767c2081-c94e-53fe-95c3-0a17d053f75a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
0052e574-ef81-5e86-84d4-2bf2083e975d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
fcb8ee5c-ac1c-5c6e-b604-e4097dc801c3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
e5579e5a-d168-53b7-b41b-4fd8b8ae8dd5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
e97627f3-0e80-53cf-9f51-10a6e73693cd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
58ffe9ba-cbc9-5bd2-89d6-f2c4ed476152 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
2ae169b7-a30f-58b1-ae08-6adce5df6a27 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
b9625c12-bff9-51cd-bd9c-48cf42f567b2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
f29d328d-93a4-54ef-9b09-9cf9bde2bf6e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
c2d4005b-8a2e-57ec-af6b-8c0383495b00 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
b724c47c-6da5-5aee-873c-fdc0bbe9619f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
179db56d-2c25-52bd-9c32-199ab4fdaed6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
31cf5570-9491-512a-bca5-74a4f7730e71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
e0353dfd-65d2-50ef-8de1-666fc67131e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
42824384-9abe-5992-b4de-099a1ff00bca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
cd3bfc7b-275a-524f-852b-9b138b6b1d38 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
0649ab40-9590-5cb8-8d65-26eff91b5102 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
b0055a99-afc0-5ab6-a188-7a9a58cbce3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
60c390f1-aa58-583d-8430-de988dbaac61 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
3f4dbca5-fe98-5414-8669-50f8adc6dbe9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
8d26bfbb-db12-5dfd-8268-b388772b9a12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
c8fdcc8e-211d-5fa1-a034-2070d8cb2b6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
73744383-cb94-594d-be55-964d9d9ea9c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
e5dbc351-b0d7-58f8-a579-9d0b89aa37c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
3200aec2-e1e3-5e37-9685-8146e8805ff2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
359e37c4-52c0-5a1a-a395-64c5bc6ae8f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
b27d0c7d-944b-5243-afac-5e745ee41f1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
55fac720-355e-5a17-9976-0b253dd2a6d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
00d96906-4461-5942-9b32-1fe52c6ff489 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
621bfb96-6e03-5dd5-8786-2171489736b4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
aa2da73a-8c8a-5ae7-8fee-6949a97d64d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
4c25b6ba-39f9-5362-8426-0cdc0e0f3dd9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
1dfa5691-7f47-5985-b30f-20ccc3096f7a |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
e9c54eff-b6cd-5d15-b8b9-9ca8b88d62bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
17d1694c-e288-5713-9d18-982aa3d6c101 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
ed159fa0-8788-50e6-b6db-162738fa3179 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
138a48ed-7693-5bc4-8936-c537a530f224 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
088bd3a5-3d75-5277-b45f-0dc97351dbe8 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
17694f83-bdcb-46eb-9cc5-3253f06942a7 |  | not-started | ITP - Pavement & Surfacing - Kerb - Rev C | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C
d8cb8dbe-5783-5308-a254-34b48be4f477 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
43e8b9e2-aee1-54e9-b647-827f10562384 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
28c229e0-8ef7-5d45-ab4f-f46e994831c9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
149dad19-28c0-5446-a0ab-86ef13406638 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
b2ab939c-ae82-5596-b8bc-8b36397b0002 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
e90e31d8-605a-5e9c-b583-08d152dc8c42 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
0019b77e-9af6-58bb-b170-b63ce19bfe81 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
8fb230c1-2a2e-5f89-9792-78a783d06fe1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
e365fb2c-b659-5cae-afe0-edd7f37021ad |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
0def1cde-1b7d-5014-93a1-c224f65be9cd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
8d00512b-7dc7-5f00-a33c-2df028acde09 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
a74fbe89-ed4e-57c7-b3b3-9a601ede7c55 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
2ab1f9a7-9305-5852-8e50-c7a0de7edd80 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
8cb636be-e115-5895-91e5-9ecd38856621 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
69ac9405-1f7a-536c-a5a9-6aa72efba8e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
62c413d8-5b85-5374-a818-dc6fa283899d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
9549787b-bdd7-5660-b476-c7d175e4f2b3 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
ff330786-ecb5-57b1-a72b-2f51a6710f90 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
3abec916-d0ce-5e24-87b9-1a589a515780 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
18b276ea-ba75-542d-8449-007911e9f3b2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7d41b51f-b98c-548c-b895-3b152669eb27 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
a1ef1d79-709f-40b2-acf0-e5cd6b381eb0 |  | not-started | ITP - Pavement & Surfacing - Basecourse - Rev 1 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1
f41448c2-d5d0-50b4-bea4-a6cda787e9fd |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
f0a862fb-04fb-57d2-86c7-1604d583e6e9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
3c9545dc-b233-51ab-89dd-50781b67c6ed |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
e5fda88d-94f8-50bb-a6f0-eabd1a3cf424 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
7676443e-967d-55b7-8122-8a37f8f3f62d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
646f654b-9fe1-5a99-8a65-6660ae8ab121 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
d2ed8788-251e-548f-be24-7d2ba88fa96a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
b0b861c8-9a02-5f63-bfc1-3ce57a74c695 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
23b01c30-6d5f-598e-b018-ef7eda81d2b1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
80b80537-f5f9-51f2-bc7c-c6829e1c9694 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
7a779e70-0390-5c5b-aa8f-2efd2f6a043a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
46166d4f-5454-5b71-8b7d-5131365740dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
d626794c-1412-5859-ae32-a21076e812b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
04cafb72-0010-5161-a890-dd6768edf245 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
a25a9dbc-30bd-5760-ae58-694d4a1cb622 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
a6ed999d-a7b1-5ea9-9ad0-003aadf6b077 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
3cf58c6f-155a-5e19-90bf-15617f30e676 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
bce01eea-f6c2-5671-ad5e-9b162d890b7d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
3c5c27cf-b954-5e4b-acf5-0255b89569b8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
52649e6a-223d-5cba-841e-ef492adb2478 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
54cf955b-fbbd-5ae8-8fb0-f4ac01f61a6a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
e6715326-3c7f-5a8f-92b6-9140dc48de1f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
ea156fa6-032a-5140-94c5-8619867308ee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
7249b270-4fd7-591d-858e-3d8d4b706f8f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
6e5355f8-729c-5348-be32-82e943bb2bce |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
a235b649-0948-574b-955b-e8ba77a960a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
d04243e2-58c7-5110-ac17-e38ae0ee8f70 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
ca065288-73b9-5401-926f-4893553d5d84 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
5d514f3e-5077-5049-b557-da3b2022a244 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
370d2da5-d8f7-5e84-b497-2a01e26dac7d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
6f9dccdc-8c7b-5c2c-b8be-a9a7f0dc65c7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
e2f7a61d-772b-5842-b665-bf915c4087d6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
70576699-cd6b-558f-8dc9-3eaa8cb37f5a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to EGB | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
088f72a1-b71f-40c9-8246-c9f3d5cd41f9 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2
d8d56821-98a6-4d90-94b3-83776861e78f |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600
1824002a-8f68-4a51-85a4-02adfaee1c1c |  | work-in-progress | ITP - Pavement & Surfacing - Subbase - Rev E | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E
78336d41-8441-50e0-b517-22afcc403381 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
b7e5bc85-4234-5477-8def-e23be9c043da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
295c45b0-eadd-5293-8064-4c0ead6dfc01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
724672c2-8323-568d-87e7-8ed724ccd442 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
f194846c-5e8d-5b14-9a19-15f8f21325db |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
a8b3d0a9-cb72-573f-a0cd-d980dac1db47 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
34f79574-1065-581d-8aed-a1f5b32fd261 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
c79357aa-ae60-5858-a4f0-894cc2314a0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
7a17331e-5b85-5179-a1a8-32d7b096d318 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
79d5c210-ab00-5448-97c1-870ed1f901c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
67b62953-6dcc-5306-a082-92ca899fd5c3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
ddecd55c-5b43-5c35-9805-7311e2f15208 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
46b5a6a2-faef-5442-91e2-b2c8d9722790 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
a5ab4697-e097-50b0-b7f0-efef7db3a768 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
407f2ead-36f5-575c-b9a7-3e1e75642c7c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
a3cb25c1-01e4-56ea-8623-d3a973144f32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
3fdfe87a-3424-5c4b-b85b-f3d772c86262 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
b81dcf9f-c79b-53cf-aa08-36ad1e2a870d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
8cbd06d4-9df8-5219-a28d-20c609682f8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
2c6fdcf6-cb83-5258-91fa-cbe17ab97bf2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
e4bb12b2-c92e-5509-af12-acf6c38ce82f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
550a5c7e-a3f0-5a58-a135-ccfcf00acc22 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
c4c8c53d-0197-5db9-b535-524ad0ff2376 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
97a25a40-05f7-5bf9-a151-3d0db9c9b27d |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
6b01efa3-52f9-59c2-876f-5650f1f964ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
61ac62f3-4970-5323-ab7c-fd90daaf8a12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
e08d0fd2-58c2-541f-82fb-108b4e84e8f1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
57421662-16f4-5234-ac37-84874b43bed4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
747c68b5-7811-511e-aac5-7ad437daef57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
f1cf74f3-a813-54a3-b098-ad9d07750f9c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
8221fb4f-0184-5948-8784-975cc0f0a58d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
039f71a2-3eb5-5e5a-9d3e-68e425baf53d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
0c5664c4-80c5-543d-bc19-9900a8e5aabe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
d8a290fe-97ef-5c69-801d-e51ff4be4252 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
fde99716-31c6-5154-b242-e10623142fc7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
c3de4841-93eb-5f6e-b719-e23acf9b0e49 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
f5a975b8-578e-5d72-8cf2-983a9939d762 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
bd53cafb-c2dd-5de2-a8ee-3a82d07c0941 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
3aa17269-7407-53d0-985f-743d365b60f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
8bb65d26-5064-5d82-a1ba-88d3eeaa22f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
ba6b0fe9-0f52-5f73-a893-bc47efd2eeee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
0069d343-ebdf-5043-bed0-952c1d0ca05a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
df211181-ef0c-5795-b32f-da845d9273f3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
8905f88a-dcc9-5837-acf5-19002adbd673 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
02f30a86-dcc8-5622-ae65-bf5832635616 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
ad5d7e40-f611-5c95-8a88-e67eabd9f84e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
5056ebd9-59fb-5803-bc6a-7dde92ebc4dd |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
618f5e44-ed19-5ec1-afcf-030ba86c2c6f |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
188e4b48-9e94-5379-bf21-65c7ef0fbb45 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
05e0e3ae-0bef-5f08-bb03-472c072be553 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
61a4d781-086b-5600-83b1-5b1fc6bd57ac |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
919fe1eb-c737-5c41-9ef6-917f7fb297cf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
038fbea5-d115-5164-9330-8bdfe75435dd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
df5a2495-3ad6-5c23-a755-7aa0d50f779c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
d51f44b2-afea-5099-85e7-5e63ae888d8d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
97b813a7-a59f-5142-8655-f266bd975601 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
cc054f0b-ee4c-55bb-b83d-439936677318 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
79356d6f-1281-51f1-846f-9154eb665085 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
8939635f-c588-56b0-94f6-2ed8f4b8f49a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
8a3da342-f77e-5ccf-9c38-8c34b17e5818 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
08edcd4f-c960-511a-8c48-f7025c668957 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
06b0c891-ac43-5abd-9472-a57fddb62cf5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
b0fca313-cc87-5854-a069-d31f397d5521 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
46f63637-e77b-5449-99da-a658bafadf74 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
51ce72ac-bf68-5a23-8c0a-44c80b047fbb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
9ad3c77f-f5f8-59db-a0c4-04978b0824ee |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
0c4f23a8-6a6f-5641-b600-f095d8477edb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
249c3cb6-e1c9-5413-9d36-2ee92d868c36 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
f7dc5371-688f-5812-8d65-01e8ac79b327 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
a2a6146c-2467-540a-84a3-a366df98b900 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
8e7e4304-4204-578c-b02a-38d86a645649 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
e6bc502c-6a86-5151-bd02-2cba7b773f8e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
7420c963-68e6-554f-aa23-7fcf0e576cdd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
043ee431-2b25-5518-b264-a309ce03b409 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
df358df5-9350-5a94-886c-3b9e3ebd462d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
92a12d2f-ab26-5ddc-9b17-0a9ffa98573c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
5818ba5d-d095-513e-b39b-513012e4d894 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
a166fb73-389c-41f6-a761-41bccbbf1a9a |  | work-in-progress | ITP - Pavement & Surfacing - Basecourse - Rev 1 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1
5a058c9f-1336-5bf6-9fe7-b5e8d19ef7b5 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
b9723a7e-e6c4-5a9e-aa93-738a21c55aec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
cddfcf07-4bd2-5113-8224-b912b7208851 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
25b96580-750c-59d6-aa68-aa82a3227cd6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
427c05bb-e378-5016-8e44-4a9b52245064 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
0f56b2b0-673a-566e-9a56-dc8fbff81ac9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
43423757-c229-5838-8fe3-f748c307ca13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
3495ccdd-b075-5694-9bca-803984fd2b4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
10efa153-111e-54cf-b2fa-b10196eb099f |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
e2da3a2c-26ea-5c83-8344-2070597b348a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
4d8c8b2e-3692-5171-ba61-49d071d77872 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
f650b3d9-d78e-5b1e-8f74-f543cb28add1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
7e228255-f35a-59cc-9578-e0b9c4d74f17 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
cc3e1dfa-636b-5437-8e22-e9a2b1148b67 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
8920dbf8-e71c-56cd-a47f-1d1c6b0a07e2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
ccb08166-5222-595d-830e-99e88b8b2514 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
9b608003-3e33-5698-a4e3-96b0635f3ac2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
5d188d80-e50a-593f-8bee-6527108356f2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
9afa298b-9aac-5b4f-a1c3-bcb64035e552 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
71cd258a-daf7-59f3-8db2-9cf97c55a81a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
8b980b45-dd98-59ce-8df5-8785f675f96b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
f6445882-156f-5e47-89c2-3217c505284c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
460ae273-2253-5957-ba7c-51d6285ceff2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
3ae00e90-dcf7-57e6-a398-4da3d5cf62ec |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
7dd2b4d0-85ee-5076-ac68-8100f92c16b7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
182d7414-0424-5690-a3e0-143189945d0c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
ad573f19-4202-5879-9f32-278b5b6cf094 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
2ea91ef4-1d09-54e8-b8b3-52b3410ffff3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
8e16d5c2-39e8-5e8e-8b75-78c27ec383b5 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6a4470f3-085c-55b2-8304-f856066ea067 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
8b8261ed-fa0b-5fec-b9ff-b805d7caab58 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
45b7b0c2-c938-5b1c-9f6a-af4a82802e74 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
079f8eb2-7c48-5d36-b79a-b472a62a4d9f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
67d16cef-7541-4f60-9709-6af1341fd88a |  | work-in-progress | ITP - Pavement & Surfacing - Kerb - Rev C | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C
d11f48e7-6328-54df-91d3-8420de065298 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
f552b800-8ba2-52b5-890b-add1bf1a80d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
47b2add6-b5a8-5c5f-aa69-8700585f92da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
5e4188db-d0a8-5cbc-86f9-ee723dbdd87a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
def3423e-c456-5a0f-9d9c-4581dca57301 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
28545cd8-69be-5771-8c08-b043a834fe8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
654ef666-89a2-502e-8d8d-e9eb77aab479 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
86434678-54d6-5725-9233-e24be9adf107 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
9023573b-e84f-5b7b-aee6-72efd5d88dc6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
3009cd09-9934-52c7-bff1-b393ee8fb4ad |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
262dcdb9-7cfd-50e2-9ef7-e1887b22e81a |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
ea0835d5-f147-5bff-9cac-72d1272c7341 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
4bff6cc7-f387-5c85-a978-521fe10a8856 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
aaedd17d-7a3f-54cb-ad67-f5614862ec09 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
a9e45daa-15d9-5fae-b149-dd2c25151600 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
1b4f6bba-65c8-58bf-bd39-89ca64f31744 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
f063c18e-fc0f-56a5-abf3-ba7569331276 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
42b85258-bbc4-5b1c-970f-82d1fb66ef28 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
76139ed1-7f74-59bf-889c-03bc8d922da4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
962fe315-d91a-5766-9c39-b74a80993199 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e2c182be-fec1-531b-86f0-12e42672b63c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 2 | Pavement Type 1 -Area 2 - CH1180-CH1600 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
8035fc3c-9496-4e6d-887c-4a5cd136b375 |  | fail |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3
51d5769e-a8ff-447b-b088-485e587a2dd4 |  | fail |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200
03389484-f446-41af-a77b-8bb98c0920e9 |  | pass | 063e740830527b1dbf72a9fae99d75366e0cb00c6ea1b12172a94088440b8882 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E
f042ba52-9514-5554-8b17-c53aeceb2ab0 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
6c4a439e-345e-5664-b5f0-da66b7f570d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
0294eb48-eb4d-5fbe-a070-eb5eb4e18b9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
8de45c85-1e4e-5f86-8168-d36c7b3da24e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
8af81d99-365b-5f49-8e66-05d9fea28261 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
f85db0d8-36a1-5209-9e51-e2a1df190438 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
a3f95542-727b-5c70-a6cc-01910970e6f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
40822b02-b0eb-570d-be23-f965e77a53c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
4281742a-df1a-5780-b3b6-25a18d4d7d20 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
c8f52187-55f8-5618-8938-a5f569c0761a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
2296018f-e9cf-5b3e-9558-66a68518283d |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
f7869737-4b5b-500d-a758-6c912c2691a6 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
37817c64-a2fe-5c41-9182-f24964d9dec3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
21adc93c-b439-5c34-8d23-de3796cc6eac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
00e12f42-a4e6-5467-9c80-cb54481ea515 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
6366c4a9-0d4a-5ba3-a2fc-ed7b6293eb99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
e24b8883-acae-55bc-8fd1-7a50af46f8e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
40c3c4a5-677e-50db-9621-dbb1828347bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
5ed352c0-04f2-5780-acb1-2978673f417e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
b1c87759-98a5-55d0-b46d-18fb7b5cedca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
0741c91d-dc05-5b5a-b472-3580c18c7562 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
dd0b7024-af57-5e0d-80d7-ad601bab78e2 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
d2192780-ae65-5a4b-bfbb-37ca9cb409a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
fea17023-fe72-5ff3-808b-52a3e4e40894 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
347d61b2-55cd-52e5-8f5f-c2080150535d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
8cbb5b4a-ccfe-5e26-9902-d96f9692399a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
e61ef7e5-230f-5a61-97dd-d73f150d9c52 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
e603e9ba-970c-5ea4-ba3a-4ef36a3b089c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
69d97d43-d2c6-5194-8efc-c505dadf1529 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
34f9658d-b686-53fb-84e7-3305cf307755 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
7ca271f0-0a25-5446-8265-15d03acbf37b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
adbb7e14-9cf4-5814-a486-a8e7cd22013b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
cd1c925f-e221-5006-8df8-b885e9c89387 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
963bf6de-cdd6-50ba-98c3-f313e7c75df7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
7b270a13-d12c-5518-a316-2fc834f2ad80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
eb586165-002d-504b-a336-f9b636f12de8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
d2de3855-0a4f-54f3-9b75-575ab20628b5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
9429c711-4232-5cd8-8330-dcd4af9c02ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
7e7dcfbd-de8d-5f0a-8b5b-04e006abca91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
f8dac153-4800-5f64-8e72-fcafa029d4b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
0ab3706f-67ab-5033-bc19-91fb8bb17282 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
8a7c21a3-17b5-5559-959b-924a18a398d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
7ebd08e9-2f16-5985-b726-a15186a815fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
51592843-7a8e-53f5-b74a-827080cc8f1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
86557e20-8f70-5109-b531-fda00b16aef7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
681e0a36-23f3-5186-b55d-99e2f075fe23 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
7c627332-58d0-54d9-a5a0-4f82dd28567a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
d8a7948e-6985-54b3-bb2a-bd89f22c5a32 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
9f86ad7d-2663-5a7c-ac86-e0a39b3dce15 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
7e67650f-9346-5ff2-aeef-3886e5387b59 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
3599955e-f601-5748-ae97-6d1a619c68f0 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
ea7903f0-7fcc-53c6-ab6e-31b9f80e3263 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
c119f269-1bec-5057-9f7f-2630753979aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
5a813eff-d48a-5c1d-80a5-35bff3662c37 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
15012ba9-b8ab-5868-9ebf-5df87459eb1a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
db1a2e45-d0de-55de-b061-601128eb21f8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
4e56eaef-9e66-552b-8049-e4ec04e560c4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
70f7eead-99dd-5a27-957f-fc281d1a254b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
583151a3-265b-5d56-a0bf-9624df1d50b4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
2eb4470c-ee8b-5adf-8514-db88e111c975 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
e66f4c38-d3be-5d22-9c95-67c3dbf3db25 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
f7d064ed-3b62-5b7d-8dfb-6c65d241c214 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
c3ce2bbe-f895-5dc3-bb15-590b13e2a00f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
f47e6d1e-3bbd-56b7-8ed4-b6b889ffc1f3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
d96bee57-8c94-5f10-8455-ce6e374fe0e1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
7e3e91cc-39db-5a45-8d18-59c234b51b95 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
9687a070-8eee-5bc7-99a9-652cccfaf020 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
f0934261-4050-526d-9649-bb18f012d8d0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
4d14e1d2-f21a-5a00-9fa0-e5bb33597bcc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
ade13142-1765-5817-abb5-7e030c4cb3c1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
c6f22be0-9068-585a-aaca-d93dac0f8ecc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
cf24bf30-f0c1-5921-aa69-9aa799e56c9b |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
2aebd0a0-d0f4-5ef8-972c-2af1e55cf1ac |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
dc0edd5a-fc0f-53f6-b8e4-829e725b4f52 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
852fdacb-7e05-5feb-bdfc-f2bf13fe84d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
b876d434-7432-4ecd-93fa-3b2c2fea9c1e |  | pass | 1e583f8b70273eabf004fcc38eca8c02710d652e820a3ccc1f9a151f83465210 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C
a2622183-3803-5172-8585-b4e8744b7ca5 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
76d4aa37-41f2-5c02-a205-88dc7044586c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
989cb1e7-adb0-5a34-beeb-2d935dd718ea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
9ad89c66-7c67-5079-b4e4-9cc1f23adf97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
ef2878be-5ffd-581a-9a6a-f259099a76db |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
d9343a85-6a4e-50f0-9806-7f958d2d16d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
f01047a1-59e0-570c-9e94-2989f05af286 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
299a76de-3773-56d0-9815-6e117e16cda2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
256c04c0-4f05-50c7-9a00-2394df42a84b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
fcfc3485-f81a-57a4-8799-826a15a798d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
599b4e72-d153-5639-9f75-88b641ff9136 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
a94fa051-7550-5825-b483-bf7910306000 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
6a014f57-0206-594a-9cd0-1f2984af26c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
b25d2c76-80ef-593a-9e09-2aac9c166c4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
a0c620e3-2ca2-5b89-9bb4-96015619fb13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
b19c555f-0d77-59a0-8aa9-d6d588430270 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
3c613502-5e8a-5df8-ac9a-45f40dc26cde |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
379a38f2-1687-5e80-9aa0-63e11ad83416 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
a30f4330-0ed8-5d0e-8d52-b5aba138da34 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
0463d09a-c7e4-483b-94c3-f66074c3aa75 |  | fail | 63b1e491901cfe89030f9bfcf85c2fe0f9b00560a68517104fc1e1b1037eef12 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1
e2ee9be4-64db-5145-bc20-f65017c29be5 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
4411f630-5b9d-55f7-8c96-a232e3cbfc92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
c8834a3e-3d83-53df-b1bf-acc7f1b165a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
6a8d7f36-1df0-5bd6-8fd3-3a255d5d5323 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
10f2cd59-3203-5502-9a7f-e813cf76304b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
d412f72e-36f5-5467-a691-80b2724bf9df |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
d0cb3fbb-a4af-5fbb-b416-86423a6aeb3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
4a21a81f-70ba-5029-a590-fc93963376b5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
b5f2d86a-37ab-5b51-be43-7cb42bfe6c7e |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
f3c9e5e9-6d26-52db-aa9f-7b60afc8a959 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
56a1b906-30ca-5561-974e-236a58630ee4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
dec86f4d-796d-52ec-a4dd-e33f2c2311c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
b542c2e3-cd13-52e6-bebe-e9791dc067e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
1fef5eb0-6d59-55c9-a5d9-83c9848e5468 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
a3d534d5-fb80-57ef-931c-5dd3d1a9faf6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
814eb665-ab80-5a65-b7e9-72473703c9cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
c48fc805-6d51-53c1-add3-05c6448f0b25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
8bf3f39b-fa8f-5b30-aa47-9e7177a2e0ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
20f01b9a-447f-506a-889d-6568b202f678 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
2cc85d52-4f02-5cf9-ae95-7013bff1b452 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
a3aebb5b-5da1-5a40-a773-31582017a252 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
1e29d754-68f1-55c9-b2b2-2dc3e50c146a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
70c26ac2-f911-5116-aa34-b03c7da168ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
0b1ecf96-20af-50ab-b419-05b71304fa57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
e07b935c-129a-5749-814d-8059c81a3914 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
a23967ce-c273-5f39-8cd5-1d2b0a84b253 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
9d95c68e-56f6-5c2e-bf73-557e5a66017f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
a75d5740-ced1-5d46-a809-be598dbbf03f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
2663cdc1-e55c-5e92-8f2a-6c1407fa27a8 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
90045f6f-5c6e-5d4e-9777-664d2b5f8aa2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
23377982-23f9-5293-8044-3224e50b074b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
b2a25b87-405b-4f53-8620-070a1cfad064 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In)
81e42605-3484-4a3a-add9-38b2bc031e3d |  | work-in-progress | ITP - Pavement & Surfacing - Subbase - Rev E | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E
6457f361-558e-5f5c-a259-827f6a1b0c08 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
cfd641a2-b4f1-521c-b601-6d68abb61420 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
be7731b4-920f-597e-843a-1737f8f21168 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
99578e92-5f5c-5437-8575-a96d8d5d9668 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
5dfa7669-1794-5308-8606-29f0de08c579 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
96b68cce-f2b3-57b7-bf2b-3a4471c452c6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
e65054d0-1918-5d3a-a2fd-f025029bdc82 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
02d28f16-b804-595f-a599-86c77d2e6378 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
d2cdb4aa-f526-5a96-9603-c5d22502e581 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
d7776b8d-ee23-5c6a-8a38-5f8313ea5a48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
3542a550-eb11-58f5-86b4-63a740ce7009 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
2ecf466d-b223-56c6-9864-beebc378996c |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
93b209dc-942b-5856-af5a-ff622f9e6518 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
668d0477-dee9-5a18-9d9a-8a6f0efd104e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
bf81c52d-1a8f-5364-9598-9ad304e5f932 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
4aa75a1c-3d21-50e5-ac25-929eaa23497e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
cc533d07-b49c-5310-afb2-51355e7828a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
63faa349-3186-581f-bda1-008a91cd61d4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
a7bc8dfa-6003-52b2-89f1-dc76d353e2c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
2c79d92b-6b30-5572-9745-fbd4f3517ee1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
a410c36c-4a2d-59b6-b65d-c6b1da794610 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
a49ad8c0-d3c0-504e-ab83-7d8ba994bb98 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
3b5e379c-30d5-59aa-a47f-baf63fb1111d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
69ab28ae-96f2-5674-83a4-51c1f14d022d |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
a658133c-88af-5f5f-918e-617421d0ec4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
613c3480-42a2-5dd4-a2ec-8cc2fc7f1995 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
8ecc4b37-3c22-55e7-ad00-960372774253 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
a2bfa6d4-d503-5858-b4ba-0c7be9c21c6b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
ea04a0e0-d56e-58ff-89a0-877edbb280a7 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
6eaed945-a8ff-50f4-b09e-1d68cf3ac042 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
6440be6e-6063-5ced-a579-b9c61942eeed |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
7a6cb49a-7a07-59ea-a460-ac6718b0effa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
2a5e3d32-221f-5d79-a404-65f858b3bb29 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
89a12ed5-d864-5a5e-80ec-4d5cefb5da08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
5db95fee-aefd-5638-9e5f-1543d66766f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
c9f0824a-2df5-571e-bc88-c8e4036c6e60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
bc70e898-0c1e-5e41-afc0-d47575e2782a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
f06094c0-fc37-53fd-8d14-3f95cec926fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
86856568-e1da-56a6-b73b-7f11bd0c7e5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
41640124-4906-53dd-8c81-92d2244c40f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
94e21001-5a1b-530d-8c83-c2c0a07ef1d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
9a84c3c8-20cc-5bd1-aa47-b5373ce006e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
07654168-bd28-5ae4-8902-75eb59371ec2 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
3ed25865-506a-56b8-be93-0a049117b14f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
f7404e76-61da-50d5-9970-cba4bba5c519 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
d0232a04-a80d-512e-9b8d-08b5f5adea67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
4b745ac7-fc8e-5b8c-8ee4-9d6b9c244963 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
e765c380-050c-530c-995f-71323ea4919c |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
f9e5da08-a1b9-5112-973a-20896a1f62ff |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
2ea52a12-2d92-58a1-83cd-378cca34a16b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
6a8240b6-a0e3-565c-8727-5b292da18051 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
096f0616-3879-50ac-bb04-1fc85c05f19f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
0799f687-7586-59c4-a41b-7d46f305717a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
89fd4c53-9a7e-5b4b-b52f-79bb854d7f68 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
7c102dc7-c41d-5fc4-9678-b6473bf2a869 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
77e3aeb5-c22f-533c-8d1a-64c40e92e944 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
26e9f52a-8f46-559f-8c12-9e84408f3be3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
2c82664e-f98d-598b-8b2a-050ea32a31b7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
0175f645-46a9-5496-b7a8-85aa4d462773 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
f5248ef9-6da7-53fe-b9d8-f2be9664dad7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
eccbfda2-190f-5cf9-abfd-bff9529a4193 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
16ed7405-24ed-5395-910c-1e3b7ab18469 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
0bdf9d85-66ae-5686-86a1-2eed1cc05108 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
51339d83-fc8f-580c-80c7-f65f6aced3bf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
74b2de84-0cc7-5eb7-9077-1953adfc241e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
5faadff4-b195-5221-9598-d6dd55ddee6f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
c420480c-e018-5830-b026-83fb314c5bdf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
cbad3d37-4c0f-5500-8c81-7fa45f5525f6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
e81af5d5-f4ff-5580-817e-82b5d4eb528f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
b8e17e89-006b-516f-99b7-6bc51ff862ac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
01e293b0-907e-51b5-b3a3-700dd6e23b22 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
86d7428c-f8b7-531d-8c9b-8de26a9c1f52 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
c68939c8-cd2a-576e-aaad-8ae1473aa40e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
4d498a94-bf47-5d74-a172-9f8cefe07d93 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
082698f5-a10e-57eb-bd35-39665cee262b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
fdf31863-bee2-5aa4-82ef-778c3e479c42 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
3bce3922-bf48-5bf8-8169-e32e4e31faad |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
678f60e7-347b-4647-8e29-dfa3cb7be614 |  | not-started | ITP - Pavement & Surfacing - Basecourse - Rev 1 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1
5ea428b5-198f-5e86-8f48-8fce7a772c6d |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
13a6cc59-e52f-549a-905f-9311b8caffdb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
920a6d0c-c946-5975-81d3-b59742045ee7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
8539a531-7546-5282-88dd-67d40f7278cc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
fd80542f-8db8-503a-aa07-74d98bf71129 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
6428b05a-7087-5dfb-8aa9-dec37e21e005 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
61ee192c-c334-5d2c-a8be-7160467313b3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
03128f6c-f29f-52f2-9962-ad6bb88ff840 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
96f7c3d0-af8a-5e34-a700-bd44940e151b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
d8fa4c99-cbdd-51d1-a064-65b1dbe9867c |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
52c83e20-cf39-5534-84c9-7a7c5ec94773 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
9554f015-747d-59f8-bce5-4709a9eb776b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
9ad67cc8-d4dd-53d3-a35e-f418ba2c225b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
10fdfe92-2391-5cba-9a23-7ecd8e2fe008 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
dc517417-088b-5396-a877-f7c2bf9b9037 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
3e3e50d7-b373-5cc5-a0a9-cee0b68334bf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
d81e882b-a1d8-5bbc-ae77-69d104a4d1b9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
a8153d91-bdd4-59f2-a9e4-a0fe92f01ccc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
82422671-d1ec-5dbb-bebf-b6fb890f36ee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
b41a15ec-d74d-5a38-b709-bc70203fe8b0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
ad516c47-9bd3-5faa-98bc-eb86a8db7595 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
d21c06fd-0124-5749-9263-aaaf8d8ca48a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
c3be7bce-a242-5b27-a4d2-dcd2555300b6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
ae52d180-4064-520b-82bf-57bc22cab880 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
d3fb01dd-7688-5c26-8ed0-9b0166073968 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
8837ecf9-5236-5eee-954d-98726b83d725 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
bca48654-17e1-5c49-83ca-7574bdbc99dd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
8fd78672-0f08-57a9-adec-46fc4d37b862 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
34ee90ed-2cdc-526c-b1ba-6393fe8855a0 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
9b989b13-fd9c-5bdc-9f5d-de8bb47c9f0e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
fd74a7a1-5610-501b-a669-2418bb49597f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
fcb16ac0-c48d-5f2f-9b22-a2e220f02375 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
88a67217-a929-5751-ac94-40e77be8a7c6 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
0aff54fe-3bf9-4a32-9907-8ee7a1ce62e0 |  | not-started | ITP - Pavement & Surfacing - Kerb - Rev C | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C
a946d55d-9800-5163-902b-4c0af6e2ba1f |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
52cd162f-b95e-5d7c-9630-9129282e9c08 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
de857022-8ed9-5908-a45e-97e256b54836 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
36db8ddd-9469-5aa7-8887-898407ef259f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
e3acf8e3-a7f9-5999-982c-258315ff979f |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
e421e8b9-aa35-5d08-849c-1d8ee2f29e8d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
3e93affe-4b11-5fb0-89c7-170166f04792 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
5eece408-0280-5f82-8142-c8f90fe8598c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
d5cc439d-4e00-5557-a066-398e1c453469 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
ddaf7e14-22c9-5654-bd65-79347934ed2e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
bfebb66a-0ecc-5d85-aeb2-c6de18bb5ca2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
1b48e4a6-c8f8-5517-bc9d-bfe0807a13bc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
bc1176e3-e38c-5cd1-877b-f3e95b5893a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
a77b3234-e554-5d4e-a0c6-f349dc5248c3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
a28f0821-afa0-5090-830b-ce5aa4371cee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
29092038-5af1-55ed-8238-be7bfe19e62f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
7044f330-f348-5145-a8d8-45a32068f9b8 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
4e37609e-483c-5e7f-92da-6a17ea8a7526 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
b5702cff-edeb-523a-b6ae-c34b0d7c7297 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
50685cf4-dd68-50bc-9afa-c0aaccba7681 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8ec38f7f-3e69-5cfa-944d-701aacb47e69 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1200-CH1260 (Bridge Tie-In) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
3efc2658-663d-493c-a382-7434e5afc466 |  | fail |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road
7d79c7e7-252d-492c-8f30-a6b34946fe4e |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860
699b497f-1d1a-499f-96be-75dcbd674b10 |  | pass | 063e740830527b1dbf72a9fae99d75366e0cb00c6ea1b12172a94088440b8882 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E
55358423-1cbb-52cb-a3de-6df9cee3b040 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
0c34468d-ce4c-587f-9149-c2314836e20f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
029ced71-ceb9-5009-ba9a-3bf1080e0f19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
5d2108af-8bdc-524b-a42e-1a41c40bf5ab |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
3c1d86c7-f18e-59a5-8318-0b16932357f7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
570909b0-98e7-5f63-8178-e6f9101b6b54 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
88150f2c-568f-500f-993c-62233ac12ba9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
b909aa1c-3520-5602-a1d4-36804e9cd065 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
f6c1721a-ca67-5d38-9c66-af068a1e1ca0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
a09af57b-aad5-58eb-9cb4-c5a41f85bab7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
e734c46c-fcde-5942-9271-04ff041b88e0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
0afc0678-496b-5a23-ad8c-78ff54bd7bb5 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
b3faa7e2-6a03-53f3-b732-84564048ff32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
668457ce-3a7b-5252-895b-a9cf44367c45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
43f9a4af-6532-592f-8dda-6529171cfe63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
8a71c6ba-d469-5f31-aef3-958d8e9a249b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
91a943f9-6949-55b1-9113-ab4cc8f90e10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
38eea497-a645-5356-a92a-e5f00aa9df07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
5249f0b0-d6ad-536e-8f50-c6d6bcb9f44c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
e7457e94-0fcb-5744-aff8-e9e104912241 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
e27daaa4-1d5e-51bd-bad5-3266fe67106b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
d3686dd4-a6eb-51c4-ad3b-d0b50a235800 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
713ccb43-cd29-5e31-9e71-2ffe978235a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
00ddd4e5-88c5-59b5-9a47-6a8161228a70 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
5539dada-77a4-5d54-b078-f4b591e1471e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
54c159d5-7f88-5e4f-8210-908cdaa825f3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
0c64597f-fd07-5d18-b9d9-ffd6ea8679fe |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
0c5b3b7b-d434-517e-9569-feeda79ef698 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
36a4a615-a75f-5073-b358-1476f807e013 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
47ae1aa3-0d34-5d58-803a-19a9d1f92444 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
c7cc6faa-86d1-5abc-b9af-41ea90b201fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
2588cdb8-6a5d-52cd-b31a-0f5768467a53 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
32bbfa96-a0d3-590a-afcb-41a428bdb0e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
dc8a6165-a8d5-552c-9789-bb1155df3fef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
af36e06f-2088-58d4-9694-0209fe84c5f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
2db1898c-dd2b-569a-8bb8-460fcc9395f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
8fe36d78-a5d8-5516-8221-1b06ddaf6e06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
1e4e3db5-6ffd-5db2-8c52-73d2075a29d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
c8140009-e6c6-5610-ab96-03c7d00714eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
fd901a36-ffe6-57b7-88ab-a84321733230 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
0c143250-7948-5ce6-b7dc-3e35837e0802 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
548059ef-d5a4-533e-b16e-0612340ff756 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
35b9e83a-b191-5ae3-adc8-b7fef8b61449 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
d8a8ff19-e547-5b46-97b9-f5c942f32b3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
5409eed6-885e-5628-b1d0-312f2b5a5e9a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
90c3af51-277d-58eb-9e27-b1b5a791960f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
4137b2c0-1351-58ec-9766-c7372d6aacdf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
3f125d69-d86f-5ad6-b67d-bc1e6aed839a |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
b6df41be-e7cf-58fe-a22d-bdd735b47be9 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
ab85d5d9-d88a-5295-a9f4-4c9757baa698 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
7906ebff-a7b8-528f-aef6-15709f1cac90 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
000cc2be-55f3-55fb-95f0-b7acbd7cd57f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
09f43a7e-55c5-5a5c-8253-63165954b4d8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
936b65c3-f063-5e13-88f2-01d1aa91a38e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
74d4bb84-8d9f-57b2-a2d4-9cccfb166e85 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
e874258f-4ec6-5eda-92f0-8870b7a66712 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
a7d6b19b-ffbf-5ee7-a204-0f8419cfff96 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
fa66d065-ae76-5897-a1cc-abda768f9de9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
cebd4087-bc7c-523b-8497-bf832876d934 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
a50c04d9-fc71-54d1-a32e-2ee885040887 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
234b705c-43d2-5ed3-9640-559c5af8e7c2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
b38cd96c-0c50-593d-8608-a0187fbc76fd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
fc0a0589-206d-5d1b-b167-f5a5c8fac830 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
4617ec32-c8f4-5419-8ba8-5f7cce11ba2b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
9b2bcff9-f54f-5c9b-846a-efc3cfdc5be3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
1cc1f007-d50b-5dee-bdcf-267f4d0fa9e0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
25685b55-311f-565f-97d6-bf6931b3dd4b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
3efda1a8-c7d2-50a1-b497-3132f8560c1b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
cbaea039-7936-5d81-80d1-b7703af62d13 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
26472531-ed44-5b36-bde8-51b149431f41 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
c02cafd2-004a-5657-bdc6-590bff9ef3ee |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
43a77910-92c0-59dd-85d2-e010d4efd0ab |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
a96597a5-9855-5a36-9248-48b4be06b28a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
4ce92eb0-b327-5e58-82f9-2f9362a50b92 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
4ac43f0a-e7a3-58b1-b868-9492e524be03 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
df64af88-8fa2-45ca-8494-0186c85417da |  | work-in-progress | b863db18264ab499953369de7b16574a1a138b1aaa83c8bdd511bf3d8bcde8b9 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C
c48c2768-10e2-5b5c-8f5e-a91073902bdb |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
0ceaa9c3-5fb1-5a4f-91fe-bca8d3364545 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
f0623711-9324-50be-8925-0dca79b5be99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
b1e2bfcb-c4e3-57e9-8337-2e75d623b66c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
25db7f84-4ff7-5684-8d48-32d1c2f3e7aa |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
a22667aa-bdf3-5c39-a6ae-3319e1c4477a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
64803475-02eb-5aec-a65d-b6a0186e42ff |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
13fe703b-98a1-584c-9af6-961b70377d8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
7726a9ec-30c0-5c83-bd96-abcfdaec3a19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
d5758010-efa3-5092-9171-4a3d30b291f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
d556662f-23b3-5a8a-ad70-243bfeea5496 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
61932139-9824-5359-97b9-e74fc6054e43 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
31c355a6-db95-594a-9ab8-129d3e414c92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
262aa2d4-486b-529b-8820-80765703f15b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
793babf4-daa5-50ce-bded-2eaf7a9e9a3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
1cb01be1-dc33-5cdf-879c-0947a2822b08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
3331b11b-5445-5e61-bc54-2f46d4f37d38 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
f5468990-79b4-5d97-a860-23cfc4290497 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
eb49af1d-c9e3-5cb7-8dbc-2f5df0694e5a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
7fe4563b-b06d-4ea5-b4df-9f44ec20dc2c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
0c6dc88d-5cfb-5820-b987-bb3cb67d8e67 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
5619410c-bba0-40c8-860d-326e7e79ed29 |  | pass | 63b1e491901cfe89030f9bfcf85c2fe0f9b00560a68517104fc1e1b1037eef12 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1
deb2b8dd-44e0-5a63-bd33-49cb341de737 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
b007901b-02d9-54d0-8f76-406edc38f020 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
074aa352-2be6-5384-b281-897c6cfb2529 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
6d25fd67-f26e-5850-8a03-33d5edd3a096 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
e1909110-0979-5b8d-8a00-5048a0313cbd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
5b634bf1-1193-52dd-8c9c-321fde8f21f6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
855499cd-5f6b-551a-b7f2-05728867987c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
cc0ac939-4c73-5a70-8496-536d61aeab8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
a63b9ea2-ce85-5ded-803a-1ce2cbed7001 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
be973941-3688-5d3c-abc2-e3a58f2f62d4 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
e830150c-a462-530e-a685-f85d727f374b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
a55a464d-027f-50a4-9108-6a3b5abba154 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
3f032ec1-8888-5e56-97a3-7255284a996b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
c6c0b914-1ce4-5a1f-aa8a-db269cdc8f7c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
d9aef268-3d34-51c9-8fa7-319cd0b4ee2c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
8a2f1cd2-de74-54ee-b3cf-b5771a0f296c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
06d776eb-2f77-5bad-a598-d1db0fd26dbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
dcfcfac4-6a11-5140-9dad-12848fcf8bce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
9ae77f82-c491-56e2-9b71-b71ffe6c1ee6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
3c4511ce-04f4-51d5-aac2-4fe120251de1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
ac2a6ca6-cea5-566f-9777-4683660f8440 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
0b0871a0-69d0-59f3-af42-7d66eec358fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
2e62a223-8ced-55de-ae09-a63854c0e4f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
b051f37c-9352-52e4-979e-ca5430a8f4a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
e6a0e5a8-1321-52aa-b1b8-79953f6728e8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
9f32b87b-6a44-52d1-878c-0caf35e0b2ce |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
82da0d99-ffb5-50c0-9a80-a14b4528da32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
a40de67a-4f14-594a-813f-c93adbfdf84a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
e6a29ea6-10ad-5347-baa0-fd14ff9f24a6 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
9835d5a5-29ed-531c-ba52-395f621860bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
6194883b-dffc-588d-a104-1622fe87ecdb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
cf0cfdd6-b097-4a24-b108-55ffb023f264 |  | fail |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in)
692b1c6a-ac1c-4fd3-a6ef-062f6aac87bb |  | fail | ITP - Pavement & Surfacing - Subbase - Rev E | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E
1b963c50-7e0d-51cb-906e-5846c5296595 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
e34ce830-8859-5c75-9038-e01109699db7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
f3d7fa0e-1c28-552a-8ed4-34da0b47faba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
cdcfb1ba-40ac-5671-8b0a-f75614fa82ba |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
9c5eda29-3ab7-53a4-9023-eb54e7215ef7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
e1bcd007-edfb-5e42-b39a-d8bc4a8224d8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
c031386b-2117-547b-b645-34b62128a1e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
e8d1d243-928c-581e-a2ce-ea29f71e414e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
a265b09d-3888-5220-a8d4-cba69cbf7303 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
ecb935f4-d364-57e4-a6f0-c1c35ab50c89 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
5ddd1bcb-32db-54fd-9ffc-d2ffcd0aa1aa |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
0c0dcd57-45d9-5030-8e98-c52b5f9984a3 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
e86daee6-5e1b-501a-91fb-531b5c67f99a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
40aee377-c39e-5d6f-9c4f-5fa3f78e95e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
e83d8af3-060c-50d1-86c2-fd6af926686a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
c36ca2e4-29d3-58bc-b19d-887daa8262de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
f601c830-4075-5eb7-990a-7696f4f4cb0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
ab1a9630-7399-5e99-9de8-2f7ac2037f6b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
9cc8407c-9282-5431-9d8e-bb3547c6336f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
83adda52-b7b3-55e0-8896-a132dae25a02 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
4b420b8d-4bb7-5ee8-a6e1-569842809480 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
ae2597ab-e261-57aa-b419-a86b76cbda43 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
c9a9d55a-748e-52ef-96a6-3496e5bab0b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
9ae2e353-8665-51ef-8e50-c7725038d152 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
a0d294bf-bf59-5056-b39c-891ea5e55a95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
be3021db-151c-528c-a8cf-ace63d13aa8e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
e6192c4d-936c-54fe-a12d-e576e422aa6e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
1aac2a0d-87a5-5ae9-90e9-994a8b255a7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
2bcaaa7e-e219-51da-92d8-e845aa8dec25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
a4f2fcda-50b6-595b-8bfb-c99c7066e414 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
91629703-fe98-5234-9aa1-9dc42e805bf8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
4235ac98-923f-5786-95ac-3e49aaa46c2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
4ee51426-cc09-5871-bff3-0f3e390ea27b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
13bc0568-68f5-585d-9e46-0585400f6795 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
d6d64c68-73c2-5a77-82db-93309dd62ee6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
5cc880fa-2e02-50d4-bf1b-16fa8bce80a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
22c74f19-bba4-51fd-97e6-791292e8021e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
eba69179-1f74-5d8d-a775-de61dc10e882 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
df89e769-5ed9-5db0-80fb-d58032417869 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
a8af2c22-bda5-5960-9b03-7adf4e4a8c03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
4070b9da-e8ed-54ec-9ec7-fe0371ded67d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
75a459f2-edae-5b48-b634-995137b486b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
5ec9ed2e-02db-5f47-8b54-9ce88130e5e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
3bb14010-5e49-5ad8-b5a7-70a6f6349bc6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
b71e5194-22b4-5693-a6ec-f39ef03c19cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
13d2e5de-5376-5c60-ac04-297931863b50 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
29fe6a1f-fe22-5f0b-9c70-eb53c60b462a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
265f8a3f-7dd6-58ea-bdc3-1ffadee77d58 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
efb03613-bc82-59f4-9ada-c543cb19e257 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
47ae37bb-8332-58f7-ac7d-a6b6b7cae16a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
44a15e71-949d-5766-845c-6888b61f7436 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
a22cde6c-2c3a-5642-97c4-e3e0c05fac35 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
0c322a79-23cb-5341-a3a1-34e32b854c71 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
9e6582aa-490d-5cd3-bed4-6cf5a6b0fdc8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
76c8c324-7d5f-5076-96c8-efd2eae0cb2f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
60ff1863-934f-5ffd-bdfe-be7916001b2c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
4d49f546-29cc-5cd8-afbb-8b148cf9b02b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
52dd7067-61d5-5973-9a3f-7808b607dce3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
cbdb4c3b-8425-5fde-b694-9631f1f74ca5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
1dc41f19-d53e-5d86-bbd2-518e4e7ffeba |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
f7e1d74a-374e-507b-88cf-1badb9fcd260 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
9b40532d-b148-5dbf-9aa3-7c83fc617b84 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
034aef56-397f-56e7-a5ab-8a94701a54f1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
e638cca4-816a-54d6-a8ee-2af9d2fde615 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
b7f4211e-81c3-5602-a2f0-7bdb6d44a128 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
e3ed50bb-0fd9-5c74-9ca3-a5637d36afeb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
e86e867d-40ab-5f4a-8ae8-e4dcf8e798cf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
f9ee7939-8d96-5db9-ab98-a8573696e58f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
fc30dc3b-2bcd-530f-ac46-ad339a5c489e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
28f389da-3920-5340-82e3-95ddbd1cbc2c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
b2de9060-56bb-5a01-858c-6f5748e6eb34 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
6f991a43-91ca-5147-b888-731a78f120d5 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
a560c2d4-e73e-5a60-a778-f3cc939e293c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
8c5dfaad-42d7-5b53-a7dd-dda3592c2e08 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
231a6ac6-8f76-5543-b3e2-e9b7bb8bf0a0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
362d1661-e038-4932-ad8c-bffaf28a81c4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
60ec67ca-ad74-5d70-aebd-f832b69029b9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
dadbecc3-915d-4940-b884-ab49812d6720 |  | work-in-progress | b863db18264ab499953369de7b16574a1a138b1aaa83c8bdd511bf3d8bcde8b9 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C
bf956dd9-9316-5cbf-923c-70f78738b91e |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
0bcdd406-c65a-53f3-aa62-9ffa9019d80f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
9e495215-b505-53e6-887a-2d8783f3cfb2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
d03a37d9-4f1a-5b61-886f-b81abfd990fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
77a498ec-6dd2-5fd8-b0b6-593746230a41 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
75abd8b1-cf10-5d02-b965-ea9404f47f2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
49335221-b670-5580-a562-90a96a967b5e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
1849fa00-cd5e-5f05-985b-b337519a8eb2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
bcb3bd70-3db4-5b92-b33e-3c2d17764a18 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
c1d21f6b-cddd-57a3-9977-a038e30a514c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
41320f76-3b3d-519f-bd6c-7171412545c5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
475debb5-52b8-5189-9bd0-b467debfff69 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
fe7e9d04-5201-5c02-941a-95b67bf4c699 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
0714ea76-3710-5b38-9014-aff1f24ea7ed |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
068ffa3f-6306-5f40-b9af-7c64c8b9daf9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
839077d0-67ca-5a01-a27d-6a193f0b2755 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
ab4f2d13-d805-589a-bab7-970a7b68e1f2 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
ac5b4a2c-6493-5701-aae0-466da1b7ec84 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
29d9c21c-093d-5a95-b8f8-7b6caceab724 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
4d25a91e-d46c-4587-b389-859ee02f8bbe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d91818fe-cc32-5d19-8944-5d3e9a860784 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
170b28a6-b1df-4b98-abfd-acacbda06159 |  | pass | 63b1e491901cfe89030f9bfcf85c2fe0f9b00560a68517104fc1e1b1037eef12 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1
5991bafd-ff9c-5bf2-8933-96dfd4916681 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1e25892d-8bbb-5652-a1b8-0ece480bdc53 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
b8fa21e4-42a7-53b9-bb1d-fd0013837b07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
79271ee4-677a-5b0c-9d6c-bdcf600f77af |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
c674906c-3292-5f0e-9ef7-51fcfe43c7f6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
ecc7f35a-309b-5b08-9cd6-54a4f04f7b86 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
8ab778d4-74b6-5103-a7c0-eb013479d9a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
0c5397a7-9572-5393-9809-c8f0729d82f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
85a4ad39-b67f-5e88-9b08-92579292617d |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
e977e0c9-0122-54ee-b070-cc621c45e207 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
e48fedaa-b2fb-5aa5-add9-be4584be925d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
d9d31811-2f12-5924-8904-5f44c75dda3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
c84f49c9-5934-56f3-96bf-9173c0cff45c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
ac519694-f585-5ad2-a66a-08e5f076359b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
1232f0aa-ae81-5a8d-bf12-12c81b321dd5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
6a03960a-2117-590f-b9d3-a6ea414c0a25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
94e1623d-fd14-5292-8d09-07eea8516715 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
990480f5-0f3d-5324-bf32-f843b93b2c52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
31ca362b-c34d-52fe-bc05-a3a8d0ac55ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
7af3b8a6-0a96-5756-b417-71486631e4e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
0b57bbf4-4adb-50b6-a535-8b80403ff824 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
5336a77a-30fa-56b2-b7be-d4a0e7355b9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
c621fe5e-0d1d-54bf-960b-7d9b09ce92f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
d136249d-2b9b-56f5-bf5d-f35c9af0ecc4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
a70ede78-f3a4-5af1-861d-10d9b9248246 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
93e566a3-25e4-5452-9720-aa6003d9cd1a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
41eea6e9-b94c-58ff-b3ae-ee7517113884 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
6da7e560-973c-5b2b-a214-b3d2daa46fac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
b725c0f8-fdec-5e3f-883d-758f00c65b9e |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
85a8057d-fe59-5d5d-afed-8296741297fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
769773cf-7059-5000-9cd1-0b0378b7cc7d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes East - CH1270 to CH1500 (HEB Tie-in) | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
9117e5d2-aa56-4341-b904-aafebc38d9f1 |  | not-started |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860
1db23417-8cb4-4e58-9ef0-5275ad566dac |  | not-started | ITP - Pavement & Surfacing - Subbase - Rev E | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E
b616cbb9-c5c8-5caa-afb1-a4d7769a6ee9 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
0b3dc4e1-c9b4-5ae6-88f1-a6909e4aad9f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
f507de1f-d9b3-52d8-9e04-b1d2c959315c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
6cd5f9e4-0045-5f4b-a34a-ca238293e5d8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
aaf18703-da2e-54ed-8846-26a2f7b3332f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
28f2bdb2-6256-5393-b0f2-a13b706de9c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
81668a1b-b21b-501c-b277-2291d85f0288 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
56d663ff-ae9b-5857-8925-8c47d0500734 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
6e06b2de-e782-5c24-bbe5-bd26c035b010 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
0e1b9856-cd47-56a4-9fb6-349e1458e65e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
95f53ba7-1337-574d-b122-a1ee375f15aa |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
7b0b7af1-4772-5c8c-b2e8-9f23f0c1404a |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
65cea02d-5b7b-5ee3-b656-0d5d7fe23e95 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
c00a2fc5-c074-5e65-9240-15441cf61405 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
e37241e2-7624-5dd9-b021-da1f57c8cbd0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
3713505d-c5a0-5901-95f3-c2fe3e72db11 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
fe5747e5-d602-56d9-b020-85b9afec479a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
e558ba7e-b1c4-525d-94c5-d22ac11d04ab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
36bdd34e-41b5-5dc3-b6d0-77e4b949c5f9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
274e540f-4e97-5bf7-bca0-a088428f139a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
3f67accf-fb84-5027-86c1-b022d936616a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
47e851e1-9f78-51e6-b946-d7960772fa6f |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
08ddca77-3b53-5bb3-aad2-0ed6917c9b66 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
98e39599-8ad2-5b46-a712-53f91c24ea5c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
7ab05fcb-8e6f-53cb-ba87-0b7bc4cb639b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
75135af8-35cc-50f0-8885-580513b9afb1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
d5e39392-f3f4-562b-9a77-142c185f3365 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
fa9b6068-7484-516b-8ce1-b8a544621af9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
c64b26ef-be82-5d2a-8805-5eea2ca9b3a7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
8eacf208-8906-5997-ade8-084bb548a9a7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
5f15d767-09c3-5e92-bb3b-10990e5ac964 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
02e583e2-4db8-51f6-a122-5866df563257 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
c4763553-00e7-56ad-9fd1-43e3fedd6e6e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
562c221b-cc07-5915-a8a4-d5e091b7f6f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
829c09fd-c5e4-5483-90d4-e3cd6cf00817 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
92f71130-4d17-5267-b2c4-f9f6385beece |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
1cc0e210-bf38-5a88-9a0d-e33cab16d86e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
08836a5c-ac3e-5095-9063-2309cba0a9f3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
891b253b-d5dd-53f9-b87b-326833898990 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
4ba08dfe-7f9e-58c6-9fb3-0c7a27a2d38b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
6cdd5f47-f105-55d8-b410-66d9ae76e07c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
3e21e560-9026-5f09-bd01-bf962faa5f82 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
7afbbd3c-b808-57b3-b5d1-ed6471cfc331 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
7e8d302d-edd7-57ac-abf7-11b847195827 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
a4198baf-02d8-50ec-89d5-19d097ae07d0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
66167ec3-10eb-5ebb-a849-2a5d47219b2a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
b7bf8e3d-7a63-5ae5-a642-577031f0196c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
2a4b95e6-3f3c-5f0a-8bd0-9c94a08f212f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
45837bee-0440-5a41-b1cc-f80cdcb77a7c |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
8421b6a1-f608-5095-a525-e4702bd8a11e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
ef6abe96-6888-54e8-be26-879fd3d0434b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
e83cb61a-08ce-53e5-8365-558ff738eb25 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
1554413f-b9ff-54bc-93c0-0a7da6d53eed |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
db9ebe59-336a-5649-ae99-0aa991258109 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
fa030db8-70f4-5929-b559-c15c929c8d83 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
aa5cdd28-a5fa-52ec-b2d2-036f768610ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
536259de-d1da-53f1-ad54-5a6d74ee2579 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
44c49107-da84-5ae4-b78c-8fe06a8cb72c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
303bd266-e26c-5b90-8375-f195416fcde2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
460da900-37de-50ec-bb8c-879aa9f84f90 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
fe757ec1-24cf-58e5-96c2-095df837c1b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
e768e880-5362-5475-b83a-9c518933a621 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
56c5c495-4de1-5dff-b5dd-722e03e704cf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
07d5fe97-8bd3-52a7-b818-04be250a27b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
56fb852c-6333-50e5-8f8d-ea78d8d78faa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
585ddf20-b97c-5203-9308-faedf7341b1a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
a736cd1d-a57b-566b-ba34-f8f2981bef71 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
237134a3-4fe2-59f8-abc0-75cfede63b2e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
e1370d92-2600-5e70-86fe-265d4fb07e03 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
85fb26cb-ec57-535a-94a0-3ef807844093 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
2e6a3d7d-ed07-5623-ad6f-26aeb1f81557 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
d0e7449e-396e-5111-b14e-6b79ba0e788b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
dd5a0ea4-eaf3-5be9-8f74-36a7e64be62b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
38713275-2478-5867-92e7-aad58247e6b4 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
4925d2c4-08d3-57b3-b9b3-68dea7eda139 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
b1360760-559f-5e97-a782-cb9b36d53120 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
267c952d-cd76-552f-8cb9-2261b921f32f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
6ca5b7d2-e407-44b7-acc1-b66c53bdc7c5 |  | not-started | ITP - Pavement & Surfacing - Kerb - Rev C | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C
4e38a241-5881-5129-8555-5e136ddc8ed2 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
e732a4b7-57f6-5660-b4d4-61d37c9c3a72 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
e33464cd-d732-5ca1-9ed1-f974afdb94e5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
004cc7ad-f3bd-5d76-b58b-54cadddf6e24 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
5ad9f64f-5df8-55e8-8289-3dd009c624bd |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
b897df60-2399-59a3-81d5-21976185dbbe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
d8342ba3-3e42-5262-895c-97babcca992e |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
dc09591f-d249-5c99-8268-6bdc2644d4a1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
face2c8c-20cd-5c88-ac38-d6fbea8ae237 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
34c28765-3328-5c78-93de-b6e191adea7e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
8d658227-8cfd-527d-af72-a58a71aac6aa |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
ad35b8ce-be18-54f3-8a77-050e956e15a2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
0473c2d3-5440-5344-a011-fffc8a6d244b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
3d09020d-e33c-5bd0-9eca-14171c3d1f82 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
406fde8e-7246-57de-a8a7-61af232a2176 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
113b032a-51bd-57d4-b5de-82f1c0bf0bcf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
d2f4de7b-b0e1-54b2-a9da-c1433efe8b43 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
c8bee8dc-b128-5eb2-a010-dc00ad7e2a54 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
e43b119a-46ac-5ccb-8571-d47ec35a03a7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
40e5c704-7422-5a8c-8094-a9e039540b14 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b8338ae8-e4cd-5078-b3f8-f3365091e935 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
b59baa55-daba-4301-a282-742f0923664e |  | not-started | ITP - Pavement & Surfacing - Basecourse - Rev 1 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1
d621c552-a942-57f1-bf1b-020f060d6b2d |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
030cc9ec-0980-5ea8-9fe0-2c5ce7f7ea3c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
44b9dcf5-22f9-5cf6-a023-f92ed5981db6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
c4c50ab3-1f04-58e5-acb8-a961e2054bd2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
2cad7de0-1abe-5305-b1d9-6215fdad8c4d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
77da6870-7326-5e47-b86e-cfbc5ab2ba79 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
354ea12f-c901-5a13-850b-9b358b8e1dea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
0cc4e201-7c2c-55bd-af44-e4cc66731433 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
cbbfe8ff-9e88-5ef5-9103-3a37c51f09f7 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
729ec120-84eb-5b1f-b4fd-c233fd7e4e66 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
a9bbf861-e5f9-57be-931d-551fa1a263d9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
d92ef3c2-1d05-5877-aa89-50b5f8197773 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
62d9bfee-924c-5be7-b444-2446fb741530 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
f817a1e4-eaca-5b94-93ca-eae8ae68f614 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
927800c6-1dc7-5de0-a6f1-fd5af30e7933 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
eeccfef0-ee14-5231-8b59-ed61fdc6d659 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
99e0db14-ccff-5c0d-b224-9901f5be0aef |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
ef0cae35-2444-5860-ae3d-1f7fb7f19d55 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
8b0f065a-a41a-57cf-9499-8df37f66508c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
ddb432e2-63a6-5378-97bf-85c69ea8721b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
18bb9d74-348b-59a0-9e00-fb1a787d9fe2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
7899142b-f7ab-5129-b219-b392a6e6a64e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
fdb1bf0b-1f9d-5221-86a5-94bb2cab2cda |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
4461eb87-d969-5d1d-80a5-4c0482a789fe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
eeb7a9d3-6bfd-5036-8ec2-72992771a74f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
ff23eee0-5951-5b33-a586-7328fc42578b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
f042230d-a191-52e2-b721-46d461916f80 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
1a8c66bb-9cee-5269-bcfe-faf882f420b6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
27e178c8-b91a-54b9-b21e-e40c6146ec5b |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
0c86a061-a226-5d4d-a077-f6a23ba45e73 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
2000c66a-f767-5ade-adee-fc7a62bc8c59 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
0eb71a81-9043-51f8-b969-c3275c8066ff |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
7654d81c-e252-5719-ba1c-b7293d64354d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1580 to CH1860 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
2ae48be0-8569-43fd-8812-bc9b21847e17 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580
20528756-17a3-409a-9a9a-54937fbea741 |  | work-in-progress | ITP - Pavement & Surfacing - Subbase - Rev E | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E
877641e3-ff9b-54db-9a6c-e150526d54b3 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
f5fdabdf-a28c-5c50-a0a3-2637db7b951a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
4e703b97-7cea-560d-97e6-a662865decb8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
34f8cdbd-1618-54ea-9dc9-59f0158eff46 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
b61e73f3-18e3-58e2-b113-7f477efaab02 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
2e333776-9403-5e8e-8a88-764e3fb3f073 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
b29b5134-1ef9-5418-ad6d-8042ed8f48d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
ceb0744f-7835-51d7-b7ab-abb015317a4d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
626dd72e-61c8-57f6-b7f3-4c99a9298317 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
904d2e2f-6132-52e6-a59a-4abb8973c776 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
512873b2-c45e-5652-867e-f0058524277d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
511b2436-b51e-546a-ba7a-da2c1eba601d |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
f981e25a-7c26-54ec-8333-3ac477fe0992 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
c556c8d6-953e-59fc-9aa8-0b446e7a1e7e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
82b8e9d6-fd11-5033-b84e-54adc7a986f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
40282fae-3cfb-515c-9cfd-5bceefe0a757 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
452f2ff0-a1d3-5685-b014-f06c6fce48fb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
170e6160-f021-5abb-9c7a-a655dba57cb5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
6425eb64-05ef-5c32-a332-ebc37ad5b3af |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
24a02ed1-a331-5926-8d54-c1d73e329cd2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
74b18469-dae5-519a-9898-39b0160e26be |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
91eeb8b4-f9db-52e7-b113-faf3bd6d8a89 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
42c68de3-294d-5aaa-aac2-de6ceb0515df |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
599dad28-3751-57ed-b42b-5a4d1774aff5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
beda8067-5ebf-5d21-8946-6ff699039e78 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
bdc75995-4448-5623-aebd-9eab1c2b7644 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
209521fe-28bd-55d4-a61f-8063ef7e1555 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
26b43670-e87b-5391-a214-ae73d7827878 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
2654bf09-0be2-5212-b87f-a26f2c371051 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
18ebc602-eed5-5c94-835a-f2c94eed656d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
4fa66059-a05d-5346-87f0-f6ea73db0a88 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
ccf0957f-d811-5bb3-b991-216ec7662093 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
32e50d9a-92bc-5945-8f28-0a72ca342dd2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
cd2f1177-630a-5675-998e-1482a77cf022 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
bcbe3c14-8f67-5343-856b-5e9c21b91206 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
84ba87f2-8021-5ca7-97bd-91d04bd424f4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
fe95453f-aabb-5120-8c95-a04a309f8cf4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
d215d6b7-2e27-558b-89ef-802d78ae3d67 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
f4f8dedd-af88-58f8-99d9-c37caef74a9e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
a837b166-0eb1-55d9-bc9c-1c10158dd37d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
deb1f6bc-1110-5b2a-bd82-64e540327b12 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
7e99d63c-d524-5c19-9e1f-82bf642b561a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
07e0c6f9-c411-56e7-98bd-98268b86ef93 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
997da62e-7302-53b9-9f81-7c48b5347646 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
f8066615-9adb-503a-be33-e4d0cc867954 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
f8739803-3f11-568c-8b9a-541a6f6ef9ae |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
b709f1bd-4e41-54ce-b568-3819ed67eb49 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
a9030902-4e09-58d6-9679-100bffd6ac6e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
92d89809-ab7d-5538-b45b-248fa1e3261a |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
65e1d0fc-fc6f-5b60-bc4c-0bb3bd47eed9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
c7564627-d546-5e45-8651-5e9781379b67 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
8fb70558-2a9d-50ce-8d11-e72295a79b98 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
f153b059-bbae-59f5-9f41-69fbd505fdec |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
c48fcf51-fa78-5fd8-972f-45eabe30a9fc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
b7d7f932-51ff-5f30-ae3c-d65485ddfc3e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
decf6dbe-00a3-56b4-8a02-2df393181e92 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
2309a53b-23b1-58e1-8fac-27cc85048530 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
b075dbe8-617c-5c6b-b264-10b203101748 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
fca05fd8-f842-51b0-adb1-d85a190bed05 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
96250ab6-300b-526e-816c-f871165c184f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
5fc7eaec-b2c0-558a-bbfa-382e2834b293 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
03f2b68c-40a1-5dbc-9d32-277c62e9c1ad |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
8d8e88dd-7910-5535-9aba-606a51428bdc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
4d848750-1aef-558b-b624-f5e5d013e157 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
d2ca4431-2356-5fd1-92a7-55f8cdbd99bd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
8ec1f65b-b62d-51f6-b306-f1ecb1e67d97 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
94d89d83-5bc3-50f5-9b0a-28e8a527d38e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
d10ab90c-7c72-5d06-bcbc-212c4cb8b886 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
40c45d05-590a-5442-875c-7a359fdf94c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
92ab1230-1353-5423-90e2-7b43f6bf0cb7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
4f13c892-44aa-58c5-9b7a-55c3c2df20b4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
3278262a-3153-57ba-9abb-2d751521c597 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
7854ece7-c535-589c-848a-35bd285d4981 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
cda8e07b-4cf3-5925-b760-4a6f00b01788 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
9e2a9274-f520-5a8e-8412-670410f0bc63 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
81af3d32-e499-55e4-af4c-41b2dca0847d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
620c5db2-2e5f-50a8-9e3d-30a03779a3bc |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
7db92d48-6172-4973-ac48-f37c3f225258 |  | not-started | ITP - Pavement & Surfacing - Kerb - Rev C | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C
6e25b2de-05df-5581-8757-55903f8feffa |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
0c40ee3a-6200-5866-a92d-85486d2ac119 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
ac601f08-43fe-5b43-a60f-803bd3589b12 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
cb964989-345c-5459-9154-4f5cab6d067d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
c104df6d-b23d-5a0a-ba54-760b8ab724e9 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
b1ae9fb4-d992-58ed-a1ef-a90b5cbf139a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
d6b20a0b-6add-5290-bcd9-0d9bc05b7421 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
c4cc4373-2058-5bf9-991b-ceeb5ce04288 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
0799864c-6533-5418-81b0-2d31f6089e58 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
c57ceb57-84ae-58b3-a7e9-75dbdfcf3d0e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
5efcf497-4593-570c-b184-6d66f451dc62 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
2d5ebe4a-aae0-5f05-bfe4-b9c61926bef0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
b057afb3-d120-5d6c-813b-34add00df7d5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
0b851c82-7134-5e8b-83bd-0d39022605d3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
81a8eb22-04cb-5bea-8ee9-d09113fecbd4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
d836660d-4f52-5f3c-a970-2d9f5134a0c6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
2886e053-259e-51d6-8cb7-e91ee909803f |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
6f3bf7a8-8f33-5f15-821a-770385944673 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
7df80d22-89ab-5722-bdd6-78e6f973d37c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
06b51077-0cc9-58e3-8019-1013d1659a13 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
437d6bb0-1e3e-53fa-b8a2-e11aadafd74a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
1a9cbf26-6e59-41ad-b6a1-71ce34eb6fa9 |  | not-started | ITP - Pavement & Surfacing - Basecourse - Rev 1 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1
b3a675bd-6885-5cd6-b4e4-08d9e88d05f1 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
a37ac342-42a1-5799-8a79-3df1f66c2a7a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.01 - Construction Pack
0b907645-f139-5c41-842c-b33da2aa11d6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.02 - Survey Setout
58dea8fd-5b8b-535b-908d-a47025f8f5a3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.03 - Service Location
a1f0b44d-09df-56d3-8b27-a3af398495a5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.04 - Internal Permits
6922a699-4412-5a8d-8d39-ee383f78e425 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.05 - External Permits
12a91770-d398-5cd9-b8d7-5f5f654abeda |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.06 - Approved Construction Drawings
f0fbe934-9859-5924-acb1-c5a38d925e0e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 1.01.07 - Subbase Approval
dc8cf6e7-ae22-598a-a161-6f89fca0c6b7 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
3577b3a0-1c4d-5d8e-aaf5-38eda82309da |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
647f1f55-8e72-5824-9251-5a258be66f7d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.01 - Average Uncompacted Layer Thickness
e19b55c1-2d67-5857-a03d-598d478e4a23 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.02 - Basecourse MDD and OMC
08785eaf-8a64-55ed-af46-ad7c9a13d29a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.03 - Plateau Density Test
81f4d2db-3d7f-5a77-ab08-b22f2bd08905 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.04 - Plasticity Index
fced697a-d039-598b-a897-6f3f4c86488d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.05 - Clay Index
98474b2a-90e3-5174-9da6-bf35483a7659 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.06 - Sand Equivalent
33f2cd85-e49b-5506-af79-97777ebc09dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.07 - Particle size distribution
cd31911e-1a1b-545a-b1a0-d6f7e80a55ee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.08 - Basecourse Pavement Layer Compaction
f75606d3-6dfb-5aee-bfd3-c665a11c8bc2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.09 - Surface Shape
142259b1-e21d-5713-aaf3-2436b370a9f4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.10 - Holding Water
4b80e513-93e2-52b9-9ca8-fc71b3f307d5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.11 - Maximum Width Variation
57afcd91-2043-5c6a-9796-58afde918fd7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
0bcf9150-437a-5be3-abee-79fc15acd2a7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.13 - Maximum Crossfall Variation
9e6850e0-fb82-5177-a462-447973006254 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.14 - Benkelman Beam
c789e03e-2599-54b0-99a0-92cbe6a73ce3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.15 - NAASRA roughness
663b3e18-b415-5f57-92b2-8d0d411f3376 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.16 - Running Course
cf9fc3e5-e5f7-518e-b244-0d9c474474f7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.17 - Surface Finish post sweeping
76a5259d-cfd8-572b-947c-068f6b856a94 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 3.01.18 - Tie in into Existing Pavement
fbd028d5-5daf-56d0-9adc-34b650374110 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
07edd506-f15c-5729-8e17-044aab1c10c2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.01 - Survey Records
d842817c-8be7-5dc2-9287-cb5c3060b058 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 4.01.02 - Redline Drawings
4f84755d-8d57-5363-a65d-a2cd2c48c673 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
28d1a98a-a333-5e72-b554-a5f558366cde |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Peacockes Road | Peacockes West - CH1270 to CH1580 | ITP - Pavement & Surfacing - Basecourse - Rev 1 | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
74dc9817-a057-4334-a941-87d5790c5339 |  | pass |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Material
fc74cc9a-8db9-4160-878d-3a255af79319 |  | pass | fc4b710d6655cad98ea118d813ea70e83478b4dda246d4be011c75e50f91435d | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1
ac29f3bf-3474-5139-af11-d2cb4eda5028 |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
36e10a6c-8212-5cac-bcad-90f85f31b1e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.01 - Basecourse CBR
0a6ce9c1-043b-532c-abfa-81d8922b31db |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
01ef47f4-5f67-5916-963a-cfb6f2352bd5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.02 - Running Course Material Approval
6fe0d22d-4e87-5822-bcea-56e3e5cbfdbf |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
7c770135-bd1b-5463-9790-b69d66a961ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.03 - Basecourse MDD and OMC
32cdefaf-53c9-5f2e-961a-56f40f992db8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.04 - Crushing Resistance
ca31e9dd-cadd-523a-91c1-292978f69819 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
a52145ae-5981-54f8-bc05-282b08c883a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.05 - Weathering Resistance
02dfc485-d3fc-5c05-b604-10e9ae51359d |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
f915c519-bca7-5096-8903-4d9838ee7340 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.06 - Particle Size Distribution
bff55945-e190-571c-b778-4c58d3ff03fe |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
a6762e83-71b6-526d-a832-d26f902ccdcb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.07 - Sand Equivalent
afdeea27-2b24-5fb4-b1c4-65715beb89b6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
05c215e1-e688-58a6-874e-9204164acc0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.08 - Liquid Limit
dc427570-48a5-55f1-af57-9349f262b5a8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
c9fdf750-6405-5d2d-9ad6-3654f816c426 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.09 - Plasticity Index
7789ee39-2155-5d6a-820c-925beb5280e8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
28c3fa15-058c-569b-b7e1-129e8461dd96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.10 - Clay Index
8d983e84-ee0f-511f-947c-b56cb8f1fe32 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
4430b9fb-a5d4-526d-8ecc-38eec37f7148 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.11 - Accelerated Weathering Testing
e7f3128f-32db-59f0-bb3b-dc7b727edf8c |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
52757e54-7ef2-5a70-a4ab-549a22a28640 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.12 - Repeat Load Triaxial Test
60e6c2ad-0c76-51c7-8f4b-e5f608a50f62 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
37ae30b0-ab76-52fa-a7db-799ae2349c78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 2.01.13 - Broken Face Content
84ff7145-8148-5a0b-90f5-dd9a2992e86c |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
27aa6d20-0274-4abb-8a6c-bcab05241b31 |  | pass | 8cd81b1e3a19f210429116ab2db6da17262c00d00ffa37305cd3321942f7e0bd | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E
83d0e710-edb4-5b62-8bdb-c87ee8aba23a |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials
131359d8-e038-5df4-b650-50808c11971a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials | 5.01.01 - Sampling and testing
6abfbe4b-e463-5fee-b6e5-eec034fb4e2c |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials | AUTHORITY HOLDPOINT
4b5938c2-2a7d-5a36-86ee-346c8313acd6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials | 5.01.02 - Sampling and testing
31935fe3-9ad2-5027-80f3-df2bd05b156c |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials | AUTHORITY HOLDPOINT
2a5b0068-f7a2-5b8d-babc-b03273623d2a |  | pass |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate
ef1f03b0-c915-5800-93e7-dc70e08e5eec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.01 - Sub-base MDD and OMC
88b03a21-c68c-55fd-8057-762316afaaf5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.02 - Cement for sub-base stabilisation
1f7de0cb-e47d-5a3b-9efe-a4a7f91ec5f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.05 - Crushing Resistance
0384ba9e-df54-5e44-ad90-af7b391d1c5f |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
09e21736-0235-5806-9e8a-31c06ebf8c1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.06 - Weathering Resistance
ee2483ce-b577-5e4a-9b1f-99394fa272cf |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
ce911881-795e-599d-87ff-27c4e3b889bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.07 - Particle size distribution
5296c113-022b-5ddd-999b-ece1f5555427 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
b0721462-0da6-58ca-b8b2-0694a092334e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.08 - Sand Equivalent
0934c062-3c8e-5751-82b2-416d266441db |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
86514026-1f0a-52ef-a35c-bf5f67e029c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.09 - Liquid Limit
b086eb78-0bd9-5f95-b4e1-305a0362778b |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
fb4e2821-d0f3-5a09-a77e-f6d718615374 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.10 - Plasticity Index
bf80c366-61d2-5377-926f-6e0621278a24 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
f35e13da-9658-59b7-af03-3e66ed74965c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.11 - Clay Index
35321dbe-35a8-5def-a8af-6b85cbed6302 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
fb1cc60a-0960-5f4a-ace9-2865ed723f07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.12 - Proportion of Broken Rock
b61027ef-ab28-535a-83b9-465db5992960 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
d5e1bf49-17f9-5828-9874-76a14bb066c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.13 - Organic Matter
495855e2-bfd5-588f-bae1-090d225397c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.14 - Accelerated Weathering Testing
903d020e-9afc-5609-9e55-f6d118716d42 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
97349484-1463-53f0-a598-d24b557b0668 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.15 - Repeat Load Triaxial Test
aa4bd81f-2c87-5e44-9b12-df154a373198 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
afe22aac-e74e-538c-82c2-19ca2ac6467a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.16 - Unconfined Compressive Strength (UCS)
5c1f9a29-d336-51d2-a89d-ab4bb8aff640 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
cd3f60ea-b991-5ddf-9f8d-8ad181d9c11d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | 5.02.17 - Indirect Tensile Strength (ITS)
5e677676-95b7-54d3-bdb9-44be135e1a03 |  | pass |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Material | ITP - Pavement & Surfacing - AP65 Material - Rev E | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate | AUTHORITY HOLDPOINT
89e6154f-d74e-481a-bb55-53a8bed4c14e |  | not-started |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2
4a57ed2e-35c5-4ac8-89dc-ad2530f5a969 |  | not-started |  | folder | TRUE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection
52e81748-789c-4b19-86f3-ea4d491e148c |  | not-started | ITP - Pavement & Surfacing - Subbase - Rev E | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E
eb368c8d-8bd3-54ba-b236-d31ded11ae6f |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
ae52cd82-fab7-5a9b-8ca7-6a4db74bfc06 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.01 - Construction Pack
094768bb-2707-55cf-9a74-a3c92152b373 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.02 - Survey Setout
a7598d65-6219-54bc-a95c-3cca6d056983 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.03 - Service Location
ecb3d9c5-403e-534d-b359-c61863ba226f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.04 - Internal Permits
3ce03401-2a9d-526d-9411-367670a4c9c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.05 - External Permits
16c8e746-fa60-5eda-acba-ac36b67ba2c3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.06 - Approved Construction Drawings
31a59a8e-0156-5d70-8fa6-e138014d11cc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.07 - Stabilising Methodology
de4cd689-f1a0-5e66-9b8b-d78c6ea06def |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
2e599837-0449-5fd8-bc1e-b6ce5a82e323 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | 3.01.08 - Acceptance of the SIL layer
67d00890-ef57-505e-80f9-e7b761ecba9c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements | AUTHORITY HOLDPOINT
cc9185cb-4ba4-5e3f-8230-49f709be5f7b |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
ec2c004c-e42e-51c8-b13b-793a2dcbcf20 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.01 - Sub-base MDD and OMC
4f3163ae-fe8e-5e85-99c4-b1f0f5b87388 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.02 - Plasticity Index
c701b271-3b9e-5da0-b313-1382fd41623d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.03 - Clay Index
5296c481-318c-5099-a523-f7d18d8924ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.04 - Sand Equivalent
6d839fa1-8f1c-56b7-9932-55ec2077de50 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.05 - Particle size distribution
4c99e4e5-02f0-5398-bb2d-736b726aa179 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.06 - Average Uncompacted Layer Thickness
4658dab8-1ca5-5efe-864f-32b50d452d67 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.07 - Plateau Density Test
e0517190-f0f4-52c7-af40-06c6920275ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.08 - Sub-basecourse Pavement Layer Compaction
ec52ea8b-fe6c-53bc-a557-e269b5be4f36 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65 | 6.02.09 - Surface shape control
cd12078e-1708-5b22-bda4-1e54992b135f |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
bfaecce3-182a-5e64-a385-b3acbff61f16 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.01 - Stabilization Production Plan
ca8d23c7-e0f8-544f-9ff9-5b37e2b9a281 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
2d194f01-7ebd-5bd7-b0b0-3f27d2f61b26 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.02 - Longitudinal Joints
9c596646-9cbd-5f40-9308-53d3e5ece484 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.03 - Stabilisation trial
d28a80f8-6b2e-5d3e-8d7c-f996c48d42e2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
99b97323-173c-5f78-bb7a-8d66f294ee59 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.04 - Stabilising Equipment
ecc3210f-a52f-5568-88d2-6c2922423bce |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.05 - Stabilising Supervisor
f29d13f3-7bf2-578d-b318-632b1a48b887 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
9b8fa3d8-4c6e-50bc-acd2-a9dea6908c80 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.07 - Average Uncompacted Layer Thickness
aff852af-893d-545e-9ba3-d5aeb8da78f5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.08 - Pre Stabilisation Compaction
d25a3aad-d3b5-5a11-acc0-9760faa43a0e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.09 - Pre Stabilisation Crossfall
da46eb49-d036-5921-bdd0-434a9649ef56 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.10 - Stabilising Visual appearance
d392b0a2-c7e9-5b56-a17e-95f4619c735a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.11 - Cement Mat Test / Spread Rate
e4b15dac-ee11-5731-901b-3d91680d2269 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.12 - Cement Average usage test
397a9fe0-b635-5c7f-a9d5-314a3acdbc03 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.13 - Control of cut depth
ff64beca-22f5-5720-a181-64625bdaf442 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.14 - Plateau Density Test
cc926ef0-f478-5644-99eb-6567de0448e9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
0b5f1887-ea56-5004-bf96-1ee8efeaa30d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.16 - Mixed material testing (ITS)
cf1969c3-6cdb-5cf9-afcc-e03fa750d332 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.17 - NDM Water correction
01b7f58d-5431-563c-8ef6-02fa665605bb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
010e9789-6208-552c-936d-ac7c0fd5d2ac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
9801a9b0-bc4b-5ebf-8115-a2d58f4b6ff9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.20 - Protection, Curing and Maintenance before Overlaying
8e52d918-bdf1-5e71-adf0-f8fcb7d8a974 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.21 - Benkelman Beam
0ccc8e39-795e-5ec0-8445-1ef525d04787 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.22 - MDD / OMC / SD
564b388e-87a8-58b0-b5ef-dfbd1fd35a7c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | 6.03.23 - Sub-base stabilisation trial
4acc707d-4ad1-5256-a1b5-e161f87665f3 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial | AUTHORITY HOLDPOINT
9e27f136-49d6-5c85-bd1b-bd2450d4b4ed |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
b651f702-61d0-508c-8f3c-8de17d53556a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.01 - Stabilization Production Plan
1f9f6f69-a439-5dd8-9bbb-3b2df628f1a2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
1ba213be-22f1-5d19-8364-e1ba1fbfec50 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.02 - Longitudinal Joints
fad5d53a-a015-5ae3-b559-c57a83137a15 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.03 - Stabilising Equipment
825dacb1-7308-59cd-ae0a-9251e46ac01e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.04 - Stabilising Supervisor
e4742f40-6aa3-55b8-975a-b64c8e199238 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
6dc10fe1-095c-53f8-92a1-c7efc40b554e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.06 - Average Uncompacted Layer Thickness
eba0fea8-7227-53ca-8ca7-e9899d1664b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.07 - Pre Stabilisation Compaction
52607fbf-9e34-5c07-8fdc-d419af68e661 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.08 - Pre Stabilisation Crossfall
4372756c-bbd9-5df2-ae24-b9e81ec7fb21 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.09 - Stabilising Visual appearance
753f8c01-4251-503e-bf24-8580e8f3344f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.10 - Cement Mat Test
311299ed-1c85-5d32-a36e-309cdf5955a4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.11 - Cement Average usage test
39040c7e-cbf9-52f8-93ef-aaa3073ea860 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.12 - Maintain OMC during stabilising
e60e324e-f3a8-5abe-8e8e-814c51b7e3ac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.13 - Control of cut depth
d8f6413e-5cd1-5a08-ab9f-0098cfbc757c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.14 - Mixed material testing (ITS)
6ef14872-97c1-5cba-a3b5-09e3e79cccf8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
73bce518-7b56-5987-ad8a-6403d9284926 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.16 - Plateau Density Test
ab5ef69f-4d03-50dc-a91b-824a02d5cac8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
cfe79c00-856f-5936-b828-c34174e49564 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.18 - NDM Water correction
c197b7ad-ae9d-5aac-a076-7c8890c8a0f9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
1dd85383-d3bf-5e55-ba98-8869dbf1702d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.20 - Protection, Curing and Maintenance before Overlaying
2b092d2f-b052-56a8-a198-b440985962cf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.21 - Benkelman Beam
f4814e11-c9ed-51a8-ae5b-b76b9b048ae3 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | AUTHORITY HOLDPOINT
1496107a-cad6-52aa-8aa9-e66f141755bd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base | 6.04.22 - MDD / OMC / SD
a6ee4101-4bb0-56c5-9cda-a4c96a15bb02 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
cc1bc904-acf1-55c9-bbdb-1d411dceba66 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | 7.02.01 - Redline Drawings
aed30413-deb6-5b48-96f0-03b367133f51 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
6e499fe6-d381-5f55-b8bf-527c23b4e093 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Subbase - Rev E | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities | Add Signature
a968a349-d96b-4778-a3d5-67dbde37e193 |  | not-started | ITP - Pavement & Surfacing - Kerb - Rev C | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C
f986048b-89fe-512a-8dae-fc598c2e9e43 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING
78e047fa-e5ab-52bb-b5be-5b53e5436677 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.01 - Survey Set out
c8eebd42-aad4-57d8-b7d3-82a9a17778f7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.02 - Kerb construction Set out
3a59f0e1-4250-519c-b31b-502fc2b0f684 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 1– PRELIMINARY - KERBING | 1.03 - Approved kerb and Channel profiles
7807495a-2944-5413-97be-aea672a958e8 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
ae261ed9-b400-515e-9cb3-88dcb5addcc4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING | 2.01 - Approve mix design from Certified batch Plant
adb07c8f-9294-556d-a05c-853723722f3d |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
abf7544c-07c5-5e09-b1a6-30e22094ce68 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.01 - Survey Set out Confirmation
6e03fd6e-9055-5dc0-9338-844bf723f679 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.02 - Clegg Hammer Test
d7102e43-02df-590f-bbc2-68eb30e6e4bb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.03 - Pre-pour inspection
91623400-3016-5d2c-85ce-c922c54f780e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | AUTHORITY HOLDPOINT
c2a05714-f1ed-5fe0-9ca7-92af15be71b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.04 - Concrete Cylinders/Slump
f833d719-98f1-504c-a1d7-186ff6485da5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.05 - Curing Of Concrete
7da0465d-9936-58a6-87a7-3b457a86a5b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.06 - Post-pour level check
b8a3092f-6efd-594b-aca8-3a5222b99249 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.07 - Contraction/Expansion Joints
85a99c52-8117-5cfd-a83c-f2aed056cb55 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING | 3.08 - Concrete Mix Dockets
cc1d3528-43ad-575c-b866-313b425ff4b9 |  | not-started |  | section | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING
210a23d1-3b1d-5f22-b84e-6e6d948ca837 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.01 - Post pour inspection
019dddec-c8c5-52c2-8325-2337c2329790 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | 4.02 - Redline Drawings
6d83b3d4-b7a2-5fe0-9895-44d1cc52d7d6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8be899b5-6aa5-5f01-ba8b-5afb4907d78d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Pavements - Type 1 & Type 2 | Pavement - Type 2 | Whatukooruru Drive/Peacocke Road Major Intersection | ITP - Pavement & Surfacing - Kerb - Rev C | SECTION 4 – POST CONSTRUCTION – KERBING | Add Signature
d0aaa639-674d-4c35-8707-5ecb09db5f32 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Surfacing
5001f1c7-049b-4e92-a29d-f7dc48765060 |  | pass |  | folder | TRUE | FALSE | Site QA | Surfacing | Area 1
e5bd6ab0-6a4c-4bf7-8225-9eab1faaebd8 |  | pass |  | folder | TRUE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960
da482613-b08b-489d-96c6-d2ed47a41d93 |  | pass | a83c92be17ef255d65b7d7d79441fcf3ffebdf903e4e863bc0190c282f1da53a | checklist | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1
5a1b2ec0-2f18-5ba8-a280-cebb86291dc3 |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
d0b30268-15f2-59a7-a648-49574aedf341 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
597b1901-0b24-5dcd-b8e4-17a69d0b33e5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
179c3b16-291e-57a5-9ba8-1740a91ea7df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.02 - Sealing Chip - Production Property Test Sampling
65c4a65f-f1fd-5dbd-9e2e-ea046a091144 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
7faf5f76-97c6-5bfc-a44e-551135a5b9ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.03 - Bitumen
5d4b9b62-7a86-5b7a-844c-cb746e05e792 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.04 - Sprayer E-2 certification
2c9e6635-2866-55b1-9596-37e09a25a7e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.05 - Sealing Design
7196c564-23ab-5dd4-a8f4-b0aea81bac79 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
771d103c-ce0d-5c19-a476-1f092b6a5539 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.06 - Bitumen approval
11174d11-5538-5884-b745-920a07c88cf8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.07 - Bitumen Quality
2e561a65-eea2-5193-b925-a667c27907e6 |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
3e675a35-b03c-5c3c-ba23-fa8911e0f8fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.01 - Sealing Procedure
aad9ec64-7f2d-58e4-939a-c362471eab3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.02 - Sealing Inspection
4d0773d1-0ec5-5f81-b07a-b6c3feffab10 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
82dd8b39-0c88-509d-a7b9-ce3b7e4032d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.03 - Presealing Requirements
f974c57d-4ea9-54c4-a6d4-c35305804b8e |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
bbe73ca2-e8c1-5ca8-9462-f60c37a19f72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.04 - Adhesion Agents
7b2c0696-1819-5ae1-a9ec-2e6eed004921 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.05 - Post Seal Inspections
d3f1af0a-93f4-5fed-83d3-d300e0d22e87 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
4de0a8db-3e3b-5e96-8330-1c8a1827005b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.06 - Bedding in Chip
25757a7b-cfba-506f-8558-5447c3093fa0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.07 - Surplus Chip Removal
a596163e-bc66-5385-9204-7b41cedf98f7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.08 - Chipseal Repairs
46d707b7-f1d2-50d2-aef8-1a4c6f8ef10f |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
f4a1e4cc-e670-5a52-bcff-2a586784702d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.09 - Weather
1694358d-10a0-5698-8956-5f0f7c9805f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.10 - Protect Road Furniture
f6ac975b-0c3f-5a0a-b452-44166a2d3244 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.11 - Joins, Overlaps & Hand Spraying
e01a4183-80e5-5933-8cbe-a622db5f3705 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.12 - Binder Temperature
36018303-a1e5-535c-a143-f165c3a23b0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.13 - Binder Application Rates
b1b3057e-6e3b-57e9-a795-baf9db884df5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1A - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.14 - Chip Application Rate
acf8429c-4e14-4b28-a4cb-6b86775e0e96 |  | pass |  | folder | TRUE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960
91a02c88-1951-4610-8e11-6a87a533016c |  | pass | a83c92be17ef255d65b7d7d79441fcf3ffebdf903e4e863bc0190c282f1da53a | checklist | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1
877bdf94-b6a6-5850-bc25-1720c836a96f |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
96dcde7e-06ae-5f43-8216-c4cf81951b81 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
7ec3acc2-2272-5ae5-a468-1c2fd94a60fd |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
10fdfc6f-762d-591a-a5d5-81410f47484b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.02 - Sealing Chip - Production Property Test Sampling
f5c8c5a1-9d80-5a10-924a-ca020fc218af |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
b92b0ae1-8fd1-5691-bd5a-bf98266ac28f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.03 - Bitumen
924d08ac-3801-58c6-9551-80191b9ce5a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.04 - Sprayer E-2 certification
3f8414af-37da-556b-b73d-0f6f827f9d6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.05 - Sealing Design
bb4cddcf-da94-5c83-8933-6e809655f912 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
4d8e65e5-2263-5139-a063-7039ead47167 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.06 - Bitumen approval
acc75140-6e74-5712-9578-e5c66fce79c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.07 - Bitumen Quality
a5aa0e58-ef5d-5325-9e00-dbf74cabb8d0 |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
14c2bc70-c7c6-5c9d-9880-8ccdc4db72c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.01 - Sealing Procedure
bf919f52-6e14-5f4f-9c7c-f3b9fe790acb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.02 - Sealing Inspection
6dcbab16-7aa7-5c78-a035-e48cd0f3dc35 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
b8a34f06-a424-5684-adbf-3fc9a0fa8e01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.03 - Presealing Requirements
5b24e29a-3115-5c6d-bff0-f55d6138fc25 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
69bdfdee-73bf-5145-aa33-4101c6366a4b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.04 - Adhesion Agents
75f2a8c3-e606-5379-bbe0-087439606b4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.05 - Post Seal Inspections
3da165d6-705a-56b5-9918-d62cff118e68 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
b217219b-dd2f-5329-8487-5aa40bbe5d09 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.06 - Bedding in Chip
73aaa52a-5682-5052-9a4e-505ca0325c61 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.07 - Surplus Chip Removal
5c101464-b009-58c6-aea6-b9cd02316fa8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.08 - Chipseal Repairs
041b6c5c-290a-5388-8633-333f29bd132c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
09d7d7a8-48eb-5f11-a130-cbb8e7493898 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.09 - Weather
7948d756-82f7-5c17-9108-cc0daaa44d79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.10 - Protect Road Furniture
636794f3-20b0-5ef5-a549-8dcbea80b00f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.11 - Joins, Overlaps & Hand Spraying
1a61181a-79e7-55f9-9dbd-69f46a5b34a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.12 - Binder Temperature
08b6ff0c-7b3a-56df-8e99-a075fe4ca7da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.13 - Binder Application Rates
3027a5b6-7c7d-5fe5-a0c5-de1c49ce2eb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1B - CH1620 to CH1960 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.14 - Chip Application Rate
8d7fe3ec-9acc-4167-b6fe-93f5a1d29e40 |  | pass |  | folder | TRUE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220
b9cf444c-2107-4bdb-a1bd-97417324bc6f |  | pass | a83c92be17ef255d65b7d7d79441fcf3ffebdf903e4e863bc0190c282f1da53a | checklist | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1
df783b9d-8a78-5093-bc45-3cf8475ed803 |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
ff25ce5f-dee6-5f10-9b37-6d9ccf73e51e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
1f27b460-8d3c-5f09-92ec-a4ff77da3044 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
cfb8a681-2c31-5cd5-8fae-c78188bcab4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.02 - Sealing Chip - Production Property Test Sampling
4a1bd88b-eb7e-53b4-89de-943839a015a4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
a22f92f5-be81-5451-9ed1-23e50526829b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.03 - Bitumen
496a0b1d-efad-5fdb-af94-56eec8f579bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.04 - Sprayer E-2 certification
7bab16eb-916e-5dea-b69f-9762fc8f8156 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.05 - Sealing Design
86b8ba46-7a0f-58db-8d83-492c20a46ebf |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
eb376678-9f08-517d-b4aa-8867ec5dfb56 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.06 - Bitumen approval
32637406-09a0-5e1f-8e14-71445c211526 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.07 - Bitumen Quality
f88af181-63c9-5ab2-b854-81d41cf64ceb |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
491d447f-9e79-5ff1-8fed-401afc363b7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.01 - Sealing Procedure
1a4c39a1-de5c-54c4-b3c2-edf7ceb6b57b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.02 - Sealing Inspection
218896dd-9eab-5192-8a26-a46f4c5abb73 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
cea0d395-78d4-5147-8d14-565bf0113354 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.03 - Presealing Requirements
273ec76c-88a2-582c-805b-c9c213a243c1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
61620ff3-7933-5aed-b0c8-1e7c8143d43e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.04 - Adhesion Agents
a562c829-8751-596e-b7ff-1055516312a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.05 - Post Seal Inspections
656730a1-1ccc-5c56-9c13-ab3cc8c091dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
00ebf624-dc9f-5f2d-9155-431fc9f9986d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.06 - Bedding in Chip
4b5ed222-ffda-5f45-9e69-76e1f45f1d98 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.07 - Surplus Chip Removal
1916b198-70af-56c4-bff1-7c7769ed13c8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.08 - Chipseal Repairs
7f9dec8e-7271-5da5-9bea-55b92e26145f |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
e1d62270-c8c0-539e-b474-ae4f7c376e13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.09 - Weather
5e88c62a-2eae-53cb-95ea-3deb49bda7fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.10 - Protect Road Furniture
a282d128-c55d-5653-afaa-9670669fbe3a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.11 - Joins, Overlaps & Hand Spraying
575f9d6c-2846-5cf4-8471-ffbd8a6c22a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.12 - Binder Temperature
96316dd1-6f74-5ef3-b478-1398325b01c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.13 - Binder Application Rates
746fb70d-6181-592f-88e0-9c047d62f699 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 1 | Sealing Area 1C - CH1960 - CH2220 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.14 - Chip Application Rate
e5060d41-3ec6-4058-874a-72b0cb7fb802 |  | not-started |  | folder | TRUE | FALSE | Site QA | Surfacing | Area 2
f01755a3-e563-4443-b068-edb6320de297 |  | not-started | ITP - Pavement & Surfacing - Sealing - Rev 1 | checklist | FALSE | FALSE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1
a52641de-e385-5549-af2d-d6f0afebc166 |  | not-started |  | section | FALSE | FALSE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
df29d866-0ab9-59bc-9e20-93b1a246a688 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
ba60ea94-7ba7-5f31-ba17-382a96a6a4e9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
5a4fede9-374a-57ba-abaf-d2059476072f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.02 - Sealing Chip - Production Property Test Sampling
d682731e-02cb-5553-8027-3d7100338d66 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
abf116fe-e124-53d8-b63a-29c883d99ce0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.03 - Bitumen
a10204e7-39cb-5972-9958-292c9c060ad2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.04 - Sprayer E-2 certification
47ba7d14-94d9-5727-8df4-7c4ce7414650 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.05 - Sealing Design
61a55a62-ceb7-5ae0-b522-71a12ea8e965 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
3050345a-677d-5495-af30-c685a6880ae3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.06 - Bitumen approval
8048317c-5d90-5d9e-8c48-d54765b2f019 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.07 - Bitumen Quality
533c3d47-504e-5eff-9bd0-08ccf8945676 |  | not-started |  | section | FALSE | FALSE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
b7d3efa3-2886-5a87-b651-740a46a73cab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.01 - Sealing Procedure
f51ac95c-1d1d-5dc9-986a-2680c4b8e620 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.02 - Sealing Inspection
155c4de8-94bd-53fa-812b-f4c4c1e289de |  | not-started |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
ca8590cd-7b8c-5056-b461-375f386538a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.03 - Presealing Requirements
acdc52a7-f5d6-50ed-a6c9-108f717e4955 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
e1437815-5cbd-55c9-9556-d08e62233fd8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.04 - Adhesion Agents
69a8f940-b39b-5bee-9aaf-6d140d5b0389 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.05 - Post Seal Inspections
72d67a98-e6c5-5d76-b68d-e4da4f638e88 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
4577e738-9006-5fb3-9d07-1f0b470a6c07 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.06 - Bedding in Chip
0807931a-7327-54d4-ad7e-67d0863d6d90 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.07 - Surplus Chip Removal
36373a69-1a54-538d-a8c1-22058513894f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.08 - Chipseal Repairs
0af61cad-c86a-51bc-85da-e09aa48d8a6b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
b08300c7-c438-55c4-bfca-cf399310f1c8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.09 - Weather
436f4b2d-d407-5496-976d-61eb7e044468 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.10 - Protect Road Furniture
4cbdf42b-d443-5916-a18c-8efaa4c94b3b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.11 - Joins, Overlaps & Hand Spraying
77740fd0-177c-5e66-ac31-d368f6cd7cf6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.12 - Binder Temperature
c73da468-0247-5c96-bfdc-c439e97f76a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.13 - Binder Application Rates
eb6c9e6f-2905-5f8d-8c38-cdcd736c6623 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.14 - Chip Application Rate
2b3c81e8-0334-5ff2-941f-22ee9a5f0f83 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
25dc44e8-5875-5f77-b8cd-0a4bc22cd854 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 2 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | Add Signature
930b055d-dfd1-4cfc-9e4c-8610386dc472 |  | pass |  | folder | TRUE | FALSE | Site QA | Surfacing | Area 3
25890982-54a2-451c-840e-856832f2b106 |  | pass | a83c92be17ef255d65b7d7d79441fcf3ffebdf903e4e863bc0190c282f1da53a | checklist | FALSE | FALSE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1
de99c25c-c3a0-53aa-8a67-77a993282cc1 |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
0dfa17b4-a2cd-56ca-852f-d847f707b2ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
b16e0b4f-2175-59db-84a5-09496c15af99 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
1c76da39-5244-5ac0-983c-d139ae23d6c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.02 - Sealing Chip - Production Property Test Sampling
9f06ba04-b44e-5fc1-9075-447ed048c25c |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
855e7876-12f5-585b-9722-d3d3728fec65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.03 - Bitumen
6713f10e-30dc-522a-96aa-c839d76c1b94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.04 - Sprayer E-2 certification
bdd20ae3-82d7-552c-b3c6-9353badafe1d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.05 - Sealing Design
9af903d5-b278-5875-91a0-46d15a722d7d |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
8cd9d7a4-b97c-5704-a86f-45abec761f40 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.06 - Bitumen approval
63e5b3f8-caaf-5bf0-bd32-c7af99b38447 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.07 - Bitumen Quality
08cb4ba5-6b86-5308-be73-66dc39e4360b |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
2ede99f9-09fa-587e-be3e-19fdb60fb225 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.01 - Sealing Procedure
999a793c-5ee8-577a-92b0-2210ac515b23 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.02 - Sealing Inspection
8ca19168-e549-50d3-b706-8d1ee02843b1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
9b905c1c-4323-51af-b598-26bf3e18faf6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.03 - Presealing Requirements
b2d9b404-48d0-50e4-923c-a85794b649a5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
efd4dc24-2866-5e04-90dc-cfa3127308ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.04 - Adhesion Agents
e82e3b38-abe7-5dfe-948e-beef5490ed4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.05 - Post Seal Inspections
b72cef19-0e3a-5cf7-85bc-17386e8b97af |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
4494a84f-9cb3-574b-a5c5-350b0dde9943 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.06 - Bedding in Chip
a3c32df7-27b7-5bd4-a928-5cdbc4dad545 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.07 - Surplus Chip Removal
11964983-a0fd-5a9a-9aa3-b38a8f46a1cc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.08 - Chipseal Repairs
c9611feb-6869-5734-9f70-8a2a9b3db71c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
08b8cacf-668a-53a0-9389-5d462a64189e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.09 - Weather
8fd7d873-21ce-5c9b-9a67-5b6895806974 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.10 - Protect Road Furniture
09bed0a7-a2e7-5161-b6c0-2613fb13a7cb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.11 - Joins, Overlaps & Hand Spraying
93cd3d00-95cf-58a9-8fa3-8d74917d0843 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.12 - Binder Temperature
e3a9da72-3903-55d2-b9dd-e50e2d5ba03b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.13 - Binder Application Rates
81b357dc-2784-56f1-a0cc-a72d2b2e9934 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Area 3 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.14 - Chip Application Rate
1333b98b-4737-4dfd-947e-1684739ebedb |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Surfacing | Peacockes Road
a8335768-0452-4353-b1e5-2ed7c0dfae35 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in)
5cc286e6-5d5c-4331-b87e-9b669573a0be |  | work-in-progress | a83c92be17ef255d65b7d7d79441fcf3ffebdf903e4e863bc0190c282f1da53a | checklist | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1
d5495788-87a6-580e-b4cd-5ca922c24d52 |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
93af239e-288a-5b39-8538-bdc842bd0fc1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
09685652-c6ad-5bb9-ab9a-93df8cd8998d |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
49f94576-33f4-5790-96d0-7739675f2b88 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.02 - Sealing Chip - Production Property Test Sampling
8bc2bc40-af81-5159-ad06-59b79857a1a6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
dff4186b-b406-5f41-bc5f-5e15921ecc21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.03 - Bitumen
c75c4d29-7faf-5279-98a9-bbdebce23a4b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.04 - Sprayer E-2 certification
8484bb99-7df3-5044-b071-5ec4fa4f9ac2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.05 - Sealing Design
18cfc000-568d-53a6-ad4e-38e5d286862f |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
175f5e0d-ce1f-509c-81e8-dea9162a162c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.06 - Bitumen approval
c3aad064-c228-5175-a61a-9b6a89f73aeb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.07 - Bitumen Quality
4487bce9-954f-5b67-8ad4-a270df676d0b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
0e985fa0-3cc7-5a1b-bb9d-06766016d554 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.01 - Sealing Procedure
26832404-9959-5434-bf48-ff7167d5e105 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.02 - Sealing Inspection
707a0310-393e-5014-a3d6-30d6109a2851 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
ddf0f9c5-8d63-5f29-9a90-6657940d14ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.03 - Presealing Requirements
9fbd010a-13f7-5efc-8204-62d5bbcb79b8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
9fe8225c-9ae1-54c0-a15c-57a34bee0ebe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.04 - Adhesion Agents
f707d11e-ecf0-5ac0-9b5e-aa9a578b115f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.05 - Post Seal Inspections
2c871ada-3ff1-5115-b6ba-20761a47e320 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
33d44292-3f39-59a0-b80e-376824567188 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.06 - Bedding in Chip
1bb59e41-50db-5915-bd07-25a7ffaf6f0d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.07 - Surplus Chip Removal
1e839f64-9336-509a-9770-82621d90732e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.08 - Chipseal Repairs
bb10cb60-4aaa-5e6c-ac3e-24b4ee0116f0 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
aaacb9bd-9662-5016-8b66-402e8944d093 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.09 - Weather
9d9d6b33-f164-59b0-b2b1-32cdd4fb460c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.10 - Protect Road Furniture
8a864fb0-6915-5875-b76f-3f359b80c0c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.11 - Joins, Overlaps & Hand Spraying
f8099980-a650-5090-8c50-1c1fa0762475 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.12 - Binder Temperature
334c760b-bb8f-5df5-b9c7-3e47d097f74f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.13 - Binder Application Rates
bbe8a5c5-a88b-50cc-afc1-c84ab7573651 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.14 - Chip Application Rate
9982552f-5cff-4892-bbc2-5b2a7fcadea1 |  | pass |  | folder | TRUE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860
8d5862ff-8aa8-4c8e-9c8b-57808ac8bc0d |  | pass | a83c92be17ef255d65b7d7d79441fcf3ffebdf903e4e863bc0190c282f1da53a | checklist | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1
122081cb-786e-5354-9ab3-d7be5a7f9792 |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
a0c2d671-4f69-5b63-86fe-a0f2d4d97718 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
da4aba3e-cf83-5ba6-a93d-302becc443eb |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
0a06c766-791e-51b3-a4f7-35ff6d6bbde7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.02 - Sealing Chip - Production Property Test Sampling
1eee4580-9e23-54a4-90d5-4a83723689f4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
d921ad6a-5888-5f42-b4d9-e105a9efaee1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.03 - Bitumen
af079471-a28e-5aed-a429-8796e4b3d17f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.04 - Sprayer E-2 certification
ef58fa6c-164f-5109-837d-e51d19efec2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.05 - Sealing Design
e6a06193-c003-538e-9445-affcdac254d3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
8465b8f4-254a-5802-9f55-94bc1c9bd180 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.06 - Bitumen approval
ed7909ad-4a13-5ac3-bb68-610a3f7d55c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 16.08.07 - Bitumen Quality
429794bc-26c2-5e75-a253-e01aa11c38ea |  | pass |  | section | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
40f7c8e6-6e61-5aa3-92f5-cc6a1e983411 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.01 - Sealing Procedure
7cc43b86-40da-5beb-aaae-4ca23566c591 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.02 - Sealing Inspection
402af7a4-81bc-52b2-bbc5-e406cf0f0717 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
f8b82306-1bfa-50ed-8960-bb49f59c1c72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.03 - Presealing Requirements
c3925896-6f89-5d67-973e-b4b2f0ec7177 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
9ecedbf6-bd30-52fd-a7e2-e44f501b3d2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.04 - Adhesion Agents
950e18c5-efb3-593c-a6cd-a7f237f23ec3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.05 - Post Seal Inspections
98f58f6a-9f07-5faa-ba40-2c2223afbb77 |  | pass |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
061a61cd-8182-5fc8-828d-f66e47649aed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.06 - Bedding in Chip
4c0b2805-8496-52d5-90ff-161ad543da34 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.07 - Surplus Chip Removal
9277a4a8-f5ef-52f8-9f6f-d8c6455e6078 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.08 - Chipseal Repairs
cd1e1012-a055-5f44-afea-3ef15c8fdc7c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
cdf6a6a6-7174-598b-8a9d-992ca1c539a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.09 - Weather
ea53c46d-eac6-5ab5-8286-da4d8abdc42f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.10 - Protect Road Furniture
37e8f8f1-9e60-59be-97b9-a3396701f6c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.11 - Joins, Overlaps & Hand Spraying
2b539a99-4555-53b8-897f-e3857473a084 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.12 - Binder Temperature
b4cfd609-45db-5c09-868a-33f861224225 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.13 - Binder Application Rates
d832b4b6-caf0-5d44-8481-a8d1c83fba84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1860 | ITP - Pavement & Surfacing - Sealing - Rev 1 | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.07.14 - Chip Application Rate
423d18d0-83b0-4dbb-9abb-1f3170a0da46 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Surfacing | Peacockes Road | Paving - AC20
65f914e1-8db5-4aee-b0f3-135b650ac160 |  | work-in-progress | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A | checklist | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt
caf07197-d20e-50c9-a97d-d9954a1223dc |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3 | section | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
32c950b1-97d9-5817-b9a9-fa4fdccbac72 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:93af617d-8481-4055-96e0-9f733cfd53d0 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.01.01 - Coarse Aggregate - Property Tests and Sampling
43a6f9e6-a0f0-5324-9c3a-bf3f0edd0196 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:85aab887-1ca1-41d9-bd36-10c96aa7f4f9 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.01.02 - Fine Aggregate - Property Tests and Sampling
c1bcd59a-8543-5195-8f0b-70dd40f09712 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:5d412691-91c6-4d06-9adc-375d66591c11 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.01.03 - Coarse Aggregate
7264c91d-f2e3-5185-ac62-9912629390bb |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:f84fd228-4f29-4062-a6f9-9eccd5f61616 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.01.04 - Fine Aggregate
84370239-5e87-561a-bdc3-c7f136d6d2ab |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:3903f36e-6cd4-4da7-b049-af24b1667c62 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.01.05 - Mineral Filler
f12509e6-0d19-5f2c-9d60-ac0fe8c79c32 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:d40d5892-b148-4288-ad36-0363cd8e8c5f | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.01.06 - Bitumen
54e983f9-01ab-59bf-8a6e-c2df6e80a2bd |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:e66e6e6b-9272-4dd8-93df-a876e1bde420 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.01.07 - Aggregate Wet Strength
030710a7-b715-5b7a-a3b2-d59254295cbc |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:71ae40a9-8d5b-4104-b452-fee959fdbf19 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.01.08 - Wheel tracking Testing
f5f6686f-3cfb-5075-bfd5-6af086d3ed77 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:bf5a7da0-fe54-4095-a350-0a15a956d0c6 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | 01.02.01 - Mix Design / Job Mix Formula
c28e704a-49b7-5774-822e-df86b990283f |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:cc7c9d80-ff45-4bf8-9c17-d940de7f64b3:bf5a7da0-fe54-4095-a350-0a15a956d0c6:1d9667bc-f2af-4de2-bb59-317ecb6aaaa4 | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 01 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
ed57c8a8-13af-51a2-b41b-0eb06f1c2e33 |  | work-in-progress | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb | section | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
b38845f9-e01d-54df-b247-4408cfc2cbb3 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:e485635d-cefc-4c28-902f-cc2b7a4b6c21 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.01 - Paving Plan
89854801-56ae-5451-9851-5651e28a867c |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:e485635d-cefc-4c28-902f-cc2b7a4b6c21:b1b2fe42-c0a2-4dc6-8a26-66e8838c0d1d | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
a9c9ebfc-f4a0-5f03-8ffe-d0fdc865b936 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:efd16165-e8eb-464b-b41b-87fff546411d | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.02 - Sealing Inspection
22ecd8df-265e-585a-91a2-44877cd42fff |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:efd16165-e8eb-464b-b41b-87fff546411d:8e5f2cae-1950-474e-8cf7-121796d92e60 | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | AUTHORITY HOLDPOINT
cf815197-f345-5e30-b384-5c912f87d89e |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:7435d3e1-5fd4-4c66-b713-c98b267edc58 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.03 - Weather during Paving
d4cb44a7-9b2e-5766-9b24-5500c35bc47d |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:3b8ed5ad-f7d8-4194-9710-1d0e7944ddde | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.04 - Asphaltic Prep
773e7ab9-9740-5f2c-87e9-2c5d64937467 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:c390c4b5-4590-417f-9d74-d667ec650f77 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.05 - Tack Coating
ab9f0c30-ec4e-5ccd-b06f-d039669f16ff |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:110d57cb-04ca-4adb-a247-ab318ff56ae1 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.06 - Asphalt Production Conformance
9c09fb00-b1cf-5472-91df-39ab0d795b8d |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:b747fb4a-27c9-4dc9-a3e5-253e05ae277c | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.07 - Asphalt Production Conformance -Volumetrics
57aceb30-4b86-51c1-8d74-ba66e7dae28a |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:eca13dc3-3a49-4996-864b-ec46af9cad90 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.08 - Mat Density
0aec9c5f-dd93-5f14-ba4c-a3a0018b187f |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:b0ffc1a9-c92e-45b8-a064-2b6a04d80fb9 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.09 - Joint Density
84debe32-a861-52b1-bea2-4874b3da52c2 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:76703371-f3da-463b-9fb8-6e7101c50404 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.10 - Density Testing
5d08eb17-3e8b-5b40-9629-fc900cdad784 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:c6083640-1311-4065-bd41-8dafdf4d4e54 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.11 - Core Thickness
744d2803-5fd4-5bc5-9a3f-53081079e799 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:067d2d35-0157-4d08-82f1-c83524778612 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.12 - Mat Density
f02c5e7f-dce2-5835-bf38-237f049e6a11 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:9f9a9739-fb3e-4f1d-ae64-a2a9054348e3 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.13 - Joint Density
f9790727-bb2a-516e-b751-743d7810efc0 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:53a2a340-1a8a-4048-8279-f7e09084f053 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.14 - Density Testing
7912b829-c2a0-5f6b-a584-6bc7a8e546c8 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:0d694d28-b2f8-4a6b-aae4-b7cd3b5390c0 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.15 - NDM Density
93fc85ef-048f-5e3d-83a9-a8e925862f0b |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:e1fcb6c5-69df-4b15-b863-39f931c24ad3 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.13 - Transverse truth of the surface
78d07dc4-455f-5e30-8cf5-dc4eb32fde47 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:d7aaf001-be74-4a26-8b7b-369bbcb45485 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.14 - Finished Pavement Level
fe2df52c-8294-5047-9c26-e7ddd43ea9c7 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:ab2edf96-b6da-45ec-9fab-8f1d231799c8 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.15 - Finished Pavement Alignment
22e22130-13f4-5cf5-aec5-a3bb43f9702b |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:bf6d1f5a-475a-4896-938c-57e749d9f568 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.16 - Finished Pavement Thickness
260c658e-f916-550d-bb3c-d4c1b9d2b46e |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:2ceaa4cd-8d76-43e2-aaad-10f58191a41b | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.17 - Transverse joints
f26569e6-d9f4-5fb2-80c4-d7a94d2d526b |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:af130c55-6aab-4181-a3ed-777856db8026 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.18 - Longitudinal joints
6745c670-0b34-514d-9aae-1d121fc8fbd4 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:89591b2a-f56b-4b73-85c6-3f80a6afcad0 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.19 - Asphalt delivery temperature
c7b3cb4d-0d24-5b47-a069-e9b21a1fc7de |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:b642a560-6dc0-43bc-8f88-69eb6bd3d90a | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.20 - Depth Checks - Loose during paving asphalt material
6713dee6-1eb3-500e-8eb1-7c645cb64d54 |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:e63e2155-b71b-44c4-9500-478d66a2695f | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.21 - Plateau Testing
dda01c13-a3d5-52b7-8536-005db68d04be |  | pass | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:2e2379c9-4161-42ae-bcfc-6c0af4e4ee2b | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 02.01.22 - Backfilling Core Holes
e4376cf0-5d00-5e53-b4a3-2042a4883dd3 |  | not-started | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:1e77a789-af13-43e6-8f78-7b187f881cfb:86bcfc35-c512-491f-ac73-61c1586ab3f7 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 02 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING | 28.09.01 - NAASRA
f175a683-6f40-5bf1-91bc-51273e93c9cb |  | not-started | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:d24b0ddf-f351-490f-b6c9-e82ca89dac95 | section | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
b54faaa1-00fd-5cb9-ad0f-bfbf09f7a361 |  | not-started | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:d24b0ddf-f351-490f-b6c9-e82ca89dac95:8dfae0b5-0c42-4f18-9980-c33327f9c589 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 39.02.02 - Survey Records
20a211eb-3609-5ffa-9fbb-7103fa43583c |  | not-started | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:d24b0ddf-f351-490f-b6c9-e82ca89dac95:b337798c-8444-4603-a0ed-321907226477 | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 39.02.03 - Redline Drawings
b8cadd08-097c-50c6-b9b9-b3d62490b696 |  | not-started | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:d24b0ddf-f351-490f-b6c9-e82ca89dac95:b64ee940-4979-4488-b7b2-c357adda795b | checkpoint | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
ac6f1c50-a65a-5cc1-b37b-f137ca0740dd |  | not-started | ITP - Pavement & Surfacing - AC20 - Asphalt - Rev A:d24b0ddf-f351-490f-b6c9-e82ca89dac95:b64ee940-4979-4488-b7b2-c357adda795b:e16fa880-5e03-43a8-9c0b-eb976b0144f6 | signoff | TRUE | TRUE | Site QA | Surfacing | Peacockes Road | Paving - AC20 | ITP - Pavement & Surfacing - AC20 - Asphalt | SECTION 39 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
92ab87d8-2407-4f5e-a79c-5581e5ad9e33 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Street Lighting
0fb2bee3-0c4d-4217-9056-23d49cb64ddd |  | work-in-progress | ITP - Streetlighting - Rev C | checklist | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road
4c4ec144-514d-59b3-905a-7e33adb1ddc0 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General
58c6256c-e91c-5730-abf7-0e7f0e5618c6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General | 1.1.1 - Drawings
ecd7aa4f-6c80-5724-8f44-1b5d219da74a |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General | 1.1.2 - Power Connection Application
b0d97d42-0ecc-5480-a420-afea0b01b742 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General | 1.1.3 - Construction Pack (1)
fbaf0b05-d19d-5246-b165-c8ffc51724ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General | 1.1.3 - Construction Pack (2)
ee0405ec-1eda-5b4c-a4fb-167ebd88aa8f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General | 1.1.4 - Survey Set-out
16dd738f-8e4a-58a6-acde-a41a6a87e937 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General | 1.1.5 - Environmental Protection
9153bb8d-9311-57db-b67f-318fa70c6975 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General | 1.1.6 - Stakeholder
fee97716-a251-55e4-88ae-19e6abf0f0bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 1.1 - General | 1.1.6 - Permits
9843e4ec-348a-5219-ae08-7a7d7938c4a4 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 2.1 - General
47aee2e7-bf33-5858-9bed-cc4177ef20b0 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 2.1 - General | 2.1.1 - Walk-over
f4666187-b5fc-51cb-a755-6883d8098930 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 2.1 - General | AUTHORITY HOLDPOINT
9f3e5db7-6a4a-5dc7-865c-5a789e124475 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 2.1 - General | 2.1.2 - Light Poles Materials/Delivery
2cd67e18-9d7e-59dd-bd4b-35ffa3b4a33f |  | not-started |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 3.1 - Civil (Pole) Installations
95328f96-d42b-588b-b55c-cc91847780d5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 3.1 - Civil (Pole) Installations | 3.1.1 - Ducting Backfill Material
8cb05f8d-adbd-51b6-946c-85acfb6933b6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 3.1 - Civil (Pole) Installations | 3.1.2 - Access Hatch/Door Accessibility
fe6466b7-2925-52c3-b6fd-8fbe946e91ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 3.1 - Civil (Pole) Installations | 3.1.3 - Pole Installation Positions
85277389-6935-52fe-ae41-adccfda0f770 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 3.2 - Cabling, Electrical Testing and Commissioning
71389d98-0616-584a-a8d4-a2a9c95d1194 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 3.2 - Cabling, Electrical Testing and Commissioning | 3.2.1 - Earth Wiring
d2930fa9-1e03-5866-a379-7d85173dccf4 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 3.2 - Cabling, Electrical Testing and Commissioning | 3.2.2 - Electrical Certification
e4715475-cdb9-57f6-a007-3b4031505789 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 3.2 - Cabling, Electrical Testing and Commissioning | 3.2.3 - Network Company Acceptance
727c4a0b-bf91-593d-b210-6c6aa68253f9 |  | not-started |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 4.1 - General
2c02c56f-9b71-5a0d-b550-908495b1183c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 4.1 - General | 4.1.1 - Survey Redline Drawings
c34a280d-a576-4fda-bc83-69a56f57d6fe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 4.1 - General | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
962e00d9-eae9-5bce-8bff-f4df12a6e3f1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP1 Whatukooruru Road | 4.1 - General | Add Signature
ca77d62f-e56c-4384-9c09-72de7bd1572d |  | work-in-progress | ITP - Streetlighting - Rev C | checklist | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road
72d26b3f-ab1b-532c-a575-08075eb30d53 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General
8f3fb4d5-2fc3-5e12-9aff-1a85d1a943cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General | 1.1.1 - Drawings
b540db76-3dc2-5285-a0c1-7088508f1df8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General | 1.1.2 - Power Connection Application
4c925b3b-815f-5798-afc1-6291c571b294 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General | 1.1.3 - Construction Pack (1)
9ca5c423-7696-5416-8ce0-715ce5beccde |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General | 1.1.3 - Construction Pack (2)
91b553bc-a96e-572e-8257-bf8bf71bdc8e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General | 1.1.4 - Survey Set-out
679792fe-ff8a-5868-8749-ac23042e71d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General | 1.1.5 - Environmental Protection
17f66486-ab22-5763-a4ff-3f879f71804f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General | 1.1.6 - Stakeholder
e761d84a-f303-5dad-8393-d12e7f691ce0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 1.1 - General | 1.1.6 - Permits
47d15363-5736-5cee-bccb-67a78343db23 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 2.1 - General
bcfef44f-b18c-51d4-a826-fd10f1f1615f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 2.1 - General | 2.1.1 - Walk-over
56b02fb6-63f7-539b-a2ab-4c0c0a50bed1 |  | work-in-progress |  | signoff | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 2.1 - General | AUTHORITY HOLDPOINT
cbfe8824-176b-57d9-b223-1ddba9c82976 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 2.1 - General | 2.1.2 - Light Poles Materials/Delivery
05677529-71b1-5d84-8466-20b099e9ac63 |  | not-started |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 3.1 - Civil (Pole) Installations
1015ded2-8fb9-53b6-be7f-3f3c6be86066 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 3.1 - Civil (Pole) Installations | 3.1.1 - Ducting Backfill Material
eeac7c90-0fc9-5e73-97a9-9621de436eca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 3.1 - Civil (Pole) Installations | 3.1.2 - Access Hatch/Door Accessibility
d3169159-4a21-5c36-a4f1-c22487ccb3f2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 3.1 - Civil (Pole) Installations | 3.1.3 - Pole Installation Positions
b64af4cc-e6dd-568e-92f3-ca77bbb34864 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 3.2 - Cabling, Electrical Testing and Commissioning
c92503cf-61b0-5658-b073-19f92cd91c27 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 3.2 - Cabling, Electrical Testing and Commissioning | 3.2.1 - Earth Wiring
30615592-aa17-5cec-bbb4-c3714038a41a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 3.2 - Cabling, Electrical Testing and Commissioning | 3.2.2 - Electrical Certification
e6781319-6339-5367-8a9a-238e3e41f83a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 3.2 - Cabling, Electrical Testing and Commissioning | 3.2.3 - Network Company Acceptance
dd3be953-38f1-5659-a316-032dbc0f47ae |  | not-started |  | section | FALSE | FALSE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 4.1 - General
4c3b6801-1867-504c-af19-25a34f5f8beb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 4.1 - General | 4.1.1 - Survey Redline Drawings
5595bd48-449e-44ca-b632-323b2c610ea2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 4.1 - General | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
6da48a43-329a-528d-b10e-1ded677fbe24 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Street Lighting | ITP - Streetlighting - SP2 Peacockes Road | 4.1 - General | Add Signature
ff718337-b4f5-42b1-9de3-0486671588e1 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Traffic Signals
5f0771ab-6823-49d2-b8ed-2f0c4f0d2e6b |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road
5612f46b-c0c8-4a88-8cc8-c2bdae833eb1 |  | work-in-progress | ITP - Traffic Signals - Rev B | checklist | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection
17155b23-8829-5270-bdcc-6d4911dce469 |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General
bc4a98ec-8fb8-5408-8e98-ff7caa2bf605 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.1 - Drawings
af7f7c38-a739-597b-8ce5-e47701085d65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.2 - Construction Pack (1)
353793a2-df46-5cbb-b1d1-2b86269fc642 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.2 - Construction Pack (2)
875e5f90-a41b-547b-9665-c6b96ce37c9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.3 - Survey Set-out
01df0c08-9e4c-5194-935d-226c5c92eae4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.4 - Walk-over (1)
eba0b480-8561-5940-be74-8ca7bd9e5ef9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.4 - Walk-over (2)
7c3b556b-d10b-5b2b-95c7-561ee906077e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.5 - Environmental Protection
990b0794-f85a-54d2-8293-cb9a2c8007a7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.6 - Stakeholder
ef36da9c-7d3c-58f3-850e-11d1ceaab37c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 1.1 - General | 1.1.7 - Permits
a30b8d39-d480-502c-b0c6-383c76630597 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 2.1 - General
1966e5ff-2bfd-51f6-afa3-301f770a60c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 2.1 - General | 2.1.1 - Pole Producer Statements
bb190242-c346-5c53-bb93-e5d7314147dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 2.1 - General | 2.1.2 - Controller Cabinet
78a8a50c-af4e-5f7b-9004-d0e59bd0ef93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 2.1 - General | 2.1.3 - Site ID Number
76a89626-f3b9-54cb-a3dc-2b4584328d3a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 2.1 - General | 2.1.4 - CCTV camera
51fa4462-e1c7-5941-be28-9385348294ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 2.1 - General | 2.1.5 - Communications Connection
6a1b0b18-4203-5dc2-91bc-1a443a21cf82 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 2.1 - General | 2.1.6 - Electrical Connection
d76f0645-a1f9-5967-8955-be742b47681e |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.1 - Software
b9535089-8ab0-5413-9076-647bda758cb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.1 - Software | 3.1.1 - Software/personality files and CIS
ad688f99-fd89-5083-84e1-2dc9a1c4226b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.1 - Software | 3.1.2 - Bench Test
6ec382f8-8eb9-5d76-b15a-5cf699b4da50 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
644ecc3d-c1bb-5378-9801-c0a90b95e036 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.1 - Soil Bearing Strength
5d7a82bf-eff7-5e50-97dc-4c1b545f7ab5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.2 - Pole Base Photograph
4ade44ff-832c-5bb0-be16-73ec586b9a16 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (1)
c7de7faa-855f-560c-b6bc-776eea730c70 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (2)
f573a3f7-1e07-5a18-a7d2-923017de2bba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (1)
ed9036dd-b3a7-5134-bc0d-5d6504100693 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (2)
bcac8582-7b1d-5920-be4d-51dba6a92ce0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (3)
cfd95d66-794e-5384-b302-b1f4645e240f |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.3 - Cabling and Electrical Testing
2a28364b-3160-5bee-b288-3562dbd66d4c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (1)
8111130c-ff89-5fa6-ad89-f5a71648ea5c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (2)
55fe6d2d-bf1e-5414-b907-0ac4a006a8e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.3 - Cabling and Electrical Testing | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
0d3331db-82ff-5ac8-a868-562b0ba78dc0 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.4 - Site Acceptance and Commissioning
bb84bdf4-72f7-5f73-b757-c7937a9162f7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (1)
2e11b2e2-8406-5b7e-a721-68268617b57b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (2)
66c073ae-5ea7-57bd-9d69-64e78f387b09 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.2 - Documents
1e4ead38-1f27-5e0e-880b-db0941c3ec8e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.3 - Approval to Commission
06fb56cc-e93e-50af-85a7-6c7882bdeb93 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.4 - Site Acceptance Chart
a3e24874-5dd1-5931-84ca-38330f3a1c3a |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 4.1 - General
624aae91-2f1d-5962-b3f1-8ed218498edd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 4.1 - General | 4.1.1 - Producer Statements (1)
4971b494-c221-5ae0-889c-94d951341c8f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 4.1 - General | 4.1.1 - Producer Statements (2)
7122f03d-5128-5b7a-b5ff-7852e30a043b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 4.1 - General | 4.1.2 - Site Handover/Acceptance
58570683-f7d8-51b4-bc5b-9a961566af97 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 4.1 - General | 4.1.3 - Survey Redline Drawings
ef817f6b-425b-4fdf-9a81-d0556467ba2b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 4.1 - General | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
bb5717fe-29cf-5ecb-a29c-876e1a849fcd |  | not-started |  | signoff | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ Peacockes Road | ITP - Traffic Signals - Whatukooruru / Pecockes Intersection | 4.1 - General | Add Signature
d645f4fb-c196-44fa-9064-b1d06d9692a6 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05
06316258-b450-4b28-9eac-4f5efdc9a065 |  | work-in-progress | ITP - Traffic Signals - Rev B | checklist | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection
15c11fd5-0213-5529-b0da-3de4436e8a9d |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General
27853b27-a9af-5027-bf68-89f4fbe2e021 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.1 - Drawings
2c7a3639-b5b6-584c-b902-fce4349a0f6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.2 - Construction Pack (1)
2c004e8f-a8d0-5740-a998-c9040837faaf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.2 - Construction Pack (2)
fd229e9c-ebef-58f8-a027-5f535c54b4f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.3 - Survey Set-out
8261a6b1-fb82-5273-8d1a-5799f553511b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.4 - Walk-over (1)
6dab4c6f-9bf4-5d4b-aca6-3c49b28c7ce8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.4 - Walk-over (2)
3d6133f4-ea31-5807-a3a9-260e1913c14c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.5 - Environmental Protection
d950d3b2-33c4-5864-8220-91eaa4d1d211 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.6 - Stakeholder
bc42a02f-2f8c-5546-a964-0797f3b18961 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 1.1 - General | 1.1.7 - Permits
88bfbbf4-5d63-5cf1-a958-b1f501428d91 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 2.1 - General
56d9bff7-4e53-556a-b2d9-d49c0366a1e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 2.1 - General | 2.1.1 - Pole Producer Statements
c6eb3958-ba87-5fa8-9e60-96c25576b2de |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 2.1 - General | 2.1.2 - Controller Cabinet
517060bf-20f8-5afd-b027-240b49ae3a56 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 2.1 - General | 2.1.3 - Site ID Number
7a8de8e6-1f33-5d9b-968a-eb7f2b898310 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 2.1 - General | 2.1.4 - CCTV camera
aee7903b-a288-51ee-979e-d6b7f0e3d9c7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 2.1 - General | 2.1.5 - Communications Connection
54a84227-e969-58e0-a5ea-d2ad3b5604d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 2.1 - General | 2.1.6 - Electrical Connection
9a9ee22c-45cf-5d53-9772-6d5c357e2747 |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.1 - Software
21c4918a-eda9-556c-8fdc-c114580ee28d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.1 - Software | 3.1.1 - Software/personality files and CIS
efec29fc-7f40-59fc-82e7-ccf6c195cef5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.1 - Software | 3.1.2 - Bench Test
5a8e724a-5620-5bac-8e09-0f2e30f2c0c9 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
e24d6323-660d-5668-b34b-02696b77c57c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.1 - Soil Bearing Strength
7f9f8215-a6ea-54ba-8e47-64813bbdecc6 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.2 - Pole Base Photograph
cfc8e9d5-8575-5417-9677-76c0715ab2f7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (1)
4ea6d5c6-7586-5556-9375-8113543dceca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (2)
4ee02fa6-01c9-541b-8d32-89b7cd1fd25d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (1)
6d2f7cb0-19c8-59bb-8493-6a12ab8652df |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (2)
926537e8-505c-542d-bb79-462be9530c6b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (3)
7b7d0931-f736-5102-b0e4-cf6346c43d39 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.3 - Cabling and Electrical Testing
c5361cab-fc53-51b8-bfc1-68ae51c7e733 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (1)
d7b3fbd1-50e8-58e4-98a9-7dffe45a9a3a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (2)
e9035a95-daaa-5877-8715-3c4dce5882e6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.3 - Cabling and Electrical Testing | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
715df7b9-6742-5759-a712-aa94782336b7 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.4 - Site Acceptance and Commissioning
4ed0d241-eee3-5355-8604-229a8f7bf8a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (1)
68f2b7a4-27d9-5ff4-ba30-a5c41511afd7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (2)
66db34cf-e81a-5c81-a857-e4d34ba1524b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.2 - Documents
edd62424-9666-556c-878e-6b9f14ff78c3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.3 - Approval to Commission
94dfac9d-1bb3-511c-b51b-f0171d631bc8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.4 - Site Acceptance Chart
76839c63-b508-523e-8627-7b3be7da257d |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 4.1 - General
0a1a4b4e-e822-56c1-aad5-4965282276ab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 4.1 - General | 4.1.1 - Producer Statements (1)
5038427b-8132-574c-8bf3-f391d7071e74 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 4.1 - General | 4.1.1 - Producer Statements (2)
acc8a8bc-cc06-5c19-90e0-089d34f43855 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 4.1 - General | 4.1.2 - Site Handover/Acceptance
ed3d51d0-af07-5231-acbf-ca29b42d0ef2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 4.1 - General | 4.1.3 - Survey Redline Drawings
cb1caf27-bfe2-43ef-8c2f-62d0e98db3d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 4.1 - General | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
cb72f33a-c10e-53bf-b2b9-fcece57373c1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS05 | ITP - Traffic Signals - Road 5 / Whatukooruru Intersection | 4.1 - General | Add Signature
74d4aa32-5ba9-4382-895f-d6f8ae959ebb |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06
331f537b-956d-4783-af3f-385fc0c358ea |  | work-in-progress | ITP - Traffic Signals - Rev B | checklist | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection
ce330178-682a-5892-a971-b305c1e97a5a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General
1fb6ed54-a646-5a3b-8872-8b635ffeff1a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.1 - Drawings
67e9d6bb-beaf-54c3-8402-273098cf25cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.2 - Construction Pack (1)
a087ef5f-318a-5cdc-9b75-04dbbf72d262 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.2 - Construction Pack (2)
179bea6d-7b54-5d0c-8fa4-5e7a06173542 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.3 - Survey Set-out
c5da7274-c123-59be-acd6-a70615c3a11b |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.4 - Walk-over (1)
fc84643a-8956-5e0c-90c6-e95c2c3c4e97 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.4 - Walk-over (2)
2feeeb10-7155-52c5-9cf1-2e0d0c0908ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.5 - Environmental Protection
ee22485f-cf51-58b8-8fd2-8e8817a97fdb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.6 - Stakeholder
1e37982b-81b2-5b69-979e-fa0863b8728f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 1.1 - General | 1.1.7 - Permits
60e4b15a-7658-5497-8642-ba41dae7ea46 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 2.1 - General
6479389d-8c6c-5106-a52e-c064dc183c16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 2.1 - General | 2.1.1 - Pole Producer Statements
27d06736-2aaa-5577-8cbd-6a468ea51a1f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 2.1 - General | 2.1.2 - Controller Cabinet
e216c787-7905-5a14-ab6a-ac72ed599088 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 2.1 - General | 2.1.3 - Site ID Number
f52f72c4-c5b1-5209-a0ac-e1ed58e89273 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 2.1 - General | 2.1.4 - CCTV camera
24196536-91be-5917-b914-0c36b2ef5325 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 2.1 - General | 2.1.5 - Communications Connection
e98125b8-ceb2-5760-9116-9a2a2cf660d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 2.1 - General | 2.1.6 - Electrical Connection
cd56d77b-1f29-50b0-9d6f-1ab0a7cc8eba |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.1 - Software
4dea1161-7ba8-565f-ab3e-8b326791e97c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.1 - Software | 3.1.1 - Software/personality files and CIS
8c0fce2b-b309-5d6d-a76e-85aef477c0a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.1 - Software | 3.1.2 - Bench Test
f4288f64-537c-5db6-9034-faa2a56c44bf |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
11a23b68-d8dc-51ff-9f66-3617ce479fa8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.1 - Soil Bearing Strength
c103c7f6-8a7d-5a8d-a2bd-bc84f29e45e9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.2 - Pole Base Photograph
8972fa21-7317-57cf-bef7-4efec241d796 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (1)
e84499a1-2a39-5945-be57-0c261f380bac |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (2)
ed86348b-3ab7-5611-b675-6169f80df136 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (1)
5da5e7da-627d-5471-be04-707193f96d21 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (2)
bd2c1d65-e79e-5817-9027-d65389e2a74b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (3)
2fa47f5e-8981-517f-918f-7565410594dd |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.3 - Cabling and Electrical Testing
2b673754-f5e4-5103-a6d0-382dbd401666 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (1)
79da5c0c-3a18-5dfb-adfc-dffe49783b0a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (2)
3da7d9fa-ecdc-5d82-b868-86b60f8bebe4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.3 - Cabling and Electrical Testing | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
b8c17d66-9c3c-59ea-b4d2-c2345e2389b2 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.4 - Site Acceptance and Commissioning
fe163047-19e5-5674-9db7-d1a9033d3496 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (1)
cb90095e-0440-56f9-afa2-15c7f9364299 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (2)
85ca1483-0d0c-5926-861b-5c2b0617340d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.2 - Documents
595aca76-363c-5190-986b-9ed9fd45d28c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.3 - Approval to Commission
e4beb2f6-0b7f-5a61-a1c3-783f8f4a6d05 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.4 - Site Acceptance Chart
c170cf91-8c95-5341-bd18-97688b85936e |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 4.1 - General
554287bf-06a6-5aa5-a09b-6d9c1ece4039 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 4.1 - General | 4.1.1 - Producer Statements (1)
573ae9f1-60c7-5d4f-96e2-6394116342fc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 4.1 - General | 4.1.1 - Producer Statements (2)
b61e8e97-1c05-5b5e-8fae-9ebead253069 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 4.1 - General | 4.1.2 - Site Handover/Acceptance
58eefd96-ffba-500a-bee1-f7bc1421baa8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 4.1 - General | 4.1.3 - Survey Redline Drawings
94afcef7-3396-43a2-a94a-de2153192f47 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 4.1 - General | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
c2f1f1f3-3a4a-5e8c-952b-0fa2e15c6cf5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Traffic Signals | Whatakooruru Drive/ RS06 | ITP - Traffic Signals - Road 6 / Whatuooruru Intersection | 4.1 - General | Add Signature
0e4eb7a9-89e6-4007-823e-1dec22dcccbb |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21
329778b9-22c3-4d0a-96a7-115ee36c0ffe |  | work-in-progress | ITP - Traffic Signals - Rev B | checklist | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection
8fafae7c-ce2e-5360-a288-539afa0d277f |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General
bb13958d-3b29-5d20-b6c6-e90d4ec0d226 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.1 - Drawings
ab6f5ccb-2223-5c66-90d3-6301925c7d11 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.2 - Construction Pack (1)
00029707-db12-5a61-8fda-a1bd5371ee4f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.2 - Construction Pack (2)
e6766e30-4c1f-5db6-8604-6c8cc3e66c1d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.3 - Survey Set-out
c9d45953-dd16-5129-8df4-9c2453dc8d34 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.4 - Walk-over (1)
2dfbcd02-6aae-5c17-abd3-1093add42b4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.4 - Walk-over (2)
8f7e5cc3-1339-5717-829c-773bdb8e86b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.5 - Environmental Protection
5eeab0ad-8f2b-58fd-88e0-c00edf4a1400 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.6 - Stakeholder
65bbdc27-2317-5632-bbf5-835ecaee7ba5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 1.1 - General | 1.1.7 - Permits
47c18a44-adf0-5e50-a207-8a4315807fb2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 2.1 - General
3b507696-9b25-5f7e-98cd-d6eddee6f101 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 2.1 - General | 2.1.1 - Pole Producer Statements
3f207ec6-405e-5bf6-9387-7888997b7168 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 2.1 - General | 2.1.2 - Controller Cabinet
216b716c-ae2c-544f-9514-77d02f4a5d91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 2.1 - General | 2.1.3 - Site ID Number
91be6146-86d7-5c73-bf3c-380ec071d144 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 2.1 - General | 2.1.4 - CCTV camera
0e54cf74-0b58-5af5-9d66-9a33c09aea28 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 2.1 - General | 2.1.5 - Communications Connection
b2cab736-70ad-55c7-bc7f-37e63e788257 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 2.1 - General | 2.1.6 - Electrical Connection
ea7a369e-fdaa-58fd-affe-3e6b10bef37d |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.1 - Software
f2a71dab-eb7c-5001-9f0d-8cff2fd86add |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.1 - Software | 3.1.1 - Software/personality files and CIS
8ae2f6ed-a861-5647-ad95-a1e6e550c513 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.1 - Software | 3.1.2 - Bench Test
575ba5e6-6206-5369-b8cb-aab017acb277 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
a54c356a-5fc5-5aa1-8792-1fcee039f276 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.1 - Soil Bearing Strength
32603cd6-6206-5cd6-9798-cd20ec950429 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.2 - Pole Base Photograph
ce9f7fd1-26b9-57a0-9ab2-addf6bb58acd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (1)
d2bcd4dc-ef1d-5ce2-8b82-ced523a7d959 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (2)
5864b921-5ca3-5e6a-9b4e-128f4fe862e4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (1)
c3ea06c6-e157-5cec-95f0-3fe7b6e6a941 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (2)
3417ca87-3aeb-5b35-87d3-638633b629b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (3)
b11e2f83-20ec-58ba-9988-5f9c238f4688 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.3 - Cabling and Electrical Testing
bf6bc711-2e27-5ea7-bf0f-e9e41e1d2f8d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (1)
151c4c26-9fe3-5e73-9c7d-c082fa018ed1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (2)
8b78a825-e285-5fc4-a375-df0582b0ea49 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.3 - Cabling and Electrical Testing | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
a49b41d6-aa5f-54b6-920d-9c8e2b39f4ce |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.4 - Site Acceptance and Commissioning
0f1f3ea7-7726-57aa-ac33-f3ce42a87c99 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (1)
de2af31d-9e1f-5ad3-b058-06d7c871a8e0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (2)
9ec9d21e-51ff-515e-b569-cff3e99d5f23 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.2 - Documents
27a2fab8-065e-53f4-9df7-624783e0a67f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.3 - Approval to Commission
282abb0d-25d5-5300-aebc-0cc0453e5679 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.4 - Site Acceptance Chart
aad4d59f-2fbf-52d6-b4d3-eef2ccf05a67 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 4.1 - General
898d6ed1-08ab-5cda-a489-8f0d57deb11a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 4.1 - General | 4.1.1 - Producer Statements (1)
370e1005-0bd1-5b00-8427-701970a092bc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 4.1 - General | 4.1.1 - Producer Statements (2)
127461d2-247d-5f6a-9597-22e3bbbfe0bf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 4.1 - General | 4.1.2 - Site Handover/Acceptance
36619df1-badd-5203-8697-cbe34777c692 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 4.1 - General | 4.1.3 - Survey Redline Drawings
fbe63f0c-463a-4573-a794-b50ed6e1901c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 4.1 - General | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
111a4172-21c5-5b89-a43d-f3d522a0c0a6 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS21 | ITP - Traffic Signals - Road 21 / Peacockes Intersection | 4.1 - General | Add Signature
5bf6968a-7a98-43e6-92c0-f904b57da980 |  | not-applicable |  | folder | TRUE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED)
aa800302-d167-4d16-9a24-1faae902af12 |  | not-applicable | acc2b89cb863d8d6e6735a13cbb5225bf02fad07656ee7446412807f5fbc421c | checklist | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B
a179bc16-f9b1-5fd6-bba1-fe324f40c654 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General
14a39d8c-489d-5ed6-a1fd-70e8f0f8c44c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.1 - Drawings
5e18613a-5f38-5f11-8108-4a85eb526dd6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.2 - Construction Pack (1)
2430d631-065f-502f-821b-247d0c25ba17 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.2 - Construction Pack (2)
9676c14a-a3ca-5034-a344-795829be596d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.3 - Survey Set-out
94fb8637-a625-5e6d-a94a-9a063198a205 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.4 - Walk-over (1)
8155db71-ce43-5928-8469-183151444daa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.4 - Walk-over (2)
889593bc-39d1-5321-921d-29c738713152 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.5 - Environmental Protection
51b4ea5b-811c-5a7e-91db-d42ad11b757b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.6 - Stakeholder
3ddcfc5c-f522-5b90-bbbd-01a8ffa41f32 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 1.1 - General | 1.1.7 - Permits
51225e2a-6a21-5674-a54f-7b6a4d84724e |  | not-applicable |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 2.1 - General
3f720107-353d-5959-80cf-a42b3632cf0e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 2.1 - General | 2.1.1 - Pole Producer Statements
2f696e27-9840-547b-862e-e21d985f2543 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 2.1 - General | 2.1.2 - Controller Cabinet
9e9c4712-6c57-526a-a424-8be08af4c319 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 2.1 - General | 2.1.3 - Site ID Number
23e201ce-76a7-517a-8a89-4d90667f40ce |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 2.1 - General | 2.1.4 - CCTV camera
11dbc542-c783-5bb4-b385-5e3a81bff73a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 2.1 - General | 2.1.5 - Communications Connection
7d2d8686-624c-5243-babe-2a81da45d1e2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 2.1 - General | 2.1.6 - Electrical Connection
bd8ffb17-896d-5b9d-80e4-768a028c36bd |  | not-applicable |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.1 - Software
f9870f54-3a0e-587a-9cae-70d304b40441 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.1 - Software | 3.1.1 - Software/personality files and CIS
fad25978-4c91-54fd-a299-34c2f960ac28 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.1 - Software | 3.1.2 - Bench Test
db5faa75-9110-5086-a1cd-4dcf28d1c801 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
f93eb4f3-c6fe-5d76-a600-e893f946f7a0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.1 - Soil Bearing Strength
79fc9e8a-f26a-5b76-b065-0e31257356f3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.2 - Pole Base Photograph
91f14bf8-89a4-5d5f-b7de-f6df5551bc97 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (1)
7a043456-bc0b-5d87-9bb4-e5a4c9d1801a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (2)
29f521a9-f5a1-5924-93c7-59172ef6dfdf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (1)
07139ea5-f8dd-5d34-8a19-94a8a675cae1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (2)
2d263883-918f-5bcd-bd3a-e3ba0bca9d3d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (3)
88da648e-13aa-5be1-9545-207e393d440f |  | not-applicable |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.3 - Cabling and Electrical Testing
ddbe9ba1-f535-5be9-9ea2-d1ce07dbe0de |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (1)
2b52d327-8876-566c-9348-20c56d47b537 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (2)
08a59097-69c4-5b86-be02-8ed58930183b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.3 - Cabling and Electrical Testing | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
ce4fa307-bb82-57f4-945a-3fd45032a7ea |  | not-applicable |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.4 - Site Acceptance and Commissioning
3e907dbc-90b4-504e-afb4-3c9b0842ab68 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (1)
a0a0c2c0-6de1-5029-8026-69357db1bab1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (2)
a66e2d4a-87ef-50d2-b022-9b2feee87cf9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.4 - Site Acceptance and Commissioning | 3.4.2 - Documents
b6899076-9f9a-5af7-9487-02a035b86288 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.4 - Site Acceptance and Commissioning | 3.4.3 - Approval to Commission
bb6bee1e-dc28-5151-9804-51bfe5773a04 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 3.4 - Site Acceptance and Commissioning | 3.4.4 - Site Acceptance Chart
e6438a8a-1c27-5b08-81b1-126eb13efd5b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 4.1 - General
d0ee2486-a632-5f99-9cd5-80e54ad0fe6c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 4.1 - General | 4.1.1 - Producer Statements (1)
0509936e-24b4-508e-809a-dcb23d9ff64d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 4.1 - General | 4.1.1 - Producer Statements (2)
7a4eba50-e313-5220-b3ce-94e559c89792 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 4.1 - General | 4.1.2 - Site Handover/Acceptance
aa04fe80-8633-581a-a2b8-a644e18d83fe |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B | 4.1 - General | 4.1.3 - Survey Redline Drawings
be1b69e3-faf7-4f94-ab6d-bb3c514429e5 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A
2ee153a9-ea13-4110-8b9b-e34a481dbbf8 |  | work-in-progress | ITP - Traffic Signals - Rev B | checklist | FALSE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection
6008ad85-78b4-5c54-91b9-57ecbfc7b933 |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General
8b215107-0bfa-5ad2-a72a-7f8b90a61be3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.1 - Drawings
8343f442-192e-5811-a1f2-d79ec99d5a6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.2 - Construction Pack (1)
1041ab7b-b65d-5873-957a-bc1a1e69c962 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.2 - Construction Pack (2)
8fde28b1-8057-502e-a462-bb6cea32495d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.3 - Survey Set-out
cd7b59cb-51a4-599e-a8fa-661c81618b75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.4 - Walk-over (1)
6bc38d52-ebf8-55fe-96c0-1ed296ba6d2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.4 - Walk-over (2)
3fa21735-64df-56d8-b7e4-617fa8cb0a3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.5 - Environmental Protection
af696e97-e844-5cc4-a825-b6a3c74ccdc7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.6 - Stakeholder
bc796b2b-9e00-52cd-a481-678afa9e36fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 1.1 - General | 1.1.7 - Permits
fc2391eb-1ece-5244-b003-c97a48242590 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 2.1 - General
69bb9134-62ec-5321-bbf6-616fd97acfa1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 2.1 - General | 2.1.1 - Pole Producer Statements
49b0cdf8-58a1-50bd-bc87-5fa7810858ec |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 2.1 - General | 2.1.2 - Controller Cabinet
e2daf276-cec6-5da0-bcf2-d6327cee694c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 2.1 - General | 2.1.3 - Site ID Number
9d308c3f-453e-5929-b7f1-369360efc1f7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 2.1 - General | 2.1.4 - CCTV camera
49a72809-d73d-50e6-b141-44fcfcf9ca80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 2.1 - General | 2.1.5 - Communications Connection
3d14167d-28b0-54e2-8da7-5e0cb346eb5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 2.1 - General | 2.1.6 - Electrical Connection
7db31cf4-cde2-5c24-9391-e1ace308fcfe |  | pass |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.1 - Software
ec5fd8db-fb7f-53b3-92d0-5dfeebd87730 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.1 - Software | 3.1.1 - Software/personality files and CIS
acb00494-c48c-5d1f-9e5c-b27994aafb4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.1 - Software | 3.1.2 - Bench Test
bf7e50e2-b6e6-51dc-9f1c-41159d6fea0b |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
6a0bd990-1a51-5154-946c-693e2e2b2931 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.1 - Soil Bearing Strength
d49d94d1-9159-554f-b458-55aa026e24d5 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.2 - Pole Base Photograph
7ce118e4-1433-5411-8f54-9af1bf91b77e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (1)
6a22a4a3-dce2-53d1-abf9-ac6fbd07e15f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.5 - Identification Numbers (2)
fc24ee88-06f0-5713-b250-d009ca7a807f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (1)
5d24c09f-95fc-51f6-b8fe-5c112331d0d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (2)
03c4c815-ba3c-51c4-9d2d-201014a2496a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations | 3.2.6 - Mow Strip / Concrete Surrounds (3)
d59078fe-0acf-52ad-8c15-059fd63028c4 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.3 - Cabling and Electrical Testing
e8571689-b413-5df4-bba4-21e4da05c50b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (1)
b3976a2a-669f-55a8-a85c-4484421ae391 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.3 - Cabling and Electrical Testing | 3.3.1 - Loop Cutting (2)
202c8994-26b5-5440-af00-08420e2a3dc6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.3 - Cabling and Electrical Testing | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
52312c04-d672-5fb8-8140-3e0d322dafb2 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.4 - Site Acceptance and Commissioning
25125425-ad58-5673-9efd-5bd3693e5eb3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (1)
158bebf3-6abd-58e3-8fe1-8b77a803b02a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.1 - SCATS Connection (2)
d1a9a017-b3bc-50a1-a689-5822511f834e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.2 - Documents
c2491977-3b82-526a-8557-ac9597a35453 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.3 - Approval to Commission
d9e76a4e-f18c-5053-893f-68b6e703cbcb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 3.4 - Site Acceptance and Commissioning | 3.4.4 - Site Acceptance Chart
ee97df4b-2c2c-5760-94d8-1702557d6486 |  | not-started |  | section | FALSE | FALSE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 4.1 - General
8579c34b-b2cb-5b92-93de-ba01ee95dce4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 4.1 - General | 4.1.1 - Producer Statements (1)
4ca968d3-4dfa-5b5b-b4de-c1c78fdeb831 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 4.1 - General | 4.1.1 - Producer Statements (2)
1ac060e5-c476-5a2d-a2c0-ed7557671f39 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 4.1 - General | 4.1.2 - Site Handover/Acceptance
d2b8e6b4-8588-5cef-a8a5-6cddc7c9a889 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 4.1 - General | 4.1.3 - Survey Redline Drawings
2716af93-2377-453c-a542-add88b97beb3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 4.1 - General | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
1e3466f8-4f36-5837-a194-913021e25fc3 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Traffic Signals | Whatukooruru Drive/ Road A | ITP - Traffic Signals - Whatukooruru / Road A Intersection | 4.1 - General | Add Signature
d62d02b1-7770-4a5a-b6a9-b2827c4086d5 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Barriers
7d5964eb-ecf0-4160-9015-b9a4860aef5c |  | no-status-not-started |  | folder | TRUE | FALSE | Site QA | Barriers | Area 1
a11f0e08-1362-427f-a9d0-b7b3bea50ad6 |  | no-status-not-started |  | folder | TRUE | FALSE | Site QA | Barriers | Area 2
61b991aa-4261-446c-9547-636247a8988d |  | no-status-not-started |  | folder | TRUE | FALSE | Site QA | Barriers | Area 3
6144e07d-0c94-44fe-8764-8386b89f96f1 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Barriers | Peacockes Road
7b81aa4c-d7fa-425e-8a03-12e989d7480d |  | work-in-progress | ITP - 135 - Signage Rev B | checklist | FALSE | FALSE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP
c64e062d-5925-5cfd-8b60-ca7f8b62abc8 |  | work-in-progress | ITP - 135 - Signage Rev B:e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e | section | FALSE | FALSE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
ab98ad48-ddbd-5750-b70e-0fc71eb889d9 |  | pass | ITP - 135 - Signage Rev B:e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e:efb997ca-5ac3-4799-a350-5b11fffef586 | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
c063b784-cc3f-5117-aa55-dbff421b66f4 |  | not-started | ITP - 135 - Signage Rev B:e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e:59cfed46-ab28-473f-91dc-c83d40463b0c | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
ef2a027b-6ec3-5fba-90b1-1c9647adacd4 |  | not-started | ITP - 135 - Signage Rev B:e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e:8cb668ba-dd0f-4532-acab-e8718618b2ec | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
9bf968e9-8dcc-503e-946a-2ab1bab6b96f |  | not-started | ITP - 135 - Signage Rev B:e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e:f76873a6-12ce-4288-a49b-2df804faaab6 | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
67a06e2b-a0c8-5706-a44d-000f2aff361d |  | not-started | ITP - 135 - Signage Rev B:e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e:ea1253c3-0871-4aa4-ad5b-30e6caf5d33c | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
2cedc894-8e17-5b2b-b426-a093018a56a4 |  | not-started | ITP - 135 - Signage Rev B:e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e:2fc6ae45-d2ef-4dbf-a57b-da7a09613bce | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
d5cc904c-e54d-56b9-8b07-328206438b2e |  | not-started | ITP - 135 - Signage Rev B:e502dcb4-9ed5-46e8-91f0-0dfb6d5c9b5e:528bcb1a-42b4-4c7f-a899-5bc5377d9f8b | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.07 - Subcontractors
34195426-9d09-5cdf-8a12-742f152a45ea |  | not-started | ITP - 135 - Signage Rev B:98e43908-a6fd-460d-a1e8-cae69ac42ba7 | section | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
0c2b6a41-5cc3-5539-9690-598e7693ca16 |  | not-started | ITP - 135 - Signage Rev B:98e43908-a6fd-460d-a1e8-cae69ac42ba7:2f984469-85af-437f-b44f-b731b0fcbb7b | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.01 - Concrete
8234e856-944d-5edc-983e-ebbea19c0322 |  | not-started | ITP - 135 - Signage Rev B:98e43908-a6fd-460d-a1e8-cae69ac42ba7:0b05d125-015e-46ba-b61e-9cd2b81b79f5 | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL | 4.01.02 - Steelworks
733aae4f-35c1-5a1b-8664-2a1f5581b12e |  | not-started | ITP - 135 - Signage Rev B:e9227117-b3fe-46d7-aced-a19bead5c4a7 | section | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 5 – CONSTRUCTION ACTIVITY
320b96ca-a0bb-5263-9563-35be422c5a6d |  | not-started | ITP - 135 - Signage Rev B:e9227117-b3fe-46d7-aced-a19bead5c4a7:826f3d46-1f09-4fc7-80bd-14825f2de55e | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.01 - Signage Location
f37edbab-2b52-5d2c-a788-dd317c3f2b14 |  | not-started | ITP - 135 - Signage Rev B:e9227117-b3fe-46d7-aced-a19bead5c4a7:826f3d46-1f09-4fc7-80bd-14825f2de55e:b9b9fd2b-859b-46e8-b4dd-81e813506cfd | signoff | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 5 – CONSTRUCTION ACTIVITY | AUTHORITY HOLDPOINT
e828623b-417c-50ee-aa65-1d3e000b5181 |  | not-started | ITP - 135 - Signage Rev B:e9227117-b3fe-46d7-aced-a19bead5c4a7:40af3d67-a1d5-437d-9319-5eaf5618aa11 | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.02 - Footings (Sockets)
d3575ab0-0672-53d5-bd12-94e3105b7f7e |  | not-started | ITP - 135 - Signage Rev B:e9227117-b3fe-46d7-aced-a19bead5c4a7:11efe1e6-6c9c-404d-bf11-64e379e48f24 | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 5 – CONSTRUCTION ACTIVITY | 5.01.03 - Sign Installation
c878470b-4498-5c09-9e2d-774d51ac5252 |  | not-started | ITP - 135 - Signage Rev B:f58d5e0e-605a-40ba-9481-46f17ab46c3a | section | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
1e9c96ca-4c9a-5c26-8098-ecc626b03a49 |  | not-started | ITP - 135 - Signage Rev B:f58d5e0e-605a-40ba-9481-46f17ab46c3a:e97b6b00-3a47-4e70-9672-bfd9c911d014 | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.01 - Red-line Markup
8e0f7fa0-4ad6-500a-b2a3-9773f87f165b |  | not-started | ITP - 135 - Signage Rev B:f58d5e0e-605a-40ba-9481-46f17ab46c3a:bced1797-4abf-4681-9959-7050db1f57b3 | checkpoint | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
0809b753-def6-54ac-a4a7-324ac452ccf9 |  | not-started | ITP - 135 - Signage Rev B:f58d5e0e-605a-40ba-9481-46f17ab46c3a:bced1797-4abf-4681-9959-7050db1f57b3:246908ec-6358-4121-9cf5-f92b15220d46 | signoff | TRUE | TRUE | Site QA | Barriers | Peacockes Road | Peacocke's Road Signage ITP | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
b1bb4e7b-2f9c-4c99-ac42-def891227c56 |  | fail |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge
de8be510-5de2-4fc6-9954-1716e9af2414 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall
d05e0765-ad58-4eb4-ba32-bd0a991d7196 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A
3724b744-b2ba-4859-85ed-a190f91edde0 |  | pass | Stone Strong Wall Installation Checklist | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist
61f958aa-f406-52dd-b21e-10fa04bb88d3 |  | no-status-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Details
fa2c62b9-8737-5c10-92a9-c8ed8af2ce51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Level foundation installed as per design. (Base layer only)
b2cda6c4-cbdf-53e6-bdbb-be5bf2c5d26a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | 2 x Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Tramsfer Platform. (Base layer only)
c42cdba2-e47f-526d-a5ca-5a226d965884 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Blocks Installed within specification tollerances & block pattern as per design drawings
2bf8eeb0-650c-5f03-b32e-baf7cc2d96b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | The correct number & length of parawebs are to be installed as shown on the construction drawings.
2798ba6a-1a5b-5094-bc48-452a383d3ec3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Paraweb is to be placed flat or with a 1% fall toward the rear of the wall.
317c6074-181a-58c1-8e7f-7214163a33b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | 150mm of fill cover is required before construction equipment can travel over the area
afbe79f8-fb4b-505f-a46d-bf67123f43a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Backfill installed in max 250mm lifts
bf3dad34-4b8d-581f-a24d-21b73753c780 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Proof roll completed on each layer
c59766fd-ecf3-5eae-92a5-39ddfc3387e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | NDM testing completed
a1397d82-8746-5af7-9733-627266935989 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Clegg testing completed (GAP65 only)
bab5844c-2822-5915-9a99-236b8811546a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Scala testing completed (Sand only)
722d8af9-48ae-5139-9b96-0a6aeaf5745d |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | ADDITIONAL NOTES:
eab039e5-e50b-4855-9bbb-92d8965380f0 |  | pass | f1864b69de1a686d46caac1366faae8ebaf4ba8c283eef7ba2ba6429f5c6540e | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls
c1721a59-344a-53c9-9e1d-adb53567a236 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
d1d90d35-10a0-5288-8bf1-0057329a4fb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
e1a68eee-5144-5772-b387-e3adead2688b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
cf9cba69-1bd5-5ee9-897d-e87d6c46ba68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
d3b6a569-b8e6-5310-82ed-9511a6a13857 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
6c4a7d39-2f85-59de-aa02-88c08cf924cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
59bdf536-dc2d-5a22-acd6-840f3c5f55a3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
5bfaf173-1e89-5594-a0ed-a743a921cde5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
a502ad1f-91eb-53e8-a22c-175bce03f9fb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
b1876406-910d-53f0-ba17-1745b64c5d40 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.01 - Stone Strong Block Molds
f8858cb5-87d0-5d92-9a23-6d0146c05910 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.02 - MSE retaining wall backfill Material
20f89019-1fe4-503f-a9d9-8051ba914992 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.03 - Geogrid
6e0eaa85-152c-50df-a9a3-f6df42047be0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.04 - Para web
73e3d50d-04fc-571c-b26b-0c2b5bb0484c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.05 - Drainage Pipes
259ab1b5-15c8-5b73-8308-12ac696faccf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.06 - Geocomposite drainage board
df3a9114-8e26-5ea6-b002-58b4c8567923 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
a5c4d705-ef35-5206-9b1a-816b1e45a4a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.01 - Excavation to subgrade
b0edafbe-82a6-57c0-b77b-8fcb8cb597b7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.02 - Foundation Approval
37ea1ee9-d4fe-509c-a312-09dfb7a23fe8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
4445643c-31af-52a3-bf41-73a4112c9c98 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.03 - Undercut subgrade
49644add-35f8-5a09-a578-a5bd52119930 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.04 - Undercut backfill compaction
0773901a-3e90-586f-b609-dc3badc180c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.05 - Geogrid Installation
0c655fde-20c5-5cda-9938-843c2edd0d9d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
1aeeafd5-2e39-53ef-9211-f42dec2d1ba8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.06 - Backfill Installation
6f81b28d-14ca-5638-9ffd-912534043270 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
bf511e40-f563-5730-96e5-b23ec4276935 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.08 - Clegg/Proofroll (Gap 65)
727f6104-1e09-51fb-9964-9688e3feba0c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
1cd48db4-6232-51a6-9375-25c66d6f3cdf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.09 - Scala Penetrometer (Hinuera Sand)
92aca17c-5a83-5b44-befa-9142fa5b5251 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.01 - Level founding platform
ae54a39f-6106-5462-b722-251e137560a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.02 - Installation of blocks
53e24466-924f-5820-b398-8ca81118cb7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.03 - Paraweb Installation
9f23080e-cf5d-5484-b5ab-6e7cf45fb358 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.04 - Geotextile
b6165cb7-aece-56f5-96b1-4f654f614a4b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.05 - Drainage Outlet Installation
e8c36e68-9edf-5de4-80c6-d3ae89c7f45a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.06 - Backfill Installation
b234f7c3-ba27-5bf8-8ad4-69635fa522cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
aee4a1f7-706d-5d6d-8897-69cef93f35eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.08 - Clegg/Proofroll (Gap 65)
f9bac814-93b9-58a5-93e0-20d7f74cc982 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.09 - Scala Penetrometer (Hinuera Sand)
73cffbab-3244-5c55-a2f9-c81f11157b0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.03.01 - Tensar Triaxial 170
4cd33f2b-b43a-56a3-8427-ff2594445e1f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
272a7009-ee63-5c49-a63a-f6a988ff26bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.03.02 - Tensar Uniaxial RE580
1b789430-7c14-5a4a-981a-8105deaeff6d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
7d49689e-b20f-5866-b9c1-e0a5b8c6ca9a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.01 - Settlement Pins
78039722-87c9-57c5-89c1-43ec2731d2c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.02 - Settlement Targets
b52a86cf-9d8a-5957-94d7-096a1763e64d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.03 - Engineers Approval
a1f056ff-8660-5fb4-889b-d7192ac56d60 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
e29aa9cb-c633-51bf-bfe3-a24386d9eb9a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6b12f132-788f-5478-be80-7465772d792e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Draft Redline Drawings
3b925e25-a7c3-4373-8f5d-64297aec5182 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D
3be7fac3-73c7-4acc-bdd3-e819e72badff |  | pass | f1864b69de1a686d46caac1366faae8ebaf4ba8c283eef7ba2ba6429f5c6540e | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls
5fa8fcf5-4c47-5e3d-8cec-6d7ecbb987ca |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
51f8b713-0300-57c4-954e-6eeb23142994 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
ca7b6316-a2be-50a1-bd5c-47465325eade |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
25c9f386-f50c-5750-a9cd-2ca2f735dae8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
17e9517f-c67f-523f-b9c3-a950574fb561 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
e101a222-7f4a-56d1-97f9-d92a3b3937bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
a3f0e6f6-5c1d-5162-b40b-c9097af27c61 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
e5fea590-b9f1-5be0-b4c4-5b658e3ee982 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
f519fb85-c535-56e4-ab49-5711ea824b90 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
529aebc1-d3df-52a6-b1ef-dc168fa7b357 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.01 - Stone Strong Block Molds
f5a245e1-3f44-5480-83b7-5a915c51478b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.02 - MSE retaining wall backfill Material
f6dc24a1-7cb0-56b6-a283-409800a74130 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.03 - Geogrid
95ecec6f-d162-595a-a24d-85ead53352be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.04 - Para web
1f409510-bcf8-554d-833d-ec7e5d88cc8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.05 - Drainage Pipes
2603a54d-6e5b-51b8-8930-5dd298de7230 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.06 - Geocomposite drainage board
04e341f0-dc69-5c47-85e1-5d77d6c938cf |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
5bde676c-57b0-5427-8dfb-490c29ff0ae9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.01 - Excavation to subgrade
79e866e5-2efb-5fd5-94fc-e4ad9346b53e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.02 - Foundation Approval
3b06f02b-c0fe-51ee-9e45-7ec318bb29a4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
98a84f6f-fd36-53c8-825f-b03c7be9ab8d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.03 - Undercut subgrade
fd657003-52bf-54e7-b71e-e9f09d61dc1b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.04 - Undercut backfill compaction
96fe5f2f-4615-55ba-87d4-1b609c983286 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.05 - Geogrid Installation
6f15afea-d740-5fec-892d-46a5c623c33d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
2b420fc6-a2f7-5d43-bb43-0bf33d924d15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.06 - Backfill Installation
06633835-813b-59d8-ac71-563912aea7ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
84c68dc0-98d3-5012-968f-67f03f1eb4bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.08 - Clegg/Proofroll (Gap 65)
e4bc9660-9bef-53c4-8cb7-800676a7a96e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
f3dc1f02-4721-567f-837e-f8130ab8f585 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.09 - Scala Penetrometer (Hinuera Sand)
99f8915f-40a6-5503-9316-24e8f2aed92a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.01 - Level founding platform
296c9bc3-37b1-519b-9fe8-f5a1d22146c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.02 - Installation of blocks
da34b8e6-dab8-50f5-af47-15c336934403 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.03 - Paraweb Installation
bf250861-2183-543a-be53-ece73e25fb1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.04 - Geotextile
423e3ed7-c9ab-5995-83a5-8160855ab278 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.05 - Drainage Outlet Installation
b72c4d88-4b39-5533-bbb1-a1fcbed68136 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.06 - Backfill Installation
166c6df8-fed0-5c2a-af79-63b2328a3946 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
12f1e14b-ff33-57bf-b386-12903575ed15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.08 - Clegg/Proofroll (Gap 65)
d7073e39-46a0-5a37-94cc-fdbe3e280749 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.09 - Scala Penetrometer (Hinuera Sand)
6f81b672-9187-50f9-9df2-a87bacab3d58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.03.01 - Tensar Triaxial 170
3dacb4de-af65-5ab3-aa92-ab92e7406037 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
5c7abadb-529c-565f-aad5-80965087e821 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.03.02 - Tensar Uniaxial RE580
95ec18f4-9edb-5977-b931-18f4491a2e50 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
fb07b20e-a2d4-5c83-9cd0-492fbd90d047 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.01 - Settlement Pins
3b549fcb-ad92-52ac-a254-74e3f0b92f59 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.02 - Settlement Targets
062508a4-b6c2-5851-b4c9-82cc1bbe8b0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.03 - Engineers Approval
b9b9ea0d-d046-5f12-b093-292f0e8bda91 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
467f8467-8c26-550b-86cf-55660ecec9e7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
75958e46-1b63-56c8-8cb8-658bb5a06a30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Draft Redline Drawings
fb3dce94-7601-4b90-b57e-5671ab4eb95c |  | pass | Stone Strong Wall Installation Checklist | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist
6d0a27c3-e19f-5f64-8a1d-351cbbef716d |  | no-status-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Details
33df82fa-09a1-5326-8e32-f3b321f38518 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Level foundation installed as per design. (Base layer only)
dd7cc975-a4b2-528a-a262-841412853fbd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | 2 x Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Tramsfer Platform. (Base layer only)
19e78f20-bfb9-517e-806d-b7b7ce9e69f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Blocks Installed within specification tollerances & block pattern as per design drawings
fd0b9ff6-ea55-5114-8c9b-901418c68a79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | The correct number & length of parawebs are to be installed as shown on the construction drawings.
5faf5add-fbfc-5d90-a284-c66859900203 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Paraweb is to be placed flat or with a 1% fall toward the rear of the wall.
e7bb57e1-1eea-5f5e-a42c-6bfcc7c675e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | 150mm of fill cover is required before construction equipment can travel over the area
1f7cfead-9cf4-5ad7-9ada-c4ac219f19ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Backfill installed in max 250mm lifts
d5efc5a9-37f0-572e-944a-5c5a75f282f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Proof roll completed on each layer
b3b4ad05-8f4c-51ea-bf12-7e7a10d837aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | NDM testing completed
d456568a-f454-5c00-8ea8-c91aa582869b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Clegg testing completed (GAP65 only)
5f83e382-feb1-5d94-9341-a450fa90f0de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Scala testing completed (Sand only)
e3b0fe68-5a3a-55c7-a2e1-d5f1cd48f22c |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Eastern Gully Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | ADDITIONAL NOTES:
5f9bb0b8-97d1-43cf-8310-03202ab549f0 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Piling
46906d33-185a-43d9-8721-c5ddfcafb19c |  | work-in-progress | f2478c84926fe662594ba8557dff929c9396882445c4a69fd6fd36686b397d03 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE
7f80af7e-a5a9-58cd-aa9e-a29230c1069a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction
40e53667-9dcb-51e6-9189-3f75176f5186 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | 1.1 - Accepted Method Statement
9cae7651-8064-5141-840f-829673f49280 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | HOLD POINT (DO/BBO/CLL)
360fd17b-0792-5071-9634-963c073e12c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | 1.2 - Accepted Inspection and Test Plan
722e74ff-c3d8-5dd0-8081-3bb82ea4c402 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | HOLD POINT (DO/BBO)
69c3fe05-1c35-50d5-b5d4-211dd22df8df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | 1.3 - Accepted Safety Plan - SSSP
c1f76bda-6cc8-5ada-887c-9889877e233a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | HOLD POINT (DO)
dd3d45e8-3343-5319-aaa7-521b112fac10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | 1.4 - Accepted support fluid details
bd2e2890-ca9b-5d5c-8603-168eb8ae6688 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | HOLD POINT (DO/BBO)
06a7772e-ae40-5f28-b892-6e78e367f875 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | 1.5 - Permits issued
c89b015a-55bb-5a31-87df-afdc7f6e77df |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | HOLD POINT (DO/CLL)
922a5df9-bbc5-54b6-a4fe-1b572a23ca1d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | 1.6 - Concrete Design Mix Verification
591c22ec-9ac7-5445-a6f3-ee6cad3e5562 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | HOLD POINT (DO/BBO)
ac73c74f-8df7-5e4d-9153-cbc8c484d15e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | 1.7 - Reinforcement Steel – mill cert
6668eea6-a23a-5efe-a6aa-d092700ddb6a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 1.0 Pre-Construction | HOLD POINT (DO/BBO)
5f6ba09a-391a-5c75-9f75-25aa2de38022 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring
0d143de9-b3b6-50bb-8ae3-41a47d92c02a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.1 - Client Notification
435a882e-9301-5cc0-91ca-e3f45a7e1c62 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | HOLD POINT (DO/BBO/CLL)
691643a0-8293-554c-8361-8f6b70e6ea5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.2 - Check drill tool diameter
5ea4a3a6-cdf5-51b7-9d17-9d412af4d9bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.3 - Check depth gauge/instrumentation of piling rig
efb59c17-5b42-5258-8e0d-e01ad48f5e8b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | HOLD POINT (CLL)
2a4f5cdf-b6ee-59e7-b0c5-e053d88cfd87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.4 - Ground penetration and extraction with due diligence
1bbd01d9-cc1b-5fff-a51e-19db3685fd69 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.5 - Check pile position/pile numbers
074041d1-8310-5022-bfe5-2241ca2d101d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.6 - Pile Setout/Offsets
f8917bc5-9582-5559-a962-0e530835e6e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.7 - Casing Inspection
03737448-318b-5cdb-b447-1c2ebfe0d08a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | HOLD POINT (DO/CLL)
ee83f1c7-d1a2-5e05-ad63-1539c9d30166 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.8 - Measure and check position and verticality
6704200b-b004-5983-a908-723addf62003 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | HOLD POINT (CLL)
4b165764-c109-5297-9484-eb6e79b74aa7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.9 - Bentonite checks
ab690019-7106-55c9-a928-1f54bff484dc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | HOLD POINT (CLL)
0764f15a-f1da-58e5-95b0-ee0528782604 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.10 - Bentonite level
1dbc533c-dd04-5977-8183-bedd2268ae25 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | HOLD POINT (CLL)
e61dbbde-2d95-5e06-832f-87c638ec2811 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.11 - Soil logging and bagging
73976b3d-80eb-545c-ba41-98c60fbdd244 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.12 - Confirmation design minimum toe depth achieved
64e499af-a362-58e0-8145-7d15c1bf3048 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | HOLD POINT (DO/BBO/CLL)
43b15f43-5bc2-5b2d-9d2d-e5c4227a26e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.13 - Base cleanliness
bd985cf1-b58f-5cc5-998a-dfd1b5891d47 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | HOLD POINT (DO/BBO/CLL)
9d96a1db-a4bc-58b3-910a-f2dd553fb5fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 2.0 Pile Boring | 2.14 - Pile Boring Monitoring
e0932178-f20a-50a7-84ab-61c76fc0845c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection
6e8e2358-4e3b-5045-b4c2-8d427e5be501 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection | 3.1 - QA check on previous pile
f0e80589-44b6-5ef6-b7cc-21f259e35943 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection | HOLD POINT (DO/CLL)
cb42a307-68d4-5ae2-82e9-8d4ea75643f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection | 3.2 - Reinforcement Cage inspection/ check spacers, pile bore tolerances
c2372fc3-53e8-5d0c-849b-c212a66c298e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection | HOLD POINT (DO/BBO/CLL)
fee921e5-4928-51fa-b754-9edb521ea7e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection | 3.3 - Stabilising Fluid Verification
497511fa-70fa-5ae0-b18b-71da8f0b35bb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection | HOLD POINT (DO/CLL)
27ad8caa-3ad7-56a0-95d1-6ce3b56ee54f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection | 3.4 - Pile cage installation
b0dcdd56-46e5-5d64-91dc-dc6dc945a68b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 3.0 Pre-Pour Inspection | HOLD POINT (DO/BBO/CLL)
6ea8a377-4f7e-5fd8-b2bc-512a3e6d1961 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement
972bfabd-c87d-5ba9-890a-06f39618dabd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.1 - Verify Concrete Mix – batch times, mix
be8dbdb6-ae3d-5768-8ed7-a3ab0911f812 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.2 - Slump/ Spread test
47223818-0d0d-5fb8-beca-6b92ddb6566d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | HOLD POINT (DO/CLL)
bdc620e7-febf-53ae-a925-fe46aec41de8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.3 - Concrete level
0b160815-d24d-5b1b-9f23-75a3f8b46530 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | HOLD POINT (DO/CLL)
255ed76b-3f1d-52fc-b0e6-2f6e251f632e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.4 - Concrete placement
e0ca6c15-ed87-5b44-9100-901ed0b749fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.5 - Concrete pouring – Check volume
1112d458-19e8-5f2c-8f54-c4c0a86f51c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.6 - Pile concrete overpour
e93a8151-89a5-59a5-9468-010b02e83630 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.7 - Formation of construction joint
cfd71ef7-6c76-5fce-9f53-6623225b5347 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.8 - Concrete curing (tops of piles)
1bca556b-6684-5302-a2e3-e91f43f011bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.9 - Compressive Strength Sampling
a46f6e8d-b134-56b6-9327-1de3a5300685 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | HOLD POINT (Sub)
66ba7f06-7b7f-5b58-944f-efb147a1afd7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 4.0 Concrete Placement | 4.10 - Post pour/ Post casing removal - Reinforcement and concrete RL, orientation check.
fec23b47-5ac9-53ca-8859-58c9539f794f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 5.0 Close out
9619b4c6-aa95-5cae-a45d-2d31cb598752 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 5.0 Close out | 5.1 - Pile Cut off level verification
d83e55db-e4a9-5b63-882b-2c7e0e31d8fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 5.0 Close out | 5.2 - Pile & Reinforcement Cleaning
8e177597-af0e-5a5b-b3c8-2d901748788e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 5.0 Close out | 5.3 - Reinforcement to specification
9b72af01-de4f-5d47-8e56-0070ce63f8e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 5.0 Close out | 5.4 - Pile records
a4451dd4-188a-5710-a8de-2d4e5035d5c8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE | 5.0 Close out | HOLD POINT (DO)
ec1bc14e-b532-455e-8d03-969ab81243a7 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns
4fcab001-0f26-4579-9f05-98dc1011dd65 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B
d433d6a1-9395-4c43-b44c-743e7fe5d487 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1
58c25770-d321-445f-814f-3b002acb2f5f |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D
9f2dca95-c052-5cf7-bd0f-4ef5f8ab3a14 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
2b3656e6-1004-57c6-b4af-a395577ecaec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
96511031-a874-5893-a73a-57dc9aec0aad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
739b7ef7-5cfb-5c7f-9e82-ae3ab7675ee7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
9da25d6b-45ff-54ff-ac16-46308660f319 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
e55e7059-b509-50b5-a0ae-cecc91e763d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
85ca582c-4b49-596c-a092-03f9534ab92f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
be5db997-eb83-51fe-a406-f79ed1feba09 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
14953479-5184-54cf-8d25-7391495a484b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
f26dab39-9de0-5867-b848-eeaa352b4692 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
a884dc6e-285b-5b65-a1f3-adf349bc0c69 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
2aaff69d-5c2c-5216-afd5-4e2bfed1bcb0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
6f730899-9d6e-59c2-b4fd-6201cfc9267f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
052d3bdc-e890-5c9e-92de-860db61b6480 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
de601773-5179-5ddd-830e-13fedcfc8010 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
67eea8c0-f9ef-5981-acbf-0b8b90131584 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
9c829292-746e-54ac-8e12-e205d42a18cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
3b7742df-fc13-5c40-894c-25db9739d64b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
09835fcc-47b8-5998-b34a-cbf43209a156 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
e4168f99-15e5-5acf-b43a-9a2774080215 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
e666f7e7-9e22-5806-a3ef-e973050809bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
120b4fc4-219a-5fda-827a-e71032e57193 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
e1188f85-d884-51bd-ad47-c68ab3f9e566 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
cca3b08b-733c-5757-9691-5c46b7fe83db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
b416c466-ee8d-5063-8211-53ed5ee20cf0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
e9d2d6b6-f501-5194-b110-1fda9bc5f9d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
0d39c293-6223-5964-81bf-bab9a2962eee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
4718f25e-df95-54d1-8a07-23011958bb37 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
e1498986-b075-507c-a333-41a17737ecd1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
f1220806-a8b7-5af5-b6a1-7af6d9df3692 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
621e27fc-a16c-5c55-a2ea-44aefabcc3ed |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
c3d6a9e3-9f56-5bba-8cf8-dadc66f0944a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
74985b3c-5ade-5bab-99dd-d61b0ca3a66b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
319e986a-2f50-5e55-8358-5cac80a029ba |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
9478e2a0-20da-570a-8396-d17c55a13bd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
e77ef5b2-466e-5f7a-a289-da14a68ddc81 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
c86efcde-bcd8-5ce8-9066-991b5505eb8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
d028ea53-464d-593e-8212-61d18a0f3129 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
bf08f462-42be-56ea-874a-531c352ec6f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
c03eec66-e12a-5063-8001-fc84b42bd608 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
6cdabbb2-b6cb-55a4-8dd0-3a3b3372120e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
35eb7530-51de-54f5-811d-bdb396617e27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
4ea6f8ae-4b22-5c8a-8366-f69faedb4527 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
d21b7f28-a7a1-548e-920f-95cadb93e426 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
1eba2326-b346-5390-b254-e0755e476a16 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
3054627d-ba3d-5cd4-b260-cd1ba8ff48ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
7e0e855f-e860-59a8-9db1-107ebb857255 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
f7b35065-95bf-5efb-bd84-534835c3b427 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
a8513ac6-ba38-528a-9433-e31301e72e05 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
434239fa-aebd-53b0-9a80-ccef0e615ccf |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
576e1538-3b4a-5a1e-91d3-3ef51fe76d73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
c2e44632-33fc-5167-b9e5-a9027f173470 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
c64b7e51-f5fc-5b89-a31b-0613e0819edc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
420c17a3-5998-550e-8097-9201b2e048fc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
ca02e1a0-40b0-4b61-9ed7-a3337a1de43a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
2288cfb1-0091-531f-b0f4-db84ef66ef98 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
ff23b8d8-c8ca-4383-81a5-b4104019d891 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2
459965f3-e822-4843-9f7a-6e2e3aaee75e |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D
1d204f03-726a-5388-acf4-b4685504f1ed |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
97cad569-1384-576a-855e-76a5eb8132c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
8e778471-0263-545d-b16e-6fb65923206c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
e8776bdf-8478-5806-8f36-93d12fc10717 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
63b4cb2c-a1af-5572-a7d8-2851dcb6b2fc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
87246c8e-5d17-51da-977f-b5efcf82c568 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
0eb7744e-100d-52d7-9abf-230f99543d86 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
ded449f4-9919-5e54-adab-c911b21b8ea7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
59a8d38e-adea-5c04-882a-bdafc27c24e2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
7a60d7aa-5718-5b1c-902b-eeafee288c06 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
607d8362-179b-539b-90ab-515ace0f7b95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
f28d1bc8-74ce-5be5-a5ab-faa0ece88017 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
f1022728-eb7b-5c87-904e-211827eed2f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
d84cd887-b428-5e12-ab49-b0c09e84d62a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
8aa9c0e3-a0ca-5d29-8ad5-16cc47d09205 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
7ef1fabf-96a3-588f-a429-101ca9f69050 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
1a8b61b2-9584-5b77-92c2-b49dc2af0017 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
0a92f161-1597-5f46-b18b-d834936b48aa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
43d0c132-fff0-54a2-b7ca-9da5bf1cee55 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
468ad094-a239-5d9c-9e9f-4cba6c97ecf6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
647684be-801d-5c7a-bf08-a291fd3dfa03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
fb70e8d6-75a9-5ffe-ae32-6e6429f2ebad |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
07801145-5ebd-5024-b000-ac95527719b9 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
6fcbda07-d380-501e-b6af-67b09fa9a12c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
199a776d-dcee-5da8-8494-b41f2a6644c7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
3a30d818-1deb-5dfa-a2f1-6545b02e6f16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
ce87ded6-4d97-5a76-8f6b-db8609e80649 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
50f87e69-b235-5fe4-8c6d-01302b38ab5e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
89694cea-5cce-54ef-8924-37690fbedf62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
c2c1cb6c-dbea-52be-9de7-fd248948af83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
63ccb57e-0822-5265-97e5-6f8f1fd33565 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
a8f9cfda-cbe3-5c44-bed4-b39f4e7f05c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
3aeed3a9-1209-5846-ac06-76b0954c3e5a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
a7dcabed-0871-58ce-9a27-823f84568c91 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
b673acba-7bd9-5592-bf17-3f17f952f72d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
cd8cd4e1-58c3-50d4-9b93-a42da2f36a82 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
2c095878-da7f-5adb-b4a9-4c7e561fb802 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
72d780d5-7544-5572-85ef-f42e564d66dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
460c082f-f3a5-52d3-a9f9-6380a3140fdf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
979e4586-8add-5ad4-87a7-5690ddb83eed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
8dd8d410-b4ac-5d0b-b01a-39a3c745409f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
f6787dce-0c74-55a3-b2ab-b10ffdcbd9c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
33e6cedd-fc6d-59b2-ba03-b58ddd911eb0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
4006da32-e653-5196-8c7b-f826f54f9b7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
45ef03c7-69a8-55c4-9a51-6d1c9728d3af |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
4e809e3e-96da-591d-ba7b-82b25c27055e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
4610db0b-0147-55e9-948c-fa6c415cbfef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
d178b9f3-caae-5334-938f-cc307f743c70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
005fdd70-ffe0-5aeb-8c5d-de54eb308675 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
f24f3d8e-7d70-53a1-86a2-c6e1ae3eb518 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
7d6b4036-3ab0-54f4-abf1-abc8ed7a0c60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
4e324ef8-833a-56d1-b86c-6f556b6a3cc3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
1024ca68-6634-5dcc-a3c6-ed4830a14f5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
2e0ea62f-a210-5157-9f0d-9f357b8a74c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
e6bf35d8-1175-4bf2-8e89-755e4d928a44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
8dd787c1-6929-51b8-9a9c-e2fc5805e639 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
bd8c614a-98bf-4316-9dcf-c86518ddd922 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3
c4546518-c591-4961-ab4f-ad0d3ef2664f |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D
f1e9d5a8-dad3-5161-bd70-9672842579b2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
e4e48ab5-a25f-5d82-8f25-9a5d9de84f0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
ca761c86-cda8-5a16-abe0-dbc9d001b1ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
4eeebe95-b19c-5ca6-a46e-477951e09166 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
d548b302-1f63-5fd3-8e5b-03876f2a9c0e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
0e77ca1d-e960-549e-b353-610eccae1ab3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
76dcd223-9b3d-5fbc-8fcb-b47a3f560b46 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
0a2ed7dc-30e1-5377-97e8-ab339049d1fb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
1917d7ac-4d31-54de-96b5-d87d5ee6eea6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
e1ad588d-62db-5ad9-bd53-2888fa9c2f64 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
e9ee46c6-fe05-54d1-8c83-3fc2817fcec7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
95bd29dd-51d9-51bb-a8ca-f335b52579da |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
d0c59064-c5be-5f7d-b4cb-8db575a896c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
d70d42d6-0532-520e-8852-0a68249947f9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
a7e066d9-0f16-5a24-95c1-cd4c6b6df30b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
b51063d4-6c11-542e-ba76-003a40adb1fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
3eedccbc-e1a5-54d4-90cf-957a9abf8cac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
3105b751-f3a4-56dd-854a-2c6b46389537 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
75c2ef32-c946-5ce8-ba8f-c4768a8905a6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
38c81509-4772-5ee7-9b6c-3c9db906ba6a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
46bc72ce-7b43-5696-ba00-013adfe6ee27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
76c22f13-c245-5f74-a1d0-f159877659e4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
14804cf1-c80b-5969-8034-dbab857742ac |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
0b141901-7464-5094-8403-e7ae8051666e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
29dc0cab-2df8-5bb0-94dc-50bf63858a21 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
31648979-7bc1-54fb-abad-cb5ac6e670a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
ada26d24-2c31-52ba-88e9-01eb5c05cf58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
8c8bd25d-cc6a-581e-98a0-aeea536cae75 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
7ceaf21d-39a9-5f55-8a0c-2fadaed48da9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
a9e8248f-e7ea-5e9c-8368-f5680f95f1e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
9b37ac62-3d31-5555-9ab0-bdfc3f92f62a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
f860f890-afbc-58d4-8400-c350ae0db30a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
795a11c4-1598-5269-bc2a-3b296a78d4b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
7480fe2e-7b1f-5e3e-923b-bccc8325bda5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
a7905a0f-b10e-5239-9095-2f4e5ea5d53b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
a2754c1e-3302-5732-935c-7544261843fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
feb55e57-ce90-594d-bab2-ef06df8151d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
f2468950-3bfb-5dc6-b66d-43edf249d9db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
7a2c0ca3-619b-5763-95f3-1ea9c1ee6d64 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
3c84e285-a652-5f92-87e2-04fa4909d3ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
97c3d597-c17b-5f71-8e7c-b7514ad181ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
c1e73065-aa0e-503b-a41f-1450910acadc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
a90b933c-7823-59d4-942c-233f95c12813 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
cd2ce080-efe3-5fdd-972e-f6ae40853c87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
5345ce6a-9671-559a-b50a-79e177101039 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
388a74c5-99c4-5925-af34-85c7a37aeb0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
fd821453-2309-5b94-a887-d085dddfb9b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
36463d36-7229-574e-8bfe-36a24862ad52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
3a7fd4d2-c5b7-5d74-8399-a2324be5916b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
9df5470f-6050-5559-be4a-dcd1c8d20a45 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
56cb44ae-9d79-5d32-a363-7eb61cad940c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
d5f49691-bdbd-53cf-bdbe-77ec99dbe23a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
5725634b-e2f4-540d-ab14-379e837515db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
19f28b6e-b40d-5f93-8849-99edc609035b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
8237dca6-b325-45e8-914f-91d252bd2844 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
1d069b63-5de1-570f-8feb-a7fea62ec52c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier B | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
1c979769-2c38-4bed-873a-b0ebb6b8401e |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C
ba77b93e-2c13-4e9c-8eab-c635793c504d |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1
24b0b03e-a8fe-4cd8-a817-43779bb0b448 |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D
a9b2da27-71be-59b8-8435-69d4b0256f39 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
8a77c305-9115-5f8e-bf24-bfd08ab9308f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
7ff28fa1-4ced-5e5b-b28b-15e9c0e0fced |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
4a1952c5-7d0a-5981-adb1-0e52504637df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
d0fd973a-c569-5254-b5d4-d92674ee4d6c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
8b3885da-1673-55d6-8c79-081594aabc80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
3e4c5c03-307b-550d-921b-5318fdd87e94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
ec7a0497-be00-5213-8cc9-5416855f9dce |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
cbed30b7-399a-5260-8123-832890c32f8e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
349dd8a8-f3c7-5aa1-b8ce-0693bb992016 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
c6dffcf1-8a8c-5fe1-9061-f7d5f823ff81 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
a8d14303-4798-5ee2-859f-e92ac35fad0a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
61a7afb2-163a-57a3-ba68-c82b1b666683 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
2a2edf17-82fa-5750-8ce9-6967a2dd883c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
7be11e3a-4513-5c81-ac7e-3f220a3324ff |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
6992ee9b-e1ab-56c1-92d7-ca4fd5f095cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
0faca7e2-19f0-5388-8151-3c22878d75e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
07c3ffea-a2d7-5fe4-9bd4-55f4baeddfaa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
71950f9b-85ab-5e53-b89a-18f53a74cdd7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
5ddc4b80-1364-50b2-8196-ddccbc830cb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
9478d5cc-7a01-576a-9ace-6205e2b5cebf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
9cd8dfb8-8d9a-5cd5-b3f0-24b60b466af8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
d92c81c5-a14a-5cc7-9106-4c27ba01a4de |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
54c368b3-9e39-53d2-bf28-c6255655d5aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
22e89a16-b405-55f7-b753-3ee63faf6896 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
7325e168-470c-514b-9fa6-141ed26a65b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
2e7c9c2d-70a6-5ba2-bb87-acd424cd0790 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
41d9f53c-a4c6-5fae-beb2-0cc2809f454b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
ded96bee-6a85-597f-a6e1-d743f046e181 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
12a5a9fa-87da-557d-b569-a90c7f034c66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
a11a43c7-ada3-5be2-ba65-c2e02743528a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
469e9c13-4bf8-5f93-89cd-73501f6354cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
ef702876-65a1-523b-911c-eb92fb51fe2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
9e1d6fa9-aaf7-5532-80c0-6c73d7a09167 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
4169c0f4-7481-55a3-b660-4df5583531e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
c0bbb70c-8efe-511e-a5ca-3dd7f0480001 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
e9cd161a-a0dd-5bc7-ba31-cf766e72765e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
980aa97d-4729-5688-83ea-cf4c447deaf7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
82f63da5-1337-5473-ba8a-7bc640e878b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
386981ab-22c8-5680-a8ac-a47ff3e67a79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
3d859df3-20bd-566c-8879-e89134d6f544 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
4b26419b-f7aa-5516-b9b6-ffbdf117c87a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
942ef115-18a3-534a-8548-7f5ab1c4f7e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
0d9052b8-7a0d-52f9-ba23-db8821ede7cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
9830a8c1-b7a4-5ee1-a54e-7e0566914fed |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
8f1e444c-b0f3-5c02-89e8-ea9a0e7e395b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
b029e454-97cb-5957-89bb-9cc5facca192 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
aa831671-8445-567f-b124-1e8a767c2395 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
844e93cd-b166-59cd-87f7-d1f7292114af |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
a9d69f05-810d-549e-8b25-71d0572b4bed |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
21f23134-d3c8-5256-ba63-e39c34c50679 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
f9bb2c3a-d55b-51dd-b7e6-49b49370f567 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
dee4f51c-e825-55cf-a00d-82de2096e673 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
c8bd304e-98a2-5ad4-adb9-dc485cab6b83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
9de3a8f8-39e4-406f-9c9b-25ed701eafe4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
f1bfb837-deab-506f-a74e-8ee19c1c74fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
dc94f98a-4a61-4a49-bc30-73a062998575 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2
c582676f-ef67-4ce5-8e31-eed1737eff51 |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D
5b671454-9f61-58f0-a7c2-465d73d7392b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
3bcc6d17-91bb-58be-8142-f89cbfb41032 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
c6386661-68b3-523b-be7d-240295a7c7f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
83122e1d-6669-548e-b5ee-b681289220c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
b2ff1dd8-32df-57bf-af75-d9f3531c2c8d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
a85766c8-9967-596f-94d0-d303c25cabbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
a57bd406-ed08-53c3-8fe4-640b00917330 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
2df0c542-e46e-5b57-81a6-eba8c6b5aece |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
10b86a5b-90c8-5cd2-bd19-34223c479279 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
a4b3e161-fb70-5943-b7d8-0e24de242d75 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
8d30166f-ea5a-5997-a294-3032a6b7102c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
b5c77a09-f6a2-5c43-931f-19df9ab11b16 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
8655d213-f55b-5343-80fb-a6b4b62cea7b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
99459dd5-cb0f-5f07-bfad-37b01d1e8222 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
12bff447-af5a-598d-8015-c2fec54128c4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
70b57497-221f-526b-a41c-429effafc483 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
01e47cba-8572-558a-b79a-a21b56060ad1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
26044a25-19e0-5fa1-a847-c7e6c1a55d4f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
042aa3f7-3730-5d55-a4ce-4b6753fa419e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
da1cd7c5-6900-5b47-9027-c9eb8eda05ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
729d48ce-21ca-52d1-a54f-5d1d680b0471 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
e3a303ec-1353-5e0c-8540-708e16cfdf49 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
548965f2-a6c2-5eee-a4e1-2a579314027c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
f11604a9-3f00-5cb9-9087-65fc3f97877a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
5dfb3d14-f4d1-56fb-a35b-dcbcb6ae8fa0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
08a6d515-2fa1-5929-a36a-862a912f8aa7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
cc964d78-764c-5392-ac1c-3d1ac6e42899 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
f767f492-d050-5c83-a0e1-8d441183683b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
05307b3c-f9dd-5deb-af25-542c8bd436c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
dec91aef-5caa-56bd-9983-0fdf0d3e99d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
4ece7f2e-af03-5a65-96e4-c89138c5fc29 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
1487a5c1-5770-54e2-9fa6-a7c74f73b8cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
2dfb33b1-039d-5a62-9fa7-f8aeb3a07bf4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
c959e4bd-3463-542f-8928-9af5f0c26984 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
b69ae5f7-bcb7-5456-97b7-38820338ed3a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
c360293d-5310-547b-a40d-2579799bc812 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
e1e8b35b-a6db-52c2-8b53-9abbab05ce8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
206506a5-9e13-5dc5-819c-4125c3cfbbd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
9c89a642-ab92-5a74-8780-ac843f3faaf5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
097493d6-1b64-55f2-903a-a4826b58665e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
843202c4-9c23-553c-a017-82006f3d27e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
ccff9eb1-349e-5b5f-9feb-bb6e9384cc1c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
04050b68-1b17-5fb6-872d-dbba976b1b4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
d3dfbb7b-3dc2-5238-b4d5-e9ccaa900865 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
3b31fb40-9b68-50c5-ad89-826ae3acda3e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
a9ed9a21-a115-5c0d-898f-6ec75b74b45d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
e6ee8937-350f-5ea0-93d8-f3ce73eddb01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
2b9f7145-fb39-5c5e-ae5d-f80f02b9856e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
7886db9f-bfc1-540d-90d9-4d6dff0201e2 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
29841719-9d00-550d-8fee-fc0a2582a8d4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
97a372cd-0f75-51b2-adb4-4963a0cc332f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
0eafa93a-1c5e-5acc-a07b-7e36cb6b5e15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
3adf86cc-c120-5b8e-9643-0d85b536524e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
bea0509a-75a3-52c4-a0f1-183c5d327100 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
5b0d87ed-f495-445d-991c-05fa43d85a08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
466f92cf-5a68-599d-8ab1-1095a9432290 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
27d6b44e-9b54-444d-ad08-4f67d17f9363 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3
27042dbb-a4e5-4194-957f-6b72d19733f9 |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D
a89051d2-5de3-51ad-962f-26aab22afc87 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
4a563043-0cfc-5eae-8aa8-b4e423d611d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
6e389d5d-99fe-5267-a1e2-42724a9f1dee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
2f09b558-4c67-596c-83cc-3a18a140b1b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
8768d1a4-775c-5ef7-881b-4fb79092d1e5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
925c89a9-12c1-5cdd-bc65-14d76dd6b3b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
29a78d04-5a1e-5535-9724-ed96288ee43f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
701c3389-8272-5725-b445-005c0b233e8f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
c17292d7-db65-5cb2-9a9b-a2f036a28809 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
bfaa3368-0df9-5bbb-b578-25c70b5d26b5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
86794789-5220-55d3-830c-56238472fa65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
79c22897-3546-5185-81d1-2fa38b07ab05 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
3402502c-0392-5d1e-a568-07c1de8e2d75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
43f4b594-55a6-5327-8dca-7b493c3af680 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
74ad61be-1162-52f2-a38a-e7d411f5b203 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
277bb460-bf1b-5aaa-b129-5cfcf050a465 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
ef1eda4d-17dd-5985-9fbe-73c5c767d3a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
2df0847f-7ae6-5b58-883c-72693040c920 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
38c4a19a-f223-5112-847c-98666651203c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
8e1f2b6e-782d-5b27-9334-51900514002b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
565be017-d6ed-5b49-90cc-087d7f556f11 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
3a268864-2d3e-5ec2-8d0d-ea2610a80289 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
d66defa4-ee9f-5c3b-a2fa-5425f5789a9c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
0c8b3160-9fb4-57be-a318-de5512fa0d88 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
927a27a4-31b7-5428-827c-3ab80027c35e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
f01816ce-40c2-56bb-9163-b64bd431c9c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
1e9a4a09-47cb-52c4-9c85-69ebc7c39982 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
045b2094-e9f8-5976-beeb-8dde06933e1a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
ac58f603-b44b-5f1a-b739-104cf2c336c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
d2cc02a5-59db-5151-9611-8889db9334a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
1f60fa4e-bdfa-59fb-af65-299b98276680 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
88a64ca9-dcde-5739-ad8e-afc420671894 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
7b142e5d-24a4-5039-9f45-993e909ac5e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
d36bbdb2-c7ef-5297-b018-c3155f54d696 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
41a67200-81c2-52bc-8358-d13380c5810a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
31827ebd-8706-51e1-aa7b-3f247c55b3d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
b57da81a-fd69-5c29-a552-25d3b6834bdf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
4f3011ed-9af2-5132-89d0-c2ab169fdac1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
9fb02ce4-c7e1-53d5-bf67-680a456f3b24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
b0fc3c6b-3620-581c-9634-501134ff08b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
b7426522-7668-54d1-8ff0-2f8d84e984bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
d16141a0-baf1-51f5-8fff-4531bd61f3d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
01416470-b332-59df-9996-a8922766b58b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
fe71413e-2574-5f6e-9fd7-ad3187db5168 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
5184aaa7-1cff-5bbf-88f4-d8cfab897218 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
25068d6a-49be-5e8f-8af3-3abf244a5e8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
af0ea8ba-a3e6-5014-9ed7-722a0b1fd815 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
5be2d6fd-c45a-5aef-94c1-fa11a9ae225e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
e26b939a-e70e-5d89-a19d-adcd21570841 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
dbdccfe4-8431-5420-a0ef-5784a2496576 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
e148d107-32e6-5045-acdc-6d6f772ea686 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
129d992e-ee73-5f26-8d68-0140e701c6bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
0b68fbc6-81fa-5449-862f-071433a8b030 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
8f945be4-7e82-57f2-bb58-6d9a948f8a86 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
31233dae-b73c-4f1a-bfe8-d90ce6e7463e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
fbded1ec-a6c9-573b-aa82-0bd60838ed01 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Columns | EGB Pier C | Column 3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
fd98ee55-96da-46ec-97b5-b0afe61ea07f |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand
be1d52f3-de68-4fa3-b740-eaf1ed09bcb0 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead
c46fc04f-dbf7-42d5-8c2c-d0f433f50ca4 |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D
c04181f2-16c6-5f96-a768-a14ad3cb1400 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
a4f0432a-1795-5fda-bd2a-26f0fd480f8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
d6121509-11e8-5763-855e-3881bfe01e97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
75dedb77-6778-52fa-b6f5-ddd44de4660a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
8a631147-9ad4-5d80-b770-ed61d5e3080b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
8d73b1d7-7615-5660-a4a6-da35f3e49720 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
9732f313-79a2-5c7e-b887-b2140f58801e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
10c9a8b9-6085-5e09-9f93-0106ef821394 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
94f206c8-a6d1-58a2-b9c2-8eaf97c397ef |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
e5a95c85-841a-554a-b95a-ec7c16bd438d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
ab0cb2dc-3a86-533c-9217-ca189f2b6259 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
71249a55-0f22-5af8-8d55-5287c307bbe2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
8d82360f-f965-53ee-8567-3be80b1468a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
55018cfc-fed7-5f64-b4e0-03e98dedb38a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
06347a34-9754-55c0-ba64-0e411a5045d6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
c08f0a6c-755b-513f-a180-a3e835f9bd05 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
4d4062b5-51f6-5c0d-8099-b1bea47377a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
d2f16295-485f-58fc-9bd2-69f6292b6d1a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
049ecd8d-5b5e-5b36-9977-a9310e1e44ca |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
9c8a384b-5054-58fa-8a27-4e7ff4391dcc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
08a387ca-e063-596e-8c25-bcafc073f8e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
261eb79f-43c5-537e-b892-8db8b7eba8cb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
f609e6f1-77a8-5287-b114-75f7ca24aefb |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
4846f693-2543-53eb-8e2c-4f9e355e97dc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
ef9fb298-4624-5b45-91e4-7da824953ad5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
268cb558-34ed-5998-b08e-a2355475de53 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
40209918-9202-5ef7-8f2b-cd0a2382f62a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
b5207edf-d498-5b52-9490-6daef15e751d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
389e965d-349c-501b-b993-bf9e14666b6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
9dd1a239-fb4e-5705-8e1e-983550af5fa9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
460adca6-8508-5540-b32b-af4655842246 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
0a5cd8fa-ddea-515e-9b11-e9ffff7facc5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
83d854cf-e256-5584-bb4e-3d5a3eee5396 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
a9ce5ce0-009f-5370-9e5f-711cc182bb6f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
92a200eb-5920-5d4d-aa94-cf0638f205d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
5b44f896-f024-50b3-8ded-84ebb5776bef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
efcedea5-87d2-55fa-973c-3008f10846f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
00fe542e-f81f-51fc-8b4b-a2dc7f6b4779 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
7feacd3d-d54f-53be-8139-bdf964874989 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
0124def2-7861-53b9-a745-6e993d6726d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
248ea23c-72d3-55a7-a033-0475c99347d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
7753089e-b258-5044-b025-85da2d74ff16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
b1918405-f4a2-588c-9dc9-c082de1805a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
570bf771-f25d-586a-b6eb-7775ad164c85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
0244711e-df4d-57de-8370-30e7bb817097 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
b1a5e5f2-68da-5519-9e5b-2afd99fa0a17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
b9214a7c-7c64-5c8c-8978-cc37ccde52b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
bcb98fe5-a5d9-5e29-8981-250dac1f07b4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
dc7d2a90-ac2e-5de0-a759-c48591d47c35 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
80cda6a2-3430-5ac0-bfd6-9ce44b80828b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
d4de7f2d-1243-58c7-87dc-ba41222205fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
ce5bfbaa-9623-5947-bce2-57e40f72881e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
46c9b874-5044-5ad4-9624-958bec3b4047 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
16b89219-f5cf-56e5-b7b1-36aed41108e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
ffd49229-8ea5-4b07-ac02-6e043e74fb9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b78efd76-d5c5-5837-bb27-8fe3830f405c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier B Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
1635a7b5-1364-404b-a42e-6cece481ca73 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead
6f27e650-1618-4411-8172-954e0b52a5d5 |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D
564bca06-e13c-50f3-a4cd-a24bf3e2dc1b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
b6926422-c3f6-5383-860f-ded8caa3abaa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
10c0f373-870a-52fa-a666-3a218757c3a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
bc5f79d1-1e2e-581b-a456-6ecd2dabf2e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
52b4a755-a5fc-537c-9dda-6ed6776749f1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
fdd74276-817d-59ad-af59-07bf4a1b1715 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
d01d2ad0-809e-52ad-a577-0da9a22cb9e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
172cd64e-0f71-5862-b603-1352d73fb0bd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
221b4744-8dbc-5fc8-8825-6ff3ffbce9e0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
1c3f4eb2-bc73-53b3-a59f-5732099d0916 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
bcf03558-44c6-5373-aa00-5a93c0a569e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
48b04744-7826-5569-961e-8bc84b2afc28 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
7985bb8f-54d9-5d33-80fa-5f312d83bf71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
4492ee6c-0e2f-5c9a-b6a0-274f41e1907a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
8a1c99b4-9b45-5484-8d84-124064572b5b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
36b13ac0-5ed7-5475-80c7-474d8f335ff8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
56abbea9-e73f-56a1-979d-5ea6301a40c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
2ae207f4-5860-5ef6-adbd-69768f6b1e35 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
e7ec997c-790e-5a08-a6a1-db28aa967f9b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
8a284231-381a-59de-a538-3c7327160830 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
526696b7-5c04-5352-92f1-f96f876d495a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
b11d1fd1-ce74-5a61-af41-ed70b81300b8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
28746bdd-beb0-5258-8379-5f0930c867a1 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
159b852f-ec25-57fd-90df-d5af381bb1db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
90dcba87-819b-5fe3-af52-969813ac3e6d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
c1abd4f2-b40c-56f6-9348-7ab19de50c0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
9a28c371-33dd-5dd3-b5ed-0f97b0f8b195 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
41a12c12-ad10-507e-b8d2-0b5dc58921d7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
3db84999-3d4c-57c3-80d4-c0a0b4d9582e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
e860dec8-b3a2-54bd-8ef6-b8412eaf94d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
2f86fc20-5148-5dd5-88e1-747865f3ef90 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
5ff220ac-525a-5c75-9762-99dd2654d321 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
479ae69e-b63e-5160-9dd8-44c05c810e5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
a8805793-f9a9-5353-ae54-bb0bf493c5f3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
dd1c4a9e-092a-5fc4-97a0-98a4ece38094 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
9ba1c779-e75c-5671-901e-012110413325 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
ea74ca66-b907-5697-bb6e-45c5c5596a89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
0d1b7b77-f32d-51ce-ad99-f7281024a4d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
66edde45-fcdf-5e63-b21a-fb4793c97c47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
7e53f6d2-7713-552e-b704-b1f8d3209163 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
a8c261eb-cb83-5e71-8195-410eea16900f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
e985446b-8f68-5078-9b89-44b27d694e3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
fd9c3679-f6fe-5f18-8a25-d59de1784f24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
f7bc85db-f67b-5b02-9728-45673c8eb81f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
ee3394c7-c573-518e-9641-7854568c32c7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
931d4036-9b9a-511e-a95f-6e752ae9687a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
2fd6103d-29f7-5b80-afd1-aa4fa61ba1f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
2ea987ca-2720-53eb-9839-7763631085d3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
f46d7966-78af-52ef-8869-32d32f803a92 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
d1e02832-6809-51e6-aac6-66dfb6bb626b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
8e7ce365-8b24-542e-b102-a66d6e4ec09c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
40e3d16b-492a-5d12-ad7b-72608b001ab4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
663ca3d3-755a-5058-9c29-66be9cb05282 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
9be14840-f9d4-5ebf-8133-c38b986cac67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
777f897a-a365-4180-bd62-85f293a7a760 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d5482e0c-1373-59b9-a2ce-ef269ac30a50 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Pier Crossheads Downstand | EGB Pier C Crosshead | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
8687aa8c-6ccd-4606-879b-5e5f6a069625 |  | fail |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams
12d9a150-3092-4b14-a1dd-0cadcb3ac8c8 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections
12d681f2-2459-40c9-8192-975c5f21b76e |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A
616dc504-47d4-4427-ada8-9539fea28937 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection
afd2b946-72e6-52c4-a52f-7674f050f587 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Preliminary
75cd5979-e634-5c70-853e-daac5afa5cb7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
13d1fd49-24e4-5c86-9333-ed675e6111b6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork
67134731-09be-5f4b-afc8-ad015111ad17 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
ad50c976-6a5e-598a-afe6-0bb26a81dcdc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Permit to load issued
30b89bcd-138b-576d-b43c-490083d8bfe2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Dimensions correct
b2956ddc-fd95-5887-8c34-f07fc7da0396 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
2b7b7803-dd94-52db-b60b-89e635a25fc9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
d13cb836-2d7b-5aa2-9ddc-6c970130c619 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
485facff-7d52-55aa-b045-79f591804571 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
0bf20e44-66eb-5733-b16f-a40f70d0c849 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Joints sealed
8e79cfc0-98bb-57db-b735-295766c4f0e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Formwork | Pour level marks
e6759509-6698-5638-81fa-21458e7c1e04 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement
0a66b556-6865-50ef-81b0-4480941868d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
84187758-849b-58bf-9868-4975c6adf2f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
16018601-9ca9-52aa-b96e-67efda495dfb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
d7b9e262-d3bb-5687-a5af-55cfe402917a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
b590a30b-feb9-564e-bff8-1d996a24d1d0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
ef540f51-9053-5576-b3df-150d0e70f8c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
a3cdbe7f-ffad-55e2-b0c1-5482885468ab |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
78b40b4a-c39a-5050-9be0-3b80d24ca786 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
d3fb329b-c147-5466-ae14-f8ae45ec7072 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
c31d87bf-597a-5ae2-94d4-746113ace750 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
ae140bb8-a357-50b6-aa5b-b677aa91d21d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
ff8be09f-20a5-5271-87ac-c5a38a6e1828 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
78168150-7847-5289-803e-a7c3ee059d21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
2754824f-24a6-51a6-8d2c-e92c2e790ea6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Embedded items
4d2a404d-4748-533a-9042-7b30679f2305 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
dbe6b4b2-ad48-54c9-9edb-ae05c3a820f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
1472d9a1-554e-586e-a1da-367b4e54e244 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
22a75364-24ec-50e9-846e-2d6e9eacf5ba |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Construction Joints
12f94276-bb7b-54e0-a885-0c59ee22eb36 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Construction Joints | Correct location
618057e7-a211-51ca-847a-1328adaf887d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
5d0d6bb9-828a-5988-ab4f-69f63c856108 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A1 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
7aaee76c-3259-48b0-8356-af211a6e87c1 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection
7402ff22-eea7-504c-a4ab-31c1180b718f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Preliminary
927ca271-0565-5972-8844-cf7542501af6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
e34143e6-f96b-5bfb-972b-a085110b3d26 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork
8ec376b7-75ab-57bd-aa4d-bcc33b533d18 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
09c69edb-9bc5-517c-8319-cda8fbbc2c03 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Permit to load issued
bbf278e6-027a-5fdf-b7ab-bb15c886c635 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Dimensions correct
08fa9bfe-eaff-5aeb-8ba3-5ffd10bc7660 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
73d71c0c-a03b-56ff-8c00-e97d976b31ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
7c80da8a-95f9-5529-b388-a30f1da3080f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
6991cd87-7d09-57c9-aa31-48c4fcfc35f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
e9df0987-8b15-59e7-a8f1-698f6361c352 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Joints sealed
efd214ac-2976-5c7a-b5e6-16c38dc63606 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Formwork | Pour level marks
826fa31b-8a55-5bbc-bce7-cdf01d3cbfa0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement
490046f0-9c15-5ec0-b00e-b681b15aecb1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
2e17e142-d036-58bc-b1a2-2225c7b65b5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
935ff98d-996d-5fe4-aee5-e36685d6d89f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
4a696b02-2416-5277-8bde-d468a0d899ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
d52c112e-b9af-52bc-8a9f-2215c37c8426 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
61a975f0-3415-5bc5-8d19-a62b8e7579b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
cb69f78a-b74e-56ea-8c3b-10088bf0d01a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
e48a6cee-9424-5672-8c36-e950f413ce8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
f53ba895-2818-5b72-a7f9-fe347aa1e699 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
62fbc261-61c2-5e44-9da6-b73b4072fec0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
479f010f-c153-5e04-a0ac-d9088f1d8917 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
82414ddb-0868-51a5-a751-46be46937c57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
c3088361-4e5b-598c-92dc-1eb184f647e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
a5c044c9-8953-5f31-a06b-91c619b6a21e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Embedded items
09fb1328-95c3-5819-b030-1b5e62bb6aa7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
ddcf68bb-ca8f-5fae-93b8-83e363213bfe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
dd9fd335-fa38-5b91-bf80-58579ca9a387 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
3f67b2f2-1c26-5762-b22f-974b970311c3 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Construction Joints
271fd82e-f241-5a04-89d2-ba47480034f5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Construction Joints | Correct location
d07a6e64-3f7f-50b8-87cb-d6090ed53d3f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
b4cdbbdc-6fe5-52ff-9467-41ae999ab9fa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A2 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
1ffdfe2f-241f-4583-a4d3-8f67f87fdaea |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection
9d3d9aa8-0eef-5d26-a712-83bd8f2d6f48 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Preliminary
2ca69746-850f-59e4-8eb5-086c56bf0901 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
51f52dd2-3292-58c8-b20e-313627781b0e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork
061e02a6-510e-5a95-a0d2-2a8c7edeb70d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
fbd0dfd8-2f6f-522b-b85b-cef884f3f203 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Permit to load issued
3fcecd34-a619-5cbe-933a-ed994424d1e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Dimensions correct
21045796-dd7c-5580-b315-5704fdd7695d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
70841603-2bb2-5064-a284-75687c087756 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
a0ad4875-0311-503f-9d46-ac5dd6044be1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
7f9296e7-e379-5dae-993d-ca003a351162 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
b8c6d238-e918-5074-8c34-1e5bd33ef2af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Joints sealed
efba29be-5c62-52f6-9770-67b205a6a441 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Formwork | Pour level marks
4d875b80-0f44-59e6-8c8c-4d46b03b5bdb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement
dbeefdec-1e97-50f8-9d5c-19c275c54ac8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
f2477b69-34fc-520b-92bd-07df0e5c751d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
c7c07d9e-2d25-59d8-b812-6be19d4edb5b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
a2d6334e-2123-59cb-a045-c32bf029b719 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
11b0f0ad-7056-5444-a512-67310effd826 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
70ee4bea-a870-5cb0-aa0b-ad66929185c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
4709eb5d-c82c-5f48-a19f-e6be8824cfc7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
d448aa9f-f486-5cde-9d9c-d546697e7af0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
840cb860-86b0-53ba-8305-c5ef3574b62a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
e8904dd4-4e9a-5ea6-947e-af13e5998c1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
e4d6db17-aca5-587d-8b1c-1961b05655dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
4c5c37f9-360c-53bf-9b1a-fc99ab9f723f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
faee7593-47b0-5e51-9916-c02631eee6f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
1d5d27fb-c40b-5acb-b89d-97893b1051c9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Embedded items
f33d4920-6787-501a-96f7-fdc628ebf485 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
6cc31b33-0044-5762-b887-2028cd15c160 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
a7b07161-d9d4-5746-9b2e-a7ec10b9e5b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
92e85c57-3354-577d-a3a4-10652f07a1c9 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Construction Joints
8dab043d-99a9-54eb-b029-e39df3739b3b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Construction Joints | Correct location
b94b7fce-0700-54c1-a614-997d33738c0f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
7ead5f5c-4f0a-5f7c-962f-5b871a87c9c5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A6 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
deca9900-a4d2-432a-8538-c82d02f73b25 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection
297c1f4e-baf3-508e-b27a-5b6381cce17c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Preliminary
f343a333-fb56-5ab2-95e5-66b3c223b61b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
5521a668-9d79-53b4-9e63-a4da6e0e63bb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork
03df15ff-6cd6-598b-a17c-883404e510c7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
35dca57c-bb3a-5a81-a3d6-2470f288b1ec |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Permit to load issued
a1ce6906-e33e-5bd6-81fa-2605a32bd1c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Dimensions correct
797ffbf8-1bc5-5ee9-8842-fb1a24b756b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
f2dc8b6f-dfbd-53fe-bdca-6e13620b01c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
92092977-78d3-5936-a1ee-67acbdb629d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
1f296935-9d04-5ef6-8e9e-084e7a434c89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
58a4dcf5-f6af-500e-b9da-2c5b41df2015 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Joints sealed
423f2549-3cd8-5bad-aa4c-b617f4a21583 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Formwork | Pour level marks
02d710ae-dc1f-5be4-8aaf-a1a63b953756 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement
41e480e1-f55e-5dd1-860a-344e7376dc5f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
67199da1-dd59-5f1a-84fa-a730ecf56244 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
3b645fa8-7644-5813-87dd-51e8de726ce4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
21633032-01ae-58cf-896d-b7412ad3c0cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
cddc77e4-2aa3-5ae7-a93d-efd122b3e225 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
4e4bff34-c572-5bdb-8d30-fffec9a3736c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
4a20fea5-312a-511f-9a16-9e2454b7db81 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
89d1b60d-d380-5c7d-a37a-18bd11148457 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
f2e8657d-101d-5967-89e5-0d1bdc0818aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
6138795c-4806-51a3-9276-5d0493f86883 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
392f4754-8378-5689-8df8-f4cc16ca8059 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
36a22dd7-4337-52d6-a608-398906c512b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
c0c0eb17-74ae-5aa9-a8b1-3d2dea7a02bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
08d58cb5-ef10-5b02-9563-8acb095ae92c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Embedded items
6609ef64-26c6-5671-8ab3-b511379f1b8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
f2f0e549-004c-5b99-8041-82e5bb7d76f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
86871ad1-8c2d-56a6-a261-30062f037744 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
18177596-e2b4-5446-a1de-de7a239f085b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Construction Joints
41b56ca2-76ba-52e0-82e3-64503d12dac2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Construction Joints | Correct location
aad7934b-1012-51e2-8212-151ea1769ed9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
63a57f9c-39cf-50e3-904f-de7001b875d0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A4 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
824a887e-dfca-4b50-a845-733d2bdc1272 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection
b2d56a7f-0ab8-5e85-b820-5995a3e1b549 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Preliminary
a0d247cb-affb-5bfc-9722-f6b67d45807f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
3f31b0bd-e4d6-5202-983a-746812f55f56 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork
a689c46b-4b64-5c92-9f60-8c2749283405 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
fe995f93-23a2-5ae3-9eab-9e5199c7f4e8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Permit to load issued
329b40ed-18a7-57c8-8b54-29c3830942e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Dimensions correct
61125b30-ed06-5e9b-8f8b-9e55c17e9373 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
447e01b8-8270-5cf7-b6a4-9ee01ddd310c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
3ab800cb-8bbf-52ea-ad86-c6e18ea74df7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
565ac204-6cb7-5852-bf16-d0c969bbd7db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
67dbdd4c-a20e-5b5a-a585-6387b0aed249 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Joints sealed
baf0a552-2b71-5bbf-8d3d-8d47b9f129e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Formwork | Pour level marks
fc53e2af-48c9-5357-8baf-fbe28ce2556e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement
ee0133fb-a3b0-5473-9655-689b5ad02a1a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
ca064299-3cb3-51d9-80ed-fd4db6434a42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
cc7fb76f-b9fb-5d54-9c33-342e561265cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
73bdd502-d0af-5028-97a6-4be22804716e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
7ded9fa6-90ac-5319-86e5-363f1410b91f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
ddb1d556-c56c-5818-892a-91c4e8cbc93b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
d3f11411-13df-5d6f-83d4-8684cf0f58c2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
1eb0a777-b90e-5845-b000-903392298dab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
6c896f6a-72c2-51f1-b08c-eea4b1af9907 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
2cc8473c-e23e-5e80-83e1-6d29c659fc8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
39dc0988-3983-5009-9c93-933bb2f1ec95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
49cb5882-8cfd-5ad6-aa74-f72b552ddefc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
1312bc30-18a1-51a8-a0fd-af98e0581b2c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
b070ee38-2fc7-597f-9242-4c945026e1de |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Embedded items
7d318252-31c7-5eb9-a755-948ffcb7a7d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
d181b911-c04c-560f-90f8-5543372ce636 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
f1d18e00-8988-51ab-969b-594c805ec8fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
fbe4f4dd-8c56-523e-9330-2ab80b5c3a49 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Construction Joints
7af7b238-78be-58cd-bad1-aa07016b1e7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Construction Joints | Correct location
785e722f-0ec4-54a2-a5f1-f7f5f7b54b60 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
8294f085-d5d4-5d43-a89a-9aae3d507bf5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A5 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
537bc294-26be-4afc-a421-0ce5570a3e4f |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection
4e73e49b-64b3-5307-97d3-d68a4c55f1dd |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Preliminary
2f026f2c-1537-5650-be58-44cfa6c4f201 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
93321027-8912-5641-aaf8-7091cc4f25c5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork
b5973a47-5c74-50c2-969c-4b486842ce98 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
722946e9-71dd-5e0d-93fd-43ff98c6d8ba |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Permit to load issued
9d6a420d-8097-5d53-81bc-d336096bea17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Dimensions correct
644c7a26-e649-5fa0-a5dc-e0a710baf805 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
d7aeb8f2-80d9-59b6-ae33-49307bab7750 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
ceb533a6-8c04-5ed9-b484-3ed4f1fc20a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
9114e73e-93d7-550d-9228-f61bae2bf5e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
48aed627-8851-5d20-a0d1-0363fdcb6a0d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Joints sealed
1ffcb090-75da-5a87-9d01-9822a2ce66e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Formwork | Pour level marks
7345ccbd-8ed8-5afb-b95c-34fce8b4ad0e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement
d4714db0-480c-57e1-bddc-cadb4cc8f016 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
c5397435-7186-5654-9459-697e2a524814 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
390d30d5-e7a8-54e5-b6ee-01795e6e041a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
ee04e952-acb4-512a-b4fa-93de536bb0be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
b8ba33d8-3fc4-5216-a38a-c9d01d5b05a1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
00232784-940b-5d7f-8e64-c9d733db5aa6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
b836c863-5091-5c09-877d-bb5017f510fb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
c50383a6-6d33-5def-a09e-45a733b1484e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
262d2cfe-e24e-5e48-a95d-434deeee67f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
f4cfd993-826f-5223-ab22-641381209442 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
fbe54431-4c33-52d4-9223-fe3f3fe541a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
0cec1fed-9118-5b0a-bee8-79bd7b89cdd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
2344e91b-f8cd-50bb-8e6a-a3ff112f550d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
c645e0e7-e641-5f0f-a06f-7fb844600259 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Embedded items
b1690942-63d6-5953-bda4-c4bac7e04eb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
e22eb9a4-4ba0-518d-8136-75696ef8da9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
8608939b-f245-5bf3-93d4-eb8c8e053c0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
36be6f97-8a35-5b1e-ba5a-df7e3edeb19a |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Construction Joints
9cfb688b-1a37-5dc9-b50d-80a17dadf30f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Construction Joints | Correct location
884602bd-b733-5f9f-a48d-5fb9bb958e6b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
80c795ee-b3ed-5d6b-803e-6cce0c1fce26 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A3 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
32848d4a-8a39-4ad6-8d45-08ebb719a2ff |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection
6b3fc5ad-1592-53b8-943e-c30291c09aa5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Preliminary
878bfbd2-f2cc-5b06-9684-2bf3ee98a201 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
a284c5c3-9229-517a-9152-107e2c9e48e2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork
9d186d64-6c92-5e93-9a6a-9542f1633803 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
067d717d-06dc-582f-b261-a1268bc859a6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Permit to load issued
db4161c0-8cb1-5be9-9fa7-184e229f2fe6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Dimensions correct
17854683-66f0-5004-bbc8-62a898373dcb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
c6f20e91-e940-5b2a-a385-c84ae251587d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
7f8ad8f6-0db0-5445-a2de-d87f053a9103 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
27bf38a1-91ee-5dd9-a606-42c009260dbd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
8f173796-043e-53fe-afc0-67d72fbf1f38 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Joints sealed
6f754b51-344f-5b25-93d3-ac1bf78f5ea4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Formwork | Pour level marks
d1578d73-f1d0-5aee-b21f-26bb095db900 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement
ce137db4-be64-5097-b196-ab02a53f8215 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
15f854da-3590-572d-9af1-642b939f8f16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
5f0fa41f-15ab-5659-9883-061aebe94b90 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
519392af-2515-5d77-b121-64fdc369a968 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
21547d7e-e279-5013-9f78-b38dc33229a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
9afd938d-43d9-5aa6-89c3-238a6bbc68c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
a5a87de2-fba4-5414-b586-a2b7acefca7a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
45fe9ecd-c311-5c13-a8e8-8cd531480045 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
42724244-a0c4-5553-84df-412faa267bb8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
9d9cb6f2-5cf1-5e38-becd-db12838d7c31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
43d09534-b2e6-5bad-878e-b97c6c8818b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
bfba8235-1d79-57ec-aa66-f6d9196d4c00 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
7747a655-318d-576c-b510-d0c97c83ca5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
cde497c7-0bdb-57d4-a8b1-f3a2c6d99053 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Embedded items
8386edcf-bf70-5426-8cb9-a7042d645c40 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
49c54488-fd9c-5b0c-bcfe-f2b08e778c22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
f3838f03-7715-5402-b45c-529261646388 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
53951421-0b71-59df-9863-d3af3bcd7a73 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Construction Joints
bf3cb20e-6205-5fa9-a621-c2c271027be4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Construction Joints | Correct location
4e0018cf-44e7-592b-9b1a-fc1459752cdb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
c915dc9e-93d7-5aae-acb9-cb27181e2bd4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A7 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
a7558a15-3526-46df-a76e-94a0fb4bac0e |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection
abcb4e08-cbb8-5238-8f37-3ae06613f1ef |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Preliminary
c1f0a3a6-70b7-5ddf-a8ea-432ee98c9903 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
fe8cd411-9ec1-5742-b300-14b3a5575e65 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork
b11c9ed5-2cd7-50ea-9d94-6b09460afa01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
21e9de05-c1c9-5daf-b195-01ae49783803 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Permit to load issued
a738260c-ee24-5325-a921-4aee81a675d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Dimensions correct
2d5fbd08-77a0-5f67-b1d5-88a273275074 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
cc317e18-7276-5dcd-89f6-0146bfe474f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
c3f624e4-45ca-512b-84d8-a02e2c83eb7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
bf6061f5-84c7-542f-bb40-3cf6be0fc74e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
531fb2b1-d17d-516f-b939-67ca2c49015f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Joints sealed
95d975e7-c479-5394-8638-700838661d65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Formwork | Pour level marks
c1dfde3a-18e0-5956-882c-034bf2715d9b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement
3db3bdef-0ce8-5a3e-8a7e-9b7d627a9643 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
7cb50854-44b0-5e87-ad8f-48b882b72edb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
97130700-5d91-5ed3-afb9-82b631f997d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
2c467547-2c4d-567e-ad29-dbc8d509abf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
1ca83dce-ce77-570d-ac86-b30c57e1249c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
42ee3fcd-8710-5fd1-8c03-0cefed4c9ee2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
3487613f-42d6-583d-91a4-a91c43fe42aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
2bc98ffb-6086-5dcc-bc11-661be947e988 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
e6a414fa-7e20-53b4-8598-5ad5e8214379 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
3b2dee43-461c-5d8c-9b35-ba4c55f1658d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
010ab054-3bd9-5cd5-903b-fc1a170ee52d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
3e4932c6-59fa-577c-8fdf-ce33e7371afe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
17a09fa7-5a40-5b76-993d-0b5164baef59 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
ff3829c2-459b-5907-bfd5-57f887771824 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Embedded items
140e7cc9-67f4-5ef2-8369-5fe0910a2c5a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
5035b8a9-1703-52b7-b697-7c1089a006af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
e8af5d61-3cdc-5f0e-b29c-8da8263239bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
055b1fc7-d768-52b7-a69c-69c19fe5f47e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Construction Joints
e16fc5af-beda-5ccd-a253-7a43aa0d2aa8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Construction Joints | Correct location
026f410c-069e-586e-b4dd-022c41a49402 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
bd92b485-152e-526f-a080-ce8e6f3ffbf5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A8 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
a99f354a-a8c0-46d3-91fd-c640d11026c2 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection
00c8c65a-0df0-50c3-8dbd-fda75598b65e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Preliminary
7446077d-d2f7-5af3-b715-50c62a252e63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
a2d5826a-c4d1-57ef-a48c-7f4b9ff76b5d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork
32747806-d1a6-5266-92d1-ccc4f0441e4c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
4014b790-dc46-548c-9359-032c534db661 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Permit to load issued
8c4bf713-e73f-5b9b-833c-2725f4378184 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Dimensions correct
4b59c16b-a4b9-5b48-a3d7-942af3421896 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
3683ad38-a67c-5e63-8dc8-d2cb2bbc484d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
0e232cf4-8ac5-5cc2-88a5-37be5d5187ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
b5698f1e-861d-5c83-bbe8-b4e84a49ae07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
7e2e3b80-f75e-591a-a845-c667150b252f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Joints sealed
d8afa344-ee1c-5aa6-9d49-c9bfd656d8d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Formwork | Pour level marks
c4489976-217a-57fd-82a7-d6b12159a870 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement
065eff9e-4a46-5592-94ae-2f4c2f138acd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
eab8d91a-901f-5d1d-bf7e-1b9486e2615a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
b7e8701d-5db8-5674-af4e-9ad7aa4ba390 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
8c0a50c5-1685-5273-b7fd-362229d35e37 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
bdf1ad87-65b5-5d9f-938a-75369b17709e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
54ff22a7-20c7-506c-b01a-812b3bbc8e19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
2de04745-3b8a-569a-a05e-d2f335c63341 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
6984de7a-829d-5528-a009-720d98cac1a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
aef2001b-eb9a-5456-8594-f2021b61768f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
f81333f0-38ba-5534-81b5-3652b70703fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
7428772b-4b46-5b21-ad38-2a097c2a4d5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
0adb4ff2-a985-5a80-8782-bf81db1dcba2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
44ce0777-98df-5972-a357-008404f9db21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
3f70b569-37ee-5598-ab19-10aca40e14a7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Embedded items
683f46aa-77e0-5523-8ba8-8c24faeeadbf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
33b1faf2-8a81-56fa-9ce8-8048a4a4e72d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
c92f017c-eaeb-56d7-bd6b-0bfc63f44aad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
99b54ef5-e1fe-576c-b24b-ee563cd4523c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Construction Joints
35bd9cbe-830b-57bc-97c6-0303b7608477 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Construction Joints | Correct location
a5c8b54f-8a22-5e0b-b223-5a9e08e7ad0c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
a075815c-46c8-591b-b14b-e41ab880e74d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A9 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
fb06736c-8ec6-4f6a-bc0b-28353cd8cbb3 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection
e02f6094-0311-566c-958f-2e544bf47cf2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Preliminary
69c8098c-6e65-5323-b3b1-b9f074b38084 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
ed9c10c0-37c2-5ea4-82bb-ceae9944756e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork
7df64847-4bb6-5eac-bd26-8950d6d58029 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
4a080a36-6c07-55da-8ec7-25ac5994644a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Permit to load issued
ec2a394c-7f9e-5fbe-9d61-6778c62ee9f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Dimensions correct
360450e2-6c91-556e-a265-60b40cfce198 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
44794570-0663-5752-8529-fc507a7b522c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
e9f589ab-89a8-540b-b5ce-7061f8ce348c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
8e6087b2-0679-5858-b6a2-68cf2bd6fb67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
5ca556c0-c093-5a0b-8e0b-3c1562458c1c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Joints sealed
8f999df8-1491-55c1-98ed-71c627aeea74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Formwork | Pour level marks
a6c604d4-96c7-5c5c-8110-ad60098b95bb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement
f641e83d-01c0-5d46-9162-eb16317cd185 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
da52d4eb-9946-5f1a-9277-53970004f78f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
4efb8a99-2339-525b-bb84-dce34d6c241f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
8b631fdf-96bf-5754-b38f-2d5779a62871 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
0e2f0eed-9938-57ed-967b-5dccee955eca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
7a2c57c6-8586-51fd-b781-fe4660541aa7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
02f52311-5205-59eb-95e8-31bf70e2ef59 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
f7d3f606-06f4-55f4-9854-1213b547a891 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
ff01cca8-9fbf-5bcb-8aaf-a60472697a66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
b22063a3-a6cc-5da1-bb75-43748f84140c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
6df960a0-c44c-548d-86e8-5b5d4bd5b889 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
db8e2516-7d2e-562a-b702-292d9f5ed544 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
95a33644-e1b9-5f20-b50f-21696a3044f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
79c5efc7-7c68-5e60-acf9-5eb642489022 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Embedded items
78dd66c0-d5c5-57d8-af35-0d659397b654 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
7a04f706-99da-5949-9b73-480b2fec6ed3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
ede601e9-8f56-5063-88e7-1497ae65bb24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
6cf12911-01d8-554c-8781-e9ca5fa1c3e6 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Construction Joints
ab8b109d-3f24-5596-98b4-6f21c2912e61 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Construction Joints | Correct location
5dd4e8a1-0c10-5462-8e8e-c071926ca721 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
8bad5a73-6576-52dc-93cd-15b9b6a1f532 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span AB Beam Type A | Beam A10 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
f9abcfe5-a514-4c65-ab08-abc7d7e62cff |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B
d956b935-e42d-44b2-ad2b-73a67ec322da |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection
dbfbe547-7cf0-563a-9f96-e54980065a50 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Preliminary
dbdb9c86-10be-52c0-bfca-c3182a8c6dca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
18612e87-2c14-5d50-8890-a95126ef4e54 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork
accf7239-5879-5733-a846-6b48c6bae98f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
314efdda-91a8-5b21-81bb-e477c2c8cb4e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Permit to load issued
48c115e9-8b52-5694-b21d-d2cfb9c316f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Dimensions correct
6479f79f-7f2c-5419-a388-1c8939152c0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
9d5de5c0-9517-5edf-aeff-c9aae9dce13f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
0b949d1d-239c-5271-abd9-972dfa80a3f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
d0a2652a-4dff-5cc8-81f0-3fb9f397146a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
d3e17e97-c717-52f6-a87e-5193f9850e01 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Joints sealed
f9d506ec-9512-5161-95ed-4826b9d2739d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Formwork | Pour level marks
35fa5d40-2814-5abf-970b-b35104689871 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement
78652041-0bf6-576d-9cf8-947289a47cf8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
ab95b8c4-3f70-56cf-b952-f1f2e0414fda |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
67e6ecfb-376b-5ef2-83ff-585764964b8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
06f51261-927f-5433-9193-4bc4578b366f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
b77518af-ac56-5d8d-b854-8a0a35ba1e22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
8b0ee8c4-da31-5d34-af6a-b33cd42e1728 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
8a0aab0e-e24f-5797-abed-03318eb739ff |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
87e58c96-bd54-5e83-9002-82f7ddb85bde |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
2b31e7f7-167d-59d7-99a4-3f212dc3e932 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
3d401b37-ad39-56f1-a0b1-d339dbf3e4b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
e1c3b7c8-39b7-5fdf-85f2-6883eba17662 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
3db795a6-f66f-5994-8268-80e65fca8ce3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
03978161-bfb5-5e12-a4f7-e43b23b2bb61 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
52f98f23-a09f-5908-b084-e631027ca056 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Embedded items
16fe117e-5ac3-5dab-9373-0f2fe76f225b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
549b553a-9b65-50c8-a5c9-04ae7f027dbd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
5379a200-8ba2-5423-a71c-f0e5b030b802 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
ed831f24-1997-5967-b623-2e90095347f8 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Construction Joints
50e7f814-790d-575c-98c3-870502bc7c7b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Construction Joints | Correct location
bdba72fe-70d2-58d7-bab9-fc80f9b378d4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
d58418a1-de61-513e-bebd-2d5d4bdd85a7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B1 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
9f2025b7-7e09-4668-a20d-b371964e60e0 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection
523a83b8-fcde-592c-bff8-9f56c3b20dca |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Preliminary
1f36a7d3-a430-561b-aa9e-d614b1913c59 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
80100762-b3e2-5c3c-9ddf-adcdda72e9c0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork
ce8e4806-4af4-56f9-b6c1-f02ce83a4ef3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
13aa6599-abed-54fc-9464-a0aa5d6b281c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Permit to load issued
ba756fba-5c8d-586d-9429-77efa6c259af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Dimensions correct
831e0d78-2c08-5b3b-96ee-20e10f01f416 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
377901b7-c7ca-5fd1-abd7-3e5797574212 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
43ea1e2d-c502-5add-97ed-adbd67331c71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
75b9f3dd-1510-5d64-a78b-1cd350ab1d35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
2e9dfde5-66c7-5c2a-ad9f-a049401d63d5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Joints sealed
0fe1daf1-8115-551e-9345-19de60d88377 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Formwork | Pour level marks
5591fb2a-316e-59e8-9bae-84a6e3df7f99 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement
9370c209-ebe0-54b9-a902-27f0472ccc95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
6fd82f38-9fe9-5684-9c5d-fc9a598f4b3a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
b18132d6-25e7-5371-aa73-d64d61c0f02a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
3f63dbb2-f34d-5e44-a39c-1a3a57caeb8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
41b12a58-b33e-5132-b2aa-b8901905b6b3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
52800333-7763-58f5-b4dd-d753fe014d31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
b6ca761f-c296-5b66-8fc0-7af887f3d83f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
95637f97-f875-5113-8c6c-781ff1c98a48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
385ea053-d0e3-5585-8d8d-c3924ffb4a29 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
07adbe42-3764-5cfd-9931-002074d687ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
133a5a66-9b05-5b37-b178-1b805ac7efd0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
66b0a638-a40e-5629-a3d6-27159180077a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
bae772a5-b888-515d-8428-539c82a0dcf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
e3c2f49a-8203-51c1-9aaa-816bdcae83ee |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Embedded items
896de9a8-a02d-5304-aec9-b679852ea45b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
d596ea8f-fdd1-5af4-a053-c3dfb7afcd97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
a5f7e814-e6e4-55db-b723-0a6266d3279c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
ab3eaec6-699c-5940-bdaf-630f5be3f2a9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Construction Joints
8af241b8-27d0-5c46-8bef-b0d56d525cf3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Construction Joints | Correct location
84f8879c-9488-540d-b3a9-e21f2bf08091 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
d6982d50-2e40-5f24-bac7-c62f34045aea |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B2 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
61b01545-be66-42aa-a465-5ef2ef1a01a4 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection
a4494b2b-d1f3-59bc-8a57-addb66d6b4de |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Preliminary
000615e8-0ca3-59e0-97e1-f49c6d1a688f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
8525f560-96b5-570c-bfa3-41266e38e7b3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork
6f3ca0cf-9f5f-5d7e-945c-6a46e4a4519f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
bb7050fe-76af-5046-9d32-32ccc41de509 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Permit to load issued
0c7c6004-e10e-5531-b624-b94232ee77fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Dimensions correct
b4e583a2-205c-56ab-a8a7-129ae2104ad0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
145f082a-2370-51d6-84eb-32a6a3f1ebbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
ef4977b8-7e25-5fe1-8caa-9400e48da380 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
9372ae24-fb16-5b3b-8c80-ab5e06add26c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
e04e0c08-541a-51b8-b85d-cbff37127a01 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Joints sealed
ea814e00-88b4-572f-a7aa-63ebe52421b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Formwork | Pour level marks
17af102d-71d2-5fb0-b3f9-a497a59c5f74 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement
cf856dc6-e3e7-5e39-b3bc-d6500a1a2ff9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
bf6393ff-40f4-5d78-b183-41ba2b5e7ea0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
7bc411a5-3fbe-5a88-b3d7-650c04d526a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
ed5a8190-31b3-524f-a11b-bc9a86fb8735 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
cb0722d1-f233-5276-af5f-e95aee450999 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
2b9f6533-bde5-57ae-8800-027e4769525e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
4e6c22e2-0886-58b7-9287-0a9e260e32c8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
9a446e6a-cfba-5a61-b270-bbfddd556e6b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
420985ec-26e5-5d39-ba33-8f60233bd2b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
d3297763-ec2b-53f1-babe-fb9085d36206 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
c95bf744-2d37-5efc-89fb-14c1b4fd732b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
caf03af0-aca1-5c41-9b2c-a0c0fb51f354 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
59de5860-6a44-5aa7-b6d8-3cdb3eefe29c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
69483bf2-0809-5894-9ee8-58804f6cb54c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Embedded items
ee493bfb-7c4b-5c10-bc51-31a1a5c377ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
0983e709-4102-5976-9da8-3be6da63700c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
7b387759-3fe9-5320-a6be-1d1d336138da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
ba1b02c9-30dd-5bc2-8b16-80a2c3290f1b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Construction Joints
b8f63ebb-c87a-5c70-920a-ef31f858f530 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Construction Joints | Correct location
769ca42f-6e2d-5467-bce6-7180f5e93f0b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
4df23224-79ed-5d93-8b9e-9af6ed404035 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B3 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
388b7c34-281e-40c4-b5a4-54e90d49f790 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection
aee397c2-5352-5062-9337-ab9286556aa3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Preliminary
80d37876-a97f-5928-b57c-3523fda7c84d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
73e459e8-1262-5a64-8679-aa657f482137 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork
396918cf-6b45-547e-9ee7-4bb3ed0417c6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
f2abe291-08e6-5add-be42-fba1fc712c5d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Permit to load issued
507734f5-da01-5700-83bd-91ab06b07be6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Dimensions correct
11547255-3986-5e28-b2ba-cf2e98ab2d4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
c18f426c-8e44-58ae-aee4-a6a284e1fc41 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
3fa93395-5eae-56cd-a360-135fc06e2b71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
e56fb704-a6de-5952-ac42-de8b46ea467d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
d533907b-8413-5c72-8d03-a82294dff35e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Joints sealed
ae108e81-8ebe-5338-9514-2ed7912c057a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Formwork | Pour level marks
50128598-eaab-5d3e-a5c9-113b64d947af |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement
18dc132d-2373-5d26-8c31-cc84ac87e74b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
78d878b1-eceb-5996-bbc9-720501573d7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
83fd1baa-493e-5204-ab27-66cc2a5d9053 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
f26b3812-18d8-55bb-939e-382b0a43dec1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
8db98467-1130-5fc8-af4f-8f8768fc2448 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
84cb93b6-3ae5-5523-92c3-8fe24b161ce8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
bac1c1be-c622-590e-9692-913bc7696c07 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
38f85b51-05cc-5dcc-b68d-7f3aa3a3522e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
f4e56b0b-3861-5623-acde-e4693e9b85be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
35c5233d-0f99-5e30-8b49-688897246f5f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
bf8169eb-9fa7-500a-b768-911bdae8ec2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
8721212f-c5bc-54d9-bbdc-8ed94f71dd16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
549d6f5f-0265-563d-b87b-77e51bb48a6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
44117ceb-daa8-5a34-9e5e-841165de2c32 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Embedded items
37536dde-0bc3-5b93-9de9-894144ea8c97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
43258c4f-2a52-5bb5-b4c6-913cdf38670a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
261f2ac4-b337-574b-a0b1-b5df0353b80b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
e36f7e70-2a6d-5055-8093-bc4726ab531d |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Construction Joints
242079a0-51c8-5bac-b9e5-ddfa2a281d45 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Construction Joints | Correct location
6120b1a4-c09d-55c4-b60c-6d400e50bbd4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
ae593148-36ee-5580-b24e-8e46c4be5399 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B4 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
4d3d33f0-35c5-41de-b51e-0081908d71b7 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection
343eba1d-338e-5e40-acd0-1a203115c91a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Preliminary
2c63b77e-8569-55c1-b276-1b3d94da3757 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
c263e30a-b869-51e7-8f5b-360077b45ba2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork
008a285a-aa60-519f-a97d-e49b458c120d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
cf769674-4a74-50c1-b2ff-4b877f18bef4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Permit to load issued
a8af973e-1adc-5e35-8d32-de3061ce8aa8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Dimensions correct
d54a1dd3-f9f6-59dc-962d-17b775d9d1a5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
bdb56d26-cabf-50b3-b5b4-ac1eec4e6f81 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
52aa46ed-4899-5540-908a-6282e80545c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
9e2f0e2d-a5d4-5628-a023-d7b30fa61def |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
5e4a6e49-8be8-5933-9a7a-12fd0de26830 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Joints sealed
648680b1-d5ec-518c-ab84-5b37787e65d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Formwork | Pour level marks
4f49c252-46d3-5f89-8010-129b9de54711 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement
7321c6a4-643a-5832-ac79-12c80c0568a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
3484bcfe-a7b9-53f6-afc1-84f56279a137 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
1a452c0f-dc0c-5a2c-9cd4-945c6b02d1cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
f638d868-6657-594c-9d43-0da75cfbbdf3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
7b3bcfad-1732-517a-9c84-20bb9ff31462 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
98d45064-a5e4-541b-b97b-066f6409c742 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
6fb5f47d-5cb1-51af-ae73-a35921ca7555 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
55d8b1a0-6528-53aa-a30e-064c03fd0c74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
7c25bf57-6df3-5405-b2a7-99c1f0f9029c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
72467a8c-fb2e-5232-b7f7-35721513e7a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
c82c5de1-a7cb-5e25-a300-7edaee3f15f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
18e10fee-39d2-589d-b43a-3d91af9edc8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
b2aa9b8d-1187-5efc-8622-091402fc9530 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
6b478023-7cde-531e-9ef0-bc8a539a8558 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Embedded items
1203aebd-f8b3-5f2e-b9aa-c146e568782f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
4132b0ca-b235-5242-ad5f-421bc85c3222 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
05975d83-850c-5ee4-9c02-7fcad723e04e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
8c05f370-4f91-55b1-ba6f-1ba8e9359012 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Construction Joints
1fc4f55b-2059-5ebe-937a-de7c646c9750 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Construction Joints | Correct location
e4f87107-49cf-5034-a06a-670e4bd49e80 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
b0b34ffe-9e96-5201-8788-bca099b77fee |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B5 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
f392c136-044c-4847-afa7-c5cbdc559c64 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection
90a5f82d-a2f7-5de6-878c-4eb3fad5d36e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Preliminary
0ee10b3b-7a27-53f5-b93b-2140a6faa583 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
0ad00773-6a20-54d6-b590-9069d987c23f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork
7f5d016a-fd1d-5e92-92ed-9472336041e7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
7c6a8837-191d-5e16-bd8c-29ebd82aaa6c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Permit to load issued
81b1392c-29c6-5281-9e95-0a723e6d8bf9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Dimensions correct
2861e80f-5b1c-5b3e-9241-871c653bef75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
0d45305a-9b3c-5e53-8006-5d23a9504697 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
57cdc4ff-60f9-53eb-a1fe-1f8d0f27cdc1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
be7294b0-fbe7-5406-a390-f222f5b2ed97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
97e71233-1a62-5a64-8d57-ea87a037a5b5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Joints sealed
8c21b3ab-eac2-5979-b7f8-69b7b1b2868a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Formwork | Pour level marks
c2d7031a-2a8f-5212-9362-0f8633e62806 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement
5d5eec13-2d8d-5caa-82be-59ec62ad1cc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
9f18859a-d2cf-5cdd-9c9a-c6b705c90f54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
8153327c-5e8f-5d1b-8417-29cd4629797f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
8d566b47-0cfe-5d8a-885b-ab08a3f50e25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
5fbe63e6-d6aa-534c-bc0d-31e3514ce5c0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
29c464cb-d236-5c46-a0c2-b0d999518b95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
84f803d6-76ab-5d87-b123-776c343d5ea0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
0e99e498-67dc-5c50-95e7-255417b5a0fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
618cf061-d129-558a-9778-8ff54ba9551b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
42c9cfe4-391d-5194-9a44-ae5bb7b2eab6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
89c10076-5773-5d3f-8d91-3e578fd94bba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
7a3e4375-1dce-5410-ad89-a6aba173621a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
17f0bad8-ac17-5578-8556-1c39c78b57ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
b350b56b-eedf-5343-bf7e-a64ef04f2b47 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Embedded items
97d6f166-161d-505c-8555-4550f5bc3744 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
6910a3de-84c4-51a3-94b0-9c8a559cddeb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
327bbca8-0c37-57b8-ab7a-1a39e5f28730 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
36c6b296-369d-5e26-b4ee-450baffaea34 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Construction Joints
3352e830-9055-5b5c-a882-7e3e6c35cf2a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Construction Joints | Correct location
de22a471-6319-5df1-be3f-974456756d7a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
cc7cbb00-197d-5366-8c00-25c33f0df1f7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B6 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
1091e743-7947-4d33-b7b6-529819e71db8 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection
8a457ae2-92bf-5c3b-9725-7a5a6bb6cc04 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Preliminary
fd153f17-1201-5c4c-b3b6-e22c5e8fee31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
387c3bdd-0226-5b50-be9b-5948883b9396 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork
ef2f8dad-2bc3-52fa-aaee-ed6fc695f448 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
38cfc863-0257-57bf-94ab-0636d322744c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Permit to load issued
d033175f-2456-5cfc-8b08-a505b14205d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Dimensions correct
dbcb62cf-c502-5e59-bb9d-26411f6966e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
51174408-60d8-51b1-b1db-320c52730b83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
f94376bd-2eab-5fc5-896e-03f5573e9958 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
7095dff7-2d92-53dc-b7a3-ed4fab75546a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
abc40a79-8919-5e1d-bab7-3074f04d103e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Joints sealed
a6bf398c-ce14-5833-ad55-22f0b88a10e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Formwork | Pour level marks
97540cef-811c-5dd6-bcae-16a2ade1e311 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement
b47e6728-05ba-5cc4-bf83-b3b699e77cfe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
68e6c081-05a6-5ec2-bc85-0c28e5b54754 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
09fc14ca-caea-5998-90df-487902e9c99e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
1281e28b-e540-5f84-9e73-2d0284e547cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
dbfc0b04-e4a9-5eec-ab75-6a806f59c520 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
8027dd83-8b42-5c75-a4fb-566f47dc9e26 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
41662006-bf86-501a-93a7-a2cd9423bd2b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
27facfa3-1169-505b-934b-cea39c28bae6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
fca0a635-2cce-58f5-b0f9-5a88cd2f946f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
3a80a560-d338-5e3c-a047-822543c0d346 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
5230d414-ed4f-518f-ba97-fd07bb7d6ddf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
6061a893-4dbb-5526-8190-6f32525d3eac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
653c023e-c6c9-5fea-b182-4bf30ba3e1ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
acf80e16-a1a9-56a5-8797-c7d9d64046ab |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Embedded items
085d2de8-771d-5ad3-a54a-eba571b5ad99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
92631087-5f46-52a0-b5a7-65a2e7989cc6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
719119b8-786e-5392-a906-a9eefffc9137 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
92020afa-a5c1-51ef-9640-9f9019f182a9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Construction Joints
f558421f-e921-5390-8b95-bb99fc03a2a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Construction Joints | Correct location
61575f64-2c58-56d5-8fc9-7c04db6a910f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
32c76d39-e7af-5a39-aa7d-249ec3b2c956 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B7 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
7b93f315-23e0-4dc7-9b4c-0e163e0eb2e4 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection
3e41306c-cece-5fd5-b1da-8240034e1466 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Preliminary
5ae25da0-0233-590d-beac-7fe7fd70d707 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
6769b0da-72ce-542d-b0f6-c0aefb1ec618 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork
f52e7445-383f-52e3-a0dc-61a83935eb24 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
5a3f92c2-aa66-5815-a048-444af3c8dad8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Permit to load issued
a645e6e0-8ef6-57a6-8ad8-a3cd108a172d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Dimensions correct
172bad49-597b-545f-8b23-6bdd3c7620e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
abcbe1fd-e0bf-5d56-bf01-14b9d705e259 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
d5059613-dc6f-5c66-9b0d-2b5e163e2812 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
2bb8c742-bf37-504e-9c1c-1c793dc5c177 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
5c389834-45a3-5bf4-8137-a50d7d27c0ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Joints sealed
2d84b96f-3324-5283-82fa-06b7ac2d30c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Formwork | Pour level marks
90d3522f-f07e-5052-9501-4d8a0437bf00 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement
ba54ca13-6d29-522d-ba51-dc7f8d362293 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
4c05c8b8-ff45-5596-a951-59276483a6ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
7ff801ca-02c3-534d-bd0b-a6c15915972f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
483fb950-7214-5eb9-9a67-9933571ef7a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
47f01515-0551-55c9-8252-266110043bcd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
e8888fb0-2590-58df-a45a-22794b48a043 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
ca4ef1b8-a122-5972-9c15-4883d1d9d9ec |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
28ecdda4-7d54-5a80-9220-d8bed3cef81e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
db217501-44c7-5fa2-a90c-7bfdbabc0b12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
649bd722-2938-584b-a0ce-bb23ecc26df6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
4820fc0f-53d3-5fb1-bb63-4f5a1cb6a943 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
054d17f7-2c87-52bf-9a5d-12ecf2aa5e94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
72272764-8241-5e09-813e-95fbf54ebbb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
b41f65ab-31e8-57f1-963f-c9191cbd26d8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Embedded items
693242cc-c244-5614-84db-8ad2e74ca2ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
78b86d42-4113-5dc0-90d4-cc6c3d84763b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
284acdfa-3b88-52f2-a2dc-12e85a1c6830 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
d01e3a2f-8425-5e7b-a25d-b3a127099333 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Construction Joints
8fe388a3-d050-5e3e-9e3c-434e77390d92 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Construction Joints | Correct location
315dfb74-4323-5271-8526-17df3195ab47 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
784e9505-1901-5571-9714-357434e79447 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B8 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
4ecfc6f8-6f49-489c-8755-27ca737d812d |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection
c7f7096f-b904-57dd-8072-7e3330942550 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Preliminary
15dc89bb-b12e-52e0-a950-31a47da1f258 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
9ec43ef9-1e5c-5b63-9d6e-0ecc3c7d4e20 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork
620b0809-52fa-5c3e-bcce-4eb913bcbe81 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
06d4b135-f471-52d2-9cbe-799b48e6fae4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Permit to load issued
c5eb82f1-a196-51e2-9a67-e91b06f0a42a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Dimensions correct
7ea4814e-124b-5d45-8b31-58275a14aa53 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
fe0e78f2-7f9c-5e9d-9032-e40270be7b47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
d8a1f1e9-8630-569d-9048-3eb54bc916b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
9f99d0b1-5da9-5e28-a8f4-6fa9a174a38d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
f134b679-50be-5ac8-8e3b-6996df94c7d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Joints sealed
197811a6-ed59-5d18-b97e-fd87acda6622 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Formwork | Pour level marks
a6a0ee5a-3cd9-5f5e-8fc8-e4f7f48ce42b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement
0182312a-5809-521e-9825-d9fa3f5368b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
df61f38f-b243-5289-8b96-d4b126e056da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
f8ca8052-c7cf-5e1d-a733-295bcc97b358 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
174b88f4-2827-56cd-b12b-95606624f9fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
01d0099b-a0e6-5405-886d-c795b59dda1c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
ea6d0a3b-c8c3-563f-a354-2d6e0cafc80b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
6200bd4f-85c7-5a7b-b6a2-d5735d5575f5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
7d24b870-e746-5374-b4bd-ff6edc005448 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
3b207684-3ba9-58d3-844b-cbc3fa300985 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
c0647d41-c450-579c-9285-0980a16caf76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
18d71c36-d4de-5166-848a-c6952a299e45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
49980c78-bf72-522b-b3a3-20dd908f0873 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
443e1cfa-097c-54e0-a5e5-cca517e036e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
93f08eed-4eab-576c-931a-14c7790f486a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Embedded items
02180a27-f667-5d72-b478-99522ce79392 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
87036941-0783-5b49-bd9f-4e7de7d2d4c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
2b3567fe-2747-5a69-bb33-15ffcd90b9ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
025970a8-a711-546a-b44d-841c20f5a178 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Construction Joints
e47ed100-ea38-5c0a-87b5-a56fb7f18415 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Construction Joints | Correct location
9924c307-1d7f-5446-a3f9-552099d156e8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
f88b2b29-c9c7-5b5f-bb2c-26923ab86f4b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B9 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
26faed12-1f2d-45e9-9cd2-46de55dd06d1 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection
9a40d5e8-4226-5a38-b0be-e99923de19de |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Preliminary
5ee397f9-ffd3-5a62-9233-9d6f39a03657 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
108218ab-cb98-505d-af44-10915206c36b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork
2eb1fd33-aeed-586e-8fdb-51f27039bdb9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
7656fd45-354e-517e-b8aa-9d10c1eab68a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Permit to load issued
6686daf6-46fe-5548-9a8e-41b681036ac6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Dimensions correct
6584355c-aa66-562c-a201-33bdedbd0c45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
f23a8600-d2d0-5365-955e-11ceb1e34ccd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
c193e212-1c34-5bc6-a8d2-650ec2e8c5a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
f0834e9b-0f38-5c9f-93ef-beb224ee6051 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
e9ccd248-f148-54ec-b599-2ac8f7485acb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Joints sealed
a925772c-6a62-5c87-83a5-ceed53a8b470 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Formwork | Pour level marks
0e69aceb-f768-5855-92cf-105b370268ab |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement
6d36dcae-35f9-5e3f-a18f-75d78784681f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
941c062c-52c9-5e39-8691-e03c668f79f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
40fb65e7-5feb-5f5e-9100-4504d89d05f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
2a7b87b8-e49f-5566-a683-0848393266df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
9c18a603-393f-5dec-b7a1-e5fd37d2bcb5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
2df24c43-19e3-5c8e-ba42-e3300cc4da46 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
451b107b-5412-57a1-bb80-4b47c1057430 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
bd8e040c-8f63-53f1-845a-11b9390cae69 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
433d7eeb-8406-57d1-bcc9-167360affc9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
3fc1f516-82be-59e6-8280-24c91ef4561d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
9c48ae34-33de-5cb5-8de2-fd57ab6c8900 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
45e6c2a4-f063-5b91-830d-b3fdc2e3203c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
839198e3-cdb2-59e1-9ce5-1246c332a22e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
f8e61690-2608-5be4-b62f-bb0f35cbc047 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Embedded items
654c93c9-22e5-5678-af3b-448dd8b6b601 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
80ffaaf3-e608-554d-ae22-eb6f3c2161f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
d8dbca84-4e8f-57d2-8c8f-91e09e086137 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
5cfc3801-9d48-5179-bde6-66fc3022982b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Construction Joints
e79fd8da-013b-5654-bd6a-2d404862edd0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Construction Joints | Correct location
1f9eb7e3-1947-5589-9337-4e9a5ff63e2d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
3b5483d1-5c29-59e3-b480-192c14ca6cf7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span BC Beam Type B | Beam B10 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
abe38b1e-571c-42d0-bac1-2dbb29d98356 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C
e0d1b8a0-e6cb-401d-af9c-f22af7e15f65 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection
c7878f15-a5f9-5769-9713-68e2a6ae1496 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Preliminary
38df3af2-22b6-562f-a628-985bbe108a6a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
e24af3c9-1b64-5d32-b583-9713e726ad46 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork
e775eb07-92fa-541b-b910-56811ca5f720 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
bd672cb3-b041-50df-a77d-8be5ddfa2ead |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Permit to load issued
545e2842-aefc-5fb1-b913-612e7e792952 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Dimensions correct
a99e769c-219d-5a00-acf0-d5f380c51626 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
53e858e0-c700-5462-911e-4d6820f762e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
dc726a42-c5b6-5524-9c63-e9f32e7cef08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
9afb304c-63e5-5913-80ab-4b59c4e842d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
1386ea47-9176-55ef-8a06-19fa01b10511 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Joints sealed
2b201c93-8870-5a75-9c1d-a41bb229af6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Formwork | Pour level marks
b4118c8c-2ff2-52d1-9d80-bc9337cafa20 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement
6674772b-2284-57f1-bbb8-000bd2a9cd6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
0d24dc51-a710-547b-ba1d-1083fc12f850 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
6d4a76f6-45a1-5f19-910e-8e948dfc6b7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
febab6c2-087e-57de-b72f-305884b77d4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
28e8eb36-aa9d-5978-840a-fbf05d27ee18 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
f70407da-e0dc-5d09-84f3-58c4580145f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
67d2cecd-36f1-59eb-b262-7f74b230bcfa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
fb7937c1-18f2-53a9-bae3-cecd4a63f4f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
138f2635-a317-5574-92ae-2debd24b30d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
24123b2a-3b81-5040-99ab-69239b97bbbf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
702e5810-144d-5221-836c-72b4265581e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
0678678b-96bd-5a90-a949-dff46a526fb2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
cc17693a-d680-5123-bf43-28246b6b4869 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
e26a9272-0d27-5144-85dc-f1c5a6d5de5f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Embedded items
fd10fe1d-27c7-5d44-b2cf-6783baa937cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
2fca30eb-ea98-5550-bf25-cbc18af0d1f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
33d5dff0-fe26-590f-9de6-c130359d4a1d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
dc6d4031-b4c5-54f7-8c5f-83ca1c29dd79 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Construction Joints
7e66dac0-ae26-5417-b04b-187260cdf547 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Construction Joints | Correct location
f7e5e5b8-db38-5e07-8999-dd61075de7f6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
2fe3b69a-c27c-549d-b6a5-bb25c8000550 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C1 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
924bced8-74f2-4dc1-95c7-7bc9e28a9ede |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection
afda3537-97b5-5a3f-bf34-3e8305e8401c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Preliminary
1b0bdeb5-f39d-5f2a-866c-30d0f5fd62ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
68e5e949-9643-517a-8d8b-ee5976dec678 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork
6a21b3c6-9969-53ac-b7a7-2c116d9a1776 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
cf7c3e28-cf2e-57bd-8454-1f9b77f39491 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Permit to load issued
731314d0-9ad1-59d0-9dbf-53f6bbbf195a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Dimensions correct
c9b4c6a6-3a65-52b8-b939-8046ab8f0475 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
af275482-59b3-5cc3-aebe-196a19ca6eb8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
d88ed8af-d87d-5775-85aa-05f1d0ed4d2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
643d28ca-c1b5-56f0-a5c7-c3e9ad519b34 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
70a868aa-78e8-5c5e-b82e-4eb20b8c4fdc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Joints sealed
92438592-64ae-55b7-bcc5-72c7fb617f72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Formwork | Pour level marks
a83b2346-b302-5a21-ab82-fca793943bc8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement
fabc0df2-fd28-594f-a0da-bef6d85f8e97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
670a5b8d-628d-52f2-9787-425df172c005 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
45cc01e1-fbf0-50df-a132-e041a7d8cfab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
b2fdc107-9ad7-5a01-a1b6-1c831c8fdb3a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
f8bdd6cf-06f2-5711-bb7c-c0ef41fb1f26 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
46069f78-03cf-5684-96b4-c4949967db06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
2df3432c-a885-50b1-b467-6fb85b868a8a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
90b7f36a-e45a-51eb-8129-c52ad3590547 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
33798f79-c41d-57e6-9f77-897c67931d4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
c64cec15-ea1d-5214-a763-bb55e2f8aca1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
28dcd9d5-05f2-5f0d-9799-57bedf02af7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
7055b8ec-8468-563b-91ff-8d38e8b8f981 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
e13610d2-bb57-507e-babb-f3d6e16315fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
7e465ee7-ab55-5e8b-b68c-060551996a4f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Embedded items
8fa1e390-b1a7-5820-b569-181c1150515b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
bb821c22-339c-5a0a-9acb-fa5502f07585 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
b9f1cae9-5853-54e5-ab41-fbd6205fc8b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
dd977222-71fb-520e-a460-761db842e35a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Construction Joints
c6e3f244-db89-5793-9693-bea862dbb452 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Construction Joints | Correct location
e97da71b-42b3-5113-ba3d-44edd138f3ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
2482695d-8ffa-55dd-8e51-fb092551ce85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C2 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
9f9299c5-ca6a-45f1-9483-c274f091ee70 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection
79f5a693-5bf4-51c1-ada5-ee3b8962b2b4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Preliminary
fc475ae3-5d51-5368-98a9-cdf6be2e50c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
fc158eff-8f03-5d14-a46e-72d161004c45 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork
85af6758-013a-5eed-953f-847d5b45e1cb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
b12c1a13-d259-5290-ba2a-7eaf87dbd28d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Permit to load issued
2a29aac4-b397-58a5-8087-2df381e6fa45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Dimensions correct
f40cd892-9c92-59ab-8788-8ba7c7b84f79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
b65c957b-ab5a-5829-9f6b-1be825f39569 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
c87aa668-9e28-5327-9a56-d4d5a7c7847b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
e03d4507-320c-50c2-a772-4d8c39692055 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
cbbc9be5-61c1-5f8b-906b-715681a94e61 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Joints sealed
313ab4f8-c219-5085-b228-c6e36a4d15a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Formwork | Pour level marks
63f24a3e-3a2d-5ed3-9f39-3f5db83f226d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement
e2d2d6f3-f1ff-57f8-b9fa-692d308f8ac9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
d14c1df0-2d37-588a-aa6a-a087871094d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
1d5a3d68-da5c-527a-983d-476cda9040a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
aa3f9a43-786d-5268-96e3-27861dbce782 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
0d8afa70-8978-5b5a-88a2-51fddcfbda6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
c29316e1-405b-5403-acba-70e42fcaa9a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
8c601229-7e4a-5118-9be3-3a67c596613f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
6f87599c-6ecc-5796-ae3c-b5626f793f3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
ee4e7859-d4bb-5492-99c7-e252fc9e11de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
fb68d4d8-db9d-5da3-867e-be4a560cd6d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
7bea7cff-987f-5be4-85cf-3a29aded1d77 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
bc3c91ff-8781-59e1-966f-9957cc779622 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
821faf6a-0870-5603-b743-7ee8f144c92e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
f113dff8-6fc5-516a-967d-2ec3b9f51e74 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Embedded items
68f48102-8e23-5c3c-9e52-5774c46bfff1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
8a9db43a-1970-5b30-b00d-c1be206418de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
1b3a04fa-e1b1-542e-9c44-82fd959b4c82 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
01cda3da-c3fa-540a-8572-a6bf4fd475bb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Construction Joints
d185416e-faa8-539f-a875-b766ce75a0f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Construction Joints | Correct location
a92ddc20-e184-50ee-b612-5b09e3b05092 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
025aee2a-3d8c-5dc2-9153-d56260d01c15 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C3 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
decc01ff-2b26-4e24-8766-5711ced1c92c |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection
bed62831-33c1-51fd-893a-6e4c0b03225c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Preliminary
d0027f7d-ed89-55f3-981a-091d52aed9fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
292e94ca-5adc-5eb7-a15f-27fff4380157 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork
9f3c0923-8292-511f-ad77-3001c62b7035 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
fb7526b4-fa08-5814-8221-3e65b1e930df |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Permit to load issued
631cb3c7-29f0-5960-a196-97f9c4e2e93e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Dimensions correct
41b95bf2-74a7-5dd4-ae81-3373a2bf1628 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
a7aad571-3dc5-564a-89c5-ed605e848985 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
3338544d-4f5c-5ef6-a0fc-4e989a5a8364 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
2337823e-67ee-5bed-9849-0d6a9f12bffd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
04d83d18-58e7-5915-980a-02f99ee28d17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Joints sealed
7dc6c89c-ab69-5cda-b317-fc4db9a25d7b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Formwork | Pour level marks
bda8629e-64c3-500f-a651-eef69644554c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement
347d1048-0751-5590-9011-3d0bb4ce1f52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
35726d30-04e0-5571-b586-f41b10a206bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
6e4d6935-738c-5f04-a213-ded108982c80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
29226954-b786-5083-9805-748cd49f5595 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
71551134-75b3-5dba-9488-d0efb5202741 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
fd280bdc-58d1-5190-b831-2f9185ec537d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
f60f05a6-ba9a-5678-a819-79f17f37934d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
74acd2ae-39da-5f24-ade4-d920f5f22e3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
29a65fe8-1f19-5c84-ad96-33ce5cb8808a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
b2ab13bd-833f-5a7f-86d5-f2641fa1700a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
67414a7a-d4f1-5f0c-b38d-a6ca4307523a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
61770114-b4ae-598b-80c1-eed228635ae7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
0d367d09-0188-5e19-b276-799adfbe0a8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
6ce5bbbf-b9e7-540a-b43b-d347246db86d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Embedded items
84b653dd-177b-5d62-9b15-5c87b4242158 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
ef7fcb95-8aaa-560e-8290-fe69122f77a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
58868abd-ef20-5fc8-830c-0291a22439ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
1270bceb-2e19-5fe6-beb3-cc33c7734aaa |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Construction Joints
8ab1fb40-4dba-5891-b087-c5773bcb838a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Construction Joints | Correct location
1391416e-d095-502a-99e1-11ebfc5f4227 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
a4a46130-a2a8-5af7-b1c0-6bb0376edb2b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C4 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
dcfbbc8d-de71-49aa-9412-cabfca5daa0c |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection
d30f6955-5c0b-5abb-8851-de8bfd9ea937 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Preliminary
c3f9ccd7-5885-54e5-a452-cdb58b09f9d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
84a35af4-2e2b-5815-a791-5833ad489138 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork
25d4c7ec-2d33-5966-bb12-c7330c454960 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
e4ecbc1b-f5a6-50bd-9272-30b4fa6eefce |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Permit to load issued
e0bf0a95-1f6a-5299-8090-191170bcf2ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Dimensions correct
83c8fc4e-b51d-5e3e-ab5e-6e856b504df6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
ffde243e-4541-5265-ae8a-04e71f2a7f8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
e1369af3-6d3a-5a63-881d-12c4b15c2c04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
f3b8fc45-70c3-5288-b07c-35834d6f7e93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
6dbb8344-f133-5eff-93cd-4c59cf0b8e4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Joints sealed
e1412a0b-9ded-507b-ad1c-a4fea4200b42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Formwork | Pour level marks
1d27d93c-a709-50e4-9f3b-7ddf7c378f03 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement
04c0ce85-db83-5ff1-9a20-9a95f21daf19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
5f89fc73-f0e7-5822-8d1f-713f68550dfb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
572e9938-f486-59ec-bd88-c97fd9aac616 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
db4a2d4d-a2e0-5eef-afed-3b7f1d55bf79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
e4346c5a-c075-548d-a272-2f5cc59ddf3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
00eabea1-b40e-59dd-8375-2ae12009f534 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
2501cc49-d46c-5567-b9ca-1bff6e27dc00 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
4fb81742-2288-5366-9ad6-300b40616238 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
bb84942b-1075-5f96-8f99-14b015a6232b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
0c19880f-ef21-5107-88b5-825c9b8fa5d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
e75816f7-d8b4-5bbb-9d28-4efb56ec56e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
f076aaaf-2661-5526-a732-a551569bb85b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
67d0a41b-0465-5f50-aeac-c94a8de97ad2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
0429398e-172c-5885-9fd6-3e6483daf620 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Embedded items
104e261e-58bb-53f8-9296-5448cc1a92b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
0051240e-8446-517b-a148-b49d7e4eadde |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
2804b12e-ff98-5b02-aa17-cd7da1d9dbd9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
712905e4-ba74-5bc6-8e20-4714724a8dfb |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Construction Joints
84e686b1-92e3-5907-ba3c-d77414cdeed4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Construction Joints | Correct location
61e6594f-d631-5ea1-bf47-fa54b3b1e0e9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
16d51994-3a65-5269-9dc7-a2467bcce95a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C5 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
0a2e0cbe-fb0a-4f06-93d4-506fce8a7db7 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection
500ba1fb-49b2-5af6-bde4-b4bc6277a706 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Preliminary
3906c1f3-837c-593a-bb0e-7a704a370276 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
177a9598-17fa-5880-9216-307ac01cef8a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork
43d2699a-fc28-5046-b738-74e118458d57 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
02b58b28-c665-5b45-88b3-7870cfa0049a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Permit to load issued
95754f8d-8650-585b-8889-a3fd80787424 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Dimensions correct
c71e4d55-9dd2-5e93-a214-d54f958f86c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
d079300c-adbb-5fee-bed4-785b5eb9f9dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
755efe97-b2f6-51ab-a6f1-b3d5dea46142 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
4147251a-e57e-56c9-a089-9c59ba0dd5f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
c1fdcdb3-1c54-575a-a41c-2df300cef12c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Joints sealed
58581537-6aac-5b53-9942-e200d5e6f282 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Formwork | Pour level marks
194fbf8d-0353-5445-b094-d27ffe0802a4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement
4ca93deb-c2f9-51ac-a33a-2ae05d66a0f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
7f715be9-29ac-5815-9183-fcae3a9b21de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
c0751d7f-3d8f-544e-816e-e49d05b98ced |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
eb384693-b7a6-5613-a8ba-2e338050aad4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
9206f7a4-0827-5f76-af31-a12ce516c95e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
733d37ed-0dcd-58ed-a59c-afc60bae2be4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
c5506f06-1d97-5ec0-b0b9-341fc3a2fc37 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
db728552-ed53-5be2-98ba-279d6163a32e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
f748f549-e9ed-5fb6-8c1d-204322a6eba2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
ad2d5239-6fdc-56a0-b4ae-7879df95e2e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
b979506c-c801-5c3c-a307-c60af833eb17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
2ea1c459-00c7-53d3-a9c4-759186bd8df6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
47072741-dcc1-50d1-a47b-8ab1e4e5a284 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
abc78883-47b7-5259-9811-606fda514501 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Embedded items
2638bc5a-ee15-5dbf-b7bc-665420067659 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
d6602a73-1ad8-5ab9-b8d1-304c9b839534 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
c9c3b753-b8fe-5412-9bdc-3d729e8beb9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
b1b11291-5a56-5d1d-ab7f-1249eae499c0 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Construction Joints
f386eb88-ce35-5de1-857e-cc4b2b19c348 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Construction Joints | Correct location
a2dd42d3-0897-5c64-8a14-071a005d60ad |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
b5f419fb-07c8-5aa6-b35e-f3d22f8be83e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C6 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
03f8c4c7-bf49-45d6-82e1-d1658b08891b |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection
62d40b9b-c176-5115-9199-270d76c99ec8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Preliminary
b9b86227-adec-5d7b-a0a8-9ffd3f1671e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
8e2f81fa-f127-5c22-b4a5-8be72bac4a69 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork
193e70b8-b5f2-5c3f-a1a1-071152a0e8fd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
0337dbdb-f595-5215-85c5-8e51472a7b22 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Permit to load issued
767fac90-5330-5309-ae56-59aafdcaca1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Dimensions correct
35f62d1a-46fd-5510-824c-9ea2f6e091c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
8cfea078-e030-5497-89c1-e3627fb172db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
6bcf4b72-72da-56fc-bf34-2bc7e53942eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
ffeb04cd-789b-5801-b2d7-d5f6ff119895 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
4ce94142-eafe-553b-a178-6c77d289497c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Joints sealed
0739d48d-7483-533a-8cc9-551f56ea41db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Formwork | Pour level marks
10baf8a0-1ebc-5dc2-8d3e-c09fd0a793da |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement
6b933882-85c6-5787-a2c0-49d472c73edb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
c3f624aa-c63f-5ad7-8543-7e09097f7db8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
8300e981-d53b-5083-81d7-d563bb336edf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
4f5c031a-8019-59ae-bef3-883aab89450b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
fe7a0284-336b-530f-8ff5-de1a94c44ad1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
4f39f51b-76ec-557f-a5ae-bc3f80814ffa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
aeaccef3-0a07-5ccf-980b-5bd791ca613d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
c76dd909-6e17-5500-9d0c-8cac25c9416c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
ce5518f1-c74d-5a91-836f-a6d3ba9ce3d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
ffd4f75a-51cd-5325-88a7-793a0f0f4ec7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
0cc1543a-4a28-5551-a0ba-5fcbbcfbc9b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
592adf10-ac80-5075-bed0-fc05202d64cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
a938554b-3324-5aeb-85b2-f80434a0fabd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
6cdfcab4-ac6b-557d-b204-cb5b24866ea6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Embedded items
8263c3db-ff37-59cf-ac6f-844b0bb70b18 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
b0199ef5-2492-5dfa-808d-7911c2a58d25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
4e4165db-af73-5e36-9c8f-4b14e5c50378 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
641b7400-9969-5415-a0c1-7ec5c78c9d8e |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Construction Joints
6fc52eb8-b57e-5918-a422-ff391669cb53 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Construction Joints | Correct location
286bd79a-28a0-5841-bc45-88f3f074d636 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
fbd6f915-11fe-54d1-a9ce-e99c01e0878c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C7 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
8158c3c3-901c-4572-bafe-53166baaae3e |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection
b32a2ea6-cf54-54fa-8d8c-5494c7c6c764 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Preliminary
769cf334-0e1f-59a4-95c1-58963e796fde |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
56e9f718-8c9b-5e3d-9279-2e3706cf673c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork
9ba01d3c-cd59-5f38-b9c8-fbed328dd299 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
8c1b735e-6e1b-5409-b737-aa3ac0f46675 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Permit to load issued
0387e76f-04d8-5386-b844-8fc2f0f5c2cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Dimensions correct
ae2621b8-510b-51d9-99c8-96e9682f1322 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
8de6a9c3-b6cc-50f4-8cb6-2dd471cd5ca1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
4b150756-8a95-57be-ab6c-77ba1ba5b132 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
02397a8b-1693-50c6-857e-e773c374ebf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
149acff2-53d3-52cb-8a51-57d074cb9a5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Joints sealed
2a8218c9-f63a-5e29-accb-fd5e4da2c7cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Formwork | Pour level marks
94615f45-651d-5f4a-9a9d-42cb4924a897 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement
69ea1327-2cf9-5e6d-bf27-afc727275d74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
7bcaf8a3-4c93-5d75-a35e-609f42b229ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
f581b075-7a89-58f7-b467-110d285b8717 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
f4b4f6fd-f368-5b71-8cd8-55906fd621bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
5b1c96c9-533a-57c5-b220-70bd0af0d0b7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
1c8eb5ca-20aa-5955-81ce-b337d1d36bc3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
46cf9106-fb88-5674-a57a-eb01daa96ed5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
34da4181-b0b5-5d35-9603-9290807cbaf2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
78de06fc-7267-525e-a9de-2a14f6a4bb37 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
31597f36-603c-5fcf-a1a6-ea0c21c91cb0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
ab8eff29-c61d-508a-8408-cfcdb4f5775e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
0028af92-1da5-5c2e-9248-4f26efd4b67a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
0b4de719-1599-5e37-862f-688b7de62d12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
a116f2ab-a1bf-5f73-ac7c-1c6c757c9dad |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Embedded items
746826be-4492-5186-91a2-5cd93e05fd96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
90bddaba-908f-587f-9720-aa5587b88c67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
543c61c5-15c2-5903-a5b0-c872b82dc00d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
588d4c1b-06ab-5169-867f-394ea5e173df |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Construction Joints
13423e7c-14b8-5ab0-8727-865cf8bf575f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Construction Joints | Correct location
5468bfa3-eba0-566e-b48c-1435dd6352cf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
e242e568-c896-5a5f-95e7-bd52a23720a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C8 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
5b050e66-6b21-4d68-993d-913f2f2dbd0c |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection
3ad9af03-56e7-521e-8c15-609243bfc585 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Preliminary
8d354acd-46ef-5c75-b7c2-748e11ab9d94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
6bd0092b-b497-50b6-b99d-9ede0a8ffb75 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork
263a7805-a31e-5e3b-abe8-39566ece0028 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
a5320388-a652-5b60-9872-20158b4eedfa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Permit to load issued
a11a1f32-52d2-58a6-8ba3-673d2a93cdd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Dimensions correct
5b13ff3c-c559-553b-b849-fc5658621f81 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
9dba5351-23fc-5ee8-8806-0afe0255670b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
04652f1e-cb99-571a-9dcf-7ebe2b2f79ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
2b1f407f-8771-5764-b93a-8b6268af0b00 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
8690e915-e908-54f8-af03-437c088bfa1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Joints sealed
ef5ba27d-a67a-5cf6-b8a6-d09fe56ea3d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Formwork | Pour level marks
12f6e963-fe1a-5723-94ca-36d72bafe7e0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement
6caf5047-ea52-5647-ac58-c51e7fedef42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
d84a0fd6-0faa-5679-b952-857f305fb396 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
569b3818-578d-5229-8e99-0a9385930f19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
d7c7c56c-b8fb-5487-87e2-54d90086c8d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
ccb55969-d4a7-56a7-a170-248bea74182d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
be834f45-1257-5eb3-a9f0-a089e5b0a7a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
5b5cb711-0cbd-59b9-8f6e-8d23c9c345e1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
8cf9d351-2e3f-511e-a788-9c73bb3b3d73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
277b3c5b-f791-546b-a55f-501626287b56 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
12365f3e-9f4a-598a-a3bd-b0f1a331f283 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
33263e1b-c9fc-5f20-9c9d-90c3b57993a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
5dbf10c5-941f-5afa-9515-22b29d0cd1be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
9236704f-6cc6-5242-a0d4-077e05df7a97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
a97c670e-ff02-5b27-a923-25fe9e022887 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Embedded items
8b8ddaaa-756f-5a0e-9c0c-425910a120a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
7ba535f2-d0e5-5ebb-9d04-38e72b5f58bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
ecae51da-8c97-550d-93a9-64ca71fe7c80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
0a8b9335-178a-5bcd-9287-6e7525a11d72 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Construction Joints
9193e621-c0e9-59eb-9cdc-afc28e73babe |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Construction Joints | Correct location
5c767bf2-beca-5fa0-a7d1-cb4c3f37b8d5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
41129b8b-0e5c-5119-8ccb-ae7fdc81ad8e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C9 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
e6837415-e212-4190-9569-fe18d22f4729 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection
5ad51897-bbf3-509d-a386-4bcdaa7b6e19 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Preliminary
75bcf111-a5db-52e1-8e0c-fde7960b333d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Preliminary | Engineer notified of pour
aee1b6ba-96a9-5ce2-aeae-977568d1713a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork
615ea4c5-8c47-5b95-bf1e-80362e3ce424 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Installed as per formwork design
4263609e-61cc-5214-abed-998ade3e0256 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Permit to load issued
d8ecdc5a-9296-5a1f-b41c-4305c95a36b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Dimensions correct
7b0fa40e-76b6-5078-a7a5-30453f8f56d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Position and orientation correct
54b7aad0-8e96-5e8c-94a6-a3e9e7b64155 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Forms vertical, plumb and true
3f06dc08-ba7f-5a99-9dc6-8a4361e7dfe7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Forms coated with release agent
65fa708e-ed4d-5653-9901-ba571fa9a42e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Forms clean and clear of debris
d0410711-9bdc-5f77-879c-9dd7756c829a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Joints sealed
8961499d-f87a-547c-8616-bcdad542ab02 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Formwork | Pour level marks
11ff301f-bfc2-5644-8084-41dede86e11e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement
e5545553-785a-5e0c-b6bb-444f288db38b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Correct grade reinforcement
e4b70eb0-9641-544e-95e4-5a0ca4b7a2d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Correct bar size
cca3a2ad-2f5d-5a08-8bbb-306faf2ddc92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Correct number of bars
e0a9f3ec-0aa8-58d5-bc5c-3448be23f151 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Correct spacing
6b173e56-c82e-5082-ba7d-c2af4a9d72d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Starters bars included
e2075d7c-ce7d-509d-91e1-803c4ca29b45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
8bfd6c23-ba34-5d6f-b973-5ffb78a61a8c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
9cfec8af-3518-50c1-8e83-2bbc215b8ebd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
ff232e4f-7b36-5370-912b-c28eafdd50d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
befc631e-85d9-599b-9b83-61710289e5bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
de0094e5-95be-5d6f-bb8b-238219d2fcb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
f6a317e7-4367-538d-b015-249f07a335c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
23f13870-72ea-58ca-93f7-a5dbaf8b753d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
6a0db83b-7458-5b05-9fb0-ec04c8dad307 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Embedded items
c349f662-a702-5545-b8c4-20c7d5a0cdde |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
33582b0c-4aa3-53fb-a770-1bf457271f20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Embedded items | Correct position, level & alignment
bcc0e4ed-d807-5c29-9697-e0503def0c4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Embedded items | Securely fixed in place
e5d8efda-4f8f-59d5-9f03-695505957aca |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Construction Joints
31e72f51-5f11-55df-8b7b-e4186d38a2e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Construction Joints | Correct location
b3b11500-b064-5551-9349-fb3c3c635101 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Construction Joints | Adequately prepped
60dfabf1-0c15-5a8f-864b-4b27b89b4550 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Concrete pre-pour inspections | Span CD Beam Type C | Beam C10 Concrete Pre-pour Inspection | Construction Joints | Joint board installed
fd43e24f-2076-468c-8a08-34921fbaa693 |  | fail |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA
14a04541-2e6f-44fb-80da-876505caa51d |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1
b841f0ad-6757-549b-bd30-f68e373fc099 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests
cc4e0fd3-2a37-5493-b625-31c595fd3a85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
2e7a2d1e-4b77-5ffd-9c1c-bbda0e121b20 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
5afdfed6-d578-5aa7-a3b7-441c2b08414c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
2e63786a-3ed8-56d7-9377-ea601a0ea54b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
81f67537-a9a6-5c2f-ade0-8faf3ce3bf5a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
8e5d1b72-ba8b-5605-b76b-9c1d4b40b026 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
d88d08ae-1357-50b1-bc13-6ffef316b6bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
4a573086-f050-5753-8467-e731e15f4423 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
93aeb985-84f0-5d67-9047-16683aca0ecd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
c1046553-585a-56b2-a4ed-765c3ad851e5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
2356adfb-fa5b-5741-aecd-f386da416962 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
5dd55176-19f6-53b8-bd5b-7fd0d7a5eee4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
0e899bc8-82b4-5419-bba3-cd822134b092 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
2af68ced-0969-5c30-9ca6-17bd7100d847 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
31d29544-61e5-56da-ad00-0cf11c6bbe16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
e88d9670-6f6c-5ec6-ac66-c1de55cbd2ce |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
bd6f4c57-5b89-50f6-999c-7e8785bb4471 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
75055026-0424-52c7-8aaa-4022dbe3d745 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 1.0 Pre Construction Tests | HOLD POINT
d6b41b7f-c2cf-5e42-9e3e-b42177fd868c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing
c23df61d-22df-5644-bee4-e0eab9af70d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
814652f6-7439-5110-97ae-1eebf4454874 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
1a9fa6f9-b631-55f4-afbc-7e0ddd154074 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
eb1c7b1e-eb33-59f8-98c3-148208e092cc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | HOLD POINT
1dc164c5-eb1c-565f-ab3e-ecb1d2e8d61a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.4 - Concrete Placement
1e26ff0a-f512-5bad-9dbb-d32004d79e33 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | HOLD POINT
b94a4840-219b-5f5a-bb3c-a8f403ef2b9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
a9003658-00d4-5d6c-8636-faee4beafa46 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | HOLD POINT
4ece6c28-c4b9-5d74-b87d-e3cc15a6d664 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.6 - Heat Curing
2ad85c1e-feb6-5266-9506-d71651a13586 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | HOLD POINT
ee371496-a096-5013-9cb4-573014b4e591 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.7 - Concrete Curing
8234a2e8-81b9-55be-ba4b-64c8b0dcf56a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | HOLD POINT
67059bf8-8d62-5446-8b53-e81de7583685 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
c8fc68b1-4128-5621-9098-588c54a60abd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
4334d546-ab3a-5a84-9ba5-f2fb17d96122 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 2.0 In Process Testing | HOLD POINT
79917b5a-357f-5c04-a01c-7598d6fdf542 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 3.0 Stessing Related Operations
b773954f-9620-53e4-b7d8-0ab2b96e8e6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
4dcfb5d2-9bbe-508e-b09f-0cb11f4a024c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 3.0 Stessing Related Operations | 3.2 - Stressing
29e2e597-85aa-5bee-a6d0-6a8273a97960 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 3.0 Stessing Related Operations | HOLD POINT
45f277ed-0334-545f-a11a-ed540449e918 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
c66b4c9c-3461-54c3-a4a0-310e330b6946 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 3.0 Stessing Related Operations | HOLD POINT
3abec527-bccb-5abb-a6fc-3c96ecb78bd8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 4.0 Final Documentation
82161860-cc96-55a5-8eb5-853b2e7c37a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A1 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
2b075aa3-d7f4-4bfd-98ab-beb2eaf97021 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2
a7630e06-d28e-5ba7-afd4-1028eb93916b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests
fa668739-99e5-5e40-9d70-31a56675c2c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
802187e1-8eec-5b21-8ef6-1a516bfe941b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
103ecef7-1079-5c85-af91-e28882ecceb1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
09755435-63e1-5dd7-a676-d4a9eb09a479 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
7f47d6d3-8699-5691-acf2-448c28a9c0d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
61751c1a-1488-527e-8253-fda7b5e27c67 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
b30225ff-c597-5997-811b-f39295117d95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
97b5241f-733d-5acd-ba32-a00b5ea39bd1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
6d401fb1-6cdd-5ba1-9b0d-69daf46bd9f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
dc66cc4b-5e3a-57b0-9e39-4cdd592bb265 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
262b6c0c-2efe-56fc-a796-f8ee95f51a98 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
43372537-0a78-5a6a-a0dd-abb37e7a8a2d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
becc0140-9863-59d7-8bf0-7d8e1febaf07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
33acccc5-e5f4-51d8-926e-93727afb9adf |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
1265e755-dd67-5670-acd5-47de4a418cd0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
2074527a-903d-5c1f-9025-174e65511a8f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
50c772a3-8f1c-5239-907e-da9b3d455997 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
d1a0a375-d420-5554-93a9-b378b665e99e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 1.0 Pre Construction Tests | HOLD POINT
8e0f3259-634b-5288-9382-c43704229f32 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing
32a19bd3-3928-5a54-a128-0eeae4352409 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
e333185e-50f4-50e9-918e-eb36bbc956cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
e79a47be-62d7-5865-9fad-55dc6f43ff14 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
b442e681-a708-5031-94b1-d780f9f386d8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | HOLD POINT
d3a8be4b-f13b-577b-984a-5ab3c266de31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.4 - Concrete Placement
77e3d78c-b419-5880-bd95-551f790d3444 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | HOLD POINT
8f09075b-209f-5046-9421-c7aeff8be8ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
abd03c38-da5a-57d9-9e76-aff4538f5e26 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | HOLD POINT
21988239-a76b-5d0a-bc76-b446b0101f7c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.6 - Heat Curing
5064abd4-89de-542f-a20a-c3373f045283 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | HOLD POINT
23c0e6c6-a33b-5fe6-9123-1716c5a2410b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.7 - Concrete Curing
99a629bb-2d00-5202-a66f-7564dedf89e9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | HOLD POINT
43822ed2-cdfe-5e2d-b77a-8beee8eef07f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
49509345-cc17-517d-b4b9-f03d08911908 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
1a146026-8f5d-5068-ad2f-863bbfe47947 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 2.0 In Process Testing | HOLD POINT
487950a0-bfce-560e-b55b-e25f2358d857 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 3.0 Stessing Related Operations
9e699f32-3d5c-566a-ac0b-71820854b6b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
e9de6a32-958b-523e-99c5-5e06ab044e6b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 3.0 Stessing Related Operations | 3.2 - Stressing
4967cf43-a05c-5d6d-8c0e-1e23aed08e54 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 3.0 Stessing Related Operations | HOLD POINT
5b1bcfde-6f2a-551c-be6a-6c9e9706ee2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
b34ae99b-8778-5de7-9a86-9dee66c4a1b1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 3.0 Stessing Related Operations | HOLD POINT
bf8f85c4-d057-5aaf-bf51-5a1b8ec0c9fc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 4.0 Final Documentation
6d62116b-b8c2-5dd5-870c-c7b10c583801 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A2 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
05f8d329-e263-4dcb-9f72-f5de608ad7c9 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3
ea3a0c14-c881-55d6-83f0-7484f642a314 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests
41ac7a06-28ff-5f0f-ac3f-1975dee46567 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
309d88de-85d0-59bc-b4ba-8f7298cdf484 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
032f68e0-04c3-50c2-a978-0f47e7c3b8fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
9fa06975-d96e-541b-b047-0b90d7fb0305 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
611d2b6c-6bae-541c-8ecc-0f308e1052d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
c897e4e8-e2a3-57dc-b8db-dba53b8a7e33 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
32cc58cb-66d6-50dd-867a-b1dfbdb2439d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
0b3813d9-3366-5ae0-92f9-3093743d3264 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
eddfd021-7e93-58e4-b9ff-7bf884841969 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
0a39d926-afde-5593-ba0b-50080aafdba0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
377a7d6c-4ce2-5376-ba73-6b99a956471e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
fe4dbdb7-a698-50b1-9bbc-186bb47a27bc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
de659555-7a09-512e-9aad-39c5762ae946 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
3e9bbbdf-f249-5c6d-b892-129fb1663124 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
6cb34e5b-3bd5-5dc0-8ef8-c7709be698a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
33cf3cf5-2e11-5ba3-b31d-b2ada01d76f1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
bb5378d4-9fe4-5a62-a1f1-ffbc45952955 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
e4dad218-ef6a-5342-9875-d1ab80b2a0f2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 1.0 Pre Construction Tests | HOLD POINT
b4616366-1c10-504e-bf79-82af8c53beb4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing
63a4dbe9-ab5c-56e9-8b61-a071f041b364 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
3fdff75f-2cac-5e2f-8e41-94bfd4cae5d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
30ceb05b-70d3-5c0e-a679-bc0b1ded2d73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
35df1d89-a624-5d06-9b6a-ebbf8e8f5f4d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | HOLD POINT
e6883b8c-3fef-56ff-abbe-fdd6bfbd9190 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.4 - Concrete Placement
0326d36e-81fe-5865-8ed6-6826074c8079 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | HOLD POINT
de1dd396-2a64-524a-8bf8-747065a3c86b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
e983a968-065e-5071-8983-0c455dadef0f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | HOLD POINT
08d43a24-4a46-5ece-9ace-9ae83f915ef3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.6 - Heat Curing
dd2a63c8-5731-5456-9859-fee5c9148061 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | HOLD POINT
153c3ca8-83b0-5f7e-8699-04e9876084b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.7 - Concrete Curing
0b2d4cc6-4a8a-522b-b9a7-c3d50e625a38 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | HOLD POINT
d0b2293d-1967-51b3-80bc-95a74db2d24f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
0f490248-bedb-58df-b48f-1932d78ed1f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
7f3ba4da-9570-5c31-8f5e-bb68edfc36ab |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 2.0 In Process Testing | HOLD POINT
d1db1e92-5d35-5132-ba12-6f96fc1e4e8e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 3.0 Stessing Related Operations
8fb8280e-13ee-5ac3-9c69-dda75d1f1f54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
f3d2f870-f1d8-59a3-a6f5-438c868b6cae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 3.0 Stessing Related Operations | 3.2 - Stressing
eeaec586-b5a0-525b-866e-c83e1d96e925 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 3.0 Stessing Related Operations | HOLD POINT
4e9f4661-9d50-59de-8807-c8d9743957b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
c2cd8048-1f5c-5b1b-b507-cc2f814137f4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 3.0 Stessing Related Operations | HOLD POINT
27c2ea03-f512-535e-a179-d6da8bb9b5a0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 4.0 Final Documentation
5c28658c-7089-599e-abbe-7ed7d1c4e95c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A3 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
b5672532-2a70-4ba3-aa9a-e2c5d53e284c |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4
e267774b-9266-5ede-af69-e686bd1ae1be |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests
ed20f18b-a78b-53ac-9c3c-e25e27f5d795 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
f9f63729-5191-5924-85b0-5941293acc07 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
a07bb58a-a552-5b32-89b6-9b335e13b873 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
0ecccd2e-abbf-5708-be8f-469f62b77c07 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
5fd8af43-cc92-5dbb-bfff-fcb13630b8c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
61f941ac-a0f9-5359-a6d1-16760facf3f9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
1baaf0ce-fba3-57b7-9885-c28872fd7206 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
b01e9784-347b-53f3-8c38-0a6e0adb51e4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
bbb67bba-f723-59fa-a0fe-b1023795b9d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
4259d7c5-86f5-59fe-a4d9-f7459844986f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
cbf3104d-5a73-52dd-a639-4fb2750dcb70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
538f62b8-16d1-52d4-a7f0-cee6028964ae |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
c5751d42-62fe-5daa-b49f-ad48d13ce29e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
bdd3d733-5070-5ee4-8f18-6671c5c59756 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
69a51ded-3611-59bb-883c-ed253f1ee858 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
b2301e23-b9bb-5b67-81d9-71bba57f1132 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
004bba0e-edb2-5a0a-b6bb-add6cccd9d20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
9a7941cd-c77f-5dd6-80b2-890e769d0ca5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 1.0 Pre Construction Tests | HOLD POINT
a35ee9ae-f911-5e1f-8cea-38fd877134d3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing
d291c64e-f631-52c5-a964-e3603a371520 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
32d91980-1e1e-5145-ac60-6fbbc6f3efc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
b38a118b-44ab-5b5e-9ac3-c98abb5eecc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
6962b2b1-7ce4-5464-96be-6c3e2de97c08 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | HOLD POINT
07e4dbca-ddcb-593d-bdba-cec04dea98af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.4 - Concrete Placement
a88a062e-8794-5152-ae1c-42f0e672ce87 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | HOLD POINT
3c1364e0-9edf-5da3-ac00-524be149fc2b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
7302fad8-600b-5b57-954c-600aab1d263f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | HOLD POINT
82725b9e-aab4-55b8-bc56-4a3e252ef7a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.6 - Heat Curing
0df1fe48-f987-567c-9329-4ea74d8c155a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | HOLD POINT
c9da5f38-894b-577a-ab07-23e0f1fea15b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.7 - Concrete Curing
41f794b9-a390-586b-8d76-b1535c6d61f0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | HOLD POINT
8e63431f-cd0d-55ee-89d4-afcb6259f264 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
acf6e0e2-c913-567a-8c49-704962efcf5a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
a4743d60-d9f8-55e6-9107-f137733635b7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 2.0 In Process Testing | HOLD POINT
e224fbed-1ee0-5284-a43a-4de17c9d7114 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 3.0 Stessing Related Operations
9837f6b6-a7bd-5c41-970a-1d9d2b2f3309 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
c222e282-6e7a-5b7c-a507-7b8a4165fc96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 3.0 Stessing Related Operations | 3.2 - Stressing
bf906c97-9b84-50fe-8469-1eb47c123a8a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 3.0 Stessing Related Operations | HOLD POINT
d88aee13-002a-56da-a444-6ec887f045bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
62e54aec-7fee-552c-9edb-68e803f88172 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 3.0 Stessing Related Operations | HOLD POINT
9b000779-8c4e-534c-b94d-137492a01f29 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 4.0 Final Documentation
b1eee22b-a524-50d8-a2d0-68531219682b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A4 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
1d872a2d-036e-4921-944c-cc9d1bc590ef |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5
a6dfe06a-e0b4-5403-aba0-6505e716575c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests
b252d59e-37aa-5362-af9b-f5419048325b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
cfccb428-06fb-56cf-8198-d573838bc142 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
b7a56a08-aa0e-5aa4-bbd6-c6297d274577 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
dc467d0d-420b-592c-9d72-78aaf291bc8e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
bbb3310d-88a1-52c9-b93c-f1a3f54babbd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
6712b029-676d-5e12-b417-7ca5e63f2051 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
8f69da21-7409-5bcd-9a6a-9c24254d289b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
e42e7b52-0644-510f-b93f-da7993a52874 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
90a58074-a9db-54e8-be4a-c689660d119b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
220f2772-b614-5b1d-a895-57e3bfd8b6b5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
e0902bab-f762-5030-9ab0-cc50e0040d66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
b746dd07-9409-5d6e-b808-49302f9365cd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
b2a3c25a-3915-59b2-9e9e-ea65d179d0c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
f87b5ae9-7f4c-589e-bfd7-d6a1a268f930 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
e89b4a26-0081-5e16-b72d-a6aa9a462765 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
7539fd5c-9079-5a46-8e6e-a4f9005d5d49 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
98923f8b-4ff1-5ee1-9adf-975ccab256d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
ca4fb5b4-06c2-5d2b-8344-804ec24639d0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 1.0 Pre Construction Tests | HOLD POINT
1da50e10-4dc7-5369-be18-67c76498faeb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing
472c9569-169c-51e2-b6a2-9d7230bdf27e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
2d4ec13e-528c-5ea3-8daf-1ac53047b812 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
8d212cd3-7b86-5181-b47a-b8c9308b8267 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
60ee9634-479f-59b8-b142-278552d6e1d8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | HOLD POINT
1a59ad3a-63c5-5f5c-ad29-604ccd2062e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.4 - Concrete Placement
44370b92-fc83-5808-887c-e60ca8b770cb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | HOLD POINT
8107e801-2403-58cd-9f38-323498428fff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
5e460bb5-be75-5946-9eca-793736c5e95d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | HOLD POINT
d158ee85-32f3-5755-8a2d-6204fddd6a0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.6 - Heat Curing
6193cb49-bb3c-5ac8-bfcc-8127d60321f1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | HOLD POINT
2886a6ea-80a3-5689-b313-349df1939ba5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.7 - Concrete Curing
4a9ddf0a-153f-57ba-a839-309189a3fc6c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | HOLD POINT
f214f9b5-5114-5dd5-8b31-f09dca0459eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
b2d54978-8f87-5e62-847d-084ae040bb89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
45c3e6bc-b51f-5ed5-bf4a-7e26e6edc5a9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 2.0 In Process Testing | HOLD POINT
4a132021-d607-596b-b4c2-899720792334 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 3.0 Stessing Related Operations
4590864c-4630-5470-a623-6c4af66e831d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
ef8089ef-63b7-571c-b70b-0c6cec4f4611 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 3.0 Stessing Related Operations | 3.2 - Stressing
332f3eab-2199-5266-956d-1a75fe099261 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 3.0 Stessing Related Operations | HOLD POINT
959bd492-69e2-5a8b-a7c5-fdf3be8ddb6b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
f129991b-9450-5c9b-a4e5-110a9a4a926a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 3.0 Stessing Related Operations | HOLD POINT
bc55c012-7d39-5d52-b6ba-ea64b67ec167 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 4.0 Final Documentation
2da7801a-b99d-5d26-bc42-c641df406800 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A5 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
6d94093b-f0c8-4a49-ad2d-03ae05f08bb9 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6
05f00ae6-fb41-5489-9b5f-e145decca710 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests
6f469825-98d5-54e3-adf5-4278d154e1e7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
0f01a2df-46f9-512f-86a2-4d7c7deb7bd7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
0d5d8b7b-cf7e-54c9-9bab-b701ed59caaf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
7b8c8ba4-50d5-53c5-ac20-0793ba470942 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
fc502126-b773-5551-aa4b-04c0c08a336e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
084acf20-4549-52b1-a36b-ce17b377ed5e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
a2aff74b-5c88-5dba-8fba-d2db9c2865f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
9c470390-56e5-5eab-ba30-326569ed56ac |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
f4205e05-b677-51c2-a091-0045de10e4f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
0b22fa91-b37b-513f-b1a7-3939beae55fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
5c6bf61b-a918-588d-a2d9-65af633fa659 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
10ea2629-ede8-5395-aea4-437943ca39a6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
62699cc2-932c-56dd-9116-f40eb3384f60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
2b86958c-f382-5e28-ad4a-0f64b4efff84 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
24ac9df9-d243-5bd3-aac4-80ee94c36857 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
d02e78fc-b5a6-5a16-b006-58d08921315c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
94f194c9-ab9d-5225-8c34-4d6e34a8aa84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
0b2bef9f-65ca-5c8e-b9fe-ca3e81e258d2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 1.0 Pre Construction Tests | HOLD POINT
c5a0cb34-f441-5368-8e04-1453e4c6c23b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing
56cbf516-2728-5d1d-bf85-d15a6b4c3bf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
db689a63-86f0-5867-9184-11343af538e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
7d7f81b1-6180-51f5-8170-36709525e3a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
7368ed77-76b7-5b31-b521-e71f198ea5ab |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | HOLD POINT
dc431753-a91c-5aac-8182-8fcd817b52ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.4 - Concrete Placement
24e11843-26fb-5192-9f4f-3eed9f60eb4a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | HOLD POINT
02272c4d-ce96-514d-830c-27d2d8118c37 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
564dd989-61a8-5003-9183-88145a855b29 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | HOLD POINT
ae516165-7568-5397-9fe6-b591005588d3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.6 - Heat Curing
ce034310-4996-565f-9a02-ceabffdabc0e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | HOLD POINT
e785b18c-851f-556a-bb10-d9e4fd683bef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.7 - Concrete Curing
31054aeb-5633-501a-a683-f6aa1ca03121 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | HOLD POINT
8a6579c4-959e-58e0-aeb9-ffcbcc5eed2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
b7afe614-aa0b-54a7-bdb3-a6d55af466f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
732dee56-6f55-538f-8dbb-179f1703a4d1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 2.0 In Process Testing | HOLD POINT
a4e9fff1-3545-520b-8ef9-b1463fda4faa |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 3.0 Stessing Related Operations
19515b08-cf99-5b0b-8623-7b8f78863f43 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
ca96367a-7e5c-5881-a336-1d47a83b911c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 3.0 Stessing Related Operations | 3.2 - Stressing
a8411433-0574-5cda-bc28-6a52404cb15f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 3.0 Stessing Related Operations | HOLD POINT
ddd7df47-3e7f-50ad-8d1d-7fb781cb7d0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
dd648ae7-8a31-59c8-96db-3b5e4d308235 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 3.0 Stessing Related Operations | HOLD POINT
06194e01-45ed-56fd-a28b-6cdb064708e9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 4.0 Final Documentation
825ee89e-c434-5bc3-8415-6b8a5e2c5b85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A6 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
f154ab04-8b37-4d8c-bc2a-61d7b9a17409 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7
c3a17ab7-882a-5fda-9d7c-0763b744f7d8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests
a9073961-5014-5ee2-a8dc-f433e4c4f67a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
70442e37-ddb9-53e9-945a-fb357bda19b4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
cca02db1-0879-5bcc-9fb4-d2276d7df913 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
e09b6d76-c223-5fc3-a335-75b47e83fbcc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
3dc4f523-d8ad-5777-913a-5957e9b0635b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
ffdfd02d-c931-5a8b-89e1-793cac727068 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
cd529b2c-3872-52a4-81d5-f9d603553236 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
0be4adfe-ffff-5cf7-aeaa-c003b4a39342 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
759b1c5b-e89a-577e-ac4e-2c7912b58a8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
ea16c3d8-713a-5bbc-8019-4798e66b3f2d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
b6a0f525-db61-5eb9-9675-f6c73b2e9b1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
9e347b6e-3b83-58c3-94c0-6d83ff618fbf |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
ccce501b-aa3b-58fc-83aa-f9322dc22bc9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
c38a105a-7d75-5fb4-89b7-cf2c3fbd45e8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
e8cdd891-3534-5fa7-8717-105684cc2bb6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
7f7e739d-3508-51b1-bb20-ecdade7cfcd0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
eac5d76c-5aef-5d03-8ce8-301848bc2e0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
e5b23079-01ec-5d33-a9f4-ba5e5317e509 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 1.0 Pre Construction Tests | HOLD POINT
a507eb5d-7fa7-51aa-8a87-1bfc06f8e470 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing
646fa2a9-7b83-598e-aa3d-857d4122b967 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
90661a99-b977-5355-9b12-1dc31ccfb864 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
292be9b9-f45f-5f74-ab0e-0bc798e87e3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
4abf5e41-1c2f-5ff2-ab94-890a5182cbbb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | HOLD POINT
67369acb-f61f-5450-b7e5-8204c857708e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.4 - Concrete Placement
697f9ef0-10fc-5d14-a1e0-87642f776b85 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | HOLD POINT
88b77d49-8bbb-5ad3-a3e3-c5923b47fbf6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
6fe539bf-3423-5872-993d-7a092c96278a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | HOLD POINT
6ce97e18-b432-53d5-8e8d-1b44ecae5f69 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.6 - Heat Curing
319b7758-67fa-5ba7-afd4-75785f0268f6 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | HOLD POINT
31a79179-7b42-5e91-bcda-53b71c873ecf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.7 - Concrete Curing
64f466c9-c9eb-57ec-bbb4-005e254b257b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | HOLD POINT
bd4c4573-ec67-5d7e-843b-811fc326b7bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
2dc3f697-45fd-55ec-a48d-7982c57e6f56 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
f293f50a-0c99-5a38-9e4a-804f1c856029 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 2.0 In Process Testing | HOLD POINT
7b97a784-f761-592f-9ef8-3e894d12683d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 3.0 Stessing Related Operations
e3cca1c8-f80c-5149-95f8-0d5cc4322f79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
15416f8d-5bd1-5e50-be62-3753d02d2625 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 3.0 Stessing Related Operations | 3.2 - Stressing
4fe96383-628d-5681-a1d6-fb9625f1a1be |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 3.0 Stessing Related Operations | HOLD POINT
e4d92794-ed97-54cb-beaa-e4eaed629706 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
a0814ed7-3757-50c8-a156-4a5352382575 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 3.0 Stessing Related Operations | HOLD POINT
54a55044-4ef8-5882-a978-48adc20dd184 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 4.0 Final Documentation
32377025-a5eb-5060-bf60-ff2b94fef71d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A7 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
7a7acd32-98d9-4995-a19b-924ca67a5342 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8
d7784b2f-2291-5238-a35e-442b320516cd |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests
c42b4533-94d0-5b61-a265-42ca75c58f3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
3995b2ab-5d53-5aab-a565-5776b0037cf3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
ab3b2097-dc17-5507-a32b-240aeb4ffa79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
0291742b-647d-51d5-a266-976196f41583 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
9225839e-e6e2-5bf4-9aa1-85c921fd3981 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
03b2d332-ef7b-53e7-8cf0-c1771148aa49 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
b04ed099-c4b9-5dc0-bc0c-ffca2536b934 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
6e59eb29-3df6-52b4-8e19-e29811ed7ab2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
9bdd707a-9c51-5f7a-8c35-d72c1b7d0730 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
d992cfca-a2b9-536f-8ea3-aaec3a49f00f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
72e21961-4ab9-5e4b-bd75-6c681f510c58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
45580980-49d8-5d82-9811-33fcc54f8ee2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
638153a3-a6a5-5eca-a537-239e5ebc2187 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
952f6f40-5951-5aa6-af93-8358999f8fc8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
5eef7a24-b5e8-5222-9173-b5fc93712855 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
ff46035e-3647-56d1-be11-dc5c64564af0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
6b021eb6-1b74-5d7e-9b80-b29a96d14b81 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
89ac11c8-6a8a-5b24-98bc-93aace2b19dc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 1.0 Pre Construction Tests | HOLD POINT
d5fcd982-67e8-5c49-8740-b218664600bf |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing
7ac3dab2-cd82-5867-acea-56ccfc8f27ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
be4e3deb-d90f-506d-af93-b8f31c8d88d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
19227626-8480-5343-b137-07caf37ebaf6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
7841fe74-a18b-5f80-8bae-b0086aebb5f6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | HOLD POINT
3da62e5c-96f0-5661-b92b-5427a4d832cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.4 - Concrete Placement
7c6c1999-bdc6-5c4d-84e9-d0c1404703dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | HOLD POINT
3fd9e2e2-2a76-5e87-8260-fd70b0f7463d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
9a244491-3a0e-5166-9221-da75729483f7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | HOLD POINT
ab440acf-3bb0-58fa-9f4e-81bacd9b43e5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.6 - Heat Curing
fd4f24bd-23a9-5507-aa31-8d4fa4bb2bd4 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | HOLD POINT
df04a0a9-ed2e-51e6-8725-d795b49cbd7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.7 - Concrete Curing
d901694d-b7cb-5c37-8c8d-64c18ae2de74 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | HOLD POINT
f85b5acc-908a-5b9a-ae52-19ff6d5d98a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
36603b46-1db9-5b67-8358-fe52d2f8f199 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
de7f6aa3-93b3-53c3-8038-e4141baf88d8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 2.0 In Process Testing | HOLD POINT
f2a78d3f-f42b-5619-9761-b35d3718e5d7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 3.0 Stessing Related Operations
8baa40c6-7ec1-5973-a42a-0aa4dc940225 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
57d926c1-da2a-5fe2-8caf-e09876d66a58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 3.0 Stessing Related Operations | 3.2 - Stressing
019ec73a-f135-512b-b4ea-258b58deee63 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 3.0 Stessing Related Operations | HOLD POINT
7ba84cfb-ff36-57b2-9c33-173bbab15972 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
f2c27cde-a7e3-55e4-b016-47d1c84053a8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 3.0 Stessing Related Operations | HOLD POINT
6692a811-a019-5173-87bf-24528068f4ee |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 4.0 Final Documentation
849b8aa0-4e43-560a-8194-f923aa7e73ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A8 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
e734a401-b61c-4bb8-b052-ddc599001cee |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9
f8745121-0d1a-5d2c-86cb-5ca0d851afbb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests
7a2e7735-4cbc-5b03-bf2d-d3bfc5e92435 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
3192c8da-edce-511c-b4b3-030738fc388b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
204f8a2e-34e8-51a6-9312-242cfd9f1ebd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
673c0f83-5c76-54e3-a7a2-fa1b4c225edb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
ba660089-6c77-5e24-82b5-7af777909484 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
80702b80-5766-5481-8e18-3be7a28e8fe9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
c341b6f3-aba2-5052-a9cd-e7386693e23c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
1cb4d7c0-1f84-5294-9304-e1114419cc77 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
9bca272e-9871-5b60-8701-a3ee4f9a45a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
63eb6173-199a-5b45-a89f-dffdecb1bde2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
3f1539b6-39ad-5a85-83a1-ddaa85c8b29c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
afe71afc-3308-5b33-b3cf-ac47ceca81a6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
f19a17f8-f19c-562d-9c47-3ab7f814f365 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
84d717d7-91f2-5974-a627-03d27d5c78dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
f866e28f-603d-5c47-880a-118b6137665f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
e3ffbddd-090d-51fd-b394-e1acc3f2cc7d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
6d87fded-08f5-55e5-8798-8506351fd747 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
90913e22-925e-595a-a091-c48adf7a794a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 1.0 Pre Construction Tests | HOLD POINT
7b48e4cf-3ebd-5a58-a8c5-1eb5250692dd |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing
973944f9-7670-58d3-a0af-8d9673aa827c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
82808af7-3d9f-554d-a4d7-0a3c5067a205 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
2047afdd-d376-54aa-8ebe-3a6baa1c2913 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
c798b1ce-7d5a-5539-a04c-d5a7f433f542 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | HOLD POINT
a9f45e78-5fd8-5200-be45-3b139308fd13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.4 - Concrete Placement
0f14d7db-aeaa-5e4c-8487-a3e649559d33 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | HOLD POINT
27dbab34-5141-5f4d-b279-b05bf534fd59 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
506c59f2-83f1-5357-acb1-f643ef73a5df |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | HOLD POINT
13c787b9-fb53-51a3-9c20-777084295597 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.6 - Heat Curing
47ce1270-25e3-5f1f-834c-29d47cc7068a |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | HOLD POINT
2ac7f4dd-fd6e-5fa6-bf17-1b598d05011e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.7 - Concrete Curing
5747d4c5-18bc-5d63-93d9-7408f1a79c84 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | HOLD POINT
97ec63d0-127a-5b03-a199-160073f02092 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
3f4ec98b-6d57-532d-8b1f-3a8c9bcaa94a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
3e7556f1-0214-50c3-9c4e-1a558ff04743 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 2.0 In Process Testing | HOLD POINT
611dce30-8188-5fa7-bbcc-5b71348e20d5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 3.0 Stessing Related Operations
bffe6f1d-e03f-57fd-a7d0-4cb4d34deaae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
a3e88e6c-3370-56f7-bd05-72aeaf31aaa2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 3.0 Stessing Related Operations | 3.2 - Stressing
b5199921-07fd-5fc3-9a83-e921031acfcd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 3.0 Stessing Related Operations | HOLD POINT
9d941529-e1ca-566e-8161-4f5f200633a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
b13fb53e-4d14-513e-991e-44b159302999 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 3.0 Stessing Related Operations | HOLD POINT
527551ae-cc4a-56fd-b1ba-2500226a0817 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 4.0 Final Documentation
8804e8e0-1516-5b51-ba15-ebf31a276690 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A9 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
cfe6faca-c415-4c71-8092-715ffc3adc51 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10
29a3b3af-bd1f-5a9f-92a0-b089a150be55 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests
f04cab78-18f8-540f-9677-bc9693ec92ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
d2ae8cb4-3f22-5988-b978-fb71de9dab95 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
4edd0071-fb49-5f53-b478-9ad2f92a7c5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
277e319f-ca8a-57e4-82a0-37d23ec785c1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
4d3b0989-e726-51d1-b434-9b01d96a4c2f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
bb7580de-9dd1-5480-8f89-590301013ac7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
3c396f99-473c-5f76-b6d0-94d6234c160d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
46554a48-569d-548c-9864-4b9d1a5df3aa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
a9599195-febf-5486-a821-9cc2ee5826a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
b0f80f57-f6a1-51ce-8c5c-c8b1a0f79d14 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
dfefa6b8-9adc-57dc-aaa0-eb86039a8b54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
fa6518d4-1846-53da-a205-b441232188b2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
d958cbcb-83f7-5199-a07b-39ea6c730a51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
09d4a377-0b62-586f-8910-af390328c690 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
a504056e-10d2-5aef-916a-c4e5659b327a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
9aa79a0b-3c7e-5ec4-b1b7-5b7fb701d7a2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
e8e4caf2-3a80-5cf6-b452-e1fbaaf62c7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
1e2e8dee-4d92-565b-9e5c-a974e184c5a7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 1.0 Pre Construction Tests | HOLD POINT
5a9aaf0e-b0f7-5454-ad27-3b521c561464 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing
17ba7a6b-78ab-5900-bd7b-25bd30e1d679 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
35dd96e6-361b-5e34-a295-3767ac460193 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
1b797b46-dd5f-52e9-ac72-00a9ae23d128 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
6d75134e-cf8c-570e-a84f-b3bc40f6bbac |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | HOLD POINT
24ba7859-fab5-5f33-be7e-f0c9fefa77a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.4 - Concrete Placement
dbd433b8-d0ce-5c10-8073-b2e3d6cf4760 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | HOLD POINT
d196e01e-e112-551e-bc3e-530d7783a2d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
10ab27c2-aec8-57f1-ab7d-4baa30b34c40 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | HOLD POINT
cc8f496c-a9b0-5e59-8557-9be31c8e6395 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.6 - Heat Curing
77e63575-2f89-5bf2-b406-6210f1159fde |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | HOLD POINT
334cd596-28d3-5483-881f-9e577ae7cf7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.7 - Concrete Curing
09161edb-6cbf-59ba-b538-7e504e945174 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | HOLD POINT
6f214a69-d75d-5b40-a487-6c55f1d26cd7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
a8ac9096-0f02-502f-b1aa-67c6a94038cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
f7301256-eb34-5f53-876a-52dd3cf746ba |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 2.0 In Process Testing | HOLD POINT
229452d9-d63c-5852-a63e-66171e22ca9b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 3.0 Stessing Related Operations
cad94248-adf4-520b-9820-c7b751f9f4c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
ad4ebaea-1c76-568b-b4db-42406de99723 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 3.0 Stessing Related Operations | 3.2 - Stressing
f906e136-436a-54c3-afc1-d4e276811113 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 3.0 Stessing Related Operations | HOLD POINT
3786280d-ef7d-58c9-b3fe-d5ad49a3e5a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
22b78973-5881-5227-9038-fd27e7639d7d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 3.0 Stessing Related Operations | HOLD POINT
a2c6fa15-54ac-59fc-9fa6-c47f0771448c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 4.0 Final Documentation
70741c56-aa81-5314-9506-6dee60178439 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam A10 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
a3b01dd4-c14d-4ddb-a2eb-478cdaeac286 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1
ad7fcf2e-ff96-5938-b105-1d4f4a51ff50 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests
16b4294c-6593-568f-bf00-bc1a7b51479a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
d1b90fa4-15b8-5c1c-ab0b-7e4efeebf2c0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
2ad10d71-a007-5983-b62d-c6b4155a108e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
f2807d74-aea1-5521-8bfb-efae1ab076a8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
499751e3-8e30-5fc6-a968-62004a22bdfa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
8aabea6f-03e9-5268-94fd-aec8156e6e1b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
45ca9fe2-3316-5090-af2d-6081cd3f07e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
37d1e71e-e1ce-55eb-b4d9-753b4a0bcd85 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
1fef2571-a1b0-5c03-a0c7-9585c4487151 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
1386b417-aa58-5638-b91c-0fbe3ed94c47 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
71a811fc-729a-5ca7-8f0f-5f94aafb35e7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
8359b8bf-d11d-5051-8be4-0c819bf29701 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
50a50eb5-f51d-5eda-8fc7-ed60050777e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
493807dc-d0ba-5e86-a45d-8b2ed7ef156b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
b9c33d9b-93c7-5866-b8d5-b31eb205e8b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
5fce2e97-f73f-52c5-a9fd-8ef124c5342b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
dd91d50a-2a56-503b-8538-c680563fe16c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
e82e0d8a-209c-53c8-8d05-f58a00c47e82 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 1.0 Pre Construction Tests | HOLD POINT
592a5531-e5ba-57c9-9611-fbec75f55c62 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing
ae6b9af5-c790-5a73-bfa9-f15d325c8e44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
bf14af7b-b1c2-54c4-8d97-75980efd2f8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
a76ca948-7e1f-5a99-9ff9-990b5ad19eda |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
ed8923c9-681e-5c02-8091-92ac28a5953f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | HOLD POINT
642430cd-e261-52e2-af63-121c141293ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.4 - Concrete Placement
66e8212d-a34e-544e-a68f-a892f28deafb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | HOLD POINT
0a5a99a9-b979-5cf1-a14a-dca891d0cece |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
0f03794f-c101-5e33-8054-53e41366b8ca |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | HOLD POINT
4a2d6881-3fc2-5a77-bb4e-77cc87d71a9f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.6 - Heat Curing
36dd4241-8f8b-5c30-b975-8509c328af09 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | HOLD POINT
521df74d-b09e-58f7-9690-0d0f9c9d1912 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.7 - Concrete Curing
f891ef2c-8155-5361-85b9-255e223a237d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | HOLD POINT
8ee4263c-efea-5646-b734-cf316457c821 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
c2888c86-ba88-537c-888f-79c7db066862 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
1ae7a213-6032-5435-b513-e0d8f6478cbb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 2.0 In Process Testing | HOLD POINT
db0110d8-6efd-560c-8429-230f7e2e35e2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 3.0 Stessing Related Operations
e8cef559-0952-56eb-832b-7ee2c9a11ffb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
14a68754-0f84-5f65-84ff-52675bcab0dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 3.0 Stessing Related Operations | 3.2 - Stressing
255beea7-53f6-5f62-8fb0-0b3b3314543c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 3.0 Stessing Related Operations | HOLD POINT
ead4f7ba-0fe8-571b-ac32-c299adbccbf0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
2653df48-e1c4-5ad6-b45b-07e5236ab272 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 3.0 Stessing Related Operations | HOLD POINT
403a9964-4ad4-59f9-8440-7c31b770499a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 4.0 Final Documentation
f9f47cf2-39cf-5401-989b-7fd279a59b6a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B1 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
6657244e-2caf-42ed-8360-4251810684bc |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2
eb631ccd-36be-57ac-8532-027150c927b3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests
363de039-b9a0-5bb2-a35a-aef3268c8f2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
2912f29e-177a-59ec-b3f7-268c95cb3be5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
6ab7a82d-604a-5f7f-b275-43bfecc2fc58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
ea503bcd-4cf3-5381-ac3d-1edc8c5cf696 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
81ceba06-2d95-5996-a38e-f5db3c2b235d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
38fee73c-080a-505c-ac26-91c181edc860 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
92af49a9-e70c-54b4-8534-42dfa968b777 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
8065af78-b5a9-50ad-ba84-f769ae2d7acd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
4d410f8e-21b0-510c-9127-35a3dc99cf96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
9fdcb37b-404b-5d0a-9ac3-74722fcf9cca |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
96d77485-e561-5468-b4d3-fa1fe097b48d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
af661da0-ac65-5648-8b77-55a4f0f5dcfc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
9fab13f7-b20b-5884-9bdd-74fe0fb3c0a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
35c59581-7064-575b-9768-cc728aa10f4c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
e1773143-5504-542b-9828-f76c0d54e119 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
57cb1fbb-281d-5998-8bc8-85cf7223d737 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
6926c8ca-a820-52ba-a72b-1e8a05a715c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
3e1d30a3-4efb-5650-8353-690dc026ade4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 1.0 Pre Construction Tests | HOLD POINT
a5e6ba19-2cfe-53d1-8331-0aa5e6e995ed |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing
21ee545e-e24c-5bcd-a3eb-fa02dced793a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
198f1f7b-8cd2-5cf1-a484-66d07b3c8a2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
78a3d20d-abb1-5058-9bcd-2128eb357338 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
a894928b-9d85-5dc6-9101-a85af31f6d5b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | HOLD POINT
29756bb4-4b0b-56ac-8fa6-4f044c7edb9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.4 - Concrete Placement
f41a8b01-9201-504e-b207-c557e2524c62 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | HOLD POINT
c96773de-1ed7-58ec-9ac9-1fc588458e22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
a755ad36-af5a-5d59-8bbe-39eb863456c8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | HOLD POINT
bfdb2179-d68b-54f1-8342-6d9082de6e21 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.6 - Heat Curing
7b6c2313-6621-52de-aa91-c1fe1ed33274 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | HOLD POINT
95f3205d-1409-58cd-a2b9-2a7344a124cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.7 - Concrete Curing
93c3d738-c6ce-587a-ba7e-5ac78681bd29 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | HOLD POINT
6c2aa5aa-b28e-528e-9470-ae8538712f74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
e04a7bdb-eb37-577b-9427-a6152d5afdb6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
071de70b-96a5-5c0a-ac6d-62cba36dd063 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 2.0 In Process Testing | HOLD POINT
813d5b28-0158-5c52-85a5-40dd07a42a5a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 3.0 Stessing Related Operations
468e7c86-0ead-5ce2-8186-b57a031d8bc1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
77fed012-d9b2-5908-b475-fc5ae618b4a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 3.0 Stessing Related Operations | 3.2 - Stressing
4efb7a03-68f5-51f4-bb93-c7e040500b37 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 3.0 Stessing Related Operations | HOLD POINT
212369a9-c90f-5cd4-b8d4-fafb8f558c82 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
41df5ad8-725a-5944-a595-1ebe4e5bb051 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 3.0 Stessing Related Operations | HOLD POINT
97a82415-1285-54a2-b568-875992d03b7d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 4.0 Final Documentation
6e7885aa-95df-5e1e-95a0-69c7caf6ca53 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B2 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
8a753b6e-6778-42f6-84ce-0c96a6371ee8 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3
4d33b59c-0ee9-5185-9817-9163f604996c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests
020c5557-51f5-5366-b135-103364d3f64c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
d953ecd7-752f-5588-af65-40c7dde0d30a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
c33568c3-fca0-5fcd-a4d7-1b344a01e72e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
99cc7875-0221-5192-895a-5fca74be5297 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
0b323ccb-63cb-53f8-a1cf-9d6dcbc87665 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
c4c3bd29-23bb-5f61-ae5e-76eb328dfcf7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
8ea42ecc-1d72-5365-8cd7-ee35d0366341 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
65929b4b-637d-5e7d-a06a-d8f28b2eeeb3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
8e8c8e14-80de-522a-b743-740db29e298b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
3566a5b3-ca02-560a-9e35-010b5155d1d1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
5e99d69c-c1f0-5538-abbb-941be79599b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
38f7bd71-1070-5a0e-a9af-e4821e7705f6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
610c2806-bf28-509a-a6a4-2e8aaeac49a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
cb4a5529-65d4-5abd-b92a-b25c33827d8c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
bffa1b76-c4d8-56c1-9571-a1361dbf8d1d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
0372a646-fe21-5767-bf27-19a5fbaeb3b1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
d731236f-f623-5553-a76c-e6ce35391d43 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
4d412119-904c-5383-ba4f-edef22d936e1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 1.0 Pre Construction Tests | HOLD POINT
f5e55e7f-e329-509c-9d4a-5e9e291504ac |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing
c7d02e1e-bf68-55bd-b9bf-21ed91a263e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
fc65a5af-4e22-5649-937d-235f36ea5733 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
7cb49e5e-caf6-53c6-8be6-e8ff678893af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
9adc54eb-edbc-565f-86fc-c4191eea56d4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | HOLD POINT
d268de85-66eb-565a-b679-044be5b90823 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.4 - Concrete Placement
2b2ca809-8741-5624-8495-5116b10d073f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | HOLD POINT
927915a5-9588-5f84-93d0-7babacfe6540 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
dbf2c581-a41e-5c35-ba03-99e6ab176fd5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | HOLD POINT
1e1d9e73-9c35-50a5-bbcd-ba3f53f7fdef |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.6 - Heat Curing
ff5fe3e9-d00c-5e70-b8e8-9f6798d816aa |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | HOLD POINT
43c9172e-59c7-5493-901c-05ad10f84efd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.7 - Concrete Curing
aa44d5e3-5d9a-56a3-8966-873f25c43511 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | HOLD POINT
e6ca6d8c-af09-5ccf-940b-b347636a9cd5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
e969c236-fa60-563e-9f6a-e2aca808ba1d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
be5503a4-ba3c-525a-ac75-2917865bfa4d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 2.0 In Process Testing | HOLD POINT
92be0dd9-0485-54fd-80b9-b30477324911 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 3.0 Stessing Related Operations
05193a91-e168-5a34-ac99-d8399d83954d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
41072f1c-dbad-5582-ba76-4de06b890eef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 3.0 Stessing Related Operations | 3.2 - Stressing
d79bbe4f-bfa1-5eba-9487-0b855dab0dee |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 3.0 Stessing Related Operations | HOLD POINT
767532c1-1a00-5eb5-adf5-f8bebe166386 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
f6c1d8fc-26af-58e4-832e-3052406af995 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 3.0 Stessing Related Operations | HOLD POINT
4a3a3fb4-f70d-51d2-8d26-f442fc7326b7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 4.0 Final Documentation
cd9b190b-05da-54e9-b992-235e1325b947 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B3 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
fcfd1b2f-6ed0-4a5e-a3fa-f39b0e9a5fde |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4
ebf25ebb-d452-59d5-a5ad-a2556df86762 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests
ecdb71c8-a178-5612-b23e-793ab5bd4419 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
46386b00-5f6d-5ec2-9a2b-526262f8e370 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
d9c75f1b-c51c-5972-a83a-0c2dd9f9b544 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
3c74523f-c2fb-5f31-873a-16b4c47b460a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
a58631ab-c45b-5224-9daa-f0f886d025b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
ab70fd9c-f74a-5487-b3dc-6476343fdf65 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
4e1b9ee5-e34c-51d4-859f-803ca2e5d36a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
854954c8-3a0a-5589-b841-881edb61394b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
91fcd0c7-c767-502f-b57f-54481243ea68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
32e09801-6c8a-5bbf-a050-2b34cdf6e80f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
1071d7c6-1377-51ee-854c-ad2621f55878 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
0cb8f81a-35bd-571e-99dd-dbb159da2774 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
16faa4fe-0205-5a33-9817-d18c891b0180 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
17bac238-dad7-5d4d-8ca0-b57391d0e474 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
369381e5-6259-5f04-ab46-c52391319cd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
40fe1336-b3b1-5451-abd1-00c0ac3c397b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
e3c79639-0f2a-5175-b87a-cbb79f364b9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
22254cf1-6bcc-5e7b-a0dc-32c87ad5727b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 1.0 Pre Construction Tests | HOLD POINT
f19acdb1-8be8-55c0-9beb-7ccdddc8d783 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing
d42e2dd7-29d1-5e5f-9adf-266e658add57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
2607bd77-a6e0-5678-bb7f-bdd9d24b62c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
a6b6bb62-b08e-50ac-9deb-62a4a6fa0cce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
09cbcfeb-75b6-5e4d-a0be-760dd0a6c372 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | HOLD POINT
e98fa23b-c9eb-5370-9f91-0544b3c31419 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.4 - Concrete Placement
4782b2b7-e4c1-5ce3-acea-c3691d3c4cab |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | HOLD POINT
9f74af95-6f58-51de-93ef-b2fd00d0c91a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
4b569e2a-3913-5560-b110-fdb93e0dc76c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | HOLD POINT
d40263b5-3780-5773-a6e0-c77d3ef94a39 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.6 - Heat Curing
a0bbfa41-77cf-5689-9b31-cc0c317a91b7 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | HOLD POINT
f525777c-c87b-5e07-8cc2-416760af9606 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.7 - Concrete Curing
54a5972c-3921-5694-ae30-d490158eaa83 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | HOLD POINT
b29cf417-6951-5e75-b3a0-c8d18e41a8df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
b8c75db9-9429-5e5f-937c-4160f507a217 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
610419d3-8911-5d4d-b65b-e1b66e92519b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 2.0 In Process Testing | HOLD POINT
ab0f1130-ee69-5bab-ae32-80ef31c42016 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 3.0 Stessing Related Operations
f9832ee4-d025-5c28-b27e-352f01f79173 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
64146e71-cbeb-5ed4-9c47-5d01758fa269 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 3.0 Stessing Related Operations | 3.2 - Stressing
f81d7619-895f-5e05-8b95-7859c65be7bb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 3.0 Stessing Related Operations | HOLD POINT
0ec04895-b597-5626-9816-a6df2c27dd18 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
52d1d37b-6416-5cb4-a046-05e443e7e357 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 3.0 Stessing Related Operations | HOLD POINT
64498e6a-8562-565b-b212-f95362c600fa |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 4.0 Final Documentation
a2bdbb61-98b4-5b46-a6ff-7af143f60822 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B4 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
da8a6a4e-e252-4465-a2d8-5597dab6f234 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5
ae813de7-d3f4-5401-9bc4-5837a46a2454 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests
5f61ac27-c400-5e39-903a-527fc8477cdf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
cdc14118-0453-5ab1-8a4f-ae1c469c77d1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
dcfd7b49-fc3b-5fbf-97b5-3da18918fd6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
1f39883b-055a-5c67-ae32-3f9386bf0c67 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
e3286e3e-001b-5956-82aa-2a2628fd388f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
c3442cac-3500-5436-b5ed-c6101b136a30 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
62824b0b-6749-5aa9-82b5-dda9ea89bec5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
2ea7dd85-e333-5f13-9011-37b23b361b5a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
999251df-eb7b-5ba3-a75c-6cd914b2cb05 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
25132a93-680c-54ba-b6a4-d96a54fb0a2a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
2eadddfd-b726-5df3-8802-09b16126a346 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
035e0ddb-143d-5d14-9e49-6317d2cef004 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
88e9045f-b8e9-5a35-af63-bf96dca8418a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
39c37a15-0aed-5c77-99ff-c9efc07c0e5e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
7c7e77f3-ca53-52b1-9dff-3c9f95ac82d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
333877b8-a490-5f87-a1fc-72f192cf7348 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
c2dd5e6d-1e24-5bb1-af6b-c4d4160c7ede |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
f0aff2a2-f384-565b-a53b-c585ea6dc3f1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 1.0 Pre Construction Tests | HOLD POINT
32af452c-f608-50f2-ba36-57cc3e6114f1 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing
898600b3-70ed-5a5c-9aad-1981c877940f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
0b813182-d412-54fd-a651-071094dda7e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
f2ea4068-204a-5b7f-a273-793443d7b49f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
6a404990-139c-53b9-b53b-ad48f06824b9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | HOLD POINT
415bd6fe-b961-556b-af49-f63be243af0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.4 - Concrete Placement
c5b6074f-f742-59f8-a3e4-c8421c006cdb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | HOLD POINT
eb4a3bda-a472-54d7-b9a5-20623bf9a03f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
9529cc31-cf8a-5165-af9f-ff89d6d04abd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | HOLD POINT
abeb68b2-3572-5346-bf86-22c57481fff3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.6 - Heat Curing
1bfd5fbc-c0ef-5c83-8f4e-0f950e01d402 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | HOLD POINT
ce987376-dbc7-57b9-b3b1-96e45882f1c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.7 - Concrete Curing
4b451410-fddd-57df-9efd-a0aa9666ac2c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | HOLD POINT
17443efd-579f-5e52-acda-35adc27e08b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
dd2b6e2b-8773-5b9a-9b6e-82a5e79f80e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
869fb033-3842-5d87-92a9-41a4bb25ebfd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 2.0 In Process Testing | HOLD POINT
9aa6a360-83e8-55cd-be1d-2a5e04852807 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 3.0 Stessing Related Operations
6fb4c6ed-5831-554e-8c02-66bb05ef3f5f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
c9d2e7ef-1d67-58f2-b4f1-3c00ab731bf6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 3.0 Stessing Related Operations | 3.2 - Stressing
4459b074-489d-527c-a891-4db07e20281b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 3.0 Stessing Related Operations | HOLD POINT
e7bfbf13-fb8f-54ba-a481-de5de8bf66cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
5b2c6d47-e9b0-551a-9b1b-02962db00937 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 3.0 Stessing Related Operations | HOLD POINT
3e3c19c6-f6bd-5a1b-93e2-b45134bdcd52 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 4.0 Final Documentation
b45dadb3-4379-5a31-9166-34cea4e53398 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B5 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
28e2bfe3-821f-4a65-8abe-6746a4523cef |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6
c32de11c-f793-5a9f-b267-0e159ef11923 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests
62cf2509-6695-5946-8424-59880aa24dbf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
504865bf-2230-5f5b-b1d0-c8c2de7d5e32 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
bdd5b96f-82a3-5f24-b53b-f92c257463af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
08d7cee1-ad09-5974-a8c2-a7690677fab1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
c19f5297-f130-55d1-b93d-4d4629a25948 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
d3737c38-fe1b-55d8-a0d7-05dfa01c2515 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
65fb490e-b4aa-5337-ad8b-3f4b2e869256 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
3fb30820-83de-5ed9-a665-1a47983e03dc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
47575429-4b6e-5a40-8810-326d884ef1b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
6f9a3a2d-d3e4-5e28-a468-952ff5f85c30 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
49da1e0a-5dc1-5d5c-9e01-5f140363213f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
f3ac9b1b-d21b-5eb3-bf12-4cbc6506dc0d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
660d762b-296e-500d-9645-7da845cfdad2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
bf57978b-1110-5c07-b836-18d1830bc915 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
531f441c-30ca-5c71-baa7-79a41f1ed8aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
2d6b0e66-4dbf-5575-bc22-77d193b3a5d5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
17d787db-07f0-55e7-8727-9809f4a6fb2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
7c68d414-dfb7-59cd-8932-d150c477ce30 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 1.0 Pre Construction Tests | HOLD POINT
40957339-8d52-5f74-8c45-4941319670f8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing
5752680c-49d8-500d-95d9-ce57f206a98d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
23ad6ccc-173a-5024-b71d-33098083ba73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
fcc62fcb-f2da-5ef0-bd9b-9ed1aeb214a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
ea570d11-e702-528a-8966-383decbd1a83 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | HOLD POINT
21aab1c7-9fe4-5e34-ab9c-8575510f0689 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.4 - Concrete Placement
6d477428-50a6-5051-9c7d-0c80b1e059c5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | HOLD POINT
5690d2d9-63dc-5495-81fb-8df52e038d73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
60a62d6e-497d-573a-a31b-7bfb6e14dea6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | HOLD POINT
35a6ee61-3ecb-5ea2-80f9-54f946ba5c53 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.6 - Heat Curing
65a42db3-f752-5384-a17d-73b3c09c67a4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | HOLD POINT
936b9e68-a691-5014-9f47-321e309df052 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.7 - Concrete Curing
186c0e92-bd36-5fe4-852f-072e16d9ff8c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | HOLD POINT
c10e1ff2-54af-5705-b91a-e0581daf3066 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
f363c0b6-a3e9-52d7-b6f1-28966d8a5599 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
0d5383de-f1f9-56b5-bf48-0795960917fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 2.0 In Process Testing | HOLD POINT
3355d679-1434-50cc-bd49-844eb4bfea7c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 3.0 Stessing Related Operations
1ee681e6-6cac-569d-aa59-5616d2190e1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
465479fa-890a-5e69-88c1-1c711b26d4a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 3.0 Stessing Related Operations | 3.2 - Stressing
dffe564b-a149-57ea-96b4-73de8de9ad38 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 3.0 Stessing Related Operations | HOLD POINT
dcf93fc7-bb2a-5240-a32b-28895adbe2c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
3adf65be-1b13-5ab9-919b-47ca8d4e257d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 3.0 Stessing Related Operations | HOLD POINT
3b49ce3b-5478-5a79-a182-2598554bf893 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 4.0 Final Documentation
90fd9839-bb54-5092-9752-c40b61d3bebc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B6 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
8a4dfb11-f0f1-4793-ae3b-588f75f490f8 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7
466fc73a-07d1-5bee-96e6-a1ffab3366c8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests
c5b639dc-f8fa-5651-bbfc-098e79f42540 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
2f6c4067-e996-5601-b740-96cbf79a2705 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
7fa17c2b-8173-565a-8dd8-074d4a49c587 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
de571578-167e-5dc5-94d1-c05b1f6581fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
9779112d-8009-5521-99f0-764842410bf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
6afcb540-20ed-577e-9b4b-e7cae480b835 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
a3c699c3-69f2-5f4d-a403-4f1bce7a6112 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
b505878b-65be-5f20-b3a7-d2b94c2583c6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
78e54ab5-ab49-5a1a-be2c-1f3b2b0bf11e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
3f7318de-1d9a-5e3f-8bbc-a5ada3ad9d57 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
99a56d90-b771-56cc-80cd-9ab103387a69 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
5a03ff17-0e97-59e6-b4e0-d5ed5f2c8f7e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
c89a5dc1-db21-52c1-9408-d0db1a6a8bbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
4a138aef-6506-5acd-ba5c-dbb77fd5aae2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
80eccf23-3719-56b4-a86f-071610f02cd1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
b82590ac-681c-52a7-a311-68e32f9bafe7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
d63a726d-0266-551f-abb9-90bf9a5e1829 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
03dabaeb-6896-5de4-8293-9bc60082021d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 1.0 Pre Construction Tests | HOLD POINT
af1c1b59-438f-5b0d-b143-f4bb15d9ef24 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing
69357e3a-dd18-5e9d-9e5a-5d80903586c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
a3bdbeae-a4af-5217-832f-fa8aa21dc201 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
fc2d7b9f-4db2-58d8-a91d-0f9d90aa52be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
0cc5e174-5c40-5256-94bd-d0ba8b262b13 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | HOLD POINT
81c747a8-5a26-5409-a053-0012d505c51a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.4 - Concrete Placement
63abbab8-84ed-59d2-b49b-2a27b61d4744 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | HOLD POINT
e5d0daa2-0664-51f1-a995-d6b40521e984 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
81d3dfc5-8677-5706-a0ca-193a65ef92ef |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | HOLD POINT
5e52428d-a4a7-55c7-86da-d127027c5aef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.6 - Heat Curing
2428e0d2-ad43-51ef-8909-3e7c799add74 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | HOLD POINT
56a67b7f-a18f-53a3-b93c-d7efbf444144 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.7 - Concrete Curing
9242d97e-8be2-5c16-9afe-0dcef072948c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | HOLD POINT
dfb51e6c-a55b-5973-9c3e-c3ac6a17f53a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
28b5f8d9-b9d1-5ac9-a524-70bb7503ceed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
71df25cb-29c9-5c71-817d-7d387bbe713a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 2.0 In Process Testing | HOLD POINT
53d315ea-0304-5df1-814f-d06389195c6c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 3.0 Stessing Related Operations
673a255f-4e31-5a2e-8346-7833cef85e15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
6c057f9c-d2e5-555b-afcf-7c75a2d7a14a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 3.0 Stessing Related Operations | 3.2 - Stressing
c65d1d34-3b35-5aae-81a7-480698e880a3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 3.0 Stessing Related Operations | HOLD POINT
272c70bb-ffd9-55bb-9837-338efd757af0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
31602051-84f0-5689-95a6-b652c7a4fc1c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 3.0 Stessing Related Operations | HOLD POINT
73bafbf7-ad07-5bb6-b6c9-e784e70191c9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 4.0 Final Documentation
7dd387cc-9613-5230-bc58-a35dbcf5da6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B7 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
9398d547-b039-43e4-af0f-b92f67d9b892 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8
99db5301-0c42-5c26-9883-62307e6a17d4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests
e6ad01c3-c877-50e9-9ee7-299b4fc42bd6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
9e9e31ea-6667-5d04-a68d-a7c431f5b8a4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
e9196cb7-fbb7-5a7c-a466-826d846d8a49 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
5bf219fe-6b37-5afe-814f-4f6f834889b7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
425f6982-1542-5dd2-a411-e7f2987f71f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
6fc56eb2-e720-5510-9f43-f22460aaa42d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
761e3b47-b8ea-507a-a7ea-9f35dbe4bb3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
7f9f009c-b1c6-5f28-844f-cbd744c05aba |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
a3d8d213-a8f4-5ed1-8256-79720a979a99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
a9ce3dc4-e111-5229-b3c0-95d6a59d6467 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
9870e682-642b-5bed-9348-b332d639d34c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
196694f3-59c9-5c63-9803-9fd136669731 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
7ad08ce2-5924-5757-b004-d9a7072c2cac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
c1098712-a875-5bae-a5ae-18cffeb9f675 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
22e3dcc2-b6a1-5c00-9282-a7c538f590a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
8a19b419-cb23-5536-97d7-ce7f15ba348d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
627b72c3-bf71-5ab2-900b-b625ec7bd394 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
383e378f-db2c-5491-95fb-5fca65834046 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 1.0 Pre Construction Tests | HOLD POINT
9d5d4c62-81b8-53f3-8e9c-489b3cc591de |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing
e0a322f7-af91-5042-9348-76822f87d82c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
ca54feb3-8924-547c-b62c-bd3eeeeb4f42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
3d203dfd-af75-52de-817e-e81cd6857af2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
0c40ff40-fc53-5803-b8a6-23d676f6aec0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | HOLD POINT
ee0bda1b-8083-580c-b140-42e4526508b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.4 - Concrete Placement
bd0d25b9-c7dc-568e-be63-66c43f518010 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | HOLD POINT
7961c3c2-4c6e-59a6-8c53-c30ed9520fe5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
c3edadbf-bdc1-511d-a471-ede1b7ecf59f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | HOLD POINT
75e2604a-15cb-5cd1-93ff-4d90a7a3ddc2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.6 - Heat Curing
ae29685c-fb10-5c60-94ec-2183fd33e385 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | HOLD POINT
8bee8a6a-4379-5a04-be8d-47301cfe0350 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.7 - Concrete Curing
c7d584c2-e916-567c-9939-8489ee97003a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | HOLD POINT
30f0ed3f-15b0-53a3-b341-b425a955517d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
979cd854-74ef-568e-ab1a-8a59dccc9e5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
fd265461-bdf7-5187-9cc7-d3406bd703b7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 2.0 In Process Testing | HOLD POINT
a93134f3-4582-51ff-b1a6-89a396dcbb2b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 3.0 Stessing Related Operations
9ae3665d-fdca-53b9-84ce-43a78f298461 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
21cc2604-b1c1-583d-bdfb-637960e0071d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 3.0 Stessing Related Operations | 3.2 - Stressing
9b045e75-5fd1-58af-a736-7e23419de3dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 3.0 Stessing Related Operations | HOLD POINT
fa9b9faa-f5f3-5f41-86c2-e755d174cbf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
7460c827-5ce8-5d2d-baa2-e2d38a4e2d61 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 3.0 Stessing Related Operations | HOLD POINT
b2110686-7ac1-5017-8f46-1b8b2321e10b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 4.0 Final Documentation
f8b18b23-e51b-5c0b-887e-5852482e49ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B8 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
5051fab4-17f2-495a-865f-dc8aea5fe872 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9
d010e7c6-a631-53d1-b393-db7ea8d28d69 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests
e1f2ea6b-df6a-56f5-bf8d-6ab3f15968c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
7dc1a23a-82c1-5100-afb3-c6a67f7b6dc1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
6d91d3dd-4678-52b4-8f23-6f8966d72c6a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
d0898ad4-a58c-576a-a037-128801d76acd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
f90a7960-02ad-5292-a489-bc181261c855 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
fbd0e3b5-5492-5d8b-9214-0f62dbd10f6f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
79a341a4-fc43-57cc-a788-ce26787482f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
edfac7b4-dac7-50a2-a2d1-b7576de1da46 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
08054125-eeb1-5419-9349-e147360c4178 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
20d0aa02-9487-5dfb-a38e-0511fc9b481f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
e016126c-18d5-5dee-b04b-66ead2ea7f27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
918cd09f-c02f-5c59-8b7b-a113760c089d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
299e543f-9ac5-5e54-acb6-ff5e403df5a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
a3e3bbff-4eb2-5d0a-ac1a-10e5e116346f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
c616f9fc-f6ab-5a6e-b3ff-31cc44225d23 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
950c5ce1-5769-5d56-b80d-4d86ca2ce60c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
c7fb984c-c5a8-5edd-a34e-66ee8d3d737f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
ff595a8c-2c86-5d6d-9a36-9d308aec5b07 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 1.0 Pre Construction Tests | HOLD POINT
46749cb2-1416-5898-ac56-d39855041bbd |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing
02b6b3ff-6b3c-5c6b-84b9-cbc400be211f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
48d534dc-286f-5099-af03-4d83f008ad23 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
c2c1bcbc-0372-5b2f-9cfa-f9897deb49f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
cd118da9-3214-5e7a-acc4-8993aed0b54e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | HOLD POINT
9049e1e3-c5a2-5df7-91df-ddb1ad76ef42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.4 - Concrete Placement
0383782e-dcff-53fc-a7ac-b6e7e3164f5c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | HOLD POINT
6604e214-6c49-52be-8447-4a81978e0030 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
72881021-9311-5dd2-bf8b-9567793aa934 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | HOLD POINT
59bc4073-7665-517d-af16-6018aaa29327 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.6 - Heat Curing
bed001c3-fc74-543d-b693-1eed18b859aa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | HOLD POINT
67b617d0-20bc-5df6-a12f-c535a17a68d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.7 - Concrete Curing
f3671672-227f-5784-90d3-3ecf45f1c0fb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | HOLD POINT
5236ad5b-ac37-53da-b768-900631b03b34 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
e9e2ffc9-ae50-5e9d-9d0f-7065b71a6253 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
82e81f93-86a5-5da3-aa82-ae6bbffb41f2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 2.0 In Process Testing | HOLD POINT
b8ab4970-d6b1-5f86-940d-7b57cf5a84ab |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 3.0 Stessing Related Operations
73298d04-eaba-5763-bdc6-d046995c27ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
3b9f10e2-ed42-5411-9aab-1621050ee3b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 3.0 Stessing Related Operations | 3.2 - Stressing
3198ffb9-5e38-508a-8ea0-b101f4825954 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 3.0 Stessing Related Operations | HOLD POINT
8bf5df0c-4a0c-5c3b-90c3-8103ccd33881 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
56029a35-e3f6-5ee7-a8ee-1d49e29a09e5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 3.0 Stessing Related Operations | HOLD POINT
98af1196-7e81-53ce-a6ca-8f92a65ef22a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 4.0 Final Documentation
d55a85e2-568f-5d6d-854a-c5134a865396 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B9 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
e5e83316-56f0-4e35-bc5f-657b8721f2a4 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10
71e6b172-f6c2-5798-8e39-88ce081fb8c8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests
5947f6e4-f6fa-5ba3-a215-f7fbd094a6e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
1f83872f-9e09-5188-a349-ea032486137a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
5b4c6784-ce59-511a-bb35-134de04528ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
8fa99513-f227-5396-9428-ff3098e56a85 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
c0219090-c216-58ad-afe9-82724cd08df9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
6a667797-d3f3-5e10-90c7-9ea5957eb677 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
784020ed-60dc-5882-b0af-18e1977862d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
7e3726a2-847d-59f1-aaad-b54267425b71 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
039874e9-b7b8-512a-8143-c77ab5bed247 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
08243068-76b5-535c-9bc3-1461028d1562 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
0e3c3c9f-a873-58dc-98f0-54b449e61559 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
4948d843-e0db-59dd-b706-5f3f78418a29 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
cb22727c-81fa-5c77-8773-75a82f9ea902 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
469ef0eb-0a9e-59b3-81e9-3bfaa199d587 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
41374a24-9bb2-57db-be76-4b2c157b4f91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
ae91f01b-dac9-5bf3-9150-e40b67dcece8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
2313c1b9-9460-5530-baa7-79c6bf13605a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
548e7286-4ec9-56cb-a5fc-2452b79f0701 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 1.0 Pre Construction Tests | HOLD POINT
f3242b19-6739-59f3-8477-a30239ad1205 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing
93345433-cf9b-5d28-86ef-10bf4603e3b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
462fe88b-8679-5104-875c-7c04ab9f7036 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
3cec8b5a-d7cd-582f-a155-2f0aec126e22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
30907372-f9d1-5e7d-9ad1-90f9dd6f48cb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | HOLD POINT
4f4e09eb-9802-56e8-b831-43b7737a8b6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.4 - Concrete Placement
c715df20-d711-5429-8cd9-8bfa54ad773c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | HOLD POINT
85f68836-6ef5-5fb0-8b1c-541ee2ef703d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
fba6ca13-a6f0-59b2-b5b5-8aa47e92d533 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | HOLD POINT
57ae029d-deec-5ada-857b-999d81df7927 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.6 - Heat Curing
e2e9b44d-1438-57b2-ad39-d03354af23c7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | HOLD POINT
c3cf076e-e0c4-5572-945f-67c6200dc3ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.7 - Concrete Curing
c9867b41-47ad-55ad-a1c7-fc7e8ff8c843 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | HOLD POINT
ff85b66f-1b40-5437-a59f-9bf6b9ff7cf5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
da69462c-d669-5c86-a8f0-329179b7246a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
91361303-1a04-5241-aada-1465bde30ea1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 2.0 In Process Testing | HOLD POINT
8253b784-f4cd-50b4-8819-8fa39483937e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 3.0 Stessing Related Operations
58748ca8-c003-5675-b09e-13f98a44e3d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
ac89dd47-01cd-5697-a07f-886a42311c94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 3.0 Stessing Related Operations | 3.2 - Stressing
c0496f95-b86f-5431-a91f-f589128a3862 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 3.0 Stessing Related Operations | HOLD POINT
22202f82-cb86-5a9b-9fff-dd6af17baa35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
683d2fe5-5d37-5d40-bab7-9d3049fc9a8d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 3.0 Stessing Related Operations | HOLD POINT
b4971a44-beaf-55dc-9da1-8f341ab8a127 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 4.0 Final Documentation
e1895e7d-a7fd-5aee-9270-04e14e14b346 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam B10 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
798ad840-d050-4d89-9ca2-2b2c86ec473c |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1
66144fa7-ef75-538c-b964-70c1c510b65a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests
998030c5-f9cb-5b94-8b59-48a4e4dcd176 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
553a7c22-cf1c-52a7-b91e-2001e00e9f9b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
a4ee114d-6fd3-5bf6-895a-ea747417b9b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
11fd2669-dd34-5e41-b958-b09b6541add8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
31b96a5e-5a42-59d0-afb2-1b08ce92e1b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
6ae5761c-a829-5265-91ac-7743ad6930ea |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
072ce4d9-482b-502b-ba56-a1b144957b3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
a24aca86-9207-563e-ac0e-4464bdcbee0a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
eb07c360-6c43-5bbf-b7b1-99637647246e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
5e1aa279-c158-579f-8c40-fc25ca0be0dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
34898df2-2eb4-5fd6-8d21-be95422ba095 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
e05bf615-d000-585f-9842-30d9acab1daf |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
648d49ad-a8c6-5b3c-9cf7-134006a60deb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
a8bec807-172f-5f4a-95b0-d5407c7518a1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
de08dd05-4441-5e3e-bb51-99fcb6e2665b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
7c7d1d81-c322-5b55-8c93-f2b603d7d575 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
d16e92e2-9a87-5b53-99f2-46924f43f996 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
ac7b9950-a5b5-5d38-bd4e-4049a512e6bf |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 1.0 Pre Construction Tests | HOLD POINT
867c9a5a-df25-52a8-8cda-79d6b6926e7a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing
1de5078e-a228-5b69-866f-33acb3558c70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
09cc2882-a824-51da-9509-cf40ac7d1221 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
ad03a362-73a0-5bdf-a35b-3b11ca885aca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
aab2c2c6-27e6-5d70-bf60-41d380d01920 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | HOLD POINT
2f940c6e-9fcb-5166-bff7-1607b625c187 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.4 - Concrete Placement
6e5286db-07ab-5c54-9df6-e50e9edcc90c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | HOLD POINT
b24285d2-be93-57a8-87b4-35d4dcd0eb72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
e31369fb-d396-5793-b88b-c8856113c844 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | HOLD POINT
436de16c-727d-5753-8b78-5552d914bf3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.6 - Heat Curing
f79ffc05-d33c-596f-b069-c125786dbcf0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | HOLD POINT
bb106078-71a6-58a1-b5ba-b77a85a53aec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.7 - Concrete Curing
d6689452-c548-5277-a46f-4ea080fc6760 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | HOLD POINT
1e5bb515-b07b-5cdc-a27b-e6a2882473f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
3d7e1552-a084-5ca7-ac0d-45b80dffd3df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
8799b2eb-84cd-53bd-8b9d-6f3ccb771f5e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 2.0 In Process Testing | HOLD POINT
70b0d6a8-681e-5f97-b3f1-62f2edec174e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 3.0 Stessing Related Operations
1c21676d-2960-5047-ab66-133695956fdb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
07003fbf-63ad-5f25-b35b-3cba2d61ec08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 3.0 Stessing Related Operations | 3.2 - Stressing
4e0a599e-57f3-5eaf-8968-2209dc270bfe |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 3.0 Stessing Related Operations | HOLD POINT
0c9ac922-89a0-57a4-ac94-cb307bd82c64 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
98b99625-1bf6-55ff-bee8-e2cd5513b591 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 3.0 Stessing Related Operations | HOLD POINT
ccdf9167-5fe1-53f9-b3de-8f247a0037c9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 4.0 Final Documentation
bd589b9a-0ae1-5e2c-b26d-6595ef1475fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C1 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
83830573-241b-48dc-96a8-ded11d32296d |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2
4e92bc2f-fee2-591b-9c88-8dcdb370b4c4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests
58861b03-c8f7-5337-9694-98661be7e6a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
a31315a3-dae4-58ed-9abd-8a607d8d1b30 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
cffb4f0a-5cf2-5a01-bbe2-6b3719311033 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
47c32dcb-6494-5726-8424-571ced889c36 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
d1b57bc7-ae5b-527a-8a76-a60b34df4587 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
00b06bda-e0fc-500e-8df1-0c096f3df300 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
7641e57b-1551-5b48-9b62-5541b3cc4df2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
102dc7c3-3fa5-5093-af06-371a1c4581da |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
fc74b6da-d239-551d-9edd-b691b3a967f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
7d048f3e-3bd6-525a-a040-b6809aa84188 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
f7decbc8-ba06-5987-b555-ce76c6300181 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
f9f2a691-6b62-5a5d-a6eb-5a92a84de458 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
dc610662-fea3-53e7-8853-d15b9ad7026b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
d9846baf-6795-500c-b08f-bbcf42c99b0b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
45660728-a49a-5d65-afb5-7437576694cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
53943d1b-15c0-520f-a7fb-51df18f46e50 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
92974c79-d01c-5ec9-81ff-233748735e78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
ac2b2a26-8c64-54d6-bb6b-98cba44f1323 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 1.0 Pre Construction Tests | HOLD POINT
822f7f5d-3a29-5ef4-be10-dc9030d104e4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing
e68d94be-ae28-544b-abd6-e54bce53f860 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
6fe65fa1-7292-542e-9058-7e0b8b1aa3a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
dbea6642-c8a7-5455-81b4-2349fa7add8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
3d1bec84-be52-52e6-b93b-c8c2b8c3a221 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | HOLD POINT
9f0ee27c-9122-51e3-ae79-b33970440fdc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.4 - Concrete Placement
ee4ad484-d36a-5d0f-b2fc-8ecc7e750428 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | HOLD POINT
8ff0e1b6-1d67-520e-ac53-3404ddfcffea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
bd3fa4bf-a1e8-5036-bca1-90e6ad3fab0e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | HOLD POINT
c157f1a7-7532-5868-8af4-9e64ffc5447e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.6 - Heat Curing
5005a365-df5a-5368-b1c1-b4e0e3c464e3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | HOLD POINT
f87c0049-ce1e-5434-89d3-7c34af47b763 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.7 - Concrete Curing
b8c9754a-d7e7-5c74-ad0e-521d4a8ee275 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | HOLD POINT
7c2b90c5-e628-51ad-836f-dd4526878ac4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
f8a556f0-fdbd-5c28-999d-48bc59669e2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
1a3f6aa6-e41d-5114-8b6f-4c35996ba1ab |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 2.0 In Process Testing | HOLD POINT
8d7a2510-43aa-522a-b5a8-894fcb5c0d2f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 3.0 Stessing Related Operations
a355df6b-8a98-5e0f-8a95-a43d90d7581f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
a1e7a12a-b3ee-5eae-9f92-32c82ac222f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 3.0 Stessing Related Operations | 3.2 - Stressing
3663f012-6602-58ca-ae54-489837f7c16b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 3.0 Stessing Related Operations | HOLD POINT
1e159e42-4e37-5cd9-a03a-27457ecf2af9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
01e25dc3-2071-5605-a0db-711ee27741ff |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 3.0 Stessing Related Operations | HOLD POINT
effe57b8-25da-56ef-83b1-565013ef280d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 4.0 Final Documentation
25e4b4de-f97d-5d11-b65f-e9ec898a3a0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C2 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
2ede5763-fe11-4bfd-8d51-d3fe6f33cccd |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3
cee0d394-7679-518a-8b29-125e867e25b7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests
468beab3-4949-510b-a06e-a6280ef7c3e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
eaff32fe-7757-5419-a870-82ca93813d4e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
50d13f7b-5d37-5889-b1d1-e9d49de79748 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
377c13e3-639f-5cef-963b-d65e4feefcb0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
5c4dd832-5c23-525f-b787-45bcb9cc855f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
16514dc5-136d-5025-b36f-644d971c5138 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
77ed522c-cfd0-564a-bb00-6fdeda3bf74b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
683269de-ccab-5dac-ba84-66e44c517fb0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
5e347b3a-322d-5228-86f9-2a8d10f79e9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
8e02c29b-9d17-5228-bd8b-6d94bf7d23ab |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
3938deaa-9c25-5955-9722-0588fa7f68da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
ac8192dc-db95-5b21-8a52-04c6472c2d59 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
19f1d7b7-32ae-5fcd-ab69-7f01955a8b77 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
2548fcd6-0814-5721-828d-1a0f1efd5208 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
bb18536e-73d8-51e7-9ddb-881360044046 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
cc52df40-1570-513b-b000-2bcce8c5c933 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
abcd9142-b339-5f6a-ba02-98342c7fa965 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
6e4c18dd-4456-509c-982d-d7425417f3c9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 1.0 Pre Construction Tests | HOLD POINT
800080d8-4248-56cd-bb52-dfa38cefba95 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing
ddaafb54-a238-530c-a21d-51f7efa78141 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
b62f998e-09e8-5c27-9029-183436b86630 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
5b0f381c-bf35-521a-88ab-c392b1c1b723 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
48a71a98-869f-562a-8235-a2709ddc62a3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | HOLD POINT
c6bcb757-7e95-558e-b2d8-64975c772845 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.4 - Concrete Placement
6423be9a-70ef-5d9e-bd62-8d872cfb6433 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | HOLD POINT
64fb1c22-5490-51b5-a398-31ca30969118 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
a23fe0f1-5415-584f-86cf-e875ee8afc31 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | HOLD POINT
e4bc5ac5-e44f-5999-8edd-6dd48041c773 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.6 - Heat Curing
9936da12-332c-50e7-bac9-de25b9813755 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | HOLD POINT
9d02d222-3943-5042-8af6-75405d596f35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.7 - Concrete Curing
8f9c4d01-4e31-559f-a7f0-4f008574d5b7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | HOLD POINT
dc1944b5-5a0a-55e4-880d-dd9c9e37e140 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
5f42a35f-b71a-5ca1-9f1e-1dfd08c55705 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
b003e50d-93c7-5748-b96b-783088bf4e01 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 2.0 In Process Testing | HOLD POINT
b10ac37f-46bb-5005-ab02-32feceb6aaaa |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 3.0 Stessing Related Operations
34440fa0-bb04-5e24-ab5f-cac4b59b4802 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
c707d511-fcc1-58a1-8cea-fb5bda4355ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 3.0 Stessing Related Operations | 3.2 - Stressing
9a586f38-eb95-5865-a7e8-df37649e72af |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 3.0 Stessing Related Operations | HOLD POINT
922cfbcb-c425-5d19-b8f5-83c711587528 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
1a1ebf32-228f-5c71-902d-4113908fdd29 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 3.0 Stessing Related Operations | HOLD POINT
10af2293-9687-5ffc-aacc-b55c8f937a44 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 4.0 Final Documentation
7fe62ce7-f1f7-519c-bc59-12fee29913d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C3 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
d1ddbc72-c46f-408e-90de-fafcbe4d743e |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4
e8766960-62a2-5a39-b60e-f4eba6cdeb8d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests
d8fc1658-d51b-52d5-a6bc-72be5f1b6c6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
acec8a0d-4ab8-5efc-a293-cfbfc6b15431 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
c005d990-585a-57f8-8efc-0d357d05029e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
f0278a52-2612-55eb-ade7-ffd2f76e11fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
0fd35e07-1a10-56d8-86fa-973243e594c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
b1ca6095-d63e-5f20-9afa-41dae5a2d369 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
1aafcf96-d747-599f-8100-23c29f5785c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
5b47668d-23af-5cec-8f31-15ad0646b1d4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
bbb5895a-f871-5804-b5c4-bfc7a6ebc21c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
2301f4bf-db64-5a9e-a6e3-f43e638d7fc9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
32545b32-b1db-5171-a94a-93f1951ad3ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
41e7c8dc-cc25-5c14-90a3-612eb9c78395 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
56dc0154-5670-5e66-8a8c-0144bbdfce52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
4247af9b-38fc-5d68-a837-33c8d3df4fd1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
71dfe523-56e6-5ac7-b966-1da477f314b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
1bb5d57f-484f-5d69-abd6-cbc5a63ab150 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
3281e0e9-fc42-5c1b-8122-f96cf56dc179 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
b5c07c58-10cb-528c-b021-fe01fbb0b20a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 1.0 Pre Construction Tests | HOLD POINT
46b9df94-c395-51bc-bb14-79db58aeb824 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing
7721fdde-dcb1-5d76-b416-8162a597a7a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
0ce70670-4006-54be-9cbc-54131041350a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
b49f963c-ea1c-5833-ab2f-469af7e54140 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
b0ed7f14-3821-59c7-9f58-fefe4b9d8037 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | HOLD POINT
36fd197c-d92f-54ed-9dbb-a123257ab975 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.4 - Concrete Placement
c3324e79-68dc-5a2b-a9d0-ab6e6fcdcdd3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | HOLD POINT
d9653e33-9661-53bd-a09b-800e35b5cebd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
e755b129-24cf-5d2c-8095-c65fce918ab0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | HOLD POINT
a4c3e5d5-da17-5b62-8fe2-00294ca91533 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.6 - Heat Curing
038293f0-7b69-5c76-b21c-3ceed4af5396 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | HOLD POINT
d1e19195-a8cb-56d0-8d4d-5ec7e55aa151 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.7 - Concrete Curing
385094b2-3b84-59e7-afa5-fad138b6b0e9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | HOLD POINT
d520fc21-1cc2-5514-b8a4-25960f851640 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
91b7d01a-d3bb-53e1-a0ac-fba9fc1b8080 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
dda2ce64-7212-5787-8c15-d0cd5187ce7d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 2.0 In Process Testing | HOLD POINT
067dfa6d-87ab-591a-8ddb-b3e6c515d15e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 3.0 Stessing Related Operations
15ad2651-1b43-580b-b474-f011f0ad2a02 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
17b5ba9d-e034-5084-a4d4-e06f105dcabb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 3.0 Stessing Related Operations | 3.2 - Stressing
2ee39d98-73f0-5d2e-9650-2608eb4ca19c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 3.0 Stessing Related Operations | HOLD POINT
a607c800-fccf-53ad-ad38-48c715ebbd3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
e88c673f-8e4d-5d8b-a39e-46df8992ca4a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 3.0 Stessing Related Operations | HOLD POINT
fbfbfe64-5746-5ae0-85ac-7c4f5712c852 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 4.0 Final Documentation
313ec5c8-454a-5514-b3ac-2e6a1282e12a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C4 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
c89d2620-74d9-462c-984f-4c1a0c7f1175 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5
16a4f016-0477-5c7a-9780-e667393579ec |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests
44c961f9-68d1-5620-9e0c-e922882ad5e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
eb5282d5-5730-5909-b9ec-9a0bc9f2a2c9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
b8afec04-e479-518a-a9b3-0893601a99ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
a4e579ac-b976-52b8-acee-79c917e5d574 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
e37e5438-f9f8-5f0b-81dc-a6b12a92317b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
07a7d860-0c9e-56f8-a1e1-8d37a9928050 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
bb80feba-80c2-5340-89c1-be6d1b5868e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
5f30e63c-f4fe-5f2e-ac40-06231b7200fd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
92f7c626-6cf0-5cb7-8b0c-1c54f9612548 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
91e84e32-386a-5b14-869f-a3daea08fb92 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
73b545b6-1e6f-5e59-a17f-8ad13283a195 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
b1af8d12-906b-5356-8daf-592a25c2821a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
66d0be89-721b-50d1-9c67-faa328f0e1a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
3e75cce4-3165-57a5-8ad1-d9f2ea2318da |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
f28b99f6-daae-59d1-a16d-2feaf976ce7b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
46346d70-dfc0-577e-8ab0-42ec39d69bc3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
18b99bc7-30c4-5f82-9537-5e13325c5695 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
4d900509-c78d-5d42-887b-bb0466eda68d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 1.0 Pre Construction Tests | HOLD POINT
85cd5b28-e7ee-5b16-9cb9-087f83d1378f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing
6b2eeff4-f22e-520f-b3e4-0da07e23960f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
e9c48441-da80-5024-a393-253c7ed8a223 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
ce53749c-a8f3-5eb7-bf3a-36ce5449674a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
98ef8f93-2879-5dad-8bc6-d02ba4e5a5fd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | HOLD POINT
bba399f3-1a4e-5dc9-b5a3-0c9beab450ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.4 - Concrete Placement
8e7deb84-7443-5d3a-a893-b11572e03859 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | HOLD POINT
27672b9f-659e-5a2f-b93e-06d3de893b28 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
8c98f71e-6c86-5e9a-96d3-e6e4aed6b8e2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | HOLD POINT
2a9df1c5-b889-5481-b2ce-49b3eb55553a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.6 - Heat Curing
3d021070-15b7-5030-89a1-04a6cabb72e3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | HOLD POINT
44d13478-2d90-5a35-8827-e2ac5aa85500 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.7 - Concrete Curing
d334bb29-870d-59b5-8a02-9c16d8075259 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | HOLD POINT
7210c05f-3bb1-517a-9ace-dbb134e074f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
f5257bd9-578a-521e-8b61-998b439416f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
e8d58d35-0c1a-5d64-b8c4-8ce1252ca1f0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 2.0 In Process Testing | HOLD POINT
ccca76fe-594f-5c26-aa27-426a245fe5d7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 3.0 Stessing Related Operations
e3750baa-5d2c-5565-a5f3-e2eaa12ce832 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
4be878e5-3ecf-5fb8-a0f3-024844c04e9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 3.0 Stessing Related Operations | 3.2 - Stressing
459f4ac9-941f-5904-b861-1296d9f7c05d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 3.0 Stessing Related Operations | HOLD POINT
ae369b56-69f9-5993-b018-df731e86d435 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
684427a7-868e-5ac0-9e6b-3e8a5be77bbf |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 3.0 Stessing Related Operations | HOLD POINT
db6ff24d-16ae-5a8b-9916-eb57fc3b1590 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 4.0 Final Documentation
f8d5b7f5-438e-5478-ad57-40f56e2887e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C5 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
fbf12d0d-8052-4255-b9b6-526f6bdfa1c8 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6
1b887b7f-778b-5451-bd4c-e8812300eab3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests
550ae772-942c-58b5-b5c7-bd6fdaf4c517 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
29793a78-b11e-514c-a2c5-b06451ae3374 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
a93be895-b861-5045-9f3d-577f442ffc91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
cd85f7c6-f8a7-5865-9060-79532425d333 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
ceda8aa8-c068-5b7c-94b0-529e56cfe02e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
29ba91d1-10fd-52b3-a0cb-4347d11c0868 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
b081f69f-b6a1-5a85-861d-6031e623c2bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
5db2e364-8555-5906-a6e9-8df225c81308 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
47a412d7-941d-57f1-8cfe-e082174dfc96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
9e962217-b6de-52e7-b20a-0ef8f93e1b4c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
24f9055a-a943-5e06-a03b-66af8154af31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
003d6d9e-f9b4-57e7-8017-776e5a6776a5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
f4c9eaeb-0275-56f2-b32a-39e908e258ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
2c00120f-4ea5-522a-ba96-79ba005c9974 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
03651dd9-4dd2-5e1d-aa25-90f3797b911b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
51539d31-32a7-58a0-966c-505c41946a0f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
fd4f0ea5-16d9-5997-9b7e-d7096ca94a0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
f2260283-bb63-55d9-8cac-15b2393001c4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 1.0 Pre Construction Tests | HOLD POINT
17567076-0529-5c71-88af-2b5fd9878965 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing
5108154b-7970-5d5e-9dfc-ebcdaa9e3ea0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
faab1183-4656-5048-9168-dabaf6ee44c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
b658397d-3427-52f9-b191-174e731a7d10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
d302821c-023a-5cba-8b7f-066e2bb0a4ab |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | HOLD POINT
f1078a46-4bcb-5d24-af7c-4f460f870c5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.4 - Concrete Placement
5f711fe7-512c-5fe9-8f64-f0c1ae5931ed |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | HOLD POINT
06919b5e-0ba5-5a90-9ba9-5a37181048e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
14d3aedf-be23-53a1-a408-db559a78aeb7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | HOLD POINT
67d48ae0-aa66-5d6c-9780-e9b8780cd599 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.6 - Heat Curing
4a723d8f-3eed-5df0-8657-29aaecdf58cd |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | HOLD POINT
60de0995-5744-544d-af98-75ad00f280a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.7 - Concrete Curing
2fccad32-10a6-549a-afcb-a27bd2bca942 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | HOLD POINT
a9ec79e6-b4ad-5ff6-9713-549c93f4f821 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
701523bc-7842-5dee-805e-55b15b896b0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
e8576dd9-1871-5194-b02c-260aa04a4522 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 2.0 In Process Testing | HOLD POINT
ffbba009-32dc-5b9b-b43f-560eb439cd1d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 3.0 Stessing Related Operations
90e84f78-f0e4-55a4-a6fc-225197e80ac7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
1dae4219-50c2-50f4-a5b7-b6c2116fddc3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 3.0 Stessing Related Operations | 3.2 - Stressing
ed7fc8a0-4cbc-5296-b243-dbaa508bece7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 3.0 Stessing Related Operations | HOLD POINT
80cf4888-079a-5088-bd7e-659b0717b965 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
88e2c5e6-6197-5e88-9b81-a0e2ca0b9c48 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 3.0 Stessing Related Operations | HOLD POINT
902e5422-d1c7-5661-9df1-677fd07a5a99 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 4.0 Final Documentation
e03ea4c1-6ab1-5fd0-b1e1-e6cc93dcc9f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C6 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
4036138b-c480-478a-96c0-ef19c7065c51 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7
12a77ebb-6876-5a4d-8866-dd31e5a1cd00 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests
770ddf74-5bf2-54be-8bb8-dc3fb59e2ff0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
12c40d70-bf6a-5167-ac61-44ab29660b1a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
8d58cdad-4cc3-5946-b757-3658a31e34a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
02350068-ceed-53a5-9c5e-c0f2635099f4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
eb5481e9-aa0c-5b41-b8b7-7812dc0a6692 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
9447b736-f94f-5a19-b9cc-12ef869359e2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
7a105ebd-c4fc-5367-929f-acf514b27028 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
9afa10d2-8007-576c-8777-16107f5f7f02 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
eae7aa87-4647-519e-9335-4eeac3ebbd6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
c2a8edd6-54f8-5d7f-bfec-67a51bb2f962 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
e9b5545a-47a1-5e36-8156-f89582cfa44a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
3a1f1f62-6b54-5938-b275-0e74988d98b6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
62a638d9-d6e6-55ff-8d93-e6b509013242 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
ff693543-9524-56da-8d9e-98447ea76837 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
99fa1aa8-fed8-580d-8c40-eb19d663fe52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
42780b5a-b82a-5e4c-9c79-e63e1af24c1a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
46558cc3-cda9-593d-9faa-7b1b283f493f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
fe225c24-a671-541a-9169-dd8053fafbc5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 1.0 Pre Construction Tests | HOLD POINT
9f2a8d6c-7cb1-53e0-b34f-501b29bba7ab |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing
fca6ee47-263b-5703-8c2f-93e5e69b271e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
e9a9f809-e727-5f24-a7f8-328ecc42e2b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
aa9709ba-6117-57d9-9e4a-60bde5b6dcad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
b32a8a79-12f0-5e43-80d7-45ba27fd347e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | HOLD POINT
a24c2d0c-74bd-51e4-b01a-af00dd2027a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.4 - Concrete Placement
ed4ea251-2d45-5717-8080-2dd7f21a9481 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | HOLD POINT
dc2c1ec2-2e17-556f-99d1-7981d168b6a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
ed0209e4-1f5d-56eb-9012-4e2ed9ee5edf |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | HOLD POINT
52f8d972-2cf8-5e0c-af1a-4ed36c933d51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.6 - Heat Curing
38b3641c-610d-578b-8f19-8d2239babac6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | HOLD POINT
12924fd6-fd3d-54a3-920e-fe29df11bb5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.7 - Concrete Curing
f755cec5-287f-5b94-a4f5-c548d368c5a0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | HOLD POINT
3084b9fb-a2a8-57af-82a5-1117016f3322 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
613864c4-9509-558d-b0de-af882e8cfe05 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
1ff797b5-7640-51eb-aab9-eaa150debf2e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 2.0 In Process Testing | HOLD POINT
18d46dc6-1e12-54de-9bad-211c2329bd8e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 3.0 Stessing Related Operations
86e20d9d-91ee-5d9c-bb8a-f42554274067 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
d88d95ae-8ef8-57a3-b3ad-85bfe77f009c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 3.0 Stessing Related Operations | 3.2 - Stressing
09874db3-7869-5b36-bb6a-e6f6a4145503 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 3.0 Stessing Related Operations | HOLD POINT
f638a0d7-238d-59c6-bff6-de60b3d2daf4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
d78c93f7-aa45-56cd-8817-85386d703ecc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 3.0 Stessing Related Operations | HOLD POINT
bd6f8daa-51c5-55aa-993e-ca1370621c34 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 4.0 Final Documentation
3adb0a66-bae6-5b6d-9eae-f9a7065c63cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C7 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
4c20feaa-cb34-4a2c-b9c0-906bcfcd3797 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8
b15e2631-68e2-5d63-93bc-42053e51b2c9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests
8a912c30-ff2a-5caf-917d-8e1b30241dc9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
80b52a03-9a1b-592b-a5e6-406b80a152dc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
5a1d905e-4916-5b44-a3ce-91a3fb136eef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
87e9b07b-294d-5cfa-9515-0ca7ac81eb87 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
fb91523c-3339-5c73-93a2-3bd5bc885735 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
1575967e-a2d8-570e-bf93-9d755b1f3e38 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
6d2c8e37-ccb0-5e8b-89b1-052ef2e4b768 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
6bca9e50-fb7b-5616-99f4-3ce8b8f86f73 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
7f9e64c5-ceeb-52e8-afb9-adce555626e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
934320e1-726e-55a3-a483-290a6f98708f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
e07d35d4-d296-5214-a249-356b6ccb3ea2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
d518fd73-aaa3-56f4-8bdf-dd6c904ca619 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
41a9ed79-a8c2-57d4-bc2e-2b4d2a6f37a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
5b078d63-8ea4-5f9c-97f8-1b9dd58fde1a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
33fa1319-d6bf-5098-acc1-1404c892cca0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
c9a6ed08-be07-5b30-8d6f-d7feee7ca508 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
bcee446b-a986-5dc9-a3be-5712f4cdd981 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
cc2a9051-5520-5af7-81ea-37b40602346a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 1.0 Pre Construction Tests | HOLD POINT
63d92c58-cd71-5944-8674-6ccb625a6be2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing
0861782a-4a89-58b4-aa26-65187a86b5e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
32a02e5d-86c9-51b6-a21f-2ba10aa674e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
42dcbc44-af69-50a4-9be6-9ad2f8be5f8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
b01bc499-1d54-5bb4-82f8-e032a4872a46 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | HOLD POINT
ba8eafbe-5f8e-5bef-91b4-2c5df96e7151 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.4 - Concrete Placement
38ab9c7a-244c-58e7-aac2-c8737583ae39 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | HOLD POINT
4cb97c60-7b45-5ba5-8809-ebe35d7e2731 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
c838beea-90ac-5fb5-940f-b150c787d9e1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | HOLD POINT
2958eed8-9905-5ada-ac7e-b71155381ed8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.6 - Heat Curing
26b1da1c-c58c-5f4a-8512-b00808836937 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | HOLD POINT
86365a18-bda9-58ff-b5d6-deba5769eed5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.7 - Concrete Curing
4817da05-ff5a-5ac3-afb2-1c78eb34f7d7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | HOLD POINT
9425b103-b360-5bc8-8d4b-c37fb9eb07a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
3fcf9311-8fa2-5985-bb7c-8fcb3950a5fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
5611c64c-c3a7-5144-8e16-a4c447f29429 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 2.0 In Process Testing | HOLD POINT
dac7c01a-b090-5506-a82f-bb3726239b35 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 3.0 Stessing Related Operations
bfccd7be-94bb-598d-afd4-fa33a166e87d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
4f3d1b6a-3236-5a86-8062-67d8939787ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 3.0 Stessing Related Operations | 3.2 - Stressing
dbc07462-1393-54a6-ab4b-c014c25f4e01 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 3.0 Stessing Related Operations | HOLD POINT
f3b52721-4247-55f5-a4db-9e0a7b9609c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
dbcd75ef-40ca-5880-86c6-4e9e700a9a05 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 3.0 Stessing Related Operations | HOLD POINT
60173991-434a-5c65-ad03-2bd9485d5879 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 4.0 Final Documentation
ad601477-6501-5c22-95fb-426066216320 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C8 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
bab9fca3-3116-4056-abff-31a73e38f773 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9
a3b11257-7883-59b8-ba2f-28e0ca9b2446 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests
dd2ec7e3-ff55-59aa-8283-f46faa54943f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
1145545f-c843-59aa-bb60-0807b58844f9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
c0d917dd-5704-55b7-9132-0a0f5c02c65f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
69bb85b5-74c9-59c9-ac15-be1992081b98 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
2306bd05-cddd-5ea3-997f-f48e6e71b91a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
84aee63b-8553-58d4-b8c4-bf5b60fcc09a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
782b0b27-9a32-55d9-99af-fa41a4fdab14 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
7f0f9c43-281c-57b5-b150-2452ca0687e0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
24d45970-dff6-5ce4-9a2f-fb62d429bda6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
da8caa10-4905-5ead-84d3-8106cee83d0d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
2afe601f-4a8f-5073-a958-9f61ce22cf0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
38456cfc-c4d8-5b4c-9884-a3cb98132f1a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
cc76603c-c8be-56e4-8ffa-e90ae1635994 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
d5478688-795f-55e9-b7c8-d11ef9935874 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
7b5bb5f5-9b40-57c7-950a-7ed64c5f3f7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
b188a3fa-ba57-56ed-ac11-d6b2a9ed66ae |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
e4ec4cf8-6e54-56f1-b6b0-90078de8f791 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
e9735d20-6883-5960-b665-6d4e4e30ec7c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 1.0 Pre Construction Tests | HOLD POINT
d61b4859-becf-5276-a768-4d8f12f5725c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing
3c193146-4773-5c3d-b086-ac6eec060b1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
d2997ec1-b35a-532e-8e0d-fe0887ecb7ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
23b83b82-4a9e-5e9a-bccf-e7d470dc703f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
6499d735-2980-53ab-946c-ad85b304500d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | HOLD POINT
219c8a9f-bcbe-5a4e-87b4-6225e907ab4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.4 - Concrete Placement
f9baf698-d6d7-5b3d-8c70-39571f97cc17 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | HOLD POINT
bd7841a5-9f5e-502f-9736-5f009a97169c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
b22a0823-ca34-5c59-ad0e-84d22a4aae90 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | HOLD POINT
e3103aa8-b782-5896-a444-f37ab68752da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.6 - Heat Curing
9d0ba762-d781-5e01-9687-379b48713493 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | HOLD POINT
67751bd3-e5ed-5e37-a528-74737fbc772d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.7 - Concrete Curing
189ec857-9931-5f94-8a65-fdbce9579ed1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | HOLD POINT
e7cafbf6-ba9b-57a5-b5ed-1ec28d79319f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
12bc16bc-2503-5f7e-9fd3-6c384e71db2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
5d7cd5f8-0994-5f83-900e-8c00c1cbfa58 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 2.0 In Process Testing | HOLD POINT
750dcf0d-48c8-5bef-8434-d27217e01833 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 3.0 Stessing Related Operations
b2eb0d4f-f675-5b8b-be71-27736e087f5b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
e1e7a50f-c998-5c74-b4d2-fccf1248ef1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 3.0 Stessing Related Operations | 3.2 - Stressing
7b581da5-5cf1-5ecf-a178-4e4395b6b122 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 3.0 Stessing Related Operations | HOLD POINT
b28c0a6d-e34d-5982-9834-1ebf71279caf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
55fb02f7-aa4a-5c4b-b253-f8d46d91aedb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 3.0 Stessing Related Operations | HOLD POINT
bb6884c8-5d09-5af8-9106-785349c1774f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 4.0 Final Documentation
a19fd323-d5fb-55a3-aace-7f7531f7cd7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C9 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
144cf8d0-6b47-40f5-ae8d-ca68099a4486 |  | fail | b35d85328296dacb0a72a00770be2141bac9ae55675cd99a01ba120759375687 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10
84237e24-8c69-5a2f-ae47-e0b97d12c9b7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests
db61891d-d0fc-5752-b892-37e0fa6b4992 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Design Approval
7073ff5b-f793-54a9-bdba-aed5496c0514 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
98055b68-3e27-56e5-9065-ee15291272a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply
3902291b-0886-5f9d-be35-0adb37083565 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
f7976995-abb0-5682-9c23-74a849849896 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.3 - Strand Supplier Verification
c1f1eacc-1be4-54a3-8a5d-441e76257763 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
dc2187d3-2be1-53d2-8289-31427325e17d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.4 - Strand Supply
d5dd3d19-9dc1-5db5-8cdc-8aca9000d607 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
c8b2cc9a-4ba0-5141-a8be-e6196a437c5b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.5 - Strand Certification
bbaf26b9-fb4e-5d31-ab30-b631f08b4721 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
8fda2f28-ffd9-5b74-9dfe-0a9ebbdcb10d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.6 - Shop Drawing Approval
0f81cbc6-c13d-5890-aa77-61c96a53bc4a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
14a8eefa-2dcd-564e-bd87-465b3d01b0d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.7 - Stressing Calculations
9e363ee7-48ef-5a6d-a26c-e135945002fd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
d58e873b-79b9-54b5-95ed-8591e4c75b0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.8 - Jack Calibration
b2ad6b28-eb21-5345-a814-ea954372b550 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
b430f6bd-04e7-5929-bd4c-e6fb58e8b0a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | 1.9 - Form Release Agent
a31ae427-365e-59d0-b74f-494c51a29490 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 1.0 Pre Construction Tests | HOLD POINT
885aa646-a376-50b3-8b84-d8597b422b9e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing
cfecdc81-2427-55bd-90bd-27d6ff87a55f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.1 - Reinforcement Traceability
d8051cac-9f24-5b07-b824-4d1975d06b21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.2 - Reinforcement Fixing
fec99789-449a-51b1-9d02-82b5436c977a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.3 - Pre Pour Inspection
4a467d66-440b-5649-a40c-6088aa7029a7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | HOLD POINT
bdb17533-fb83-5ee6-ac65-2ae8931c4f35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.4 - Concrete Placement
50d785fe-c4bd-56ed-8abd-17e7f92373a1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | HOLD POINT
e825380f-6294-599e-9aa0-4ae58b6b58af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.5 - Concrete Sampling/Testing
e850c9ae-ad58-5797-a802-a723bf81ae61 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | HOLD POINT
84ddadbd-35d4-5318-8ca3-d41af543cc2f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.6 - Heat Curing
51f76cb9-0316-5dca-9008-f40a07bd92c6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | HOLD POINT
734adbb1-df99-5fd2-b065-aacb09c8d42b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.7 - Concrete Curing
6e7feb8e-f8a9-5cfa-9fa4-f8f20ae7e374 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | HOLD POINT
54050d33-e0d6-5404-905c-2e4719d4f5b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.8 - Type B Construction Joint
61d82ec4-2146-5a39-9df1-6e5d9851b3ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | 2.9 - Post Pour Inspection / Draw-in Measurement
f24dcce0-5436-572f-99c4-5e6e841c9ab5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 2.0 In Process Testing | HOLD POINT
d8e27a5c-a79b-59d0-92b2-59b05517d8f6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 3.0 Stessing Related Operations
b359ee38-6016-587d-ad71-db8dcf5154c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 3.0 Stessing Related Operations | 3.1 - Strand Positioning
0f4c484f-70bb-56ff-aa61-79c87aee3a5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 3.0 Stessing Related Operations | 3.2 - Stressing
f56d5ae7-291f-5f35-87cc-ddbbeea7644f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 3.0 Stessing Related Operations | HOLD POINT
1f71fb49-b2fc-567c-a611-d158b913c960 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 3.0 Stessing Related Operations | 3.3 - Stress Transfer
55eefcd6-ed65-53ba-938f-abb224eda9a5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 3.0 Stessing Related Operations | HOLD POINT
8c76c7b1-9546-549f-a5ef-7eac1ea86da3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 4.0 Final Documentation
b568e5c5-18de-58a4-b07d-2fdd7fbba35f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Precast Bridge Beams | HCB Final QA | ITP - Hollowcore Beam C10 | 4.0 Final Documentation | 4.2 - Producer Statement (PS3)
8534dc3a-37a2-4438-b6bc-f1a18ef585fe |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs
203357ea-f223-43a6-a343-43c332f7a76d |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A
87525d05-1977-4e46-8e17-45faa8a9ce8d |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D
d07a8ef4-647a-5cd4-bb66-5da144e472d8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
00e0fcc8-8f32-5d2a-8b08-d55152ec0fb8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
5025e4c0-0745-5207-a606-d56bed3d85d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
2e0b5e0e-e99c-5852-b1cb-bbbe81da9e95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
3a25feb4-d2c5-5eaf-86fc-606fcad91be4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
b3d06d16-ebc5-53a1-a7df-619e7ccdeca2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
d3d6694c-9d21-575d-8fe4-d8200ac2f148 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
610818c6-db81-50a9-80ec-79be32b0cd05 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
42392d9c-1742-53c5-8ad8-9ff86aff1c07 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
925630a2-e68d-5d60-988e-61cb78c5b869 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
fe9e951d-4983-5505-bcbb-d2417a385bbe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
700bf9fa-f4f2-5125-8c87-34f4dc2e3f40 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
d9195789-f3fa-512d-a9b6-ca16ff299390 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
52b68d43-936d-55d2-aba9-a735fec7d50b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
ab92ac51-98a0-570d-966e-14eb534c6afa |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
089e8800-2c08-53a8-a7a6-83d14f129d08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
cdd38615-2c9e-5ea6-b0b1-c2b2a582e28d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
60acf47f-6f57-504d-bc20-9f6ba4bc7594 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
c276fb59-dfc6-5cfe-a77f-afbc5139a591 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
057b1b62-a12b-5933-950a-e34e6557931c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
b5cf68b5-2a7f-59b2-a7d4-04e00ea64977 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
6d926a0e-0415-54f1-ab7c-6fdaddbbd116 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
5897ff11-2040-5eeb-af5c-0d88972f6368 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
ed6e56be-96d7-5b89-a8ad-e9bc41007a51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
26acefb2-ecaa-5933-8e2a-b74fdfd5b8d6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
e6241b14-0f63-5197-92d4-40f9af4ae232 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
8055ff89-6b0a-5977-8229-e896a7383392 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
701c9814-a11a-569d-9049-133ec183a3aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
01608de3-e0f4-5cb5-adae-9999e48bd266 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
df21e799-f9b9-55a2-8f26-24876d11b9bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
3397597b-cc35-50af-94ba-f12610b29332 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
07f068ce-1a04-5ca5-9825-86c5f4ab0bcf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
3b9429d8-043c-552e-ad49-ce4325ad5565 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
a99a6ecb-78ff-5851-9125-855ee364c996 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
d1484ced-f3d8-52ba-9d45-7626e56fb755 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
252e856e-faca-52c1-94ca-34942fe7d04a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
c95de559-180b-530e-a03a-a82e6f78f6f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
8984c267-f7fa-56f8-be60-696c8f8ff73c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
28a3b511-038c-50b1-b821-912cbbd3ed5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
f131eff7-a899-5409-bd03-23f93656094c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
dd041052-06e4-59b8-b120-8ab228ab5ecb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
acaa2aa4-10af-5736-a800-6d4af418c083 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
2d4d0a28-eaf8-5ab9-b63e-907d7bd9ff75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
c9ba0294-3ecf-5c7b-9063-505c80de083e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
db0678fe-a478-5dfa-8e85-cf33304f8973 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
1cc25339-d9e4-5d5d-965d-e187a736c322 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
491b8650-61fe-55f1-b064-d6bb7018c64d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
5f7cf07f-0e3b-5bae-bd68-734be07dc6d8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
62115b83-b89f-507f-ab24-4da5214f19d6 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
eaffea3c-3782-5c84-9165-c81e6bfcc7c5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
971d34fb-7ce8-52cf-9d55-5fb1614b5c1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
86e9acce-0c91-5d54-8eb0-09ad71459552 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
54cc1dba-110d-588b-a7a1-1e44c80d5200 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
0e5ede69-3b7b-5d61-aa27-bc36b74fae0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
4d477144-6701-4902-9d2f-47f1052f8ecf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a724ea2d-3b8a-5e20-b247-c237ef413eb9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
9f721603-50f2-45bf-b4bd-eec7f56134dd |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D
cc2e48ae-ecd8-431b-8a87-3dace04247da |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D
989d78db-129b-5f73-b564-0c7ec1d7a758 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
07297985-48b6-5f38-9855-7e3dc2139797 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
4eedee06-7b69-55d2-9450-8111a10ac182 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
8fb86636-37de-51f4-90b1-f02e676c0735 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
ee7e729b-11d0-5485-afc5-c5bea851a92d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
ae1eeaeb-f275-5c0e-b910-2bc412a2b6db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
7b9b3037-c844-594f-aaa5-1c095b42febc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
a8cf0476-5da2-58aa-8b23-d0992d2cf7a5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
9b2a49af-6161-5598-a8a2-ce76df580d4a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
89dd8ae8-f7c7-5a1e-b26d-c1db26ad7492 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
916c2619-7f25-5f11-8c3b-08795f2b4185 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
c649259b-6b6e-584b-a003-02f7a2a12b1d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
487fe0d2-0637-5388-a350-8808da04dd7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
e5c59e16-366e-5719-9046-01f0dc2c3475 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
646b96a7-f838-501a-9303-8e2e247da077 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
26d334c3-e541-5e19-9cc0-36c192f52873 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
8af4a962-7101-5a79-9f83-70575c01620f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
dd1854ec-5de9-5e06-bf29-e9a6f2a3477a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
89b19468-bd3e-5da9-a950-b2ef6c744706 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
6fa63795-b9d8-5e55-a663-6aec3ab6c13e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
4c3a5ab9-9975-56e3-b1f3-1ed9ad65e86f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
524c848b-5366-56fa-bddd-fe2a795d9da4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
88651f30-9273-56e8-8b0f-0d5921e6941d |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
a1e6074e-0297-56c1-a8c2-21a7e12a2909 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
8707003e-3193-5b57-ae18-da85bcce85d7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
77d203a4-9a29-53eb-a8f5-cf68d010bb2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
44df272a-4c3d-55a2-a5c4-9c09d1fac859 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
6906f5e4-6798-5f8b-8295-4063e4eb88f5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
c62646ae-08c6-59df-bb35-dceef0cec54a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
35caeb2a-3951-5ebf-be8c-d2888d98f2e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
fc100488-9860-5a91-ad3f-0763fd1b95db |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
6b39604f-f30e-519e-a707-765b34e878c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
a4bc19c0-7758-5664-bef4-a07af4d6f359 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
b33d5e8b-e117-50fa-aa62-9f218c9f88a9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
61b7b203-d3ac-53cc-9b43-382ab6b10964 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
210bb2f8-183f-5fa9-a398-b69b69d762f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
94b4b318-f873-5f25-a7f2-2e15388d65af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
a1da9490-e0f9-5832-a947-e062aadb1489 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
194f1daa-5e5f-56e8-a368-33ac4bc540ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
427eb2a1-7f7e-5cd7-a6bd-6d37c9f0b340 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
21f8f4cd-2dc6-5438-9156-1a58d7450cac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
81a45a67-c9c8-5eea-8e4e-f16a1178c34f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
2c71dcc8-d29f-580a-8b8a-7f0b482451c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
0e312745-a49e-58d5-9b9e-ca61a9b441e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
193e72fc-7238-5a1b-b310-160e314eeebc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
6420015e-d6c6-505c-87e6-068cfbe8b3d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
f1ff2a85-836d-5045-a352-499d5fd28b89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
8967c60a-b626-5f8d-b977-18c30206953b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
36bbcd06-0857-5864-84a0-0387e8f2ef2f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
7ef12213-d489-5f25-976e-c098d7e90516 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
8d6d9ca7-f795-5b03-84f1-7e5ae44897ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
7b1dfe2e-9913-50fd-b7e0-f975ea8ed132 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
8097b2b3-3e0e-5579-8106-5f57b7bd5832 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
8839e4e2-a3dd-5df0-9f89-1db545d2ac0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
ecced18b-c414-4e57-9f2b-6a1c1d65ad30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
09cf4295-3111-5f1a-84b4-d4dfcfd49a5a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Settlement Slabs | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
e5c0f848-922c-47d3-8a3d-ffd1ecea2695 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead
2d3cb95e-fb00-40f6-8f88-a28e79cce669 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D)
d9e11c93-21f3-55f7-a270-1c733fcbb5c5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
cdcd2b08-794f-55c2-b136-f9943ef3b6ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
5e70366e-c128-5e82-939d-906efa8c8292 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
5839827e-3551-5f7d-9212-cd1f625bea36 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
4591e2b5-16e3-5db2-81d7-371e3d714785 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
8df76717-5ece-5ddf-8a23-eddd5150e7c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
3624fdb8-fddf-5b5c-8889-95f4a62c3626 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
6326de97-e747-533e-bde8-9ec19404bc9b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
8e1a0d0a-0055-57c7-b880-6f17a9491470 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
2e1f92ad-620b-5010-8166-33d2a2184a9a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
f65e5408-1529-566a-ac9d-763e0cd7aa20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
104fb77e-1221-5f92-bd58-1a7b91476472 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
1ffc139f-436e-5635-b225-ee2ee658133d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
3bca90a4-aac4-5f93-bc26-7390ab2e7e67 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
a9ca39f4-d0b1-5cbe-a03e-53b8e6892f4b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
d514b7e3-cf29-52e2-8790-56aeba14db35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
47d7e927-0899-50c4-9e25-4de244bc154b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
633dca6c-03c0-54d8-a215-e75f9ada55ea |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
6e491e9a-e915-5c20-9a7a-31b2af27c291 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
20fc15f8-4205-5343-8861-150fa6d39285 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
d6af6336-4a92-54a0-8f4b-8b0133f02984 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
dd129b27-de22-5777-b1e4-41219d5f05b5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
aa7a0469-cbfb-5745-a574-856436c1a654 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
ff14eb7e-57e6-5715-ab04-db7b2d8296d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
a05e14b4-f8ef-55e2-a17f-9440d8c28ee6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
f0de9ff0-54d5-5629-a1a7-f4abd5d57317 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
f96a88b9-ef59-59ea-bc39-44c23ba2a2a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
0cf64afc-6792-59b8-ac22-6d8be732e3c0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
555e8cb2-6f94-5a28-83b9-a2c95fd90d48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
73ef0cfb-afac-5eaf-a868-68aeb2fbdd93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
54d92cc0-2470-537d-902c-8185fc6ed762 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
a2515cc1-29c1-5fe3-a1bf-65b367b5b97d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
2cd7ee98-abff-5773-828f-6f059ccc719c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
f7adb895-4752-5153-b13c-471b27843b3c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
51a90e38-5426-5473-8c1d-b59d05fd925a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
f6f76d8e-2045-5573-9952-d40aa458e6a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
878b0d94-d245-502a-b2f7-f376c661c87a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
1e4bd9f0-0a09-552a-a86a-c31a12d418d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
5b9c6595-5470-55a7-b78e-ce9b78b8f927 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
03ee4e3c-c93b-5505-b3d1-b800607d0422 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
eb7bd3ce-3e96-5cda-af77-2813719bd56b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
7b7fc131-9792-52ab-863c-1978375a3c11 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
f6d11e54-a366-5824-a1ac-718c3e7888af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
a3311b35-a4fe-592c-9168-beee026452e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
eb9ad391-a9af-5981-a28f-190d12763f54 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
cb122472-7566-509e-b869-f0cb5eaa0b1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
08e2ce0d-d650-5ae1-9ab6-2a0379bc80f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
c7642dc2-a9ab-5774-808d-a03f287314dd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
3772095c-f727-59ad-88af-0f93ed44dc56 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
7fd453f5-a0ad-5d3b-ae1a-b74bace16b9a |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
612cfa43-807c-56f6-878e-53bc4c7dc303 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
adc4e346-0dc7-5171-a442-a8d997d400e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
7de29081-957e-5ca7-90e6-7e4021ca7f7b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
006d2994-a124-5e3d-886d-b87407101d8e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
591ae0e3-f2fa-414d-9361-d4bdb1e15e18 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
6c2434f5-1787-51ee-bff6-857f6721d88a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 1st Pour (ABT D & Span C-D) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
b8542010-293b-4622-86af-50cbf08539e1 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC)
c1a6910e-84f1-571f-96d1-ad18f17e7ae7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
a30eb086-e03f-5f1c-9802-662dcf7bae62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
021178b7-9aab-5e79-82cb-3cd7130d44d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
524b68ba-d809-58c7-830b-33f0350e7036 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
32dbf604-350c-5d93-bfc9-e5d71133b396 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
063f2852-e666-5e1e-8a88-4feb936f855e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
d2498193-fbbb-5a12-84fc-9f159ebb4d88 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
8099dce7-a3e1-5bf2-a4e8-0fb4593a9c41 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
0801939d-8084-5162-a989-0f3377f38000 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
60527c17-5f8e-5c71-bc16-debb27560cb7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
8fc94bc6-50bd-5bfb-8837-8b5da135a2e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
80ca34d5-7a36-5729-8987-74490ca37306 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
8a5c9244-5482-5d0f-9ebb-d10a9eaa9113 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
725fe9d6-c6a5-5800-93f9-d0c58900c63f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
cd962086-bd2f-561c-9644-fb882eaa042d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
cbfbf446-6909-5066-b461-eb41a3a60751 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
faac0c96-5333-59ac-82f9-5ebb6b52d833 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
ecadb2da-f67a-5e4e-a5cf-66f383b772a0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
6819f40b-1638-5487-89fc-f80a6c098830 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
057b2c11-fcfd-59ce-8199-d8ee3edd49ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
dd833b48-aac3-5ceb-a528-33310fbcd694 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
4555270f-7803-5357-8df4-fb5db61c4657 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
17d2c3a5-0f9a-5219-a5e2-393ba84e92c9 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
7e113f44-a035-5f8f-834d-eb492f4a0a9a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
4d6c11e2-5df6-52a5-942f-10a1fb1e5556 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
f0e7e069-42c0-5f77-885a-5c097f7f7feb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
0c88db9a-65da-5873-b365-bf83e3e8f5a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
bc82e7e9-4a10-512c-a5e3-07826078f67f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
ccac94c7-aa33-54eb-a6eb-d6db8b657761 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
c0ae6dc3-c83f-5aab-9c5e-bd8da1501919 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
b774282c-6418-5806-88f7-bf9251667a52 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
971fa887-59bd-55cf-a988-c690ced4f030 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
dfb6f999-d2b9-582a-852c-b03fdaf95354 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
4ef954fa-f517-5881-b2d0-7cc7a38645e7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
1c034b72-b644-5124-b4d3-d19275044419 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
1dad7c01-412d-53d9-9e4e-7bd23ee2660e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
b3739c7e-13e5-565e-9ecb-02178543bb7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
35b8a643-996a-5b8e-8b0b-bd8bbdc26184 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
318c0b9e-348b-5c84-9a32-ca0bee419820 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
58e83d99-6411-580d-9694-cbe2e9ca4fd9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
e68638f4-343e-5004-ab1b-b131694a3c42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
fd99fcdb-b4d6-526a-9ac7-d5ac765aee8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
3e31ccb0-d861-5663-90c2-d0a57928ffb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
7fc2b55c-387b-5e0e-9b20-54ee24cb5d38 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
6f3bda3a-1a1b-560a-8545-863df0aded43 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
5b07927b-33c0-534d-bf6d-539fc3e382cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
23d4bd57-e186-503c-b4aa-925e9adfd34c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
f3305fde-1a2d-5236-bb21-53bfcd18b7d9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
816034c4-0823-5d74-9f0d-8363752af35f |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
a540d481-13bd-5f5e-98c0-6c85bb6385a6 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
768436cf-220e-56d9-bba5-988934c2d805 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
c262e497-865d-5f6b-9470-d77f760d2c1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
e2c2f7a5-03be-521f-a4f2-7902cdfabbaf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
eec9e7d7-5f35-5499-a3a8-070055733997 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
223c5b48-536e-404f-a0e1-4935663aa403 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9e033d1e-40f3-57d6-a20a-091a679370a8 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 2nd Pour (Pier C & Span BC) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
24ecf046-0fb8-42b8-bef8-a5879f698804 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB)
a4e1ae2b-26ae-50a5-bd1c-5a849602ff6f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
2daa830d-7294-51e4-a2dc-d484927a0b09 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
8807cd27-9faa-566b-bced-21c3b3d0a75f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
50bec0aa-bd3d-51a0-a85d-78f5783c0c91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
9af761f5-c2bc-5382-b190-92c46370e93b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
2dd8662c-2b48-5cef-a145-2db75437ca2b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
0647ccf4-b6b3-5cc7-98ae-b4d60bd2c4d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
fdd3c382-1068-5fbc-b241-60bb68f4e841 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
1b446408-9e69-54e6-b4d9-5a0a092c5e7d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
13a8fcc2-8313-5401-bf0d-2cc8c3ee97ff |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
051421a9-2ab5-5267-976d-b2034e6270d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
02abadcb-73ac-5fe6-af89-477e824a2710 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
6e170d99-2c8f-5fa5-8d0b-546887b24f00 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
3aa20bbd-b831-5b52-bdaa-6efaa2f9a0bb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
fea993c1-048b-572f-9e31-09ec7ffd774f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
3a2bc20b-b0ed-5793-9302-526e1118aba7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
09c7808e-ebea-5e6d-b553-4617ec3b141d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
8ef0d329-a545-590c-b54f-db1a33df34cf |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
5a05247d-7a8d-5bca-98c4-a2754a9370d5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
caf9dbb9-6f58-5542-bcda-b0189c2b4740 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
eb7442e6-c66b-53b8-9ca5-c4f0beab6d44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
afacedb4-3418-5c27-8dd6-2b71db5dbebc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
e3c42f9d-95f1-57a4-b1ae-c5f5acf9a7f4 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
d207afed-da4b-577a-87d2-32837d343bda |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
ab9b6ac0-4d19-5a0d-b139-1303e64ea36d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
805f6ee9-1531-5010-98bb-2aa39f70ef5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
16313404-d5a3-50e8-8eb4-3c4463944b47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
a03ef1c0-381a-5ebc-b970-455d7804f475 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
aa14fbe7-d1f0-5349-b298-93ee85e2fee7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
039c7761-fabf-5216-b801-81171315e7ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
e92fecdc-cbfc-54c1-a25c-a88a701e6b3d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
9080a00b-d475-5f56-87e6-d99d89114a10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
07406aba-ec60-56f5-9cbf-da43846d1c40 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
40559b2e-b6fa-5c79-aca5-c4b8e33e0f61 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
476b431f-21da-55a1-aefa-9841628c4f72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
cf1a9ce4-20bd-52af-8527-a5b2e9de5cbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
c2d6c58f-70f3-5619-9f4a-197b16e2686e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
6d693954-6e90-5fe9-89b6-7cb7b9069935 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
12049aa7-46fb-5728-a86b-ee8a384deb7c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
914d3962-d678-5f97-ac04-98aee7438859 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
951a6277-e1e0-5707-b048-24357466d840 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
347b27c3-b2e8-5f96-902f-03623ff98968 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
b19db12b-d967-5ae3-ade4-950389d0d151 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
724a670c-8b37-5472-8d49-2eecba29fe90 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
10fb5675-e61e-553d-960f-b7f1f62298a5 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
1c3a6f3f-d2f2-51ae-95b9-303da6bb84ed |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
fe71c10c-f8a3-58fc-8194-462b56d27bc6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
3ff83da7-05dd-5fdc-8623-b2f74f30b15f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
5cc5819f-025b-5174-bbaf-f728b80cd1f4 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
a36ed614-7c2a-582a-826d-ed8b0c8794bd |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
5c6ed1df-89c1-5271-a3d5-fe9349e398dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
ad2ca53a-e942-5897-86d4-a6d1eb78ecd3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
71011eb7-9de8-5d6a-b80c-78691e27db7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
df3f7d6b-44e0-504f-ba01-bb4c1ba0948a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
685bf30f-a652-406a-9282-af4e52a00ed5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
59ae2b64-f622-5a60-9c45-dbb9ca6ce257 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 3rd Pour (Pier B & Span AB) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
d3c86334-7c71-49c1-bd7f-d94dd1b3eb40 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining)
526e2f82-5919-55cf-8545-1582d8a5170d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
2b276662-5dc1-58da-96de-3d2faad22180 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
783aeb54-fd52-5270-adf9-3c69cc1abbd5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
35c0dd3d-08ca-5849-8038-9500438480d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
6a88408e-b0de-5f23-9b77-913b6391cc98 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
34d0a0d9-cee2-5f8a-b567-e2789801f7cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
ce060031-433f-5475-bd70-766b3a994268 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
eced8564-05c7-594d-92eb-db164a6097eb |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
e4ecdce9-bac9-5fdf-aa1c-030f9f12032e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
ee8f9e2b-49e1-5049-89ed-0fa6facffdb0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
7eb4a1d5-7add-5556-a830-03ec4a1cc004 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
d2dd3470-a026-59ca-b435-f1ea0522dbb4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
a46c400c-9fb7-5ace-a758-c9d67f2d3d78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
71bb0258-7799-5378-840c-4060f8035952 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
6733e58b-9e33-537b-9da9-5caecb8c9d3a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
4de1cb13-9cb8-5027-9059-de14e9cb836a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
63200d32-4f4c-5ed1-b2b0-b2dd3637ae0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
163a08b3-a09b-5e57-a63c-ad9bfeae1072 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
7cd9dcea-db07-5485-87c6-b66f3e756c05 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
acb0196f-4d5d-54d6-99fe-d4423b2b3e87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
2fb2e017-4536-5784-9268-b06e4e495268 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
ed19c75b-14ec-5ad1-a0c4-74a42e66ce8c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
ca8dfbea-9792-585a-b1a4-e7b592227ad0 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
399a9ab6-b8bd-58cd-bf02-6e739106f3de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
7a17c491-ff38-572b-af18-03932c0a3424 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
d8ac04a9-489b-547a-a30c-13502c7b3daf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
6b82611d-0b94-552c-94b7-2fe8d8d830bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
84f5e85b-e960-5921-ba1f-4495893e70c5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
75bad27d-a61a-5b70-b5cc-c0aee0765d0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
8a17528f-8cfd-5ab0-bcf5-803c81609607 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
84b9e234-ced7-5ecb-88ba-cdd5d3917377 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
5e9ac984-b451-538d-9cd9-bce9b8d0c25b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
85082606-b81c-5aa4-9569-a5a3be17de39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
442b0195-59da-5528-962e-3fc0148f0b00 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
56402c0e-b92c-5283-9244-96e53319f01c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
2062f7f4-e247-51c5-88be-5acb5f5e3f11 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
5f99b908-11c4-55e2-8cd3-83136d5f9ccb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
628a6a0f-296a-5c35-ac62-5b32530e9694 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
b4dac635-aed1-51c8-b91b-16ab1ced2022 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
5ee45426-e378-5c10-808b-528c38f6f339 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
1b57c5d3-98f7-59b5-95cc-aaad38ba58ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
4618e3db-feb1-5061-acfc-cdefb9ff4857 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
854b65ab-2ba7-54a8-8631-ff7e1a30de13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
52ad20c4-5369-5cab-9b0b-0e19b6ba6b6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
55fc8e63-90e8-50f0-861a-1d856d7b4079 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
5625363b-b13c-5493-a13e-4def7ec6e3c4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
887902eb-ab6f-5b18-8d6b-4d8eac962c06 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
d030fe30-83b4-5490-a027-094f8ec7b83a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
35cfab2a-08c7-5825-9f2a-188b03fd5345 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
ea328e76-d8ef-5ad3-b236-ae6514a51991 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
d71d3ba0-767d-539e-a361-4e3d6d02b3be |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
3082669a-c69c-5a60-9a03-af936dffb698 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
9313f632-25db-53ce-8e9c-1d6b2aae1d01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
3ffab75b-b873-5e10-85d9-1d0a93958f38 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
72c07097-0818-4b42-881c-e1552dd2a2e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
84680f03-81f5-5161-a3ce-e9f57967a2d5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | Insitu Concrete 4th Pour (ABT A & Span AB remaining) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
7597326f-a882-4397-9f49-7e2887df245e |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels
3d94aa9f-ad9b-54c3-ad7c-f5f217154432 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
4dcd1835-4eda-58f0-9c28-3bb976e7cd7b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
cb85d916-1874-50ca-a539-6349cd2b0112 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
711ecf15-5550-5f82-94fc-01809cde672a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
85788466-3026-5dae-a09e-d5b76606337f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
92047344-ecb3-552d-8257-14a0c3a35697 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
a1fe36ec-1f35-504c-abf4-eee89bab97b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
4d397edc-2f48-5dda-9cdd-c52700784893 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
b35d8a94-c6ef-5bbc-be5b-62cce79b0b92 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
47ab25bd-2e94-5561-b1ec-ad3f34d46697 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
f3b15184-7867-5a81-892f-ff93ebfaf66a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
dbe38d88-7cfa-55a4-a7de-1c1f602a242e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
460b6352-d18b-532c-99be-78615486f1b5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
cf7f751b-bd70-5b06-9662-c62f98585d0d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
b13983f2-304d-53e2-89ca-033751112c56 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
41be8a25-df17-52cd-9c67-54bc05257f32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
90a1d000-8a30-5970-b4c4-9f0706177254 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
50f0b5c8-0649-579e-9c4e-1a2aa44bfe6a |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
dba14be1-617b-5e99-aa0f-96d4efb9c895 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
3b4abb50-561f-53eb-89d0-7a93f5b0ac96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
c1e85d1d-0b0a-5dae-900e-925cdc65fef8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
3d614d6e-d8ff-5855-bbf4-9780a956fb2e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
0e76ad48-c828-5ba4-bb55-ba4144f76fa8 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
216356ed-db82-54a1-9f41-06529b4d452e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
a6c5f010-ec6d-56cf-adef-fa9d1760c4ef |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
035eb894-0b65-5f70-84f8-b77096b167ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
1076c24b-1961-5655-845f-2fec42b62b0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
5e379744-4103-59e0-9299-1cc10e678648 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
bf6c5a78-f700-53e2-8e25-003c6217f13d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
5f4117db-00f8-55e2-9b53-9ab14d338610 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
8638df18-1ab9-5cd8-a630-b931a3a72f6e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
cf273ff8-afaf-590d-9667-f29996f0454d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
6944a126-e018-5052-a8de-8811404fca97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
f84a108e-e3fe-53f2-8ab9-fe75e40a53a2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
ee6a4579-0460-54ea-83b8-a0c4d66cd994 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
010cd184-5168-5c05-9534-cbf80f4ab1bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
13a9fec8-afd4-5af6-971a-a95a628fdfff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
5f93c5c2-82d5-571a-ad0b-1cffaa039690 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
2d484126-add5-5c96-9a24-822973b78ff3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
4d9c7b09-871a-5fdc-a55d-49a22ea62c36 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
f3698e31-8202-5468-bf32-677c45035be4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
249e3dc1-1ff6-521e-848b-f0745b8140e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
2fa37804-c236-504e-aaca-9b897d63eb5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
3f03db54-0dca-5f74-8b6a-bc1fdda16ef3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
4f162379-b4bd-5ea9-90b8-e9788175f59d |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
15e19278-1125-5238-8e74-8b451238c0a7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
fefb0d49-2bbb-5581-8dad-6c3562434ffe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
7b66c2c0-e42b-50d3-a4b6-569c321b3302 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
aa7dedfd-cdfa-5876-ae3d-828fbd4cd936 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
c79a17c1-3348-5a63-85a0-e8bd304a00dd |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
6fc7570e-0a58-55d1-9870-10a0352c0c20 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
4c9622db-2ca7-5c59-80dc-ece34fe23d39 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
02063288-4618-5a57-96cf-dee72c60b562 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
8f40a833-a9d8-5510-95f3-a562db0f2363 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
bb8466c1-6b2d-4777-b8e1-e07e7a50b20a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
bef1a5f1-9f58-59f3-85b5-c4df4d6b412c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Deck & Crosshead | EGB Pier B & Pier C Light Corbels | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
272e075e-3c7f-4c05-8172-47e225660a8d |  | fail |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers
09e3673a-4213-465e-8378-dc6ac312a168 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection
ac0cd366-315a-4fb6-a0c6-4f5ed9667275 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02
32ec6301-7949-5f3a-bac9-f3e82a278f98 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Preliminary
b80dd049-b6ce-55d2-8d41-1b2b9559ad0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Preliminary | Engineer notified of pour
7f4f1591-c6a3-59c7-8964-25ba522a50db |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork
da1273a2-80da-5fef-9ae9-74a170c74ac3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Installed as per formwork design
b7b57415-999b-57f3-b180-552d0163addc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Permit to load issued
65c6e396-403b-5a80-9199-b8517d150991 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Dimensions correct
ae638e1a-809c-5efb-9dfe-af40abc083b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Position and orientation correct
ce7b4681-a4b2-5503-bcb8-325264931faf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Forms vertical, plumb and true
319dcee7-3f9d-554c-a363-be0d2689d4f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Forms coated with release agent
f45f9521-598e-5ef0-a34c-55f29dd76160 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Forms clean and clear of debris
42645155-24d3-5cce-9668-22bc790318e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Joints sealed
60bfcea3-dbda-528c-9fb2-540d449a9d8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Formwork | Pour level marks
1107c479-98fe-5ae9-a004-26b2befe3abb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement
ff8f0360-f52a-58d8-87ad-b99fa9128f53 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Correct grade reinforcement
9d1b2072-48bb-5368-b29f-ac045b445bbe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Correct bar size
4a187627-8a63-5265-9d2d-de931162a017 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Correct number of bars
88c1c798-bb84-590a-9d4f-45bd1f2ae8a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Correct spacing
f7cc3e94-f944-5e90-a533-bbaaf5a6d47e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Starters bars included
5a79393e-8bd2-50ee-8999-2e18b3772e80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
0f9790d7-312f-5ff8-8804-26e3ebdc0110 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
7af624c6-d175-5ba1-9593-2d1c75cb3ed6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
8c556b40-e478-520b-ba3f-1048b65b4989 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Correct lap position (staggered appropriately)
767cb2d1-3838-5925-8657-c2dcd6dfa7e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
282d8139-8476-5ff6-8db7-88bbc22aa130 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
025cbd71-bd94-51ae-bef3-763405472619 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Reinforcing adequately tied
1b434d0d-2775-59ad-afd8-af752f55fd76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Reinforcement | Chairs or spacers fixed in place
90d1d217-304b-5342-8123-2e3d4766c775 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Embedded items
83356ba2-35a1-5cea-941b-6b83cf847c69 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Embedded items | Block-outs, ducts & cast in items installed
ed5608b6-f489-5abf-ba0e-1a9694fab7c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Embedded items | Correct position, level & alignment
34652dd5-63de-541c-8253-1fc3f71b95e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Embedded items | Securely fixed in place
9f35b8fb-b87a-538c-9a81-fd784b939170 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Construction Joints
ceaab472-8c99-597e-9517-519479bb7332 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Construction Joints | Correct location
286b5ef8-4afc-561f-b598-ca869e029f91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Construction Joints | Adequately prepped
d4bc96e7-7940-506c-9f27-0f618e1d0103 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-02 | Construction Joints | Joint board installed
cc8c4ebd-8694-44c4-960b-c29a35a1e1d8 |  | work-in-progress | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03
877ba77d-5d33-5819-94e9-4ac294c98305 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Preliminary
de7d9e84-e47e-5c1b-9007-b6629560b4b4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Preliminary | Engineer notified of pour
386d6ff3-4822-5bb3-bc86-9517da83a07d |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork
1a906c87-aba2-59f2-b77a-512e50dd959b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Installed as per formwork design
59d7f532-3283-5573-8b81-7568f6fd5f43 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Permit to load issued
436ae035-e421-53c2-9428-feb08bc6ffc0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Dimensions correct
7aa33f9e-28ce-573e-9894-7233dbcb3292 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Position and orientation correct
5a682420-677e-5466-af52-26b5a8d02d68 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Forms vertical, plumb and true
75f2db57-4428-5a97-b07d-45fae0fc3362 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Forms coated with release agent
8b978777-073a-52dc-83e1-1dde55024b29 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Forms clean and clear of debris
f2037941-2e1e-5924-9c06-5572e04357da |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Joints sealed
33267d4e-c473-54c9-baf3-5683f5654d94 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Formwork | Pour level marks
fd2727ff-d33c-54dd-b242-43e989921292 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement
1055f647-75f0-505f-af54-66a5de043cf8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Correct grade reinforcement
5300b21c-d7bd-5dd1-b16c-10525c4fdd9f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Correct bar size
4f96cdd2-a3c4-5674-8294-4ba971b107cd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Correct number of bars
aee8a5eb-ef96-5867-b0b1-75db15619b9e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Correct spacing
5583f809-f04e-52e5-aa9f-0e525d4a7772 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Starters bars included
aa63e097-9c98-5c40-9910-605b101a6227 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
43af32e5-bf5c-5cdf-8389-7d94cec317da |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
76c5d678-cc72-5fd1-bd6a-27301cf2797f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
b4b98f45-fa46-524a-bafe-293de69891c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Correct lap position (staggered appropriately)
d8986f63-2d45-5acd-bb5a-17877fa5c9dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
247dcb5e-0a06-5f1b-b4bc-51ef6f51a146 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
1a22994c-95dd-5241-a40d-16f37854dffc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Reinforcing adequately tied
3d9d6cac-a95d-577c-91a4-22cf3ece3e6c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Reinforcement | Chairs or spacers fixed in place
5e4f3083-f407-5afb-a230-87eb7200dd7d |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Embedded items
8ecd4e2c-a3c8-5e93-b6db-2086350c1f6f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Embedded items | Block-outs, ducts & cast in items installed
2c1f308c-9808-5a4a-9fbc-9a0ffc7be810 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Embedded items | Correct position, level & alignment
ef3c8607-cdc3-5907-9bf1-c4ba17894ddd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Embedded items | Securely fixed in place
715b8c20-9384-5a69-bceb-b556d1cbf1e2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Construction Joints
30b45ef5-1ce2-5f22-b59a-67000504bcf1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Construction Joints | Correct location
f2a4259e-d731-5e36-a1b0-fbd96de7ef48 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Construction Joints | Adequately prepped
45f8a76e-29c9-5707-a9f8-9032bd15491f |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-03 | Construction Joints | Joint board installed
edc4c8c7-b7e0-4215-8e82-043ac3b7b276 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04
6c22cd17-3231-55d0-9589-dd4faa98d2bb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Preliminary
a00ddd28-99ec-5959-88c5-4b07fab5e471 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Preliminary | Engineer notified of pour
38bce069-2e06-5602-8ab2-8c4c42e33aa3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork
8903f7c7-4a84-5eb1-ae51-cb6ffcc0775a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Installed as per formwork design
ee5d54f7-5b4b-5d0f-8cb0-524964bbb7f0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Permit to load issued
48ea02c9-ebc3-56d6-8c7d-d0d59ccca641 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Dimensions correct
20397312-7d59-5e59-8a2f-2651dccd4914 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Position and orientation correct
1a87e8f8-9a6c-5a1f-94e4-a706bfb054dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Forms vertical, plumb and true
4256b8e3-888a-5f31-bdf7-d7d59c0d7123 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Forms coated with release agent
ef0d2a67-3f87-5690-b5af-fd2d8eef4f06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Forms clean and clear of debris
aaf57fa1-b9bc-55e1-a510-fd725c6797a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Joints sealed
a2519b18-51ac-5c58-94f7-3126d0254a2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Formwork | Pour level marks
300caa7e-fc97-5167-b659-cc057910c5e7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement
72f85402-b33f-5ed2-8529-0e47b3bb5c4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Correct grade reinforcement
52a36374-edb3-5236-8b2c-7e445ce0093d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Correct bar size
8e10a47e-32bf-5836-876b-826f1b176667 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Correct number of bars
44c0a9e5-300d-5180-8a9b-bad97c41d88d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Correct spacing
dfbdaaeb-83ad-52f4-bb27-4cd912a35317 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Starters bars included
1051e8c2-e3d8-5333-b644-7838c8d823de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
2aad31df-3d48-5ffa-97e8-0b8b173c98a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
42f09daf-36e3-5f64-b836-fb2af864e7e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
d04057e3-f710-5b6b-bfba-fc71eaae6638 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Correct lap position (staggered appropriately)
f028b9d9-dd56-5bb7-b4a7-402e1dff8341 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
8667ff16-a4d7-5e58-92dd-734859d582a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
d60897ea-2b70-5e8c-8584-83c2a8ff4bec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Reinforcing adequately tied
bbebf2a9-b355-5e89-b7d8-a8e424f3435e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Reinforcement | Chairs or spacers fixed in place
359f4e44-831d-52ee-847b-a43c2e5b899b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Embedded items
86aa7b35-d7c6-5480-a0ca-8424d8f2fe47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Embedded items | Block-outs, ducts & cast in items installed
4fbc30a0-72a9-5150-bbda-28d48834fcbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Embedded items | Correct position, level & alignment
77d37ca3-ec1e-5c4b-b71e-d4f5753b4f84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Embedded items | Securely fixed in place
e443bb56-a170-569b-9bb5-2f0b385f0ed0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Construction Joints
c1b71978-313e-51c3-80f4-8bec8e8f1fa5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Construction Joints | Correct location
13598ea7-2110-56df-bd20-dda0722c9149 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Construction Joints | Adequately prepped
8f3b6d36-4116-5d33-bbb0-8f556d253862 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-04 | Construction Joints | Joint board installed
3d2e123d-83c4-4265-a348-1ad44eefc739 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05
7f616fd6-1e21-55b3-8c59-4ae8d45b14de |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Preliminary
4f39f1a4-61bf-546e-9089-4e87f749fa58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Preliminary | Engineer notified of pour
e15c7886-a85b-5c6d-8d00-8dd7d3d18852 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork
a5b724d4-6108-5d0b-9092-88e1dd3971e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Installed as per formwork design
217323ac-7b71-54d4-9d78-481f5c47209f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Permit to load issued
d3ddc5bb-7e29-5ae8-ade5-31f473c0a9d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Dimensions correct
7514ad67-86d8-56bf-8407-ec1a5300293c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Position and orientation correct
74f02219-ad4a-528f-877a-b2d5598f8020 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Forms vertical, plumb and true
50b2202e-6f75-5813-9d9c-a78efae25d24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Forms coated with release agent
17b0d9c9-bf02-52f2-9963-ee0af3514698 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Forms clean and clear of debris
f08fc9ae-e003-5313-94d2-0387f3d14b7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Joints sealed
66501eb4-ddb1-5bae-aa9c-5e6b636e325b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Formwork | Pour level marks
3e80f1f2-e21e-5d21-93a5-60c6074763e1 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement
e4de12b6-c165-5e46-b37c-3b987da6823f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Correct grade reinforcement
73143dd1-d4fd-5c45-9086-b32aec004691 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Correct bar size
bb085209-b787-5f00-b4a2-e80ec794b0b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Correct number of bars
48d53a31-4036-5275-a04a-2b217a163053 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Correct spacing
f8e7f361-298f-522f-a0be-fd88fd89ddc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Starters bars included
1a626803-1fe7-570a-b966-7fd232f325bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
06aa2eee-eb3a-527c-bda2-76604ba9e386 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
7f25ba80-0ee6-5431-8b6e-42881548739c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
5166f139-0a0b-564a-b91c-2686ae4d5eb0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Correct lap position (staggered appropriately)
e98c6c81-db58-518c-8fbb-4a089dab3b08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
f7053049-bd75-5807-b908-1fc87c75fa1d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
168bd72f-f9ad-5097-b730-090fca326a9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Reinforcing adequately tied
602dc0e9-e92e-5c25-8081-58e1cea1e55f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Reinforcement | Chairs or spacers fixed in place
7865356a-78ae-5ef4-8cf5-fc6ecbd755dc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Embedded items
f771e168-5b81-5fc8-b63a-e6b0b6dbb1a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Embedded items | Block-outs, ducts & cast in items installed
eabb869e-c869-5f30-bd9c-471d40d5cfbe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Embedded items | Correct position, level & alignment
78261e27-be7c-555b-9385-4e4183e998c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Embedded items | Securely fixed in place
35742604-a8e7-5fc0-958e-488c0845a667 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Construction Joints
6bf05a54-645e-5587-b4a8-44ca63bf6035 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Construction Joints | Correct location
45fef638-a109-56b1-aadb-7832943fc0f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Construction Joints | Adequately prepped
2438cd61-cf4b-5777-b302-23d7ee96b631 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-05 | Construction Joints | Joint board installed
3e373bb0-a7a9-46e4-aba5-e7dc0b384b9e |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06
4854ceec-e858-5f9f-8308-3c8e7fcf3779 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Preliminary
0e7ece44-b278-5457-8d4f-19d0c948e144 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Preliminary | Engineer notified of pour
8ec1686a-32b2-542e-8b95-4c5ca0a2410d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork
e3e55f11-4379-59c2-9fe9-469934d27f63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Installed as per formwork design
64f2289c-79c5-5b48-b713-3620126ec09f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Permit to load issued
20be1df9-96f3-56c5-8948-9a3b5b006308 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Dimensions correct
ac501051-936d-53ff-87e9-a98d87c988be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Position and orientation correct
99019549-5cfd-50a7-8d9c-370260f83a90 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Forms vertical, plumb and true
115fc21a-46b4-5d50-90db-3208bab20312 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Forms coated with release agent
72324f4f-1c41-5348-8086-0a13fd29324b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Forms clean and clear of debris
3c5b4cc4-ddc9-5822-9578-74b30b75bdc8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Joints sealed
4c47b429-8636-5b4e-9758-ac72514c6804 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Formwork | Pour level marks
85433adf-d924-5923-aad9-50dbc4a0a30e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement
4bb5ce83-47b7-53de-8ef3-60a6cd49bcdf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Correct grade reinforcement
64f6e2da-2558-5024-ba09-1637d1850ec7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Correct bar size
1baee862-e9a3-52b0-bb3c-d2977c165cda |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Correct number of bars
a6fdc139-0dc9-53e6-8161-a886a0e9dd5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Correct spacing
fc130141-6dcc-541d-81d8-17af814b9767 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Starters bars included
42ae31bd-34fc-5b65-bf31-343683222882 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
d3101f69-eb30-5d73-a2ab-61f4b6c5fc5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
259e5d46-6e09-5711-ac06-81c5ae103301 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
af646c13-fee2-59b8-8745-f782795bf2f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Correct lap position (staggered appropriately)
74692338-3a40-5af6-bcde-bb0dfefc3ed7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
83d63f19-82a3-5782-a711-fc92ff592cfa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
359b94a8-40bf-5216-8da2-cee0c95724e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Reinforcing adequately tied
d1753709-a339-5037-8fcf-adb6230c9ebe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Reinforcement | Chairs or spacers fixed in place
d62f62e0-e50d-582e-b432-9d5633cbcf89 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Embedded items
b5549905-737a-5358-b0b4-55acd5fdfefd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Embedded items | Block-outs, ducts & cast in items installed
34756dbb-641a-5eb8-8564-c6939fdc3cbf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Embedded items | Correct position, level & alignment
514a4960-fd74-5510-add4-99e38455a006 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Embedded items | Securely fixed in place
4370f60f-33ba-512a-81f5-509c9d3d9537 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Construction Joints
44a95342-d1b1-5d92-a307-1e2d02ef7b39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Construction Joints | Correct location
314eb1c5-b875-5c32-ba08-c4de80aea005 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Construction Joints | Adequately prepped
92a9c5b3-680c-571d-b340-23b6cded2824 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-06 | Construction Joints | Joint board installed
32c858d6-6b2c-4b10-8859-581d8112f1c4 |  | not-started | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07
cdbbd9cc-e7f0-53fe-942a-85963c9ee3e0 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Preliminary
3a899b66-adcd-514e-a5c5-175130c480ef |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Preliminary | Engineer notified of pour
e9a9223b-9cee-554f-8edb-8b1f11b01fa7 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork
58df3255-ef3b-5956-9335-bbe38c73306a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Installed as per formwork design
5e615fb9-80d9-509e-86e3-a6b49c91859d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Permit to load issued
3dc1ccc4-dfa6-5818-abeb-61adf60b0f4f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Dimensions correct
ac372cd5-52cc-5ca6-8d1e-6990a4b46091 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Position and orientation correct
da614f11-60d6-53c9-8947-fe01c884ece7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Forms vertical, plumb and true
af496076-cf65-5bf9-9ae6-1b09dcf883f8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Forms coated with release agent
bb08ae4f-0c91-5f88-9c27-0577df8e2e8b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Forms clean and clear of debris
1114af4c-c73d-5e2a-9c2b-7986024760b6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Joints sealed
e2392582-39ff-5c90-8cc4-8b8f7195ac66 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Formwork | Pour level marks
ab8c22c5-6875-58f6-89b8-b5a4512b3b2f |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement
a3e2bd8c-2eee-56db-95ce-c900b423e4fa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Correct grade reinforcement
4382986a-cc77-5510-b6f4-38ef56f6f6b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Correct bar size
787957b6-07d3-5742-a46c-20578233a38c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Correct number of bars
deeb3620-cc03-549a-8624-5c39486d7c7e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Correct spacing
cba57ba6-ce8d-5c75-b836-b9870cf1fdbb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Starters bars included
c3337c7c-8034-58cb-8de8-c3581df6410a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
a5319175-06bd-58d0-af16-e0b9e79f767f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
825bdf76-2829-5db3-8d65-b195e76af42e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
a02e8eff-c9f6-53af-9b17-edba1900de24 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Correct lap position (staggered appropriately)
994fc773-8137-5ea4-864d-703707864f30 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
3e314d78-bfde-5605-a04c-a652fef821ad |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
d6afdfab-f9b3-5ae2-9b51-6075130f523e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Reinforcing adequately tied
3bd76d17-201a-569b-b2d4-31f2e9a3600c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Reinforcement | Chairs or spacers fixed in place
0f652f1f-f04d-5284-a0f2-eec58028b8c8 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Embedded items
86a7e4ed-3e98-5d31-b0ea-3495723cfc95 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Embedded items | Block-outs, ducts & cast in items installed
74cb8f3b-8d2d-5b97-a62f-49eacf5552e2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Embedded items | Correct position, level & alignment
2d85ad94-4929-5932-82fa-a8d3b05d2d02 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Embedded items | Securely fixed in place
817ed96c-ec38-5ee4-805d-e57fd6b2abd5 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Construction Joints
f747a016-03cb-57e7-9650-b9885f4c4bdd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Construction Joints | Correct location
984983ab-4170-5521-b368-0028bf9e6907 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Construction Joints | Adequately prepped
651d7f36-13a2-554a-b455-90af4587e14d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-07 | Construction Joints | Joint board installed
b90e3134-7101-4397-974e-0a494177ac56 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08
b138a5b3-0051-5cc7-80da-1c585a7f0745 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Preliminary
5631abac-2fb0-5861-b787-a9b0344c3795 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Preliminary | Engineer notified of pour
612b9732-1e22-51e4-af85-1b6a953f5ba9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork
36ecc3ea-8204-5d5d-ac14-083677ebe84d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Installed as per formwork design
2a8b3a05-0d4c-5758-9c79-f3f7c701aa52 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Permit to load issued
4f8a3dac-f5c6-51f0-92da-8884a8588919 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Dimensions correct
aced01f4-03fc-5ba3-93a3-0f7d2ff20486 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Position and orientation correct
3d0f33ed-b6b2-5fd2-9517-add13ea158b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Forms vertical, plumb and true
5a434c8d-5357-556d-a623-fe9944e5194b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Forms coated with release agent
27de3c86-2b2b-5555-99ca-c01a8dcfb06d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Forms clean and clear of debris
269a0226-7889-5b8e-b7a7-621d43ad5e62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Joints sealed
efbcb3c3-00dd-5467-becc-e7fb7cac324d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Formwork | Pour level marks
81589e7d-af47-5768-8947-65d93d996e6f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement
a3550ac4-2be4-55df-8b62-3386ae63ddc7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Correct grade reinforcement
23b1b7e3-e2d9-5e2d-a10f-45a9a4e05f4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Correct bar size
aea70451-ae64-5534-ae26-46dba97b698b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Correct number of bars
33770b89-1284-5dba-975b-ce31bd67cd41 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Correct spacing
c1f4e2d4-c1f6-5fad-bf3e-d01a00725c95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Starters bars included
2ee1b1e4-ba0e-52de-b39e-95b6d37d662f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
96abcf9a-0e80-5a1d-b9ea-8932578cbed6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
c9f758bc-c451-5d8e-8450-990e5a4db607 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
b1c6562e-96a2-584c-acb8-ab4b05d2c849 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Correct lap position (staggered appropriately)
bb6926e4-64f2-5489-8564-6d02ce9388ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
9ec3f9de-f6c3-5e76-b885-857425f9960f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
0a42ef8e-5ccb-5199-8c4d-73e5060455f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Reinforcing adequately tied
01d0bcc8-f99a-552e-8b07-819c09acd78d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Reinforcement | Chairs or spacers fixed in place
c535cfde-c929-5d13-a631-81aa2921566b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Embedded items
af6fda05-1b55-5b1d-b77a-c0eb54c4aafa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Embedded items | Block-outs, ducts & cast in items installed
f73ecaf2-b4d6-5f29-98ac-edb293b927ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Embedded items | Correct position, level & alignment
e3a02271-14fc-5ca1-9342-35f247a4e0fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Embedded items | Securely fixed in place
3f2897a5-7174-5304-b049-344e014611ea |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Construction Joints
07c57e2c-31c1-5cfc-9e95-aec4c7b25b35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Construction Joints | Correct location
8fa58a6d-3d4c-57ec-849c-a834760afbf9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Construction Joints | Adequately prepped
e9985e63-34d0-5a28-952f-2942df674274 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-08 | Construction Joints | Joint board installed
d1344553-6038-4f90-a72f-9e5e6ea6e616 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09
46be5142-c704-5636-85e7-668b08c2a261 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Preliminary
b49b6498-b0e9-5131-adc8-a81eb2f747b7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Preliminary | Engineer notified of pour
1ffff4e5-6136-53e2-b942-f33beee42577 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork
bed4f8e6-f51e-5472-88f6-595b48a40fca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Installed as per formwork design
466b00af-4c12-56a7-863f-4ec8541f2895 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Permit to load issued
b611aa5f-4e5c-5c4e-a163-88e8495ffef7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Dimensions correct
c38ba656-0217-509d-9c52-2a25b60a87ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Position and orientation correct
32c3fdec-6b6c-501f-85e7-0bcb2ce7f792 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Forms vertical, plumb and true
5bc5dfff-1143-5a31-b107-b54e4442b655 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Forms coated with release agent
971d5a73-d7d2-5744-aaa8-f2a94f758630 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Forms clean and clear of debris
9bb56f92-62cc-5b86-8f11-9e4add06b95a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Joints sealed
dc65640f-2d32-54c8-a351-620a60cada96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Formwork | Pour level marks
018a1be5-2d8b-506c-8faf-22e9600b1dc2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement
a629df2c-9339-5b62-baf9-1e241691447e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Correct grade reinforcement
b90fd93c-5004-5c3f-892c-0f9781d0206d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Correct bar size
c907a56d-7876-5240-99da-29981f66bbe5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Correct number of bars
f7bf63e7-508c-5531-b9ea-a6f9b025ae3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Correct spacing
a708ba3f-f09b-51e5-a5fd-42f9d4706d06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Starters bars included
fbab6374-fdee-5017-b3e9-2d53eb75d789 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
e4507ddd-f252-5922-b047-b3ee4e25ba4b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
c77a8cc5-b830-5a06-b612-12c541810f66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
e4704bc3-69eb-5a5f-a7cb-670e06403e24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Correct lap position (staggered appropriately)
bcfb7402-10b8-5006-abf7-8c01db448592 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
db640b7b-cb52-512b-932e-b3570797e393 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
c83e964f-b03c-5504-8dc8-463172850605 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Reinforcing adequately tied
5b9307b9-df7f-5843-a9a7-3a52c26dce67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Reinforcement | Chairs or spacers fixed in place
aba32cee-1c0d-5f19-8925-dd9d714b114c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Embedded items
7f1a3873-33cb-500a-a131-4d18746d453c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Embedded items | Block-outs, ducts & cast in items installed
a39addd2-1ff5-5199-af42-dc849a2a1b54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Embedded items | Correct position, level & alignment
13a510c4-0c4a-51d5-97b4-935add7bfcf9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Embedded items | Securely fixed in place
449ecb8c-9ce1-5de9-a92a-6dd4b523b776 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Construction Joints
b93f72a1-e234-5f36-b428-dff37ed12ae5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Construction Joints | Correct location
e54dd670-de92-59f4-8975-8417c0141051 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Construction Joints | Adequately prepped
52bbb957-2577-5b86-aca1-9be27950a73a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-09 | Construction Joints | Joint board installed
cb7c0278-685a-46f4-bc67-0af516d9134b |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10
f794f636-13ca-515e-ae0a-d0bbf90ba6e9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Preliminary
a9cb5590-e85e-5cba-93ec-00f1e8cb7486 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Preliminary | Engineer notified of pour
66ce6776-b4e5-5496-a297-177d8456be74 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork
d9ca66f3-70b4-5169-9791-fa9b7a2fcf03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Installed as per formwork design
6b50745d-4185-536f-84c4-f192a255eb7d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Permit to load issued
dd9e7d4c-5dbd-5150-be31-dd7c37b815d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Dimensions correct
2259bacd-23d6-5959-ad32-040853073e6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Position and orientation correct
a4d0f8a7-ac22-574d-96d6-7666c67c6d43 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Forms vertical, plumb and true
88af805c-5f77-5b7e-94e1-6038b94318ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Forms coated with release agent
faeb9e50-2d8d-5d94-8d21-faf519046ed1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Forms clean and clear of debris
9d28193b-9401-53c6-8ea3-20670635c9f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Joints sealed
dfed2dbe-8efe-5893-9afb-36fb5f83fe69 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Formwork | Pour level marks
da5fba88-ae62-5a16-8819-9f9fdf2b8b0a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement
d5727fef-462c-5835-b7fe-ddf3ebcbfe2f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Correct grade reinforcement
ebfc4985-410c-5054-9e4b-1b66bfce2047 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Correct bar size
a6c56aa5-874f-5285-8377-4ca5bb638dfe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Correct number of bars
b27ba7b5-9676-5bdf-aadf-a302920d0972 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Correct spacing
5efc65e2-da54-570d-8137-840b0808dd3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Starters bars included
ecc48c96-9e0a-5c1b-b202-2ec72139f2d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
1ee176d9-358a-5e87-9586-a17c90e14ad0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
657ed253-7ba5-5030-9f3e-5b8440f918a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
fcd324cd-b7fc-5620-b716-eeba3ae27686 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Correct lap position (staggered appropriately)
f45773aa-8612-5a86-ad99-15199ca6cf80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
426ff98a-eca0-5330-8327-1a8efe96b049 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
f34e534a-9d0d-5a30-bc67-45dcb64f22ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Reinforcing adequately tied
19de33d5-9575-5339-9d94-2065221f8125 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Reinforcement | Chairs or spacers fixed in place
34894806-8f03-5754-b83f-062f30b8fdb4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Embedded items
3f3116b8-5bec-5034-81ec-17cc14cea746 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Embedded items | Block-outs, ducts & cast in items installed
12f0584f-ebee-583e-87e8-95158ffe79c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Embedded items | Correct position, level & alignment
c7611ca7-5c58-5284-ab7a-dd9917725d23 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Embedded items | Securely fixed in place
ee239f1f-a75d-53d8-a206-bd8f523c2cc4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Construction Joints
979b7798-789b-5d47-bad3-b848a98fc6a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Construction Joints | Correct location
b15a59df-95c4-52a8-857e-b30f0fd426e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Construction Joints | Adequately prepped
2f2c199b-5c5f-5d35-ae6f-a00841e9830c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-10 | Construction Joints | Joint board installed
16c189bc-7e84-49c4-89cc-9a7c6bb55de2 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11
1335c0d0-dd20-5d37-bb2e-edf6503cbe94 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Preliminary
b664fcd1-08f4-5094-bbc7-5ebe61c56c63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Preliminary | Engineer notified of pour
2a189bd5-591a-5709-8b86-8b20e4acf413 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork
2d03f4f7-2aa5-59a0-a7c3-1a3d35608734 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Installed as per formwork design
8b702426-d328-5009-8893-f6f043644f64 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Permit to load issued
79f899bf-f90a-531a-a162-5c23c910c3d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Dimensions correct
03890ca4-80c4-59d3-8208-e8ae145e75d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Position and orientation correct
912f87a5-4e92-5227-b427-f62c562020be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Forms vertical, plumb and true
70ffd765-68bf-5806-9a13-2943f4419ae4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Forms coated with release agent
d247030e-e4af-5512-8892-4e645f2d4032 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Forms clean and clear of debris
b72ede04-2f19-5992-9e39-0287cfb14cc1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Joints sealed
c8d71470-8d1a-5230-941f-5978d7a41b75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Formwork | Pour level marks
86387e37-723b-52e6-bc9e-68f785f725cc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement
2d7bbe3b-ad08-5ba5-aecd-098f6ef7de54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Correct grade reinforcement
fa9139a1-82c6-5e5c-a934-d7354ea02fe9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Correct bar size
148b3886-ede0-5b20-aee3-a9bf1b05ca6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Correct number of bars
cfb88b1a-b240-5f95-934c-0925ac04dea0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Correct spacing
ab303ce9-3a5a-5062-8e7b-822e0416f9d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Starters bars included
fd86b663-85a5-5e51-a79e-4f1c1ab3aea5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
4f44f4ad-0418-5724-8719-f2b81379d8eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
964476fa-14d6-59ae-8006-ac994b91929a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
7c57bee7-d0c3-5496-9cf8-10f82d1ce217 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Correct lap position (staggered appropriately)
2ca3e80c-7dd7-5827-a394-9eac901d988b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
3b95eba8-d503-5fd5-b5a1-d3affc1ae691 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
b4093dad-7f0f-572e-bb40-831b732fe7c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Reinforcing adequately tied
88043b42-5aa4-5fd4-b688-5fe8f2f055eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Reinforcement | Chairs or spacers fixed in place
093d491b-701f-5437-9816-f971450674e8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Embedded items
bafeab03-bc51-559e-8478-8db0997471f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Embedded items | Block-outs, ducts & cast in items installed
cfe85ec6-8b09-5db8-a8eb-95e82e46ee89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Embedded items | Correct position, level & alignment
4af61962-a202-5883-b685-5e7f6ef67d2c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Embedded items | Securely fixed in place
2a07187b-987d-5db3-a579-9778fb0bd630 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Construction Joints
b86e99a9-8975-548b-9a2a-cdb59486fd42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Construction Joints | Correct location
f57b261e-0ad9-506a-a327-1521b3cfed21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Construction Joints | Adequately prepped
9350ce1a-9ede-53fb-8437-49ecc649f256 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-11 | Construction Joints | Joint board installed
53650b81-d9be-4e42-abd0-d00e512a0432 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12
6c8f32e4-9c95-591f-a4e2-cd4ff3757d0e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Preliminary
40107e53-60d6-5b7e-bc8d-eedf7a2a2008 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Preliminary | Engineer notified of pour
ceecf04b-1044-5154-b110-41b17994e444 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork
b4dbdcf2-e59a-552a-ac5f-d0b659a08d8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Installed as per formwork design
ea102798-02c6-57bc-b890-4af088de25d6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Permit to load issued
b38b863a-14c2-5167-bf7b-79f06c296983 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Dimensions correct
6f9e50c5-57a3-5ce6-920c-f03a7874dabb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Position and orientation correct
1d3d47fd-5631-559d-96ef-7bdfbc74334a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Forms vertical, plumb and true
53779d5e-0bba-5e20-9a63-70d939c949cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Forms coated with release agent
0026a399-5404-5caf-9806-b8f342e61ba3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Forms clean and clear of debris
818d7551-6da0-5c28-acc2-93f47edf34a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Joints sealed
36ce9561-0ab5-5561-98de-640e302e6230 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Formwork | Pour level marks
b79307d3-9548-503a-9e3e-e7d54d284d54 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement
4074fb5a-d1a9-5ee1-83fa-21e15e2be81e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Correct grade reinforcement
5ed8c079-fcb4-580c-8615-763c23970e27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Correct bar size
c8703552-4113-50a4-8b9e-db9cba765e76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Correct number of bars
2f440596-ce5a-54ee-b1fe-c897f2557f63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Correct spacing
4f2521e8-cafe-5a38-9493-74516c512594 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Starters bars included
c8e89541-7fe9-52ac-ab8a-f4d7c1c6ba9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
6b069bb8-185d-5ae2-8f21-141444786d70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
5b31aced-8368-5199-80da-b2fc9359c27c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
6c8f38f6-8ae7-5f68-90c0-608623a6b31a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Correct lap position (staggered appropriately)
18ff4b69-d2cc-5bd0-8e47-23a3d6801215 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
020570fd-1831-56f9-a46a-74c3bc6dc9bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
8f558d2d-1905-55f0-8f62-d711b1718908 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Reinforcing adequately tied
ebbe1961-d462-5396-b5d4-edd0e59402ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Reinforcement | Chairs or spacers fixed in place
17cef456-4d96-5615-89f2-95f0c509fd3a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Embedded items
c65efbda-a9d5-55fb-826d-d98a6ad80d6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Embedded items | Block-outs, ducts & cast in items installed
bf01ed74-bcab-5fd6-8310-74c6f0d90738 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Embedded items | Correct position, level & alignment
f7661bca-2526-51aa-8c5e-0390233e59a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Embedded items | Securely fixed in place
b31d19e7-dec3-5e2a-9a51-60c3de5dd0c3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Construction Joints
7040ab69-e6b7-54f8-804c-bd5353ebb767 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Construction Joints | Correct location
d1dea7b4-c646-5ade-8f9e-97d6b7765996 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Construction Joints | Adequately prepped
8405dbdd-260c-5e9f-92fe-6a93c438eaf4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-12 | Construction Joints | Joint board installed
d26845a5-893a-454a-b814-3c4f43376894 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13
2ba88805-5791-5535-9996-d7ec5613148d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Preliminary
72bdd95d-ace8-5d3d-a720-6951e84fc311 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Preliminary | Engineer notified of pour
87ca2513-cbf0-52c8-9e1f-b8406d77bbf9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork
1d3e2b3f-39b4-570e-bfc6-d8bf353dc5ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Installed as per formwork design
86e8c84b-48cf-56f9-aa47-5bd8f1f716eb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Permit to load issued
781b8f2e-9723-546f-a1f7-4526b8b78165 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Dimensions correct
0f265b51-36f9-575f-b600-839b5cd5dcdd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Position and orientation correct
4b4ad3dd-a8c7-53db-9b61-2c354fd38bd0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Forms vertical, plumb and true
049d5178-18bd-59f6-aa55-7eae67a71554 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Forms coated with release agent
44bd5436-f9fa-5327-b3d5-47609b38de12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Forms clean and clear of debris
392b5e91-7617-55d1-ae80-a22f5f5ffd83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Joints sealed
645a3ce2-7149-5d17-82fd-9fa7ab10096d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Formwork | Pour level marks
73d4241e-3f49-5afa-a5b7-00afd95492e1 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement
2ea75b7d-159f-57a8-a504-12447c13c12f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Correct grade reinforcement
79f375f9-b6df-504d-a908-22c7c30f6202 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Correct bar size
5a7174a0-02cb-5a96-88cb-940bc7a19e11 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Correct number of bars
1cb7d216-f471-589f-9e37-11266500ec3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Correct spacing
4e580fa7-a04d-5fc2-9180-fab4fc465a8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Starters bars included
ae27171b-388b-597f-99ea-2ce9749a3ed2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
83e90096-1cd4-5622-bf5b-e17903b2b713 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
4d984153-2c4e-598d-a5a7-924be5204c25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
25129046-1c5d-5249-b759-6f998e2e8ab3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Correct lap position (staggered appropriately)
03853c66-b972-588a-9ca2-abad1b127538 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
fffd499a-8888-59d3-a7c8-4692804aad20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
a8b8a7cf-0370-549c-a24c-c0223407be47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Reinforcing adequately tied
dba2bd57-47c2-583c-9ca7-90a79b13c438 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Reinforcement | Chairs or spacers fixed in place
8d3d452e-3161-5512-a51b-dd458c8e9f6c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Embedded items
e33d5300-61b2-55c1-b070-1f993eb0f85c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Embedded items | Block-outs, ducts & cast in items installed
fea750e5-41c2-560b-9a70-2fbfc9ddb51f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Embedded items | Correct position, level & alignment
3ae23c21-9dc7-52eb-b8fd-0c646cbb8cfd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Embedded items | Securely fixed in place
a5784db3-ad5e-50ff-8c2d-b180314fb5dc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Construction Joints
96b8c1e0-a1a6-5d33-8aa0-8619a98acc77 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Construction Joints | Correct location
ae241475-53a5-5a69-b86d-74035a8b3f5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Construction Joints | Adequately prepped
62d7fbdb-f6ac-5ac0-a9f7-20dc13abd451 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-13 | Construction Joints | Joint board installed
e8cef59d-3971-49cb-ac86-9a51c22f2c95 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14
e50e40f1-80fa-5a1e-ba39-98dac1fd08aa |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Preliminary
96fdada9-1bc0-5f51-ae00-83a982d702a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Preliminary | Engineer notified of pour
0cfe1cc4-6841-5b1d-80c9-91154a441925 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork
6168c8e9-bd43-517c-b8a1-cf1ab91e0456 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Installed as per formwork design
6295bc92-9a67-55b3-a59c-85ed240f4b02 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Permit to load issued
3db90da2-65e9-5150-8da9-87fe129bf48c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Dimensions correct
44664dc0-fd6c-5aa0-9003-c5724fa6ca24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Position and orientation correct
207088ab-cb67-5866-94c7-ad5d8ef85a08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Forms vertical, plumb and true
f8cb4d44-edcd-521b-a7b4-43afd03ecac5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Forms coated with release agent
481e8e0f-04ad-5997-96a9-5232074de70c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Forms clean and clear of debris
6f4defe3-b48a-5014-b635-4939c623c33f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Joints sealed
02a3d0f8-08e7-5f05-a05d-312230ebc3ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Formwork | Pour level marks
aad07589-307e-52c9-beb1-c62b36729e4a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement
fbab5a81-f03d-51a2-a808-0e14828705b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Correct grade reinforcement
564f03a6-2391-5aba-a7e2-cf7490edab9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Correct bar size
e6d0b37a-5822-5c2b-9505-d5a693ec0e0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Correct number of bars
7a37c7e4-065d-5c32-8ee0-1b2e018f89a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Correct spacing
528d15de-25bf-556a-aa7a-3678e46a474d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Starters bars included
eb38fff4-e654-5f7f-bddd-3f7ac221161b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
fd4df925-baa7-5e8a-a8f4-2d291eb5cb67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
bf61771a-0499-5fa6-bf61-5453c8dcb33d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
0011ad49-efac-5188-8354-708601cd06a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Correct lap position (staggered appropriately)
82d22120-5f5d-5d9a-8f6e-fdd70b1f75d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
b6c8cac7-d292-528d-ad0a-5f58f681ed10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
88833813-d7e3-5345-8ea3-6d9307792481 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Reinforcing adequately tied
513557ec-e375-5733-a30e-090ee2136db5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Reinforcement | Chairs or spacers fixed in place
24e5dd71-8059-5f59-9d75-5076628a4165 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Embedded items
ffe7cce1-cfe8-5006-9dd6-adbb90bcd91d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Embedded items | Block-outs, ducts & cast in items installed
1be2ba9c-8450-51cb-9084-0e5306b27166 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Embedded items | Correct position, level & alignment
8e8cee93-bd1a-565a-b91c-514419aafff4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Embedded items | Securely fixed in place
86f86bf9-e9ab-5a08-90b2-9c71997b470c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Construction Joints
356eb5d9-9001-5d90-82e2-ddf20e47d69a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Construction Joints | Correct location
71cd51bc-3423-580a-94fe-945d423b5b83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Construction Joints | Adequately prepped
c5218c5d-8ae1-5637-a967-a473e453fa40 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG-14 | Construction Joints | Joint board installed
ed8e5996-842b-40ab-9d3d-f99e795d6a0e |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15
d6c60c01-dc1f-5606-9bfb-3ca6fcf32e8a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Preliminary
64ef6db7-b4a6-5141-a368-40a96433fc58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Preliminary | Engineer notified of pour
ce3873c3-c1fe-5b87-8a7e-6c1b6ca0c5dd |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork
c6ab31e0-96af-53f8-9c38-158d1f3c876f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Installed as per formwork design
172f81f9-9683-5a2e-8012-940d929bb98d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Permit to load issued
8c68ed9a-925b-5908-aeb6-513442a79fe0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Dimensions correct
a473595c-e5b0-5b16-983d-89d270f5aa2b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Position and orientation correct
a8ec5156-93d3-528a-949d-5dbc07176976 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Forms vertical, plumb and true
cfb36c33-146a-5eab-9542-39fc194e9bc2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Forms coated with release agent
509658bc-d3d8-519d-aabd-e2e5d3cead0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Forms clean and clear of debris
1b2a269a-3534-5fd8-93f9-b1c4ca8fd159 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Joints sealed
52ac11ce-314c-50e1-9846-ef35a42f379f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Formwork | Pour level marks
447969f3-a3dc-5539-8b39-16111d7c02d7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement
4074407f-66ec-5759-aa8b-2f77a7e48b77 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Correct grade reinforcement
863935db-a8c0-58bc-a98a-e4b67aa54228 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Correct bar size
cc833302-f1b8-5cda-af98-d8232b5bf4f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Correct number of bars
cab00de2-d781-54a6-8218-512375dc7469 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Correct spacing
82d30875-55cf-5830-b8f2-386fe6821ee1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Starters bars included
60eb90e1-41b2-5fb9-a545-b033e336d5eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
69da0b8a-96a8-5fdb-bcd3-1e9c906401fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
b78d91f8-cc57-535e-a79f-1022d01c1191 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
54c611d6-b752-58e2-a943-224e15adb7b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Correct lap position (staggered appropriately)
f28250d3-4678-5b52-85b8-f5abe6470941 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
92d9fa6b-e872-50e7-bba4-1f0937502919 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
b62ba053-502a-5857-8441-eb8212516dd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Reinforcing adequately tied
9d5156be-d978-50b3-b29e-99db930ebc5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Reinforcement | Chairs or spacers fixed in place
cc7a34e3-9887-5301-9fde-54365b196540 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Embedded items
002178f2-7521-5012-aa3b-7cf04ea78ec3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Embedded items | Block-outs, ducts & cast in items installed
8fd4a919-0d75-5d4c-ada3-99a95debe45e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Embedded items | Correct position, level & alignment
6b3bc033-2765-5c96-8d14-0701f8505e7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Embedded items | Securely fixed in place
bd2d1326-bc07-5f68-a1f5-1f5e3ff24f8b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Construction Joints
040ab1a2-f245-5179-a296-a3b236cfc694 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Construction Joints | Correct location
7c428202-b78a-504d-8d76-be5eec2575a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Construction Joints | Adequately prepped
c37db41d-d6cc-5a51-90b1-dcc429d610b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 15 | Construction Joints | Joint board installed
950b16fa-9308-4d11-a4d6-f7730652beb9 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16
777f352e-74d7-5003-bf32-f2f215ba6d3b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Preliminary
47513638-6090-545d-873c-c125f4c511fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Preliminary | Engineer notified of pour
6fb2b7ba-1219-5fc1-ba7d-28b8e776738f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork
881157a4-0133-5371-8bde-a04b872e7b6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Installed as per formwork design
545d2231-e0ce-5a1b-8daa-d238356a30a8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Permit to load issued
0b00e361-01f3-5550-96fc-85eab5c72f2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Dimensions correct
d075adab-84a0-57a7-bf90-1e72d7ef21b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Position and orientation correct
e501dbf3-0a58-58f1-87cf-12470d79af04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Forms vertical, plumb and true
d1907786-cd29-59d8-9d38-88cc2062dc6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Forms coated with release agent
27e6bf7f-4e3a-516d-876e-cccc9d6129d0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Forms clean and clear of debris
83b98147-d032-5649-b041-37099e4e77f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Joints sealed
0779fe43-c521-5972-89bb-1a9c4264f31a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Formwork | Pour level marks
90c05201-0341-55ef-a740-cdffe5ee47dc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement
ca50545c-1674-55a5-9554-6b5f7275a0c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Correct grade reinforcement
e342c625-c81b-56be-b102-e24e0810cb99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Correct bar size
e46914d3-7a0a-5f6a-9022-2643da254b29 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Correct number of bars
34227aae-f337-5669-84b5-78c91ae3242f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Correct spacing
38dcb674-87ff-5730-8d34-eb58d76fc5db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Starters bars included
2074591d-f3ad-5bd9-9a8b-27619a17a446 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
8a85875c-fbfb-576b-9708-88c27ca5890c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
3cce7b64-f2e9-584e-a119-4bc7998045ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
7e330954-031e-5a01-b9e6-06339ccbf589 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Correct lap position (staggered appropriately)
3170e638-b54a-5608-9eeb-945907290243 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
029c36a2-9681-5a7b-8aa0-dacc6232c6b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
8a8e7393-8fe0-5a46-9885-57690b82f6ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Reinforcing adequately tied
fcf6ba16-85bb-55b9-9281-f798a0a29c80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Reinforcement | Chairs or spacers fixed in place
b1ba098f-ff17-588b-be12-138a015dfa1c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Embedded items
1cb25fca-5e63-5e17-a749-f5043f806d62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Embedded items | Block-outs, ducts & cast in items installed
f123905e-2487-50fc-9fe9-ab133fb07f86 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Embedded items | Correct position, level & alignment
6c6d9810-0540-5a3c-bf75-d106768373b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Embedded items | Securely fixed in place
8ce528ee-bb17-5cda-8517-32d6a91c7832 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Construction Joints
e841e74e-d66f-5403-9ed8-33e810bfe188 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Construction Joints | Correct location
e92b88df-a099-5104-8ee1-95f8b992ea30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Construction Joints | Adequately prepped
3481a5dd-872b-5b16-bd7a-2b0a26bdee63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 16 | Construction Joints | Joint board installed
1caee04c-3b44-4914-9828-a745e318ca20 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17
e5a7eaac-cad6-57d8-b8a2-08f17ee68281 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Preliminary
4e9092d7-b21d-5939-885d-05737e3b7a3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Preliminary | Engineer notified of pour
231e9b67-6445-5899-9d94-77df194849f3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork
84f9911d-9d7e-518c-a3a9-5ffbeb187fea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Installed as per formwork design
86d5340a-df4a-588c-943c-ff90dfc14598 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Permit to load issued
07d412e4-a618-50b0-bc53-d7a1a92e9f38 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Dimensions correct
531f34d6-3ffd-5819-a2b4-de1a3f5eb787 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Position and orientation correct
eb1db13f-4ff9-512c-99c0-809cc21144fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Forms vertical, plumb and true
da741773-8699-585d-a217-b9cf742a3e22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Forms coated with release agent
5cfbd23e-85e3-57da-a2ce-14d8cd10de1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Forms clean and clear of debris
313a54ca-c642-5ce9-a9b0-e1ac8e978ce5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Joints sealed
33abe8f1-4e34-50e5-a707-7a0d3a96e300 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Formwork | Pour level marks
87fe6b4a-6023-5440-9031-bdc5b08ddb17 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement
b2dca7b6-5829-5c33-878d-92c502f39653 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Correct grade reinforcement
4baccde1-55cc-5193-a917-077282b489fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Correct bar size
2418b08a-ced6-58c1-9ee7-5108491aaadc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Correct number of bars
45319132-6b5b-5c37-950f-f0f790b1ae30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Correct spacing
12a01406-a723-5965-8fec-94a5c1331dab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Starters bars included
920af6e5-a9e2-5d1c-a510-6d8c75aea990 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
862c1c25-59c3-5091-9ceb-b7e380a494af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
bcf164cc-11cf-5c1c-9b1e-28a048849992 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
eba62f7c-4893-5153-ad15-9abdef75faee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Correct lap position (staggered appropriately)
be5479bd-7f3a-5ad8-89d9-a5e58e5271f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
ae15744e-672f-5734-ae75-a246994bd4c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
6b7df711-8575-52b1-a092-89a5e2f4df63 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Reinforcing adequately tied
9014ec71-3b2c-51ef-a44e-f1f80416f9ea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Reinforcement | Chairs or spacers fixed in place
d7e7852e-7f09-5925-bd39-69a89fb0d9dc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Embedded items
f3411014-8d5f-5698-a514-f47e4ddc0507 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Embedded items | Block-outs, ducts & cast in items installed
95c71a67-f665-57f4-9c25-3a60465dc015 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Embedded items | Correct position, level & alignment
ed464e0e-eace-58d8-9856-39231a2bd575 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Embedded items | Securely fixed in place
7ff6db36-65c7-566a-8eb5-db6369c15bf1 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Construction Joints
bb9b518f-4ce4-5678-a11f-a27869feab87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Construction Joints | Correct location
807785e3-2e20-579a-beae-e72d498de513 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Construction Joints | Adequately prepped
9a4f08f0-9137-5387-ac11-42d75f6a0851 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 17 | Construction Joints | Joint board installed
02290c29-c5c3-4201-ae96-5133110332a7 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18
23e50b04-6c94-510a-82d6-bb5684be3e87 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Preliminary
3286d1bc-a29c-56e0-922f-a4a89bb2f7f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Preliminary | Engineer notified of pour
b4b40631-e46b-5859-abda-c2bf95976ae6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork
6b8a21aa-398f-52e7-bb04-001d43027f9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Installed as per formwork design
6477d4ef-8efb-5d27-b205-165d0e348e61 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Permit to load issued
4b8aafca-470d-5c92-9d4b-ed5b9feadff6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Dimensions correct
02edf719-6652-5da8-9f29-1c90fd86c447 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Position and orientation correct
e2a3ae5c-cc9b-5a5f-9032-fe06f0989c33 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Forms vertical, plumb and true
f7269136-6301-5337-9fd1-66743c41afef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Forms coated with release agent
f90f0bfc-3a04-5b66-b561-8028be571eef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Forms clean and clear of debris
d650ca64-3aa1-51b8-9bb4-f37da5a0eeb7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Joints sealed
61a1f6aa-654d-5064-8058-a4daa3ddd438 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Formwork | Pour level marks
7a581a74-2369-504d-a74b-cf489ec29e0a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement
33a76457-0d40-50c8-8fc8-1befd6d0099f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Correct grade reinforcement
9873cad9-4e34-5c21-ac1d-1453fd0a647f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Correct bar size
80b9ab0e-0105-5348-9799-b055c8452b94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Correct number of bars
286b467c-d7ab-528c-a56b-19a094bd3e8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Correct spacing
4cfc62ce-ddb5-51a9-882e-dc3e8b127a91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Starters bars included
d05593c5-d42a-5eaf-9b27-c16a8a580a25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
12f88c7b-76d7-5508-ad62-8bb9acfcd9f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
d7bc5f90-bd32-50fb-abbd-359a1289f0ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
dd005e37-dc03-5821-a3cb-8cf97fec9a4f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Correct lap position (staggered appropriately)
3a704436-4f89-54c8-8cc5-8c94fea05f2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
47dfd56a-3c53-5cf6-ac24-874aed506e41 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
979632b1-237b-55fc-8b76-4b8907bb79b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Reinforcing adequately tied
049bb991-bd50-5e9a-b70b-7eb1b672e2ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Reinforcement | Chairs or spacers fixed in place
7f6e4aec-11e7-5e03-a61b-be10f9916d61 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Embedded items
6181d493-d201-5b53-84b1-4aadea18c41a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Embedded items | Block-outs, ducts & cast in items installed
fead8729-0d95-5316-8a09-95517ecad84e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Embedded items | Correct position, level & alignment
612be18e-bc26-50ad-93fa-180be2bac6b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Embedded items | Securely fixed in place
47ba8ec8-a67d-5b4f-9cd7-77ec50ddb639 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Construction Joints
ee907080-7d6a-5508-8182-9d7e1b381d3a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Construction Joints | Correct location
9662457f-fe89-54fc-9c05-57ac59f3181b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Construction Joints | Adequately prepped
8ba15226-ea90-5107-8cd8-70238e96f83e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 18 | Construction Joints | Joint board installed
40d08ed7-8990-430c-acd0-abca0361d2c2 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19
d576099e-66ff-59b8-93cd-0c4f8c0a7cbb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Preliminary
99b0ce7e-05f4-5bb8-af07-6f7a1eb57d83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Preliminary | Engineer notified of pour
6b5669a6-89c3-5fac-a564-bb7461f6c20c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork
326ebe64-8b66-51a5-81b8-d482ada5485f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Installed as per formwork design
60ee2ff7-18af-57b7-b41c-eb96c33ae4b8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Permit to load issued
1d050c70-8d27-5314-8e25-3828ab54f284 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Dimensions correct
9340ed59-1eab-51cd-bc5b-94fed2b56f6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Position and orientation correct
d5f0736d-309b-530f-87fc-00f2ec6e8de1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Forms vertical, plumb and true
6b5c6102-df90-55a8-8633-ed3cd79ef9f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Forms coated with release agent
9824d648-f3a3-56cb-b9a1-d256d59bc6aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Forms clean and clear of debris
e7a03c6c-7ec8-5864-81e6-ec23ea083e32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Joints sealed
3ef0bc7d-7fd9-526b-9bf3-b571cd14b14d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Formwork | Pour level marks
fe750d5e-bf48-58f1-ae27-1de4c53366a8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement
e4e93d29-9ca6-5cc6-8b2d-5c4e347a6de2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Correct grade reinforcement
485716bd-d039-5927-9a95-fb86b9463399 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Correct bar size
6bb54bd9-84bf-5b85-b277-b14dceee138c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Correct number of bars
b6a495d2-854f-5bfc-a8c8-d8fe268d6763 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Correct spacing
773fc5f5-769f-53b2-9e75-ed61f8df8997 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Starters bars included
07134025-5f06-5681-b5c0-427cf919a769 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
f5c01254-690f-55dd-a9b2-70a071b748a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
8d65085b-cdbd-5892-8581-1bb7bae7532b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
e1731616-0496-56c0-bab3-1c12fb80e728 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Correct lap position (staggered appropriately)
ee89b46a-9329-5a24-a595-47d5246294e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
c07c631d-cc75-5140-8d41-28610f762cbc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
07be5281-866e-5f1d-bfb2-48a60b901d4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Reinforcing adequately tied
cc440066-75e9-5abc-84c0-f8bb97110087 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Reinforcement | Chairs or spacers fixed in place
bd6397ab-a30d-5d44-8beb-8d3bf4d71f40 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Embedded items
d6e62625-54ae-5cc1-8408-ffa9b601a829 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Embedded items | Block-outs, ducts & cast in items installed
93cfcd34-7911-5ff5-ad94-8f6380a163e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Embedded items | Correct position, level & alignment
53186848-c13d-527a-8d3c-60d66331770a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Embedded items | Securely fixed in place
f6f09d9e-2dab-5c6b-ac38-3bc21b4397f9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Construction Joints
53738580-804f-5a5d-a2f7-35602d1ce81e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Construction Joints | Correct location
2a121131-1595-5ff3-8733-86fd0553a627 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Construction Joints | Adequately prepped
bedbf7bd-a2f7-55ae-b8cf-512aade19e93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 19 | Construction Joints | Joint board installed
88f125d2-c144-4d04-bab7-2a3bc9e4f1d0 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20
a0f52bb7-122a-51d4-900f-7cd9e59ea613 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Preliminary
ed686a64-9de0-5b8c-99f5-503e5de24625 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Preliminary | Engineer notified of pour
b5511761-93cc-5f04-8129-843eec058f1c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork
9d725b14-02dc-5cc3-ae65-d8ade876a84f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Installed as per formwork design
48478bb8-321f-5a22-ae66-d5e56e44de86 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Permit to load issued
ca5c4517-60cb-5b5f-a6c3-06c072fddf8e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Dimensions correct
31d5d220-5ab7-586d-92e9-cf1fae034ce1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Position and orientation correct
10a6da8a-59dd-5995-b09c-fe82c7686921 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Forms vertical, plumb and true
bba23d97-4c2c-521c-a0a8-552080beaeb2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Forms coated with release agent
e93c8c6b-1b87-5cb8-8bee-c8c01b4a4363 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Forms clean and clear of debris
d7ee7b54-c5fc-59c0-b52f-d05fec341bd9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Joints sealed
ee78a5e9-bc33-542d-b86d-96e2a96f1b99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Formwork | Pour level marks
c1b2d3fe-e014-5348-b903-e8483d2bbe52 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement
e2074601-c906-5843-baba-858f11f98707 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Correct grade reinforcement
a1e1803d-408a-56b8-991e-a28bd7257bec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Correct bar size
8f8aeafc-7809-57d8-840b-d4a26e96632f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Correct number of bars
b17ed878-c27c-5ad6-9064-bcd008f778de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Correct spacing
11db5577-8a45-532d-bfc1-b328d0aa4229 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Starters bars included
d128870f-6549-5ef5-80e6-198697a0ed22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
3060bd73-5908-5c94-aa0f-2fdc21bcda4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
dd0841f5-ca7b-5819-8243-978b87f1d45c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
cbbf71fe-27aa-5020-b003-43b282520c5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Correct lap position (staggered appropriately)
6e29ca89-7559-5d31-a6a6-97cdaf2ce2b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
6945454f-9f9f-5418-815a-24dd40562ca1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
ccf19e04-4271-5177-b5d4-80eaad9f9580 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Reinforcing adequately tied
ac7467f1-f847-5532-98e2-9966bdf1725c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Reinforcement | Chairs or spacers fixed in place
09604957-c89b-56df-989b-0fd79631aeaf |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Embedded items
174746c6-9850-5caa-b612-7088654a9103 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Embedded items | Block-outs, ducts & cast in items installed
1b3e4ff4-3e25-53c8-b238-07b8c46ea4b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Embedded items | Correct position, level & alignment
9f434f8a-ea59-56bd-a250-3888c71c416c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Embedded items | Securely fixed in place
0f5f9723-74ac-5784-bef5-e3af3b3a832a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Construction Joints
221e36d7-bfa3-5524-ab99-c9e8ed47e6d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Construction Joints | Correct location
027220d4-23e2-525f-8ce1-31d33217cee1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Construction Joints | Adequately prepped
999a97d8-beb2-522e-a0e3-200fb02f5366 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 20 | Construction Joints | Joint board installed
596dcc56-6188-407a-8052-45d525e357c6 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21
4d69dba8-fd92-5f94-bc9c-034399247043 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Preliminary
632b32a4-4850-500c-ad79-ce762ffe9475 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Preliminary | Engineer notified of pour
266bf369-dd98-5f0a-a389-9b073d222d58 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork
82dc8a2f-becc-5f3f-9a3e-54bf73916ef2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Installed as per formwork design
084565f4-1c24-513c-9715-09fb8719a8bb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Permit to load issued
57794f4a-c3f2-558a-acf0-42fd7ff9c68b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Dimensions correct
eddf1574-185e-55a3-9500-6a925028e0b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Position and orientation correct
84368aba-4d1f-538e-85f8-05d906997b89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Forms vertical, plumb and true
74405778-4277-574e-9848-b65a79b6e0d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Forms coated with release agent
97866093-ce6f-5fca-b886-5951db683963 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Forms clean and clear of debris
1889289f-e53f-591b-881d-1c07441f6761 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Joints sealed
e59ef75a-f4dc-542b-abf1-bd15a7afd0ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Formwork | Pour level marks
55225095-f7f5-5cb9-95d3-9b2052a79c01 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement
9a554281-4e1b-50d1-b8a5-13d5cf580194 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Correct grade reinforcement
3d9b71c1-07c6-582a-b90a-e4f9739a447f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Correct bar size
85ffe051-01a8-5e95-83b1-72d8b4bc0d10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Correct number of bars
c1e0fe85-38ff-5806-96cc-7f827a0f32bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Correct spacing
687fbbfc-bf94-5f99-82f2-59bb777a7f55 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Starters bars included
4caad96f-8f40-5292-9fab-5f21d087c7bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
b11a29a5-5958-558a-b284-08ac4c0b96db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
d835cb04-d6b5-58b0-b569-8c689bea49eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
0c3b98a5-0001-5dec-95dd-406255327c4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Correct lap position (staggered appropriately)
217ac6d1-785d-5f33-aff2-b0994c850eb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
68a2904b-c5d0-5515-bab0-e022260e74c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
eb4d4028-6ab6-55e4-869d-136bbf6ea9bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Reinforcing adequately tied
3a17aca2-e3df-5c70-8695-158b87e05a54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Reinforcement | Chairs or spacers fixed in place
985a9865-6fd7-515e-89c6-8e19555f13ec |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Embedded items
6ef1f1db-9cbd-56df-9bfd-b2891a5db953 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Embedded items | Block-outs, ducts & cast in items installed
70c4215d-6e6d-53ca-b4b7-92d0720a7cc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Embedded items | Correct position, level & alignment
6367610e-aab9-5072-944f-4d4890941614 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Embedded items | Securely fixed in place
a3917a93-0c89-5d8f-8e8b-6b7a3ece3626 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Construction Joints
6d742594-cb3d-5605-9cd0-13ca1a30bcc2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Construction Joints | Correct location
872a24fc-10c9-5c2e-8592-abf5b9d531ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Construction Joints | Adequately prepped
d6e7aa77-e62f-5281-9b49-8615f04345f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 21 | Construction Joints | Joint board installed
ed8d551c-40af-47b8-a984-da0f94395503 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22
9337dcfb-f010-57b5-94fb-27984aac2deb |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Preliminary
345a7a3e-6fca-572f-af9c-e1b50a182f31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Preliminary | Engineer notified of pour
59a92904-3076-5983-9b4e-35bbcd0cea4a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork
3322101a-2494-5939-b583-5fdc7443fb7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Installed as per formwork design
c83bca4e-7f4a-5020-b1e3-5425e5b7c462 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Permit to load issued
2fa92093-7fc4-5c67-a7dd-6185739b33d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Dimensions correct
af945c1d-f44e-58aa-92c0-f4b610075137 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Position and orientation correct
cf82c35e-0029-56f5-a3bc-620c4ef24965 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Forms vertical, plumb and true
770780de-2ca5-562c-b01f-9f19d0ecaff6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Forms coated with release agent
dcf79108-d871-5084-bca1-277baad1309a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Forms clean and clear of debris
049ef3ea-63d2-5513-8e6d-06752dc63299 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Joints sealed
aa9e398f-ab9c-5fdc-bb44-252f57403621 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Formwork | Pour level marks
f3bb6881-ef2e-5173-95f3-63845be4854a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement
b5451aba-55a7-5d24-b30f-ae82fb7ce8c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Correct grade reinforcement
dc5bbb6c-10cf-5768-a30d-42d0fe62722a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Correct bar size
5ee0d4c5-f6e8-5051-93a0-517d77de0dad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Correct number of bars
616080b3-4333-5a3f-abb1-d4fa45eae416 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Correct spacing
a0e202d7-28e0-5f2d-9d92-8e1dcccd0e2d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Starters bars included
a84a6173-2a05-5794-a4b4-a1568903a758 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
3e853add-d4ce-5a7a-bcba-fe453c25e2d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
97bbd8be-ec20-5ce5-9e5a-88d9f908075c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
6811dd55-d16d-5fac-bd0b-82eebc12c8ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Correct lap position (staggered appropriately)
dc273f8b-9228-5c75-ad62-ebeb9a25279c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
cbdba1ad-e3a6-5837-ba62-de6955d6cb39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
fcfcf772-f9d5-568b-87c5-59c8f0d20092 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Reinforcing adequately tied
578fe76c-1b79-5ee8-b960-c61826a432a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Reinforcement | Chairs or spacers fixed in place
8e50b418-643b-52b8-a022-419729b80898 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Embedded items
40306391-09ae-5d58-b898-48f1dea32a01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Embedded items | Block-outs, ducts & cast in items installed
c676853e-3d07-5312-81ab-fef472a01a15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Embedded items | Correct position, level & alignment
97c7e513-d639-5505-900b-37cc8da72c0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Embedded items | Securely fixed in place
827d9676-cf56-5ac7-aafb-dcdce38f7d9d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Construction Joints
d07338a1-582f-549a-8b5d-51bc94306525 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Construction Joints | Correct location
99399456-8d0a-5674-9dd5-2de44df4947b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Construction Joints | Adequately prepped
6c2d59ac-eff8-5c31-884d-968072e60e8e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 22 | Construction Joints | Joint board installed
e317359a-10a6-4186-9b13-7ec4374a18a1 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23
f7d6720b-e7a2-5d54-9cdd-5dabfeb90b9c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Preliminary
59063cfb-a7a6-5753-ad05-fc173bca46c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Preliminary | Engineer notified of pour
45d5161f-9496-5717-bcb8-b2d6c9470da9 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork
df57f6ea-9113-5808-96ab-eec5c8f7e7af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Installed as per formwork design
e4b0bb22-0144-5137-b6a8-63b702367ac4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Permit to load issued
2e6b7157-de56-56e0-9ed8-a278c1c206ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Dimensions correct
ef68be86-052d-55ba-a0cc-cd2ea6fe6e3a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Position and orientation correct
3a7d6f6c-6eac-5e2a-8569-ccc60d29ce84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Forms vertical, plumb and true
0b966253-7d13-5eaa-a1b2-ab6ae3fc087f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Forms coated with release agent
43520045-0169-5f3b-904e-b1e8ee68ab9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Forms clean and clear of debris
0c54466a-150b-5476-b9d4-8d4147adc54e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Joints sealed
080b0355-01e5-5e9b-9bda-6125bcdc0bbe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Formwork | Pour level marks
f130cee2-227f-59fd-a254-b64d4973602b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement
07713a11-1d81-5e20-991d-ef41dfc5aea5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Correct grade reinforcement
0cbe6b7a-0b1a-5203-8f73-0d50de17e9ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Correct bar size
37fc495e-3584-59a9-853a-0811f36ca572 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Correct number of bars
e6a05234-2f0e-5a9a-9f7b-244ee9cd7061 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Correct spacing
d595a190-f5ba-5a27-9f7e-c149bd93ddf3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Starters bars included
668ae3b7-f8c3-5852-a0b1-af3774593f98 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
cf409826-ae4d-5f6e-84f5-c92e2332cc1c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
d8746299-dd3d-52cc-b1d4-7a40e7e03866 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
ce855385-b14b-55b2-b5e0-5f3bd25574c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Correct lap position (staggered appropriately)
6e42f3f4-1993-5d9b-877a-5aa10b98161f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
567e13dc-8266-5a2e-83f9-ad8d23b2bac0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
2c0daa3a-aa17-579d-a871-f59fdfe487aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Reinforcing adequately tied
01a8faa7-829a-5129-aeb5-8ea8705d0b17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Reinforcement | Chairs or spacers fixed in place
944b38cb-da3c-5bec-b824-9f08d3141d53 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Embedded items
1ac27dd0-14b3-5dfe-a529-208aee5724a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Embedded items | Block-outs, ducts & cast in items installed
d15ff2dc-d55c-5b71-93ba-1b850f8ebd8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Embedded items | Correct position, level & alignment
395eaeb1-41ee-52c3-b7a2-3dd361a1f6a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Embedded items | Securely fixed in place
282bce41-4183-579c-993d-cdbc497466e4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Construction Joints
0c9e173a-b07b-5be3-bcc1-865c1d2ee17d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Construction Joints | Correct location
f683b964-04ca-5552-a13b-77220dc20830 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Construction Joints | Adequately prepped
7b895e1a-1066-54fe-ab83-8c2f17ba346e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 23 | Construction Joints | Joint board installed
54c5bae8-cdde-434b-a874-21e2fd7ed7a8 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24
08cdc983-4644-562c-9036-df51eb53876b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Preliminary
90765a33-1c1b-58b9-999d-1e6cdd867a9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Preliminary | Engineer notified of pour
ba73f5eb-aa9c-5da3-b0f7-73fd8237f087 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork
61a29815-a862-5275-9966-f72184965197 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Installed as per formwork design
45656182-6460-5c80-b801-fecf24e534e5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Permit to load issued
eb45d360-1198-569b-87f6-a1a49694d42c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Dimensions correct
1325addc-d7aa-55f0-a64e-199a5aa57411 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Position and orientation correct
a177a7c4-bf29-5445-a845-077d5c26e1ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Forms vertical, plumb and true
a0bfe52f-6bde-599f-ab13-d08839ae6479 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Forms coated with release agent
51de46b7-df53-5dc2-94f1-b78c8b5344be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Forms clean and clear of debris
2b44a722-c0b8-5cd0-8e85-b4cd3ab3f3a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Joints sealed
bd4842cf-ad29-5aa2-80ad-610bd6bf82a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Formwork | Pour level marks
6f9d1dca-b975-5914-86b3-997f61f21f2f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement
dd0473dc-2b97-5f9f-836d-28dadaebef94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Correct grade reinforcement
317c9fc3-dc38-5d68-ac2f-c18080e57fcf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Correct bar size
56e0b4fd-0c3a-5fcb-af2b-81852889deee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Correct number of bars
b74c092f-a796-587a-86ea-6f93c62b9a0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Correct spacing
0ff6b04e-f4c7-59a9-9b65-5fcf2f79fe55 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Starters bars included
90f939e4-4d26-5167-9a84-2da622df95d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
921b56dd-9c7e-5e07-8ba2-e5870031974e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
af9cdfb3-c253-5eb1-800e-67cbc3394fb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
3666e476-194e-5254-b23c-bcf2c2f819d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Correct lap position (staggered appropriately)
44decb4d-331e-50fb-9e61-5dea9b1f7f80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
de718f52-9077-5f07-87cc-fa59a4bac4f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
705e9e69-817c-5bf6-9a0f-53c1ba1e0edb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Reinforcing adequately tied
4796e464-7299-5996-89e5-2196697f9a22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Reinforcement | Chairs or spacers fixed in place
93a33b3c-17f8-5af3-b561-452596702f66 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Embedded items
a91678ff-87a1-5291-bf43-e59ba03d5fde |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Embedded items | Block-outs, ducts & cast in items installed
84b19dbf-33e2-5fc0-91ce-2bb3a6abceb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Embedded items | Correct position, level & alignment
5b92d8bf-0b9c-5ea5-841c-19aa793943a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Embedded items | Securely fixed in place
b4cd861b-2642-5222-b27d-92d3584c017f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Construction Joints
e29db4a2-d296-51ad-bd41-9147b485d11d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Construction Joints | Correct location
10c319cb-5fc3-505d-a94c-a2bbc263876f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Construction Joints | Adequately prepped
84f04ea8-9a82-5f70-945c-50add47ad836 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 24 | Construction Joints | Joint board installed
a28ef9dc-7214-4eb7-b19a-8f83eb60e9ee |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25
bd58c9de-d876-557c-af62-9709684e362b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Preliminary
e8d8012e-c97e-50ed-9894-69dcd21435f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Preliminary | Engineer notified of pour
996918b1-9919-5e64-b8b5-721735df01ff |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork
4b93c8b8-836b-5493-b0e2-d71a47a1acd3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Installed as per formwork design
27f7e49c-2a50-5078-9127-711b45e0d460 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Permit to load issued
300da27d-382d-5e1d-ac35-1de6f71019ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Dimensions correct
bef13095-bd44-5e9f-bf39-98f83161d530 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Position and orientation correct
0cc815ee-fd3e-514c-96b6-45a2f3ee3dc7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Forms vertical, plumb and true
41a43106-f6c8-564b-8f4d-b0286b51af1a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Forms coated with release agent
393a5ed4-f8ad-52e9-9368-da9c4e6d7b20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Forms clean and clear of debris
c40860e6-d4b1-5663-9b82-f851b791f83f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Joints sealed
f6e44e51-841d-5acd-a14c-d75fa23e0a07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Formwork | Pour level marks
1debf793-a22b-529a-9500-72b6b065cca1 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement
f0ec58eb-a4ab-5d6a-bfa2-c9be8017339f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Correct grade reinforcement
0cd2b92e-911a-584f-913d-facffaa30d6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Correct bar size
2582ed88-815b-58c4-b82b-f46010a9078a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Correct number of bars
78959724-3f57-5112-ba0f-0827d105835e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Correct spacing
61485b37-ecfb-5ec1-97d9-1ae1c62213a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Starters bars included
bb7fbc8c-f1e2-5f5e-bea8-6677f3f4c2f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
72e96a25-a640-5e38-9f57-be8d3353cea8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
19586219-0392-58b5-b70d-0eb94c3a215e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
64bb7d0e-dbb0-51d8-8bae-f1ef050ed58b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Correct lap position (staggered appropriately)
d7295ea5-b4fd-5c7d-8b6e-c54df3aa80d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
738acc17-5f40-58eb-a386-6f43394cb2dc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
b8c81490-a75a-5b48-adb7-5036f38ee590 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Reinforcing adequately tied
9cde3224-0176-5f4b-84c6-11ab0678c1d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Reinforcement | Chairs or spacers fixed in place
0454053b-6e14-52be-a6ad-6059c0f0d25b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Embedded items
9ecb68b1-5194-59db-9250-39d29bbfd0ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Embedded items | Block-outs, ducts & cast in items installed
d91e9fa7-0a03-51f1-8220-e0a2d78f07e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Embedded items | Correct position, level & alignment
20bcfce0-2ab7-5e98-a8e0-60b43506158b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Embedded items | Securely fixed in place
9f397463-bdfd-5069-8548-19ab6d589105 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Construction Joints
f90cc83d-d06e-5e51-be3f-386f9092ab45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Construction Joints | Correct location
20fb5b10-a589-5224-8165-f257cae17b16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Construction Joints | Adequately prepped
6b14edde-00bd-5338-a818-74aca38c004d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 25 | Construction Joints | Joint board installed
d144a20d-9ce8-4d48-894b-c67d152e0b18 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26
f1bd3ba0-a14f-5d4e-9341-774524d5096c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Preliminary
0c797310-b17d-557e-aa0a-508180beb96e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Preliminary | Engineer notified of pour
38ebd371-4366-52cf-9d2f-20bd4563878f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork
280bc69e-e7ee-592d-80ee-2a77eb9d207e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Installed as per formwork design
203ccad2-514f-5156-9f14-410f1f09f173 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Permit to load issued
35fb0361-a0d4-5973-95ea-14b62a7efd60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Dimensions correct
88053a54-4826-514e-97e5-771d9f6bd0f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Position and orientation correct
8d1ceca3-4a2b-500d-b58d-b948becb9b90 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Forms vertical, plumb and true
b20abf14-8bd2-5d8f-b42e-22ffb4bc34a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Forms coated with release agent
479e831d-3592-5317-8d4a-616df6e1f0db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Forms clean and clear of debris
0b96742c-0746-5b5a-a398-60b26cb731ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Joints sealed
1e088aa2-ef2f-547d-a389-f5a5efa1795d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Formwork | Pour level marks
0a835c90-c639-5b77-9d38-c590359ff759 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement
22851f78-60af-5f52-a892-501f4dca2d8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Correct grade reinforcement
88ffdd1f-be1f-53c3-af0e-7cd78ea4e913 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Correct bar size
702855c7-3001-5bfb-8e84-168aedb0aea4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Correct number of bars
39fbbe31-f53d-520f-9676-1756b2039d93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Correct spacing
d191b19a-54ce-530c-b92d-edd786ca96f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Starters bars included
77747d3d-b15b-5e6f-b4d1-0a3116aea017 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
fdda1c19-e5dd-5b2f-9a21-30c76a67ac93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
1a6166b7-be5a-597a-91d5-a5b8b8ae019d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
ed1ebc2f-022e-5d00-a649-8607d7719fd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Correct lap position (staggered appropriately)
7b3f650c-1197-567a-a522-aa2e23ee8076 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
cb1d8c8a-1532-50c3-8efd-96604eed2235 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
aeedd212-4e7b-56d1-a920-7464f928a423 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Reinforcing adequately tied
e42aa670-f540-5cee-a1c7-d16f2989f678 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Reinforcement | Chairs or spacers fixed in place
07832ec0-392d-5f1f-b713-1a3c8a9f1d5d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Embedded items
6dbae15a-4285-5f15-a155-e995a7cab700 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Embedded items | Block-outs, ducts & cast in items installed
aff24841-f107-5a78-a58d-a028b0cfae88 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Embedded items | Correct position, level & alignment
7c597d83-eca5-5c00-ad4f-4fd791375942 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Embedded items | Securely fixed in place
f279d843-7919-5e07-8f48-74516ee11be4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Construction Joints
5e398dfc-c7d3-5c3f-af4e-5a7d3547ceb1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Construction Joints | Correct location
849b603d-3500-5ef5-8055-121ebb495af2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Construction Joints | Adequately prepped
887e059f-e49c-51bb-97e7-22fa85feaaf3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 26 | Construction Joints | Joint board installed
205bf05f-5f23-46c9-bb41-a98fd681dccb |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27
1569372f-446e-589e-afc6-741986acc319 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Preliminary
d79e2480-d55d-5897-93f0-e629c1c313cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Preliminary | Engineer notified of pour
f84c4177-d7fb-5b6b-93bb-b9ae7837d1c4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork
a6aabd63-bd47-5ed2-a869-d8189b9449a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Installed as per formwork design
943d64dc-e496-5643-b7c5-a2c50354422d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Permit to load issued
9bc4d74d-c578-5b4d-bf17-ff45a5a77f3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Dimensions correct
5bdf8016-9cde-5ec3-9e73-4bbe979f2b6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Position and orientation correct
66557dc5-ad85-5c77-8e7e-ffe0c555e2a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Forms vertical, plumb and true
671bb46a-c353-55c4-b528-86c38a473734 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Forms coated with release agent
ff4a3cd9-5d09-5333-b484-b3e935cbc9f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Forms clean and clear of debris
7576c5f3-63e1-55da-b617-bb1e24af10a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Joints sealed
4a8138f4-655d-501c-a6e7-8f41b539707c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Formwork | Pour level marks
ac945e8c-ad0a-57fc-a04c-3a59b0b820ec |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement
6e049940-76e3-5201-ac37-d1b67110d443 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Correct grade reinforcement
820cbe79-876e-5ec9-9b10-8f89f2aafcb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Correct bar size
ba77186f-2271-5d3f-8736-bc5293c076f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Correct number of bars
21fc543c-3285-52c0-9c38-4f08246c22b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Correct spacing
c2ac2d92-b279-50d0-8f29-278dae206ac8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Starters bars included
1799761b-f04a-5463-ae32-dc738d4950ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
e65277e7-51e6-5aed-96b6-416756c98850 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
07c05783-bc6f-574a-80a6-af28e94cf93b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
4f1579d1-022b-57fe-982d-f2eac448a795 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Correct lap position (staggered appropriately)
a2ccdb53-cd88-5ee5-b74f-1ab53a997e20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
ffd1a953-21bf-5c68-80b0-19f980c8b8f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
7211d95b-601b-5b80-b972-16e7998844bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Reinforcing adequately tied
83f3c9ba-783a-5ba1-add0-d51f8566b89e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Reinforcement | Chairs or spacers fixed in place
1bceb690-1336-5b4d-9359-0ce5b63124ac |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Embedded items
59e0d947-e668-5062-bc91-fed661894167 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Embedded items | Block-outs, ducts & cast in items installed
b7727898-163f-5712-bed8-59ec3e46507d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Embedded items | Correct position, level & alignment
51bdcb2e-3462-5c07-b471-74c02e92d944 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Embedded items | Securely fixed in place
ddfe3dbf-6c22-5813-affa-55ae2a38f2f4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Construction Joints
6ea9a0d5-a553-56ed-8cf2-6bb851b5d86f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Construction Joints | Correct location
4556927f-a5b2-508d-870b-7181d1d74ae1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Construction Joints | Adequately prepped
0d4bf376-9d03-5928-8c47-36a85badb114 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 27 | Construction Joints | Joint board installed
e3b84388-d0bc-424b-85bb-123f88adadf6 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28
63ec2f13-94e8-5ce9-822e-a687629e2f03 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Preliminary
59d9b828-35cc-5aea-a8b3-e5a8b9e9eb47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Preliminary | Engineer notified of pour
039f621f-506e-5731-9c51-1bebfce8d835 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork
0fb61c3e-b805-5361-83c9-24f022249f8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Installed as per formwork design
32a1433b-23fd-5dca-b3fe-e138da618f76 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Permit to load issued
36313d78-cfdb-56dd-90d8-9fc833b981cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Dimensions correct
030274e7-59d3-5a1f-80fb-b048232b18c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Position and orientation correct
ae4c0568-50bc-5937-a90c-914174910704 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Forms vertical, plumb and true
1c4f3858-833f-5306-a2a3-c76231041de6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Forms coated with release agent
837c3c95-3b5c-5ae9-9453-da7664188fc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Forms clean and clear of debris
1909ee68-2411-5683-b1a8-9a3fe92bbf17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Joints sealed
4a29065d-85d6-5cdc-9afb-0010f393f8f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Formwork | Pour level marks
86586112-5c93-58db-96e3-c73efe922f7b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement
c722f213-41fa-5fa0-bfa3-a76f188a65d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Correct grade reinforcement
a29ddb8f-239b-542c-8703-f861043312a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Correct bar size
55134ba6-ce66-5c70-a5e4-58087a12d9fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Correct number of bars
5ee41dad-0ddc-5993-9668-4f6739d51eaa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Correct spacing
dba78668-6816-58b3-b256-a28fec735f99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Starters bars included
9305f4f8-5447-56f7-bd54-205a18cf5c73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
6e9f24ad-c203-5dee-9626-eb51687698de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
e4868c10-c355-5d14-90c4-c71c80e2563f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
f5220af3-e07f-5ae5-96ea-6bad97f61c9a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Correct lap position (staggered appropriately)
0e7bdd25-70fc-515b-9679-deb8f1c6abcf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
2290de2f-8972-5b83-805e-88f5aab38984 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
5bda777e-2e98-5030-af26-c4efae624234 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Reinforcing adequately tied
119e16ae-0bcc-5ef1-8db3-ccb1100b2dcd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Reinforcement | Chairs or spacers fixed in place
672182f3-cc4a-585a-8ebf-0ad194ada481 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Embedded items
2de1a347-db8b-513c-a056-06b14ec483f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Embedded items | Block-outs, ducts & cast in items installed
a5811342-b0f5-5f37-a9b7-773465ccfec6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Embedded items | Correct position, level & alignment
a6fde625-9f90-5aaf-823f-16b2312487c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Embedded items | Securely fixed in place
d515fa4d-0225-53e9-9c5a-d1c87896015f |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Construction Joints
2219104d-b9bd-5f1b-aaf0-b826e126d615 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Construction Joints | Correct location
fd960705-c6a2-5dbe-b3fc-a76fd81313fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Construction Joints | Adequately prepped
296c71a9-3261-53c4-bb45-b38d8a1402f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 28 | Construction Joints | Joint board installed
1ece5d55-156d-4a54-94de-d0e531e85cb0 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29
75e4cfc1-b293-5955-a866-b1f7c9b1d4f7 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Preliminary
3bc4bc3b-22f3-5727-8ebd-b2e024b635bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Preliminary | Engineer notified of pour
7865bc7f-2375-576a-820f-f4b9a92f6dc4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork
9e1da3a7-e8f9-5657-a023-1a3000736cf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Installed as per formwork design
50707be2-6a59-55ad-9eeb-1aad3b7163aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Permit to load issued
111cdd53-b348-5dec-b7cc-87b17e83b87e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Dimensions correct
9c3d62de-ed99-519d-9633-8316af84f240 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Position and orientation correct
01263b2a-832a-5b77-8b85-f12ccdf7c2d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Forms vertical, plumb and true
aa210232-8823-5e80-9a28-05673f71ec3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Forms coated with release agent
44e64e7a-0a1a-5b36-b990-c9d2f53ef0ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Forms clean and clear of debris
d0765201-dc98-5dbe-9756-575ad30bc23b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Joints sealed
9074f60b-1966-5d9d-a4eb-0d36754327a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Formwork | Pour level marks
1c7ae905-f28c-5446-82c0-8f98819df159 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement
7f80eaf6-2c45-5195-94c5-bec64fe65d4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Correct grade reinforcement
3c03fca4-3683-57ff-a04d-4b4b5729e9e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Correct bar size
bba21432-89d3-5281-932f-e8b027d8ac74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Correct number of bars
286d34ce-462c-58e2-b348-77c1a08b6dca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Correct spacing
c0b9a74e-d63c-5939-8252-8efc7dc8d2e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Starters bars included
60b9cb7e-e0f6-5640-808e-0091c9997a8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
8292986d-70b3-5cc7-a19b-93e38e636dce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
99f7ffb3-3405-5ed2-894e-9c82810247f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
547ed363-5c66-51b8-be51-a5ab5ee3cfe3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Correct lap position (staggered appropriately)
172f812d-b1a4-5496-803f-75bd0522b445 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
eba93266-7a88-5a64-807f-8908f2e93494 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
b7bb28c2-c81d-5905-8f6f-8c693ce0d514 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Reinforcing adequately tied
260a4e43-a13a-57c6-b31a-8fb986fd833e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Reinforcement | Chairs or spacers fixed in place
c00f030a-197e-5d9f-ace7-c716cd5c56a6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Embedded items
9d034919-87e9-5797-af76-6ce4b75be334 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Embedded items | Block-outs, ducts & cast in items installed
5247161d-22a2-5d5b-ba9a-86f25c58816b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Embedded items | Correct position, level & alignment
cefc46a6-e045-59e5-884e-b66c6ebda9b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Embedded items | Securely fixed in place
d08d93a6-82f5-5927-8f67-9d6a92d9dfe4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Construction Joints
79bdbd7d-dab4-56a7-97ef-8780f506b071 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Construction Joints | Correct location
dbb0aebb-90ef-5571-acc6-62e9bd344f3c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Construction Joints | Adequately prepped
81eea468-a70a-5cd2-861c-02e51530cffb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 29 | Construction Joints | Joint board installed
f357c6f7-5b66-4027-b37c-3f7bdc2c42a0 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30
eb6bac18-7ef5-5b6f-a295-cd4d09ad206d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Preliminary
d3aceba6-a399-5509-8a61-af8a96ff09d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Preliminary | Engineer notified of pour
f6e9433a-09a2-5d47-9107-594c3383fa47 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork
9b375d6f-702d-5acc-8119-3b16433938fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Installed as per formwork design
1c1b2871-496d-50b1-a332-392e4a4b6a9d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Permit to load issued
55645d6f-ade1-516a-970b-2f5792aef4c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Dimensions correct
6b5ca7d9-b07f-5f53-b70c-d1afa3373429 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Position and orientation correct
87855045-9d88-5487-9727-984ef84f2bb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Forms vertical, plumb and true
6aa686c2-b69f-53b1-8ba2-ce6f97538e96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Forms coated with release agent
599154d9-2d26-5b5e-8c26-32e25c7df8bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Forms clean and clear of debris
9910b708-d166-5b92-86c5-38f766ba3dd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Joints sealed
c800d759-9493-5f71-aee8-8d06e695f006 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Formwork | Pour level marks
35b691f5-7721-566a-a7bc-50f46b9d0e7b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement
fd1e3c0d-666f-51de-85d6-38fc98cc2039 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Correct grade reinforcement
871b8fd0-8be7-5fed-8cd9-d8a49979d82d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Correct bar size
56d2f27a-c89a-5346-9ce3-43ff9d64f82e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Correct number of bars
79070aad-f122-5052-9d4e-6baf19da8f33 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Correct spacing
5c35a932-ec80-5578-bb39-18da35779b5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Starters bars included
0d6c1dc1-2f81-5bf9-99ac-74ebd220dc4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
ba940399-9b68-51db-a38c-90484a2ff9cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
cdc396e2-d3db-569f-9c0d-15c4fa85979a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
797059aa-f035-5ec7-a614-a337583aa7fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Correct lap position (staggered appropriately)
bffa6281-29a4-5482-870d-98a831d19db3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
925bd5e8-139f-5ac7-9a72-649537644c08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
0dd12f5b-1baa-54ac-a7b4-520f74128c97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Reinforcing adequately tied
ead01874-bf54-5f1c-b2cc-cb9477c751cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Reinforcement | Chairs or spacers fixed in place
9eab265e-fc66-57bf-bb3c-e93356e70b8a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Embedded items
4caca6cd-2767-594a-acf6-6f2b2ef48244 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Embedded items | Block-outs, ducts & cast in items installed
970a8957-38a5-591e-b6bb-4789574466f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Embedded items | Correct position, level & alignment
2c3e62aa-a7b5-515c-b4af-6d82ab8ffb07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Embedded items | Securely fixed in place
4122cd23-b5b3-5a6b-8b14-ffc7fecf127c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Construction Joints
f375e9dd-5718-5eb3-942e-1dd0c87964b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Construction Joints | Correct location
e045b9b7-48cd-5eac-9af9-bfbbf0c98e54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Construction Joints | Adequately prepped
b3301bbe-7236-52dc-9999-d4ebe1079f0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 30 | Construction Joints | Joint board installed
04f8d6e2-8c2b-405f-9a64-1c713980988d |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1
a4159d40-e134-5e03-bc99-6288d9f76acd |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Preliminary
bf0bc0a0-b12d-5733-a1dd-95710d07d0ea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Preliminary | Engineer notified of pour
9d3d6ca3-69c0-5765-82d0-58a1aa6651e0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork
fdf5b2d9-2f3f-5758-8251-ae080fed5971 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Installed as per formwork design
7d4c6608-a555-5e6e-a4ea-d01b35348e2c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Permit to load issued
d294cd61-0f7e-5807-b22a-b659883695ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Dimensions correct
b46dcca3-5b1e-5b13-8a33-0669f78eb914 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Position and orientation correct
c954084d-27f7-5b82-b783-aecac8620892 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Forms vertical, plumb and true
e44b2aa9-b800-5cc1-8054-3daa4577edef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Forms coated with release agent
cdb28bf2-26b0-5436-b56e-9a1e3ed463a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Forms clean and clear of debris
e5467ab2-5230-55e3-bad9-da7f83da7eb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Joints sealed
0288771a-f68e-5ecd-9ac9-74a18cd69a41 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Formwork | Pour level marks
c47188bd-dc46-57ca-adbd-e36dbfb2d54a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement
8afaeb4d-1cfa-5c06-8de0-f10cc2695539 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Correct grade reinforcement
c23fb88f-0730-5474-98eb-bab7afe5a5b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Correct bar size
cadbfc27-8301-5b8f-9c13-0a86397e1871 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Correct number of bars
d69d8cd1-a0b3-5616-8874-7e83cbef0ade |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Correct spacing
b038c65f-5a1c-5a60-995b-0fd1c77f0430 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Starters bars included
0dbd52d7-d2be-55b7-984c-583fe133994f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
c4affc34-72f6-5584-9636-caadd0eedf43 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Correct weld lengths (min 10 x bar diameter)
55a0ada4-20f2-5d70-b8ad-91b9d4a7d81a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
8a66232f-3b68-5175-918f-74df20c141b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Correct lap position (staggered appropriately)
f22cb764-9669-5468-9ccc-f481aff9b92d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
7ff4d419-344b-5eb1-9754-f65f3456989b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
6f462d2e-600b-5d9c-a51f-eddb98fcf467 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Reinforcing adequately tied
ae13e2ad-af28-5f15-8297-75795b4227c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Reinforcement | Chairs or spacers fixed in place
b52af537-1391-52f6-991f-6f8190951856 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Embedded items
2ccc8113-6fa3-50ee-824e-1fe3d193e82e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Embedded items | Block-outs, ducts & cast in items installed
f856e615-ce22-5eb0-b05d-859532bd82a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Embedded items | Correct position, level & alignment
ec4b4a5f-0fba-5d03-abda-79c4a926a08a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Embedded items | Securely fixed in place
634cd937-0eeb-5080-915e-678db61dfd89 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Construction Joints
f73f468a-11d3-5ee3-8855-d4e37ecf15e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Construction Joints | Correct location
b63829e8-8e68-5880-ba9e-ea757306067a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Construction Joints | Adequately prepped
d2f77ad6-578d-52c5-98da-dc286cc101e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Pre Pour Inspection | EG - 1 | Construction Joints | Joint board installed
da3fecd6-4259-4977-890b-fd2f52920fb0 |  | fail |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA
ca527faa-59ce-442a-86c5-2ef3115e9fed |  | fail | fec3058051f3508964e0c71c2171b052528e9896e8bc61497ec5db7f73755646 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB
6aedc372-df92-5584-8585-2af817f9ef70 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests
addcd98a-6179-546a-8a79-46a8bf03b4e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests | 1.1 - Concrete Mix Desisgn Approval
ca4a4638-ffe0-52f2-b9a1-5559a067b290 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests | HOLD POINT
bfdc2779-5693-5a67-a7e8-710653be8e07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests | 1.2 - Reinforcement Supply – Certificate of Origin
152b9213-034c-5a7f-b1aa-51528f879ef5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests | HOLD POINT
bec96e57-3b34-5b33-a25f-358bfb215f67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests | 1.3 - Shop Drawing Approval
867d5d0d-7fe7-592f-bb6c-036e11ab8f37 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests | HOLD POINT
1011b651-be5f-5d16-9d24-5c3f8681ddcd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests | 1.4 - Form Release Agent
995e3f1d-5d2a-57f9-ba57-0cd40787cc98 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 1.0 Pre Construction Tests | 1.5 - Cast-in Items
8b233f36-9c16-501a-a73d-ee76e65123b6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 2.0 In Process Testing
a7c9d5ba-9945-548b-bac8-88762a503441 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 2.0 In Process Testing | 2.1 - Inspection of The Reinforcing
2adba988-1cfd-50cd-98ed-ed88331517a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 2.0 In Process Testing | 2.2 - Checking Formwork
d82f17d2-a30f-59bc-b3d0-120e501b6b3d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 2.0 In Process Testing | HOLD POINT
569fc208-a435-5903-b1f2-77c76fb7995d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 2.0 In Process Testing | 2.3 - Pre Pour Inspection Prior to concrete placement
9af190db-1d1a-54db-8041-2a514cab8c74 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 2.0 In Process Testing | HOLD POINT
a8cb72e4-a23a-5b8a-81ea-7c7e5f0c56c0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 3.0 Concrete Testing and Inspection
be0a3db7-eaae-5699-b4ca-b7bf36c39d84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 3.0 Concrete Testing and Inspection | 3.1 - Concrete Delivery
20a34056-e73e-5573-9884-9779692115ce |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 3.0 Concrete Testing and Inspection | HOLD POINT
0a7d3ced-fde6-5af7-a2ea-57990a8f0841 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 3.0 Concrete Testing and Inspection | 3.2 - Concrete Placement
80a2e62e-cafe-5387-a1cc-15158bad53ce |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 4.0 Post Concrete Testing and Inspection
3ae20c3c-8863-5fec-8097-fabdd71f27c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 4.0 Post Concrete Testing and Inspection | 4.1 - Concrete smpling / testing
b68419aa-86d1-5892-90c7-93b17cb0980d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 4.0 Post Concrete Testing and Inspection | HOLD POINT
c24302a5-4056-53d9-805d-64967daa4c5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 4.0 Post Concrete Testing and Inspection | 4.2 - Surface Finish Requirements
16915386-85de-54eb-b4bf-c7824f0840f5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 4.0 Post Concrete Testing and Inspection | HOLD POINT
7801d95c-0484-5bd1-8c0e-cfebe656760f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 4.0 Post Concrete Testing and Inspection | 4.3 - Concrete Curing
bdf0bd12-37dd-552f-8791-cb1c4e32c98c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 4.0 Post Concrete Testing and Inspection | HOLD POINT
3c6c21a5-4ee3-5bd9-9450-b21651613a85 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 5.0 Final Documentation
2bf657f8-fc5d-5ec1-9a15-752a877d5be8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB | 5.0 Final Documentation | 5.1 - Producer Statement (PS3)
ec947eff-e4b7-45a8-92bc-8f6ebb9a8cf0 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA
89b9a109-b1bc-4730-bb10-9abe5e603b21 |  | work-in-progress | 220b8ccdf1bde5ca4538240bfbc232b17b9ed86b1a1d820aba4879bec05217fc | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024
471bf91e-a8d6-5f67-8e53-5c9db4eca7d2 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
e47c93df-401e-574b-80d1-a2d29fad036a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
16785704-4661-5412-9834-583f9924bec7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
1843b164-7149-5f0a-96d8-9af533af83f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
33e35000-9191-5968-b252-6d5b1c5fa9ea |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
798b5794-c42d-5254-8d33-1344c9aeea73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
ffb0e6bb-b626-5d5c-bbaf-4a937b2cb51d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
a1d7785e-9088-5530-a8f2-a65022834910 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
445a4e15-47e0-5b48-9484-8bee856fa3f3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
6603732c-0169-5c5d-b0b7-8c1ef6144cac |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
ba2ca8e0-4d51-5936-9967-8b025ca66f44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
60461f1a-2ded-5f5d-9dea-43a79518b17f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
45f83114-09f2-52d2-be1f-d74d1e2ce951 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
86a20bef-0aab-5d8f-ad37-8f054dfd3b94 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
44f117e7-a46b-5aaf-a432-1fd934e3af84 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
19720777-a1c6-591d-a5dd-3da28da99b0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
af13cd22-5cec-59a4-9af7-add55e41d369 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
08677ffb-1641-5eae-9a07-223df25fd8fe |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
45d7d5f1-c304-599c-a204-9095a1a6f9aa |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
9f6c186f-78ff-520f-b273-0eac5c71f99e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
537b88fa-c040-50b7-b4eb-e4fedd75ce3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
133541af-dcf8-5bec-b641-a43df22e58aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
ebe44f8e-33c4-57fa-9dec-eeed8084f112 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
97aecf5b-b92d-50ae-8c09-e968995b13fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
ed417cb6-2f1d-5f8a-9e70-2def14e66f17 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
bf1f694e-27be-5fa0-ac49-7f4f7ac1865e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
886e916e-6226-55d9-82a1-d0b41931cb67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
95d90a23-0dc6-5f09-baa6-f4131b098e42 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
65cce590-2e84-5dfb-aa39-51e50de88e52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
5453cee2-9b9e-5115-9472-fc85449b15f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
bbc97260-35f2-5f53-ac99-9b3d431698a5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
558d8b2f-9b67-5723-8478-e93305bbc71e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
c6278256-6497-5ced-9065-d3b37a923f7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
2a3956d0-2a24-59db-9eb9-ee4b9b21645b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
89a6be71-2e58-59ed-9b61-872c5e9308c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
6ca90d91-c6c7-50d4-89be-ec8c95ff9d47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
964d0bd5-c69c-5a0f-b93a-caac2c9f4d55 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
9fa1b682-3f4e-550e-90fa-6bf7483a531f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
b4f725eb-5b17-5848-b002-ba4ff73a161d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
3efdd44c-1317-5304-88f5-8c9c1e71fe3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
4554a5c1-a141-553e-add0-8c1f640b0f80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
adb6b610-ee83-5b7e-9c3e-56df384d89b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
c0f82d51-701c-56fe-aaef-e7e2dff9b793 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
9cb5d615-0d1a-5101-88cd-040423db625a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
1c1059f7-61a1-51f6-90de-1fc86b528763 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
65381900-d419-53ad-a7ed-5e46b5c4d199 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
49cb33be-6134-52cd-b5b6-1cefd6e6962a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
94bc2f97-c055-55b3-965e-4ad0fb37185a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
87ad0981-1e3c-5d6f-b8c2-6159adb4afa1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
14d10cdc-75f5-5ee5-952f-15728f1f145d |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
51256a7b-8970-5912-a4d5-6c8b059ad946 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
77e47a18-7f6d-593c-ace2-40b2bd6b30e1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
2d13695b-2571-5600-b6f1-95a4f00f69eb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
9815b617-f92e-5265-a843-30d5132fb42f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
9b0e79ba-5568-4e7f-b1da-fafccac0194a |  | work-in-progress | 220b8ccdf1bde5ca4538240bfbc232b17b9ed86b1a1d820aba4879bec05217fc | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024
2686db21-4ed9-560a-abb7-979a3a7e1d08 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
ec322a7a-aae6-59d1-9566-f28135c4575c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
485b4e6b-7e03-5773-b6ad-2e2e31eb8d25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
86b859b6-10d8-587a-aacd-045ee8596a65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
ee50d2a2-adb8-532f-8774-a50ec2139fd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
8b8a2f6b-9627-5697-9e79-5306b3b2ec56 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
c1a7b835-a94d-5bc7-b3fe-ad34728abdd0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
a7bc9e99-480c-586c-8f65-ed720ca96068 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
4255bd1e-3586-521d-9d9e-698657178cac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
1c0c35ce-82f7-520e-a80f-d8bc6a3149cc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
5b74c5c8-1cca-53a0-adae-3454ff857221 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
f543fb6e-af3f-5b08-b0bc-c1258b03949d |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
4d8f6dd8-96e8-5375-acdc-8f288902f5ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
60f3aa2c-cb8e-506a-966e-5692c92b1b38 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
668a1d94-6936-568b-9d2c-089c0f6e2e2e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
1448ffab-83c1-5bf0-8439-4a3999455bab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
6baa1fba-c082-5df5-83fb-55a9bb89c34d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
fab4ce47-72b4-5780-842b-0fe290dfcacd |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
31ff652c-82da-560d-8f67-b413575524f1 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
412ae4c4-a671-5638-9d6b-1640067eefae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
97792807-368d-5e03-9bb7-074d57d5f993 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
b435ccd1-706a-5c6c-846d-f00796142ad2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
cd244066-834c-5b43-a709-f438dd2a4680 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
8c1e7cec-07ab-5629-b5a9-26bccf33f889 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
debe0130-0be7-5a73-bc1a-74c33944dae8 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
eff56077-c5d4-5a83-a6b5-677e27bac814 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
080b43ad-2995-5fd6-a5ba-dc387e91544c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
209be651-fbb6-514a-a781-31781ab79053 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
1f6bb475-297a-5fb2-915b-4d783078283e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
e1e6b62f-614b-5b94-ac23-0ab90ad554fe |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
b6800dbd-ee43-59ab-9b84-a89bd0bd5a27 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
aba91493-a7a0-5797-a1ff-734ca38718a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
b7fcfe0d-0c84-59f3-9c34-28fed6185a24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
6abe6aee-3f41-5387-9321-8d03e0092bda |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
41d008a9-8e27-55b7-a50b-c0ff984bc86f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
690b7c8f-f6cd-5a5c-9167-a34dd30b4ee2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
7c4c30ff-d42d-5b30-9252-be0ed056a9be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
2815071b-411b-50f7-a932-19cf6ed6a8a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
7ceb504e-a27e-57f7-b3ab-edc451832e70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
d50ed345-6f03-52bd-a2ea-7f959ea69a16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
0bce7b8e-7ddc-553d-9e51-17d36d8849d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
0e73ba2b-1e82-5294-aba4-6f57fbee0519 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
f8dcee15-e7a1-529e-9e53-6f304faaf8ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
1d10a5b6-c4c1-50a6-a81b-726cd642c5c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
025901ac-6d93-57fb-9687-fe2995dd2227 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
e0b63cda-5b75-5c29-8446-ea6c7df2a834 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
3686a445-b53b-5300-bdad-e4b2549b9144 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
ebddd7c7-490c-5eeb-98c2-642155cb2594 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
5fa2fbf1-89a9-5150-937a-aa3354186cf7 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
4d33e7e7-6c39-595b-9242-a0273a0ac2d8 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
d64b3014-0815-5781-b7a3-613de29912e7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
17470561-f019-5e7b-8d3a-391cc814275c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
8028ff5a-ada6-53a3-b3d6-ae8b5f9f3a08 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
f7cafb4a-ea1d-57db-bf9d-2769c6862563 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
44731dc9-2aa8-4bd7-a112-40240aa0132f |  | work-in-progress | 220b8ccdf1bde5ca4538240bfbc232b17b9ed86b1a1d820aba4879bec05217fc | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024
dedf7946-a4c2-53c0-a167-ec75201750b5 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
011dcc18-b410-548e-a53b-2a647a64d14d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
f2ecb9ff-81a6-5bac-bfea-64e7c4693162 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
4992e360-92a2-5ed4-8af1-6e1bd84a02a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
05bd3756-cc50-5a60-9883-1d4a50aa1cfd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
990dfc8d-48b0-51f3-8482-d2d4aada080d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
78e3944a-4339-53a8-aade-8fd0855a40ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
9a942a8e-8a1d-5643-88b9-d4993e44b83b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
1edec80b-23ca-52b5-a006-d6c880bf4c53 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
d878b361-34e9-5bca-b8c1-501de6778941 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
4b2aca19-335a-550c-8881-ef86f9a3e83e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
ed3b9a18-c698-5187-a39c-cc500f4dd4fc |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
088d1497-1d04-5b4e-bbbb-ece209504664 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
ee3abb6a-beaf-5368-bdda-bf2d573e9c8b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
d6cf56be-3106-5bbf-bf1a-e3f1f75b7efe |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
cca8432d-e5e3-505e-bc3d-05a6025636e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
cd0946b6-a8cf-5447-82f9-b0b584cd2f5f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
a8242cea-e03e-5e19-af49-63a4f136a334 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
8a84e2fd-2232-552b-87af-6af98016d033 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
f1100aae-a8d8-5204-9e1f-123b20e57cc7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
27da831e-1827-5eef-bece-ff5acde4f9f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
9ebc6f3a-dfa5-503d-8888-5e49c4cf5472 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
9c517413-5cb1-56fd-b519-1b234dd1d630 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
d4f0588a-3d6a-506e-ac88-1b9da7711719 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
3e1f48dd-a25c-58df-a836-f012d9b01ca9 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
5ed6f64b-51cb-5219-b464-50a6a4022100 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
cc9fd851-54c1-5c1b-9e8f-b75ba1277540 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
7e77b6a0-8ef1-55c8-9902-87d36281b65a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
ac41f0da-c6b7-5295-a272-453d6507e2f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
7cb36492-eacb-5822-81bd-e89ff03b02bd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
72a7f01a-78ea-51a5-8565-80e7e8d77626 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
df1536e9-2905-5883-8828-e84a10ffe46c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
5a2096b8-cffc-5f37-84f1-2ffb29a5988e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
a80e3787-c4d4-5160-88f0-e163c4296941 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
fe44f536-7024-5d5c-96cf-de65dc127fb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
6cedb9c8-3c8f-55d7-be43-7006a8050452 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
663431b8-5f9f-5a5f-ae32-bc68ea501a67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
097762d3-2189-5d3e-94e3-1b7a05b1d1cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
76701cae-ec1e-5ebc-8d3b-b50182fd1f91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
cae987ef-3280-593d-b5e5-404c79f3a522 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
86922c6a-a234-59d2-bce5-93602ace73e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
0e4f0140-5b2a-5f98-9413-a819ef8dce03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
46340de3-0e0e-52db-a88f-612c7ba30903 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
b0d1960e-1d2c-5ca3-b823-ab61d4789db6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
2f5204a5-78d5-526e-b4a6-917e28d3f8ce |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
76c5aac9-478f-5940-b708-ca8bfa39868a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
25f597b5-890e-5f81-8832-b773aa1e0630 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
fc08fa54-9edd-5c65-8187-30cba5f1801e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
9a89a616-1ce5-5072-8de0-6d708edd6e0a |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
b634c57f-7ff7-5cfc-8d6c-a5641c12a027 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
0fb9a824-e2a6-53d9-9cf4-54d06b80342f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
2e90680e-2bcd-5e7c-9f9f-5ffcb017af30 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
944a0780-887c-5252-8340-f5d40b8b663d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
0550ff26-b4b0-588e-baa0-37de71116e35 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
abbf8f5d-5adc-433e-b8c7-357349c1a090 |  | work-in-progress | 220b8ccdf1bde5ca4538240bfbc232b17b9ed86b1a1d820aba4879bec05217fc | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024
09dacfa7-84d5-5267-8875-37ce4255063b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
f970d986-bfef-5418-8566-19d3edf3f9fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
6ba0efd0-678f-5717-9c6e-ecf06c897b74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
9faa275e-3378-51ec-aad5-ca1a53a41e3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
d439c0a0-c58e-58f6-9300-a901202141a9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
184e9cde-3cee-551a-8dcf-fcce26e3728b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
f07cc6fe-9dfd-579f-b50f-439c38b3027f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
0c42dd11-a381-5751-80c1-34b3b33e226b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
577e1775-e707-56d4-99fd-a786e33e1760 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
5199375c-e262-5fd1-bddc-d476b14b5f06 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
ab7062be-29b1-50d8-ae37-4344658e7a87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
d65930ca-f7cb-531a-9edf-90ae5c41e707 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
9922d828-bd9a-599c-859b-3a87b890f8a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
9c202902-3bec-5b8f-8982-d138237cea3f |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
ba234bf0-af2e-5c8a-b431-68f61c9911ea |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
3cbe9008-ea61-50b6-bd13-94b2f211d93f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
61773554-5a3b-5c99-b881-ce4130acba98 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
604a2038-96ab-5202-b7d9-4f9c4621e3c0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
4b9f87ca-509a-55ec-9955-bc9811895e36 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
c4706e98-33e0-520d-aa18-2a78e9384cc2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
8a105c99-eb1d-5582-ac3b-dfeab3edb4a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
771b8f44-ea6a-53e1-a50d-3e91a52e356d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
ce8b3529-4e6c-5377-8e4e-67907189be4e |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
ed5d01bd-7ca0-58f9-b4cc-8cfe56c2820a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
04023295-8224-54c2-a1cb-184efb208219 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
11ef462a-0703-573d-9028-0aedce7d987a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
dfc4bb3c-1f52-5690-b1ad-bdcbf47373bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
040001bc-9851-58b0-a087-4883332c269b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
b594ed45-35f3-50a4-9e03-6c1236b02da0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
f045d95d-068c-56a8-bcfb-37b218489883 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
29ddb3c3-4cb6-5bc9-8640-699bdd198a11 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
73188da9-ddc9-5603-af97-978cf9ee0a7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
4ffe0c3f-1278-50b9-9995-63d49a2764ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
58b64a92-cf81-5516-82f8-bd62fa0171bf |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
d851a37d-c286-53bb-b37a-ef68313f528f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
f56cb383-542a-5cf1-a0e5-8a71a1e9cdc8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
1c89258d-24cc-5911-86b1-9a10af7510a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
d8ee4cf2-65be-57b3-9704-af3a2abf7a27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
9e05048b-61ac-5ffc-b1cd-143af9260fe2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
96824c7d-9575-5868-8420-690434568d01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
c3282dad-11c8-5bd8-b5b5-ad61e7a5d553 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
b196b857-654d-5a05-b3f9-a4d259c74384 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
3553a8cd-a0a3-5ce6-8b75-3e74f6a68236 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
37f97d0d-622e-5cae-8f40-4bf3a1785637 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
5de6f7b3-6db2-5cc9-9b5a-d8ab15acf26a |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
b04ecef2-ae5e-5272-a014-80bb1260106e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
8906b7d3-f61f-5072-a475-44befe6f81ea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
48660836-84df-5063-b6f9-5f5fa1789a44 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
a18197d2-7bdb-59e7-8ac3-dd32ccdad458 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
9f17232d-5f77-57cd-9bed-80ba7be6bf42 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
0d929ea0-3afc-555b-925e-04dedd872ccc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
51fb1733-e95a-5e2f-8cf8-c3d6d03b8615 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
69779053-fee2-5d5e-960b-02bf4a3f2e7c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
9b8217cc-4b23-5407-9771-2265ef72e9f1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024 | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
4681c014-5841-41a3-9596-3d2c7b1113ac |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers
be0d7c83-80aa-4477-ba55-ecd5bea66637 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers
3b683062-be61-5da2-9980-11e554e53d0c |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
d7f26c96-c7e9-5ba5-9fc9-04f1af08f386 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
8c0bdcbd-c86b-581c-8213-6e4d1e46118f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
8c0e3069-cf30-5dbd-9c99-7ea9a8a556d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
c960dd77-9fd7-5c7d-8b87-83b509a85f7b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
f4748fd5-2dd1-515b-8d87-2a1ae85e9d9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
3497a48c-31b3-5fe2-8289-4562fe83f3aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
0a9de7ca-e3dc-5ce2-a80a-d7df4afb0349 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
f9f15eed-3a4f-5c2e-967c-4898aa94c201 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
4d51d308-1b9c-5bd1-a73e-3fe7cc6e93ee |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
025c3555-cdf0-5973-a2ca-ef69074aad24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
58c04b0b-3bf2-5de7-93b1-63bbd8f0d425 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
e2b0da6d-0fa0-5fe4-b2cc-daa173315ef4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
3cee0fb1-2eac-5c95-809f-dbf25f6f2169 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
0d608b4f-98e4-5ef2-b59d-86009022d532 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
796a5395-5709-50c8-badf-63ac070f416f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
25a37ba4-52c0-5488-8864-9b2e2552a540 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
ece6d28e-af48-5b30-842a-7c6f2674ef56 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
2e2f5420-a9c2-5cd1-ab0c-0b56729bd966 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
bc8e0192-acc0-559c-8549-33d9e907728d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
d8ed0e09-ba88-5813-8ce2-aec664bdeed7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
b60e0073-1b28-5a4c-8eb6-48a86f08eaf8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
1ba02764-73f9-5a03-91e5-24fcdd7a0d14 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
bfe7d29b-2ca7-5b4a-b36a-cbc562cfecbc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
4c88a7e1-9faa-5165-b7fd-4c64ce2e8d15 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
07b9cf80-18e6-5a1f-9a0b-f045c0da297f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
ba03b31c-73cd-5ef7-ad5f-d8dca4e91ede |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
f1386dc7-fe7f-5805-9785-a6a954b705a3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
ea3d00d3-6726-572a-9ffd-4acdc5d73089 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
98295461-4357-54f6-a305-afde3510d5b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
ce1ba4dc-ffc1-5f5a-9349-15f3d961519c |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
44f3e9d5-c63f-5f0e-9b97-6b5ef818e6c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
801f27df-553e-54e6-b1ab-a666da504719 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
2f989b8c-9044-5df4-b0eb-30a37d850267 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
2d67e191-8aba-5ef5-836a-bedd6a0104ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
48813ecd-c232-57a4-b8d8-a0bd9356de6b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
3dfce731-c11d-5a27-98cd-d15af476bce2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
b9b108d1-6e7d-55e7-b576-1da4a21c91fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
d9156202-f4da-5e74-a3fe-b69bb5d236f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
b964f1d1-4ef3-5336-87a9-a191ac4dc844 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
d3a3ca36-fc7d-5d6c-bb59-8522af7964aa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
0d3634e3-7f43-5555-befc-e4d707bf43c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
94c3975f-f99e-5a39-af2b-6255998afa98 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
68c2a350-84eb-5b8b-8d77-ce63eba29fed |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
ed2a98ee-b829-5547-a4bf-e8699b6c3c8a |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
e0d89a39-c4b4-5453-a3b3-e3a762a03446 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
4d4f270c-2624-504c-926b-b098760f0f21 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
db88b1e6-42c2-5169-a5bc-e530fc3cc90e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
9253e2ef-ba1c-5c97-8acf-e0a771c4fcc5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
36dc77af-5ffa-52d8-a25f-ec87f98bd29f |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
1d85c024-ec89-53a9-8982-e8b5291e88e3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
1c062d45-f9c3-5cf2-8468-944b4923f6c3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
90c47adc-e84b-53fc-88e9-ab071e7a63cf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
908aab45-c479-5fe9-a982-678e8702a6ee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
57b84c90-e92c-5bba-9664-532336db16bf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
5b35697b-c9c1-52a2-bba9-4fa9633e69a6 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Barriers | Transition Barriers | EGB Transition Barriers | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
92495931-256b-4486-b9ab-46958819e7d8 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Bridge Services
ac413dfe-6de2-42ad-969b-7a0f5cbeea8f |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding
78fa760b-035b-452e-953d-1c188032fcb1 |  | pass | 954c34238f3a3e3b5d1808594c6f7cfa719935c42e5c4efed86d61c01df41c2d | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding
d57164a1-d354-5367-b414-c71e407e5d41 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details
2ff49e94-6745-5c07-bf7c-97b49ba4b3c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Inspect all pipe & fittings are correct to job requirements and no signs of damage
735ce648-4e03-5a2f-9e21-653f29d2a3cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Inspect all pipe & fittings are correct to job requirements and no signs of damage
747172ab-6925-54ed-b775-48645e87515b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Familiarise yourself with the job
c041a12e-830d-58db-ad3f-a82723df1440 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Setup worksite, welding equipment & rollers
11a85e82-e351-54ca-bb47-e8622894a5c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Load length into rollers
5db5efa1-f224-5377-80d5-11bc49f87805 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Bevel pipe ends
9d21b16a-d8e1-5c12-b797-8f22be288caa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Tack weld 6m lengths into instructed lengths
98f77623-53ab-5d86-bc95-143ff702344b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Check for straightness alignment
d3ed72a5-2d09-520f-89e7-b24624562fbc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Setup purge baloons & purge with nitrogen
8303bca1-fd3f-5937-a29f-e533f5dc3c0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Peform butt welds
69b7c1d6-12ad-50d8-ac55-e0c9c208e5d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Tack flanges on spool lengths & check for square
0b608d08-c543-5879-8d2e-75305e717dd9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Weld flanges on ends
c8f84ddd-7ec7-5543-b8c6-c94d6d53e81a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Passivate all welds
c3104e75-0286-5fc2-aa8a-d6dad6b247ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Remove from rollers and move to lay down area
7923927f-daf7-531d-999e-f8340671d455 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | Final inspection
f3b312d9-26df-583b-9897-884868d81d79 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Bridge Services | SS Watermain Site Welding | ITP - Stainless Steel Pipe Site Welding | Details | HOLD POINT
0a42bc56-21b0-4fa6-bef7-0e54825ec6ad |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Abutments
250a8f9d-5fec-4f6b-85bc-3b5b057cf29c |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand
9394b725-c0dc-4969-b911-b21e0c420561 |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D
3e90510e-a0be-58ce-b498-6b8b39bc06a1 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
9cd8d8bd-3e55-59a9-99c9-e69bc67fc152 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
39a9aa24-e2ba-55ca-93c8-7c8f50924a8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
ae418a2b-6b46-5016-b2b0-b8e3201679f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
4042fa27-f49c-5a1d-a30c-d7ab5683cd0a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
367bca4d-28d0-5dc8-9f58-b61689b33531 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
3ac53cef-6e1f-5450-9d91-0fdc4965586c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
afd5f589-de9e-5724-bdaa-85b8fb4d2fb4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
465d3795-c2ba-5cd6-8f72-af556ceec18a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
49b65cf6-c6d3-55a0-bdb9-a4069d89a46a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
640718d0-e8c7-50be-9c05-392a40fccc22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
791fb2b7-653a-5dc0-91d4-f4c691ccde99 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
0bd4dd8f-57a1-556f-87de-cdf832f13c00 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
a199c999-ef3e-5a2a-a270-70fd3cd65949 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
73100854-0724-5a86-bb1f-9c0823fe6a95 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
2d76f974-fd71-5f55-b129-b5142f8c7f0e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
c2a59284-d634-5fbe-b09d-65d54adb7f01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
a1e45cbe-8e49-5118-89cd-b036f2eab2be |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
9146ebca-60e3-541c-9c2c-7f6878ef3e9d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
c61c2419-62c6-5e6b-a08b-e4609e9756ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
a685edb5-8302-5360-b8ed-a1bd3210988b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
aa0768cf-002f-5ad4-bf5a-71e41d12ad73 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
3e1fe862-374a-576e-b4b2-799b547c67c4 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
a915b113-9a4f-5a27-ad73-5a2930ff458f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
d588f32e-71cc-5fe4-b117-6c35de9df01d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
4b9398e7-7fc2-5a88-bb7e-d19489fce098 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
672f788b-63c9-5ea7-a943-79bae363bc28 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
49504e54-52bc-5b82-9757-e289c46024b8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
bb6c446d-5119-5966-ba03-53ddd32f3689 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
d222ad7d-f10e-578c-b44f-be78e1f5768a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
a110040d-9845-5462-adea-549f2310eb8b |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
60d863a9-b3f2-5e46-acfb-d015aa8aafb6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
b8685dad-2fcf-5eb7-89db-9acb29c4fbc5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
1f5bf8c5-e780-5ad6-bc7a-ef8db674af15 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
16b7c8b6-376c-5b59-a686-f1bf55eb0f72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
5cf603fc-64bb-5628-a888-a8dcbd5082ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
89a40c3f-e011-584b-8ac3-a39b57bb3863 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
64d95edf-4545-5650-9fe3-e30359c46e6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
f6113cbc-8b07-5da0-aab8-493c0a038346 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
80aee5a2-e752-5ac6-a416-dca4860df5c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
f63c3dec-0d9c-56ef-91fe-dfb547d4bdef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
8eeda909-0393-53e2-a33f-eb133e3da72a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
fcbb9b34-4e71-5f57-95e8-0c971db8b941 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
4eb82892-c59d-5d4d-ac39-a595b1bf52ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
9a331817-fe32-5541-bec1-bde4144851bc |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
52cb87d2-028c-54b9-a37e-4028e408115f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
7d75d38a-716b-59ef-83cb-05286d9ce36f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
5933cd62-d6bf-5cd7-9ff6-7475b30ac340 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
a40a22e4-c4b1-543b-8402-07498023bdd0 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
897933cf-2a75-5ea3-b307-adef13d91322 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
79f74bc9-d945-5b2a-9e44-838497f7a44f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
01e39ab9-4303-521f-afc1-90b1ae8e5b1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
655cf4e1-9807-5e30-9fd0-9b78d4005526 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
e8845482-7b5e-5a56-a0a6-2141c2b9eeb4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
639e89fe-cf6c-49ac-8bf4-f1ea2ec32643 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
1130f923-da7b-57b3-a8ad-9eb971d269ea |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment A Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
edb12e1f-9be9-46f3-a1b9-9d4626a7b218 |  | pass |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand
d11df970-7314-4c8c-8d2f-809cb5ec5006 |  | pass | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D
404ffe5c-5899-5d9d-b59b-cd2f0357ddc0 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
c6c43960-f5e5-5594-8c5b-1407feb53980 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
b0990811-a0df-5081-8f57-e665cc556325 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
a04eb450-ceb8-573d-a524-94df0b69d76e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
a3af6037-147e-57d5-91d3-786d3ed87b03 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
645404ba-e161-5d1b-8136-3cbd523b42fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
c6ed84bb-4073-54ab-a243-f731b71f309a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
10748fee-f544-53cf-85dd-59222e2625be |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
f3dc464c-7f0b-5cf3-af2f-d75a818598e6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
b7f7a3cd-e455-5be2-8c1e-610bfb7582f4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
d8d5bc50-c1a6-53a5-ae9b-4d2a1b104e7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
fa242c3f-0ffc-5652-9681-5ad16339b386 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
9d6d6bf4-3c4b-5d70-90ee-f14b493d0547 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
dd4efadd-bf7f-572b-ab59-e5b6300fc8da |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
5f6f091e-ed52-5a03-9df1-9002ca693d79 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
3edc1e3e-15bf-5bb4-8176-a92dccc41e58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
6f1f1ff3-9a35-5580-86a8-e540e2c9eaf3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
53ea7fe7-0a81-52c4-af33-59bde3e11b9e |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
7fc00f0e-8517-59ec-835a-9a1f261f5eb4 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
9c87194e-fb9a-56af-8d89-dd96976521a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
636e9f3b-4c29-55ff-8cc1-e2dbef3ef9eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
a3edf156-a2e9-5745-a781-4869d2eece43 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
24e71bd8-1a6e-5e74-8db7-74e39a03aef3 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
fb263504-5bb0-567a-94ab-74c826180430 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
db60b31b-6942-58ac-b3cd-fe77e6e4714e |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
4a5ff52b-1d9b-5dbc-b9f7-c932e4f93dd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
346fba49-79d0-5a46-bddd-6d9a2ecf8cd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
4649e92b-6a8b-5d3b-a9e1-3ad624e0a1cb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
8d8947e0-18aa-503d-ad6c-677cf4654d2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
fab3881f-98ad-5781-8034-335492d92266 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
bab7ed27-57b5-519c-aed3-55ef9e2528a5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
d14b9b47-337c-590d-95b6-cdf065a139f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
3bdde1ba-3761-5c8c-a113-75c531f16fc4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
ad1b2de5-f4e9-5342-a869-ee42cd1c0efe |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
50c1deeb-2235-59b3-a32d-7d034b707fbf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
ee8a5575-8a34-5c79-aef2-981eeb31186f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
2432a451-534e-5021-8465-43d4cab4e8fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
614032ad-0fb3-59ad-bd92-26a85aabf368 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
aded21ba-1bbc-5da5-bbb7-3c6e704315a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
201be979-7483-5288-bf77-1520b4b5df68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
7491ea5c-14e1-5033-8720-30add1a90500 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
d71a6d15-c7ba-5ccc-8020-e34d9f44eec9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
4a0c3bd0-0e97-558f-a535-cd3743c65e45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
eb8deb48-e285-539f-a436-eff234f9217a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
efe3e774-925d-5d31-a449-d6dbe0830288 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
42b7a7dc-d1ff-54e7-92cb-db900cec3545 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
3d851c52-1a0b-5d38-8384-537c0f43748a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
20abc84b-c2e5-58f5-ad80-958f5b173339 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
fc72a050-e3d7-5c8f-a37a-d59359f12e3c |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
9cfb9c28-8fc8-5cde-b972-cd41ab8beaff |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
b707c0b8-96c8-521d-8ffd-a739b60e1f0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
813a9315-dfc0-52f3-966f-c9c8fe8734b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
01f3d37a-17c9-5838-bccb-8234c770d5b3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
cf445509-b46c-5a86-aac8-dc81f14050f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
d93ecfdf-811f-4325-b28d-1f924f28b45a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
bc3a96ca-243a-5a1d-89f2-e3230a95a052 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Abutments | EGB Abutment D Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
53ae405f-9fc6-4dfc-9d78-cc6e99c8bed8 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D
867f2984-a1bd-438a-9d3e-2895cb294b49 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D
d2699030-bd3c-5687-a22c-ab3673473eed |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
6f021c86-ad68-513f-a3ac-2fae4bcb5c8f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
50ca013c-4141-5f03-9b40-9de822c9d0f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
5c077ba4-45e1-5023-8c01-946b37c666f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
2b747519-d840-5dd2-8dd5-f472b3955e2e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
359f598b-e99d-59a1-9eb1-d08942000874 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
12940ddd-64bf-5b49-963d-f118e44a7f8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
17f057e6-0264-5707-867d-f42e64f5f756 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
168dede5-c41d-544c-85e7-27d838f7fd50 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
3920227d-011d-55a8-be71-8ec5844db90b |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
c4ae70bf-ee53-5aad-a0c3-07fe0d6a774c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
91cde137-b280-5fc9-bc6f-67148a8acd27 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
775f8a75-be6e-5767-9708-d3937b099128 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
ffefd9b6-78b5-5627-bb31-45e946954bf0 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
e375fc8e-ced3-584e-9908-0783688632fd |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
fca195f1-948b-54df-a337-b7277c3f9e78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
aba16636-aa48-5f8c-a5d0-03bd28850267 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
ac6dbf90-1646-5fbf-b699-0720403f71ba |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
2dc09bf4-9663-5930-a1af-8873e4a15c36 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
d3331263-3624-5f5d-b448-7dc952716069 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
69101913-ce7b-566a-a20d-ebcf31967459 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
0276db2c-06ec-513f-9700-b0e08a9a96c2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
54373baa-2b1f-5690-b2c5-3771f067d179 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
62b8eb15-2750-5002-9e3f-1644400cc2a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
40dcee4d-bd63-5fe8-bd27-2a2c4661d7d6 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
829b8a3c-c2dd-5ce6-87b0-63e0234b16e9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
d9761479-9bf4-5bfd-9926-a93010f9aa77 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
8a0232ae-d3b6-512b-b8ee-0ad2342762e7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
206d85a7-47e3-5070-b594-77fb2c510667 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
5c44ae2e-2458-50eb-a18a-eea8d414583a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
64f48300-ab42-59a0-a293-838e4c68d984 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
bf8cf26a-b86d-5cab-a8bb-8624a65db461 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
5c7c1020-22fc-5f32-9898-a57f3b5d9c15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
b4a23b4d-9dbd-5570-bb2b-845637647f63 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
3bb575bf-1012-5a59-af2f-03ef147fc342 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
3a06ce7e-b6cf-58d9-92ef-ce750f4ae499 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
a8a9ba12-6f8a-58fe-8152-ff2080d86af2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
76cdfe6f-07a4-5d6d-ba17-d1f6502b74c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
13656e52-cb5b-52f3-9cbf-37dd7f70e34c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
5bb62b0a-2dd1-5ee6-ae16-8e93570eba54 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
d2034046-ce65-52f6-a5fa-2a749ab3ca7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
51a1f844-072e-51a2-a265-613fa1945c6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
6dde559b-4338-58b7-9089-b2477c701df9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
0ba5df60-73ab-51c2-a48e-93317081f8a6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
71b28822-7fab-565d-be26-d128becc7879 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
e0f7b229-a2c4-5b18-bcbd-ca4d63caa650 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
200b8492-b4fc-5643-82dc-81c8e093c17d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
ad5f2508-8a57-5de4-8ee4-709ac51e9acd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
7f4c2766-a4fa-5271-a5b8-6fb6b2ccd68d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
fa0a6770-0b44-53de-bfa2-017c4355dc28 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
b5a5d125-02af-5295-96b1-6968f9c92ec6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
c04c7e9c-3e1c-5455-92e8-9c967de83995 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
febd0f41-1186-5f9b-96ba-3c00741ef624 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
1b2d8fbb-10b4-5078-b8a0-af4896bc3269 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
07637410-02a7-5227-a6b6-f57643709292 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
b885bc34-7e99-5e2d-9f3c-1ec4515fffd4 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Off Bridge Light Pole Foundation ABT A & D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
dbc5bdab-b361-4868-844b-9a520785cdf5 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab
c00ca754-8482-499c-b2b9-3f30335da04f |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A
4305bf0a-1ce8-4977-98c0-b4486a7e8db1 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D
ced1c3a4-b257-5666-a919-bb19524bedde |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
6e69bd9c-3947-5417-a61a-c797c9b6dd79 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
d0a11980-070c-5901-b613-67a0c33321e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
eae50930-41ce-5dc9-9bd5-d95e1fb94991 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
c9cb0916-093d-538b-807e-7318b8de741b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
b8e59136-affa-5929-b8d9-e20c6bcfe4e1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
408f3a4f-6981-560d-8e35-444e82ddd17c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
2dc5ddd0-d61e-5514-95e7-faaf14b3d701 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
a8d7a289-ded9-5899-a183-1ec8a7631151 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
8625da1e-0ca9-5885-95ea-364064a84f3a |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
7b49e405-e8c4-5f98-93a2-81298a2bc255 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
7c7ef77e-f98d-58e0-b919-899a2a9d07f8 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
c98385cf-9c9e-5233-a6cf-aae669dd15d5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
c05427ce-087d-5462-9154-a598735bbb08 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
ab85593c-c927-5aba-aff9-b2b3a05fa42d |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
c8d5e6c1-e685-507b-bc3e-40d1848ec1c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
6e4dfd69-7ee1-5f4b-959e-c23556606377 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
b3a0656a-e593-5070-a0e4-1eb78e9bf137 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
be31236b-3846-55dc-80a3-8cd51f3aa252 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
74717578-73bc-56d9-8b6e-e43f5679d281 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
c038618a-8970-52c6-8938-e604c6d36ee3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
7ecdba43-acaa-5f9e-ab7c-3e3cedc110d4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
9fef3849-795b-585d-81fd-1ec31dad11f1 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
e2018cba-7706-512e-b2fa-78d672b558e0 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
867cb195-4e99-523b-a6c2-03421047a7f3 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
812405b1-55ab-575f-bc4c-7ec918247f15 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
9948a069-9cec-5210-87db-8031ec75f729 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
999d44fd-9298-565e-89b1-ef1307aea5b8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
1da1c030-8eb6-54bf-a095-72e1d775b239 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
db21a099-b44b-5c76-b975-0ab79499c6bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
c6bb826b-4069-50c3-9528-160248ac9ff6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
71b1c058-1f85-505a-8002-359a0d82f85f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
fd4b033e-978f-5a72-a8cb-6fd3f40a750e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
78bfaf08-668b-5aae-ba02-e45c81e4c659 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
e0b5989b-9b9d-5238-89e0-4174c51009bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
7bf42f37-0edb-5844-9d69-6f9f27e62e05 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
1083b665-78e3-577e-8f46-ffd6ff0fdcfb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
259e9758-dadb-5a74-9905-1e646c0f50bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
8153742c-f203-5714-a35d-96c4ed004483 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
cec0dec1-e4fb-559c-9429-f997ffc84508 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
f5e9aba7-74a3-5c85-bc06-0a3d414c2808 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
07920e05-8488-59d6-99a8-366c4f7606aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
cd2d0ac7-5ba5-50d4-9088-4cbc70a5dd9c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
44188b07-19f1-58d8-bbf2-2a0235ee309e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
284148a1-9753-5f23-acf4-087773f46cf8 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
09b45cc6-26e8-52b8-8faa-702af05faa5f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
e0b2f2ad-cd5b-575a-b21f-0ba5f89ff425 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
ffbf5454-e24b-5a9f-ba0b-5fd9fd6cce4c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
e3154ec1-7419-5b0e-a3cf-92f10294ebce |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
88e80bff-70e4-5ad3-8b8d-867094b12ea3 |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
fce2e479-9107-51d1-baa8-6f898ed0ce7e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
9aa5a954-d25e-5231-a7a6-d51d457b9428 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
ad5f0648-9b97-5ade-9153-d2d87e0a0b48 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
54957f15-f412-50d1-9108-592f13af00fd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
5f09b30b-2ece-5af4-a54c-f29691b5059f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e3d0829c-e0d6-5a73-8c7f-40e86cf41ad8 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment A | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
859d52ae-314e-4176-a94a-ede326f7f3d8 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D
8dce991b-e4f7-4079-8152-79e6ec1ec6f0 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D
8c4cf015-a1e8-5462-bcbb-a0b7e4ff0f49 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
d6fdbb61-69f0-59e8-9c69-d804fe8d218e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
8314c443-ce26-5d6b-a0f2-9825051ac08f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
45413fc9-ce4e-5531-bb7d-535b0d8f0a1d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
4bc06e7c-183c-59ae-ba4d-458395f9cbb2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
ae9114bc-b208-51a7-8ad3-c3e694d5577a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
7430210c-bc11-5dea-99f3-e57a5d9ced05 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
7a6cf2e2-f0fe-5404-b35c-6e38efa70ac0 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
5301907c-03a5-56b2-9990-a64a1bece40f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
edb15b14-154a-5f45-830d-f2fc23eb2039 |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
f91503ad-ab28-5550-862a-9979a744d390 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
fae96d40-4e99-5b9f-be62-efd2f425fcad |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
825aa657-bec4-5cac-a2c8-675e35889b70 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
6fcb506e-31a0-557a-aa89-68221fecc930 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
a35bb04a-43a5-58e4-9a89-eb3bf54d2d7a |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
abda9a43-5b53-53cd-b7d3-70c2e8d9581c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
756ba27d-b863-52fc-bcae-f9b438036743 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
9a4dba78-f9fe-52e1-b2c6-a6426cb937c7 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
99e70c31-bef2-5bf0-aa4c-697854749dbb |  | not-applicable |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
b724f1e4-a002-58b1-bad5-f644e195440d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
e8212d36-e91d-5d23-a88a-4f9d956e45f5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
a020b6e4-665f-5d7b-b279-1650e13b1954 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
b4c1442e-441e-5568-a9ed-0f2f3439d2b3 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
05cd07a7-89b9-58b5-b9f8-992d732e4cf1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
742e89aa-4bd4-51bd-80a4-c00c28e4ddf7 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
5a7c173e-80cd-55fa-ab6f-1587b65cdb3d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
ead86381-ec81-519e-97bf-47a4952bf769 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
651313b0-853d-56bd-9654-e00b2d154598 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
49c658e4-59aa-5cba-8113-3ffd5fd91623 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
f9182534-f0b8-5a18-8fdb-0fc2d3dda0f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
a13dbef3-7485-5904-a2c3-fb6b00af43c5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
30139125-451c-5b32-99c0-da8705bcf8c9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
14573ba3-5c1b-5b9d-bc96-c29587573d54 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
3ce4f5af-e8f4-5a03-ae01-01bb1197e07b |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
acc997a9-5c60-535a-bf20-59a31c167864 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
9d2d4a09-4d66-5b93-96c3-6793a838bf13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
2c943c61-393a-5421-8cbc-d30346a46b9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
809eaded-b474-560c-b85c-07882e53d90b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
ab6cb1e6-3e73-5cd4-b4a1-24e931a746f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
952fdcd5-4749-5e31-a9ac-6700c29a281c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
5f8fb494-6cde-5aa4-92d7-48f847779395 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
01e39956-fac1-5c58-a691-f94b31a5d804 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
3266bd5c-8cd8-5d17-8e32-2ae6356b4105 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
d6384445-25ae-55e8-bf30-f2e80c937f7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
169dffe3-8eca-571c-8a60-3351146d8778 |  | pass |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
a6ee1563-56f2-5389-a109-fba5fc3d6bc5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
08c98852-05ec-5b8f-8c69-c9ed13a8095e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
20ad163f-31ec-5329-9feb-740d73d89591 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
5d6982bd-4675-5304-85dc-05b88970ee85 |  | pass |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
05c50934-045b-59a0-b8b0-4ee16743df6a |  | not-started |  | section | FALSE | FALSE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
12c6f5c3-fbbe-54c6-9cfc-4f87b32f70b2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
4ecdeb87-b4e2-531d-8d42-ed9e52f9e3d1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
e8eb9d60-11ff-5025-b552-9f8ef1f04a4e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
4ebc66a8-7079-5f59-a2e7-ac05d10d3d47 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
a4a648fb-932a-5da3-b31b-c3bf2c23f702 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
41f2a4e1-3fc6-5e4a-8795-7d3e0be5352c |  | not-started |  | signoff | TRUE | TRUE | Site QA | Eastern Gully Bridge | Capping Slab | Abutment D | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
1d414123-08c0-4845-81cf-541d1e2e42e8 |  | fail |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge
6d373918-5187-4033-8bd5-f888eb80156c |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall
732b17c4-3ef9-4558-a52e-38e9b69929f8 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A
1ef76993-c200-44ff-a085-42cb25e122d1 |  | work-in-progress | f1864b69de1a686d46caac1366faae8ebaf4ba8c283eef7ba2ba6429f5c6540e | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls
d3168301-d413-55b7-b2fc-8bf628b50b68 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
bb69044b-1678-5811-b93a-0f0b11ca6a78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
964897c3-fd55-50e2-9d6f-8634197db5b8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
127d8997-c3a2-575c-9373-20b81ba92afa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
25be9250-924b-598e-8b02-988310aa4183 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
6d276c39-326c-505d-a6b0-4583263c092b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
bc0a773d-3e08-52c9-baba-53ed521a6dff |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
ba5de2c9-9096-5c91-8a54-4a31a4cadc9e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
11d14839-d0e8-5eb4-a68e-2d2c923e0297 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
726a718b-1793-5fcb-be02-bec3ff704f12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.01 - Stone Strong Block Molds
0ba65895-0a71-5375-a916-bbd0479f44d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.02 - MSE retaining wall backfill Material
14c39de5-e250-5499-af26-beb455007957 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.03 - Geogrid
81e9ac54-e424-52dd-bad8-a6a6228e3e22 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.04 - Para web
7c4d5dfa-5d8b-57d8-bc39-369cd1f28af9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.05 - Drainage Pipes
a0967a9e-ba97-5bf9-8259-053525e9188c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.06 - Geocomposite drainage board
f1550ac0-02ef-55ae-80e8-3cca0ce40f17 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
00e844ed-da2c-5bbf-85a1-dd491f1eb730 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.01 - Excavation to subgrade
34b90f27-be2c-5167-8f44-a8e5c3fc6109 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.02 - Foundation Approval
17377be0-f4a7-597a-9783-537856267d16 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
bd6416f3-763b-5d7d-9358-dc53f4282acb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.03 - Undercut subgrade
bd0ac5ec-f8de-579d-906e-d4adec7c0bf4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.04 - Undercut backfill compaction
0772cbce-cdaa-53f7-b922-30d894070c84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.05 - Geogrid Installation
d81acea9-4196-5328-bb9d-1d64c16d130b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
edfe618f-2a39-5b98-8306-640fe1ddf2a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.06 - Backfill Installation
dccaffb9-5bea-57fa-b670-2fd4888ee6a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
9bfa9a96-8604-5266-82c0-cac87e30d31e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.08 - Clegg/Proofroll (Gap 65)
2a337422-fea6-5984-8cdb-1675059404b6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
d523d51d-277f-5caa-83f5-92a684c0cc4f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.09 - Scala Penetrometer (Hinuera Sand)
32b5cc8f-c00b-5249-b204-bc2c9f315598 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.01 - Level founding platform
59b4741d-2eb9-57c6-8773-564201994f8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.02 - Installation of blocks
b618ef91-f82b-50ac-a9e9-6a6429de694f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.03 - Paraweb Installation
94e7b301-b189-5aab-bc9b-244260239d8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.04 - Geotextile
c94abae6-1ed2-56a7-b0c8-75752ab9dd3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.05 - Drainage Outlet Installation
8b51465e-070d-5b0a-a881-932744241675 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.06 - Backfill Installation
d3bd30b7-6e45-5b41-99f1-66a5fe167a10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
0dcbaa80-ab15-5eae-adcf-e981d7e29e0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.08 - Clegg/Proofroll (Gap 65)
380ef912-2bbe-57df-91cf-8ebb824926bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.09 - Scala Penetrometer (Hinuera Sand)
9cccace9-daab-5b1f-9f5a-b1accb2bf7b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.03.01 - Tensar Triaxial 170
442f71dc-2ea8-51e4-b6be-54ad023d450d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
0c452b16-5093-530a-8318-cdf0c34220b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.03.02 - Tensar Uniaxial RE580
bee4aa55-3325-5686-ba6e-b1eacbde9afa |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
d3910c10-d3e8-53a4-b1a3-c5dabf1f58d0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.01 - Settlement Pins
ef774751-ba10-5506-beec-f848fefc706a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.02 - Settlement Targets
3dd61362-1a12-5bb6-b6b3-4e8ec8d7840e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.03 - Engineers Approval
f209b4be-a559-51d8-96f9-73472ace3219 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
aef9ad4d-69b9-5491-8d95-f4a80a837b59 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
72e7db5f-ffd8-57b3-aa5c-a2b0f527cb0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Draft Redline Drawings
9169bf60-964f-494e-ab22-9fd8fd33ea75 |  | pass | Stone Strong Wall Installation Checklist | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist
adbeb3ea-857c-5b36-935f-b18776f1ffd0 |  | no-status-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Details
ee4d52cc-b82f-5a67-bbe0-95667a991b85 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Level foundation installed as per design. (Base layer only)
67f5b8cf-c950-5fca-8bc3-cac54d55001d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | 2 x Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Tramsfer Platform. (Base layer only)
1ce1f8a4-bd48-59f2-b31b-97329cc6f1b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Blocks Installed within specification tollerances & block pattern as per design drawings
32c2a24c-842c-5504-a619-7f8901eaf06e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | The correct number & length of parawebs are to be installed as shown on the construction drawings.
545d4cb9-09b1-5693-beb6-1f4d26958b94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Paraweb is to be placed flat or with a 1% fall toward the rear of the wall.
d0fbfa7a-ed35-554c-96c7-7d76db569d68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | 150mm of fill cover is required before construction equipment can travel over the area
376226f1-c4a5-5e3f-971e-ca879a8d0631 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Backfill installed in max 250mm lifts
5ec8009d-5134-5289-8f77-cf1a0f395e12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Proof roll completed on each layer
6e5f6bb2-ba42-591f-acf8-ef6fb10dce71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | NDM testing completed
71422052-3278-5e39-ab06-1be9d8e5d0f7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Clegg testing completed (GAP65 only)
c51f92b2-029e-5a7d-9764-119c2e878499 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | Scala testing completed (Sand only)
85e6ce01-4508-591c-aa4b-4589b462cf18 |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment A | Stone Strong Wall Installation Checklist | ADDITIONAL NOTES:
a443f9cc-286a-456a-b346-c9e42c02e205 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D
e9f8ca00-0293-45a0-b69e-a9c3fb03917a |  | work-in-progress | f42ecbcec70d9636d2abe7c00e12eb3fafdb43efb3f430b23755417d84cad355 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls
05a5d80b-7389-5b41-a1a0-eac3cb4bcc3d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
00ebc67c-98e4-5f8d-a572-18efc70adf12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.01 - Construction Pack
48d16ac3-a9f8-5309-8eef-9fb53dd3d809 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | AUTHORITY HOLDPOINT
25f22849-4d69-561c-aafd-39f4614f253a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.02 - Survey Setout
d3d34992-5e0c-5253-8510-43f1f96f0823 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.03 - Service Location
331791c9-4edc-5ae8-89f0-bb0b7b35ef13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.04 - Internal Permits
5c71b15c-7fc8-5e67-8905-db903848cfaf |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.05 - External Permits
78b87115-290c-5597-85f5-7429fcaba3bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) | 3.01.06 - Approved Construction Drawings
5ac45af7-349c-5a46-8e51-12a77f5d2060 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
cd941c51-32b0-5ad9-b661-2c64ec73e4c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.01 - Stone Strong Block Molds
275a4bd5-7669-56cf-ba51-aa4dcbb8563d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.02 - MSE retaining wall backfill Material
560c9609-1645-5a9d-8631-8918baedc4cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.03 - Geogrid
4a5ee59a-d31d-5e47-869b-541850106366 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.04 - Para web
3258c4fe-416d-5310-adc9-7f2ac1e4a742 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.05 - Drainage Pipes
1b152bf2-6086-5f7a-b361-7aba6c9a3da1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS | 4.01.06 - Geocomposite drainage board
687736a8-39f7-596d-8311-11998f28ae54 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
60206f64-8924-5498-bb9a-55e304ec0d42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.01 - Excavation to subgrade
8bf2fcae-f6a4-552a-a69c-61a13a450441 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.02 - Foundation Approval
bea1b4bd-4afa-5e95-a178-f32a283c8eff |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
9400c7af-8b4d-5ae1-b642-afac351b6b0e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.03 - Undercut subgrade
35569816-70c0-537c-a57a-abf684dd2263 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.04 - Undercut backfill compaction
d43d9ef4-8f00-5196-8d93-f9fcb7455aee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.05 - Geogrid Installation
aefd2d42-1488-53f6-bde3-4929d0e0095c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
40893edf-2e05-51d8-909a-1af737ce82a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.06 - Backfill Installation
599272be-13ef-501a-a126-f91c3790840a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
6d580777-d8b4-59e1-a58a-1153da7e0b71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.08 - Clegg/Proofroll (Gap 65)
3cf4ecd2-d96b-5665-85b6-913365656d3f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
7552fe30-425e-549e-a3ee-999b942e5788 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.01.09 - Scala Penetrometer (Hinuera Sand)
7c28b6f4-1aa1-524a-8bae-ae0b5f485605 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.01 - Level founding platform
6812c9c5-bdf2-5bde-8d81-9801d5507a00 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.02 - Installation of blocks
a3a94d13-be88-5409-be16-120ff5613f6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.03 - Paraweb Installation
d083e11a-5200-59de-9168-61aa5608d317 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.04 - Geotextile
5af39d3b-575e-5891-a07b-25b080e94d5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.05 - Drainage Outlet Installation
670cb505-b1ef-59e4-a620-a1f4c048d680 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.06 - Backfill Installation
4cb59a84-f78b-561b-a258-c81a643448ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
6b2254ab-4033-59cc-b7f7-9045b905ba1d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.08 - Clegg/Proofroll (Gap 65)
8ee811c5-ac33-5492-8dfe-d9e51bbb7f01 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.02.09 - Scala Penetrometer (Hinuera Sand)
3e477152-5336-51de-bc45-1fc0e4bc605e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.03.01 - Tensar Triaxial 170
56c457bf-eecd-5d39-b51a-b50c7a299f53 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
11f5a356-4302-5d46-a11f-6371353760d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.03.02 - Tensar Uniaxial RE580
b6a1c278-83dc-5f1c-a988-898af7ee2e72 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
686d0f12-c01b-5277-9cb0-748297f41bfd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.01 - Settlement Pins
241d9836-b4a9-5dd2-b61f-d21c4ac54984 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.02 - Settlement Targets
9f1a25af-2500-5899-93b9-4990ec47022d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | 5.04.03 - Engineers Approval
f91ad7e5-59a1-5c4f-a8b9-e21152f264d1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS | AUTHORITY HOLDPOINT
b066b0f6-7f0c-5f4f-9c22-f85e85323a73 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
c6b668b1-397d-5c55-9bb7-dd1ab8c8529c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | 6.01.02 - Draft Redline Drawings
659cc780-7e85-4eef-b755-6844870b698b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
1c4e920b-ca8f-51e8-945a-7de163b55d3f |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | ITP - Retaining Walls | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) | Add Signature
e95e3a0a-edd9-4a7b-8584-9f421f4d0b01 |  | pass | Stone Strong Wall Installation Checklist | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist
f42b925d-1b9b-5bf0-b023-0e40fe3d07db |  | no-status-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Details
82928a07-4381-59df-b100-14086cf04d5d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Level foundation installed as per design. (Base layer only)
8c8b9cb0-e45a-56e6-9199-c481b03a3e1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | 2 x Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Tramsfer Platform. (Base layer only)
287c7404-24e9-5134-bce6-a63ca79d069a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Blocks Installed within specification tollerances & block pattern as per design drawings
31431bc8-58c2-5ca4-8f3f-3a13b5fe0ba7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | The correct number & length of parawebs are to be installed as shown on the construction drawings.
d298779f-080a-5e1c-80c8-dc3a25728b1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Paraweb is to be placed flat or with a 1% fall toward the rear of the wall.
558f2404-d6fe-5637-be61-46a7ab8b8bf8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | 150mm of fill cover is required before construction equipment can travel over the area
9d629e8a-ef41-5edd-8df5-c985fea58947 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Backfill installed in max 250mm lifts
c6722c67-7d68-58dd-ac27-2735b504103f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Proof roll completed on each layer
a3cdeae2-69e0-51e6-84a0-7e78e9682239 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | NDM testing completed
e6a72c3f-d41d-52b7-b5b4-829488ce54ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Clegg testing completed (GAP65 only)
ce0067f3-0c5f-562d-9d80-0f23d867cfae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | Scala testing completed (Sand only)
5bc43f80-eb97-5922-beb6-97fe7009207e |  | no-status-not-started |  | checkpoint-no-value | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Retaining Wall | Abutment D | Stone Strong Wall Installation Checklist | ADDITIONAL NOTES:
14230244-df30-4dd6-9fa3-168a28aa6605 |  | pass |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Piling
1ee17391-90e1-4595-9049-e7b1f4d24b0b |  | pass | f2478c84926fe662594ba8557dff929c9396882445c4a69fd6fd36686b397d03 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully
c95e0bce-728f-507f-be2b-0de33b01c61f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction
ec3e01b8-6960-527e-aff7-9c18425fcaa4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | 1.1 - Accepted Method Statement
5bfd5852-a8bc-5f32-bcbe-ecf38dd4ceec |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | HOLD POINT (DO/BBO/CLL)
3e408287-6483-5ea2-9ec8-f3f680829c2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | 1.2 - Accepted Inspection and Test Plan
a3da1f6f-2604-5743-a84c-1735587623ee |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | HOLD POINT (DO/BBO)
7b79b1e7-9a11-53b1-9a50-b764b399051b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | 1.3 - Accepted Safety Plan - SSSP
7c5a07a8-332d-52df-8f19-e2d4bdc01ba4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | HOLD POINT (DO)
28d8cecc-9290-54be-820d-b95dd5efb612 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | 1.4 - Accepted support fluid details
888b2edb-7426-5aff-863e-bd89727a8984 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | HOLD POINT (DO/BBO)
dd7b89fd-dcbc-5994-b3f6-8999cf08121c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | 1.5 - Permits issued
98030dcb-0bc5-563b-94e6-049815819bc7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | HOLD POINT (DO/CLL)
5847611a-9d54-5836-a9ff-07d5d0835709 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | 1.6 - Concrete Design Mix Verification
1c7a28cd-9ed3-578d-99a9-7f5e4ada656d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | HOLD POINT (DO/BBO)
50cc48cf-5cdb-5b20-aaa8-3f3e27fe330d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | 1.7 - Reinforcement Steel – mill cert
4233079f-9ee0-50ed-8498-f6c98f890fdf |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 1.0 Pre-Construction | HOLD POINT (DO/BBO)
25b7c56c-bb4a-58e3-86d5-b88b2f6634b3 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring
1655b459-44bb-5f20-bcd3-775252ec9a8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.1 - Client Notification
2acf19ee-4180-50c2-91f0-9f81db82f384 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | HOLD POINT (DO/BBO/CLL)
208c21d0-f59b-5240-b7ea-8f1dbcfe85f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.2 - Check drill tool diameter
798799a8-8b40-5855-af37-f44e14aa18cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.3 - Check depth gauge/instrumentation of piling rig
9a7a9dfb-4781-5cb7-a961-d8cf2df51de3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | HOLD POINT (CLL)
ed972f36-3744-5838-8a30-5f3c98c45286 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.4 - Ground penetration and extraction with due diligence
25a03995-5774-5338-b42e-97caa1c1d9ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.5 - Check pile position/pile numbers
6d3f8149-7261-5ddf-965c-c52569b1a9ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.6 - Pile Setout/Offsets
cef374a7-f21e-55cf-afad-fd2e69bf1b8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.7 - Casing Inspection
82cad99b-3849-5f11-8222-d9ef0e33d937 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | HOLD POINT (DO/CLL)
74cf3f2d-0012-5062-8202-b555801a91a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.8 - Measure and check position and verticality
181326a9-442d-56f8-9cdd-18937ddee6a7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | HOLD POINT (CLL)
180727ad-efba-5b6d-aaa9-f1710f5fd6b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.9 - Bentonite checks
e7688c11-488a-55b1-83bd-fb9cb6661721 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | HOLD POINT (CLL)
25062812-fbe4-5985-926b-d5219c2cddd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.10 - Bentonite level
62bc6ca3-c227-5ead-abde-e24c5d7fa05f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | HOLD POINT (CLL)
13738cb6-88b1-5f4c-b296-1c42e3e78495 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.11 - Soil logging and bagging
fa9776b2-59cd-5d94-8495-6079caf32e5f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.12 - Confirmation design minimum toe depth achieved
b4393b7c-b4bb-5b4e-9367-cfb6a44965a1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | HOLD POINT (DO/BBO/CLL)
cad5dc26-2a07-57da-913e-51c27884a81b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.13 - Base cleanliness
c12a1b6a-3b5a-570d-9831-a6a2b737b7ee |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | HOLD POINT (DO/BBO/CLL)
7c32bff9-cd11-52ba-b684-6a50c17fa0d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 2.0 Pile Boring | 2.14 - Pile Boring Monitoring
54daeaa9-03a8-50b2-9fea-97930e22a06c |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection
68c8dec2-754f-5f01-8da9-c0c236ecc61a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection | 3.1 - QA check on previous pile
0f8f97a9-ce2f-5947-805b-61f01a5b7fcd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection | HOLD POINT (DO/CLL)
e7d4e4c5-e87d-541d-b86c-ddd10835b3d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection | 3.2 - Reinforcement Cage inspection/ check spacers, pile bore tolerances
6f08bbcb-7464-542e-bb35-05fd0f87f61c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection | HOLD POINT (DO/BBO/CLL)
3c0bc28b-42f3-5a56-a5dc-20ea155d2a9e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection | 3.3 - Stabilising Fluid Verification
22652fbd-ae0d-56fe-8de9-0f937712d417 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection | HOLD POINT (DO/CLL)
b6520c9d-f5ec-55ad-8a65-eec2961e4d17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection | 3.4 - Pile cage installation
1cc9b867-3437-5798-a114-aab0717d49cb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 3.0 Pre-Pour Inspection | HOLD POINT (DO/BBO/CLL)
d39877e9-16d2-5aee-99ec-1d7a1061010e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement
8ba6ec5d-0e47-58e9-adaa-401a4d396739 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.1 - Verify Concrete Mix – batch times, mix
763a3bf7-5e2b-54ee-8c49-2f17efc3e8cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.2 - Slump/ Spread test
f200974a-e81f-5787-8494-99e98969f259 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | HOLD POINT (DO/CLL)
140a65e8-79bf-5384-95e5-0eec3fa4ed7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.3 - Concrete level
d76c52a2-e94d-54dc-82d4-bce394fc7b55 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | HOLD POINT (DO/CLL)
58d5191b-3173-5d75-8d6b-57f2fc4a4384 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.4 - Concrete placement
e87c10d7-368c-5e3f-b36a-001ce5467a09 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.5 - Concrete pouring – Check volume
a1357ba9-f7c9-53b7-96f6-a0c36c94558d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.6 - Pile concrete overpour
0598fc95-5605-5353-9c78-92c756a6d024 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.7 - Formation of construction joint
cdb74f17-c43f-53c0-b859-c17ac55bfb2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.8 - Concrete curing (tops of piles)
8be80695-a791-51a6-846d-b4a570aad82d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.9 - Compressive Strength Sampling
8c5284a9-e75a-5874-96df-5d304016b00e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | HOLD POINT (Sub)
113385fa-8d4d-55d3-bb89-d16e363431c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 4.0 Concrete Placement | 4.10 - Post pour/ Post casing removal - Reinforcement and concrete RL, orientation check.
4ed209c8-42eb-5a6a-84ae-d553cefc9ae5 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 5.0 Close out
834254c6-d36e-5cee-8ee5-6f8bc1047279 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 5.0 Close out | 5.1 - Pile Cut off level verification
602b851a-6fb8-5298-aade-ee38aa9ccf80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 5.0 Close out | 5.2 - Pile & Reinforcement Cleaning
8899b974-71d9-5721-b8df-b148086e255d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 5.0 Close out | 5.3 - Reinforcement to specification
51f76c8d-cf2a-5a76-b62c-7b87dc0b120a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 5.0 Close out | 5.4 - Pile records
1288ef0d-485b-57dd-85a5-a3c1fb66ffa7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Piling | ITP - Piling Western Gully | 5.0 Close out | HOLD POINT (DO)
3dec6b79-54f7-4509-ae49-bb46f594177e |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns
e2d52cbd-41d3-4b37-8cd1-9d9be1ce0e2c |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B
7aed4b3a-48bd-4ab2-8737-c175b034430f |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1
92d8b28e-6d20-4656-b38d-8e180d0aea3c |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D
efb0b45f-17ae-5d7b-9607-7e47c073d1a3 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
7b6be252-3add-5c4a-a4b5-749641ee26a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
1c0887fc-7ab9-5979-a4e7-bb8ca0232c6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
e2ac640e-3778-5814-a65a-7cf4b60645ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
9c90f2df-65f4-5988-89c5-c8d6c9b113d5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
74c0a248-aa74-5eef-81d0-63a0757976be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
c3d9f3bc-7388-5363-b520-bb528ada5d71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
63251551-65e1-53ef-af9d-f4fd93e700c8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
b6f1d5eb-f549-5ef7-b8fb-33a7fabe5968 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
b62ee2ff-7ba2-5e26-9af5-ad8c963eec35 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
d30fee46-4928-5bcc-96bd-f1e56b9af73e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
3d13e7e9-88a4-53fb-bf8e-92c4fceab803 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
9fd26097-417f-5246-9f42-dac5017edf80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
539854a5-b846-5562-b7c7-af94d40e14d0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
9fa247a4-179b-5678-9fc6-c20e707d8755 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
97dbaa1e-a6ee-535d-ac11-0cfb229fa746 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
921b602b-e44d-5db6-9fa7-bf5edbaf185f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
4d90184d-adcb-532d-be70-3a4a05a48b4c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
46bc4d44-1964-5fe1-9814-908b0be31aa3 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
12bcb7bd-8d28-55cc-8f73-fa6ae9acc053 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
07126cd6-89eb-55aa-b67b-4a7541f7d1cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
e7004af3-9478-5c8c-8e3e-49ba1e1827aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
9814cd5c-34b3-5fd9-a323-abb6dc2b3ec5 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
eca2f1d5-0a49-5bcc-aec5-07dd1b168da9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
7fad09c8-5863-5ae7-81eb-67f123473315 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
34319ef4-9b3d-590b-959c-803251f99f83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
1b0d4a8e-23d9-5d0c-baf1-acb32cf0e0f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
a6d677a1-cfd6-5b28-8678-7417f37587c3 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
65636e2a-a19e-520f-b7a7-d5bc60798f71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
5868f1f7-57e7-56ee-a146-948c12fa7e48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
e65ccb32-c83c-5a12-82d9-7ef2829b35b1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
25cd976f-6ced-5303-826a-bda7df300a26 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
d465bc6b-8744-58f5-9ad1-140936d44984 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
9a985daa-ec1e-5d5b-91c6-c92fe8ec3a00 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
7f22a773-b7e4-5b76-8f81-6e48b04425e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
2d00c47e-bd8a-5a2b-a3a4-98fc535c8f4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
a13f0a1a-7a89-5f37-a122-b62efcd5f4cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
ffa4115f-5431-5adc-bb76-19a043c8a8df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
6d0322c7-6400-586b-b3cf-571d888a883d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
4f62a988-1165-594b-9780-78855ca71b07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
6f1481b0-2689-5a12-a9d2-b37106efb9ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
8af3b10a-3a59-5458-8531-e5077a5756af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
f91c1f06-fdde-531b-afb2-d3ac3716a735 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
18e12064-24bd-55ac-95cd-27eb1ee15da6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
8306bc85-3308-53b2-9c2a-ec31342e22ad |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
c2d95aee-450f-5c0c-9b7f-cc2aceb3c4db |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
aebda498-6dfd-5867-b12b-b4ad3d819f20 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
b125bc4b-eafe-567f-98d8-3678f68e1555 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
e12c8c2a-0fa4-5497-ba63-4a79232b2095 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
968f0bb9-2aed-5725-b932-28e895d07e5f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
71fc8c64-e69c-5cd6-8f4a-b534da4e287b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
93ede232-6e0c-51bf-9e63-2469b8ea21ef |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
b2813a51-bb4c-5ab0-8788-eb6001986548 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
90c265d9-c5bb-5132-9f50-182b5115cd61 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
86bcdfc8-b2d1-4974-8d9b-c4b2fab99f01 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
51a8f9b7-13aa-53e3-852b-e8e93de3fa08 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
906a71ae-d218-498a-a76b-99431cbacb36 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2
cac9e066-c764-45f6-8135-d0a870128c65 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D
a02b994d-8cc7-565e-86d5-018c2582bbff |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
2e846d18-d25e-585b-a3ad-9ec14931053d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
97343edd-4450-5e3e-b7bc-b30a62136a98 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
dcb1c7fe-1580-5104-895d-4ba7156f7681 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
4035e1b8-90a0-561d-9745-cdc4bdfe3097 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
a30fa81b-b29b-5653-b6d9-ce0b8bd2e4fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
81676606-f734-59a0-b8f6-9e44b6e47f5e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
e87a02da-bb9c-5b48-8dc0-49376fca0207 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
0601817b-5f66-540f-98f9-96b186e8bd9f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
1aba1580-337f-54f5-978a-1e8ecf505da5 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
1137b548-66f1-544e-895e-e9648be6461d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
12cb1c12-0728-584f-9cb0-c6bdd364c6cd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
0bd0a781-b62f-5942-9e65-320e4a5842e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
c844a947-1fbb-5459-b2eb-e07abe7a4daf |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
a257d86f-ba22-5f48-9cba-dc333f652828 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
deca2079-6951-5539-a04c-4a9a3d57c262 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
120df856-3440-5b7d-b5a0-b49f364aca21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
4d7059ec-b21f-5933-8f14-abb09647aba4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
b973857f-099f-5ffa-8f8e-467da4315a1a |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
23629f3e-abca-58f8-84c0-a80f8ea5e864 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
0949fb20-1e7e-5395-bdc7-d51966501274 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
f3804f2c-0d5c-54c0-9ec3-9d20881ac93f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
9f83d8ed-4452-5f8d-88c1-8fef49a9ad42 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
9cde8e8e-5b27-59b6-8e9d-999c420fdc42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
0d8ea519-eca6-5f5f-9c9d-283609f27f39 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
dd7c02cd-16d6-5757-82c7-b707ad6cacaa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
3fe153ef-a7ec-572e-ac25-b4633ea8bb65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
2e3ef154-0193-510c-bfc0-fb17bf553e6f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
0458c5e7-27ea-54d6-aac9-24493a071ecd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
773d7b68-63a2-5da1-bbb4-d368b05bb0d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
38c60f14-adbd-53c5-98be-709307ff6de2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
a36f991c-1680-5a01-8a3a-b006d2e80e94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
229cd8ef-ab92-5b1f-8f3f-64fcb9a710dc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
6640e84a-a6f2-561b-ad60-0ee852025eda |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
7bc4164d-cdea-5104-aa06-900d4fbda6b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
a3252943-8fe8-5a33-b3e7-e19207fac52e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
387d7160-14c4-5414-ae77-21aff0f381aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
003f2b14-bc0f-5a9e-8322-87c1e60592c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
fe10915f-6174-5caf-94e9-874db8f1c34a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
2bc40e78-3ba9-5dbd-8c9d-e21035303a78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
650ed712-f71e-50a5-b119-bf0574328e45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
43b55347-7d05-5862-81bd-013e2367ea91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
83c88b73-1bf1-5e7b-b452-e34be4ef499e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
954cfc94-e9b5-5a66-997d-67f92dc208c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
eb33f004-8a48-55b4-a58c-0a97ee1befe2 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
9c16b3c7-a4a3-5a0c-b3ed-ebe5f7a7e7b0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
6fac82d3-ea6a-5526-9056-015cc8fcb394 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
f1c4fe6e-3eda-5c3d-bc69-19b9d79f9472 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
6a13f17b-2785-5dd4-9586-c025770a2622 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
bff81b22-2bce-5beb-98d2-3f684c90127e |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
d5c44d0d-317e-5b11-819b-113d988015dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
ef9ccc9d-4fd7-54c0-8717-ca3872b76ce4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
4751b3d2-2be6-5084-ae46-e5623e541da6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
6257c28d-fa55-5e64-9c62-33b5655ee031 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
836ac07f-0871-4651-b405-8d6d86b0af6d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d621b5f4-bc49-52d0-8db2-d4df9fade6f7 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
6074341a-5a46-463e-9292-683af4a0b430 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3
0e9249fa-4853-4a58-9c1b-0786e3cb5397 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D
cfe74e54-052a-52bd-9d39-49f8edaf6577 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
f642abf9-6447-5f40-999d-e7184626fe5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
8de7cbd4-9ac8-5c7e-bac3-7bbe8e008637 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
9da7ba04-a86d-5f00-b24a-e0654ed5b860 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
ed63e166-826b-5280-8bae-8d0f257bc6a9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
1e7245f1-269d-5e9d-90d3-990ba537c912 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
3230bd9e-32f3-58f0-839f-69310b73b792 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
56a341dd-1654-5c4b-a6d3-c26e9a46ea28 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
ce0a7b30-ce8e-593c-9698-7637daec252f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
cc24eaa7-c80f-546e-bb73-ebb1841a52e2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
e30bbea3-ec05-53d9-94ae-262433eebc87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
9ee5dc1d-8884-5069-ab91-7315ab9d524c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
a1c66542-1528-52eb-a496-017c897be92e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
eeaaa71c-edcb-529d-986d-4ec3569e4a4e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
c4a59ffb-97b1-5bad-bd2f-e596a8940e6e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
69b04f64-d01d-5b7f-9d5e-a01c1a9fe7f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
468ebe67-17d7-5194-9a2a-4f2d15c0f03b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
b7761162-1605-5dd1-950c-5cf5ce8a5834 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
533cf5b8-e2e1-569c-a24b-04915b8b3b57 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
bad1385b-9d3c-5059-9a7a-eb1e5f2d4308 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
ada2c75a-ba28-5606-9dec-78924b5c57e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
babac4e4-00b7-56de-9e86-75391dc99211 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
7c910d30-7460-514f-bd1d-8f2727b8d6ea |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
52562e28-dc9a-513e-9fca-790d74ace7c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
d8433b7a-ef10-5d96-9b46-6b8ddd2969df |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
b5a3b5aa-6957-50f0-86a1-f20c309ebb31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
742b6f2e-cb31-5ac9-8f7c-7eaf437b3faf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
2e6f60ee-0bc4-51e7-90c8-7a692811565b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
d15514b7-5505-5147-be3a-7ea36165d573 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
98d8a3ce-6ce2-5040-890e-8e225c338261 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
178617ee-84e9-5c3b-a688-eb9d32ed8456 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
6b4122f4-c096-5d87-ad42-e88e7632f71e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
f73644b0-f896-5007-835c-ccfa6e07efb6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
57ea4796-c11b-5b7a-affa-90d21f35b75f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
978db621-5e11-5969-99f6-4a5f3883c98b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
348caaf3-62fd-58b1-bddb-db4b5f2640ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
a73a2245-d104-5707-9a19-055cf8983792 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
a7a514ba-5b5e-5e1d-ab9c-33771cb9b349 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
154bb2fd-e7c6-5e3f-9af7-1e94f3053db1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
5966823c-9761-5ba6-b5b8-878fef5da094 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
30e0bc93-a112-5ff8-975e-10fd5655cb0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
96eaa7e9-d3db-59cd-9ec4-11864b62766b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
0ddca059-4a80-599b-b093-7c14cc052865 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
7838c10f-a840-5d00-83dd-455831c6a4bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
d1727597-57e4-5461-a591-797963847398 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
bb935b30-9763-56b7-8bc4-069e1690871b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
8f0d2f57-482b-54d6-a70d-73400a45193c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
4e65a0d6-e75e-5216-8466-d37bf171a24b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
bb22ddaa-3e9d-5310-8c35-27deeabb5d44 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
a95ba54b-eac4-5dd2-9c03-91820f58e034 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
8db00cb3-dba9-5adf-a199-9c275d4d8620 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
62c33217-e152-5cad-bddb-e6cd9c888b78 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
2bc69129-56c7-5a62-8ee4-337c3e75064f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
93533369-1f40-5f24-80fe-7f8f3ed43eb6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
da84bb5c-94f0-41e9-9a4d-d41bc201b4ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
a7765b2d-3d4b-5a7c-8891-bd7907cf105e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
d46820ed-6e0b-4847-9d03-a6d16abe34b4 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4
c95454cc-090c-4ca9-babc-bfca55299bab |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D
09280440-2608-5f39-9182-e30371dc1b62 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
0ebc43fb-cf79-5c9b-9ebd-2abe72665e46 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
afa8b0ae-45fa-5f86-9c9b-40c5c72b5fa9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
b8e54b02-b57a-50dd-8d62-dd969b9fbde9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
8ef50bd9-3555-5e15-9aae-14da80beb11b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
47c5d85c-71f6-5027-8df9-66050b314258 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
30538375-a519-59c7-a3df-7a0869199ee9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
624d0de8-286a-5d5d-b2af-5aa3c722e2ac |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
df137c62-d0de-5157-a823-b7e7ee4cbcad |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
c08d6dd1-1d47-5678-aa9c-32676d755d61 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
17a038d8-39c1-58da-9270-21e90429e2dc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
57d70d83-6c28-5ce2-9243-ba671cfd2fc8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
0514cf89-6d46-54fc-96e6-a5c1c2657b25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
635a6b1f-ad1c-54f9-a2c9-cda72b3be740 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
12c1a418-8e9d-5379-9cab-da23dd57089d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
cdb6135e-9efc-530c-b1f1-0e87a89c09ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
aaa5a386-1e80-5c30-9764-d9374f234eef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
66e51363-7d3a-5590-8217-a473e745c24d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
95a9adbb-789d-5a89-bf94-bbb2ca331c7b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
7ca50e50-a309-580e-b7ff-ec1981d308e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
e6b6b5b6-fb90-552b-93c5-9fa23738add1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
bfcab519-b855-501a-9775-45ff0fc8a50a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
5e2c2582-3857-5f15-9085-e67ae853c210 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
4a7ce7cf-3d0f-5466-805f-55e759d58be2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
2ba0d04f-1a80-5426-8e7d-c253b8947567 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
9bdc1d64-1608-543c-bfa7-6ce2993c650e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
241faa4c-9805-5012-88fe-77926578e693 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
f9ba7bf7-5414-5e61-942e-103a303f2317 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
43d70666-0d19-5af9-ad5d-cedc8011be8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
af34e5a2-4c1c-59f1-bb48-5c5def91be04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
c3700989-401c-5586-8c1a-151abc77917c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
82542e92-5585-588e-8c8d-d6bdd1b4b0d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
f9b9c982-05c1-51fc-ac36-895b877ceb37 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
61be6040-2af3-5541-abf7-fff67b1bf167 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
2b09cb7b-6ec2-568e-b828-b603438e48ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
76c601ab-6cb2-5f49-891c-90269b28592c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
a6336317-d45d-5eae-8f7e-b6a473b4c063 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
0a557ebb-6bcd-5906-ab91-5f490daef02d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
8145a473-7661-5500-98de-fe79c54d5dd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
4c5a14c7-bead-5170-90c0-d4862426e911 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
f5c7a0e5-1e12-5961-9ce7-75dd1080853e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
8139c2dc-4bdc-5c28-8b7f-a1d99c447c9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
67460120-904a-5dc9-8dc3-50579c927739 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
cf9bd748-7e19-5e8c-82f8-7652b9c0ebad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
af1113df-f206-5318-afaf-5cc7a5a21fc4 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
32c824fe-f106-5206-9b5c-3ccd966ca8ec |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
3a79b005-3a4c-5d86-8bf0-b84cb313e7a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
8016a1d9-9566-55c8-badb-1e328014411d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
34161d35-b163-59da-92a4-3d574e0fd835 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
5563a8b4-523f-5cc6-8977-d7f5fd2a25f9 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
a7ed41fd-0c7b-527f-96fa-97c559985b43 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
a667fe2a-c797-57f1-94e9-e998906eb355 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
41f90810-d723-52fa-9fac-76b5c07c98e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
617a2f89-54dd-52de-82c1-91b121a9885d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
b37d42d2-c43b-44ea-aca6-4762b46aa6cb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
d1189e47-0dc3-5b03-afba-2348f4840f45 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier B | Column B4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
2970fd57-a54d-4b41-94f7-f445a31c9979 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C
71c5ce4e-46af-4480-832f-b82a725bfa47 |  | not-started | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D
51912039-1558-5ff3-93d2-481475450344 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
4ec0df46-0ef1-5280-aa55-65b1f7fb08f4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
62fe740a-ae92-55f7-a148-a75dba8b1ae6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
42d749b7-e9db-57e3-91e0-f44b9d2ce68b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
1efaf7bb-055a-5d02-a051-85aa06be6543 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
14e45628-a850-5d56-ba46-3fe2cebfb992 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
4632c537-444e-5772-be7b-b2a1f18762ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
9e7e8895-7d1b-58f6-8faa-92c16a1abd01 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
1ba55a9c-2aef-5794-b03e-485820237171 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
c5b792c1-eee5-5385-aa7f-cc141f0668de |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
8581c239-1ffa-58ca-bd5f-c8a038cd04dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
8149ce64-70c4-5443-8354-38afc6ecb723 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
8c9fe6e4-0069-539b-ab29-8c9e9426dd0c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
2c9e5e61-76c7-5243-82e4-c8fe3820a1d8 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
ab805847-4a2a-5025-a89e-b574f03359bb |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
3e1281b7-d154-55a3-affd-c4ac320d4d3f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
7a8f8fd7-1e77-5702-9642-ee62e0b0f231 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
a89a12b8-1959-5bf3-991d-62418e5a5a94 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
d4e1901a-c509-5654-af9d-a481140ac454 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
d0c0bc97-85da-5624-8f5e-95c472bcd9c2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
8e58db61-4689-5543-ad04-a627e0f02687 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
3485f333-f730-548c-a4de-874f3f413502 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
ecd0e841-a9f6-5a88-b0c3-db56da329d7e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
a193906d-953e-5d1d-aa04-5b11d18233d4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
d636097d-c183-5605-8cc6-3584ebd48bf7 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
208b8e58-4ba7-5da7-a190-ae435aa6a988 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
b6ae7b01-82de-54ad-831e-49627141dfc4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
4bd9714b-e2e5-5a38-a731-948a42003a8e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
5210efa9-ed22-5178-99e1-6cbd8036fdfc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
9f6dd03a-39e8-5f59-b355-f70d77187e5e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
3042e9d6-21da-5cd4-ac3b-1b733716f656 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
4013c911-6748-5da3-9288-051d81e62b5a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
286ebca4-1a4d-5494-b4cd-c9370c00b391 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
38217fb5-4ed3-5c39-9f78-e3b164c63ece |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
a51348d8-01c6-5af9-9728-03688151542f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
417b13f8-0868-5a33-a47d-ddc8c05bdd31 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
150039de-09f5-5900-8427-8199f12e6435 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
c4a540d8-9397-563a-9e1a-7d3dc80e4dd5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
48041f07-757f-5d01-9463-29be31df2d88 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
f26b901f-22ef-5060-8361-a6a7bafbf350 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
6d38a010-81b9-5110-9e39-8690c2933c79 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
4e583385-0f14-58b4-8218-e91d19bc487b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
057e239d-3951-5ac7-972e-96c4ac703dae |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
d01a46a9-27b7-56c9-bdad-7396aef589c5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
643af0bc-7ce8-5dda-9e5f-d2ffe6a72f37 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
12ca3f1e-1430-5cb8-b4bd-7c88678fd5e6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
597eff59-af2f-5e72-b0d5-9d36d04b4a41 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
72fdb456-1e19-50a3-933e-defbcfc04bd0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
c28a2775-3aca-5b56-a811-fd87d949d915 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
1b751137-2f1d-576b-a765-5314981f1f6c |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
eed85626-3f92-5661-8c18-5eae7ac0405a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
c065386e-5a65-5771-96f2-5927e0279db2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
613d342b-50ea-53bd-a295-f0d7541acac1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
1a5c81dd-90bf-5881-8f90-1e775fc95974 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
1ad621cf-ae28-4e57-a993-96cd7bf03efa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
dc3041e1-9f0b-5620-9c85-1a5f704d21b9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
9fa8559f-920a-4597-9f73-25897dbaec42 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1
9ac099b5-929d-4704-9585-7b0f6346924c |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D
8aa7d9f5-a776-5bfe-a051-4fc9f2a21e90 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
51c28e3d-28bc-541e-881c-3a8654b28b0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
be86cafd-80a6-5d70-9dd3-0b0b2f67b1a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
49bc6d38-102b-506d-9426-0774399269cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
42722987-bf61-55ea-baa9-677dc284b751 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
85395332-0b99-5393-bc42-21b8d17454a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
a30b778d-b3eb-539f-acc5-9db7fa8b2494 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
51c2c3cb-726f-5747-a114-056004acd837 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
73d65dba-054f-52e1-a6fc-21852f77ee99 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
bf025371-f985-53f1-94bf-9667f26a9926 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
03d0b6a6-142e-5662-b213-3249f27d8407 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
96badf63-a2ab-53b6-8c98-43c2f95fe575 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
3d737a9a-fdae-5d11-a826-397ec2c02834 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
9d9bd8e9-fc67-57fd-838d-1a12348ebf75 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
da3b389f-8a85-568e-b0b2-b99805d1397e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
ca175492-cb85-551f-805a-57b3183a338d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
473ebb99-696a-5134-a705-23f8367e0aa1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
beceead7-f3bb-5d61-84da-293125c67e3f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
a74c3229-1129-58be-8b40-1b8d48ea8a98 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
427d7d7f-23cb-571a-a2ab-7d3fff3a17b5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
4aad65d7-011b-5025-85e3-a0df9a957182 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
5057daec-9467-5b91-a1d6-883954db3ebc |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
98ca9de1-7669-53bf-8e12-629e6741d4cc |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
ffde9ebe-13a0-5999-98d0-ee033baa50db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
c46caf03-eec0-516f-8c46-83fab58c8e6a |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
b714a1cc-2fc9-5b6f-aac2-c50e30ab1dda |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
bfbf7196-16e8-591a-8c1d-ffcee87279e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
bd6d7e06-5f51-5f85-8640-c6b65643e458 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
cc6864f4-f9e8-5bc3-b6b1-b94861d8dc72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
f1c4ff2c-d401-522d-a42c-54d9e5f37fbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
9189cb1f-8ec7-51b7-98f0-d09c5e41f106 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
9a5ce3e0-2931-5619-8816-4a1388ce119b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
75addd88-f09e-5c82-be17-b3dbbebf04f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
2b6ed7d2-b917-5048-8578-6ecd1fc3d405 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
077dee3d-1e5e-56de-bd80-19ae8304ea93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
2f201f13-217f-5f9f-8366-04757adcc632 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
a284b684-f22f-5194-b90b-7a888327c2d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
92b97971-ac38-50cd-9142-1679ff8ce5e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
f48f70e4-dd95-5c92-8386-a99399530679 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
54a2e03e-abe7-541c-b60f-fa44049def3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
6449fa86-0d7c-5fa7-82c3-b901323688ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
0e678bd0-89b9-5d5e-ac2c-bbe029577dde |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
7e50e26e-0983-5c78-b417-6c47e95b7fad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
f5da3249-f9bc-5e42-87e0-3a6efd795f7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
14b7f27b-096f-5fc4-b641-82bc1dc97268 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
553914f6-436d-51f7-bf81-48fc05901820 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
ddb61302-4de1-5e74-98d1-101bd01a72bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
27c3c190-6db2-597d-8d34-33c96ac86460 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
576bcbf2-8676-54df-afc8-58c79680a3b3 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
1804fcc3-c485-5481-8255-08596a663a87 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
dee866c5-7ee8-5e9b-99c2-f957eb08efd3 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
da984d40-d11c-574d-b88d-17ee83c2e490 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
c69e6a85-f748-5f63-9b70-9d2f9e060b68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
33dd0c32-adf2-50a6-974f-dee17404f7d7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
f3ea9231-b446-4057-bd7a-a9669a8230b8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
6bf05e5b-f7cd-5309-92ee-09b6e2e827c5 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C1 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
84ee4218-249f-4c93-a913-05ff4608eab0 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2
7aa5f73a-5a5f-4506-941f-36aab4a8f7a5 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D
850b3ca5-e4f8-5ebd-a9d2-f75701d58926 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
fbc1ee34-e6fd-58cb-ae26-79571e8669f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
25da3542-5650-5d58-9e72-312f19670d8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
026499ca-9d45-5fcc-bcdd-8969a7af4a55 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
399a0c96-3961-526c-a52c-168b2bfa05e1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
e06817ae-8508-5a4b-92e2-f4ab4281f14f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
c0a204cd-9f1d-5b5a-b169-4e5464790696 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
6297c8a6-15d4-530d-889b-7b8239029114 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
fbb35f2a-2b17-5a6c-b152-f1e727c770a4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
2aa1e7bc-7b85-551c-aee4-355c58ffc5d0 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
9cd92745-8192-5bc5-a3c2-b25e257061c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
75c6e6c9-486a-55a4-a590-2562e0a8f4b3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
90bf95ce-fad2-50d1-8288-64cb633c2fb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
08e11f3b-7442-5fb2-957a-026b97189b83 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
01acd3c7-b513-58c7-8225-d66660ccc563 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
e368ff76-3e4f-57f4-95d6-ba19851678e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
aac8381a-f17a-5a5f-aa75-7e5ce83fc969 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
9f048a41-dd09-57d5-ad85-f3b561d04818 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
f39f821a-d589-528c-8793-81156bc3bd71 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
1dd4816e-8ba3-51f6-b179-3ba7c0ef9408 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
1d39f746-5bae-54d7-afd5-a5c282244c13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
a2b74e66-dd60-584e-9842-a5bef658d2d4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
e694e033-0c76-5482-8188-c760fe9bdec2 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
d40fa851-6d05-5612-945a-f5fc6a813e69 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
4ce991c4-97d9-5496-8350-6261ebbaf6fd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
3458786b-0211-53e7-8cc1-7c57043eb52d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
a501b001-3af2-541b-9f3c-a858faf23c30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
bc5cf847-cb25-534b-8583-0ad8f09f9cc4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
c9682a9e-80fb-55a1-a2f8-e15b738c3854 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
5e06d57c-a76a-5e01-b6d5-5d2f1dcfb592 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
6b9c6941-8756-5a7a-8e19-77cab3f0e909 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
5f0f1984-b2d2-5d0c-a291-94206eeb9ec3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
5a84ca70-9304-57b6-8a0f-cdb4bac891c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
9d39c055-e0d4-5d86-8854-52fbb4e1558f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
e844415f-cc15-58ce-94e6-f033ed42d4ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
08445aa7-c84f-5ccc-b97c-4b4207c10daf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
446226ff-087d-5512-8b1f-d6ccf40de19c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
e09dd2d5-ef53-5c2d-bf59-c12d0ba50442 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
4eb73fb5-a86b-5a07-a781-c6760cb4300a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
e1733e53-8c4d-5a0a-8f45-0bfbb9685517 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
73b100eb-7e23-5599-b9fc-3fefbc8e2e05 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
cab51feb-e9ff-5d0b-84ae-8859b9765aee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
5ef83b2e-5a3e-56fb-a7c8-879e3ae88e8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
aaf2fafb-6351-5b9d-bc7f-7e9737ad48f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
0fb13630-f49d-52f0-b924-cf734ab591d6 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
f7c79e8c-385e-59d2-97f8-9bfd5eade00f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
66c77b78-ed50-5938-a3f5-788e3a79aef4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
a692a462-ff85-5afe-b570-010f45a06b01 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
681ff7ad-4d82-5527-b057-43a9c064d33b |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
cd145423-6901-53b0-b8ac-319bbc55d9b5 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
ec37aac3-afc5-51f4-a326-2bda56788431 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
629aa5cb-280b-5a10-9c78-83b4e3d6b2db |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
335d691d-cc63-5de7-bd94-4c5d29a5c0c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
ccc4a193-e182-5d52-ba99-9b14b428f49f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
37a4008b-bcc6-49a1-9b98-18815a94458a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
f117131f-b80e-5510-ae61-713e728e2daf |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C2 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
baee8484-e063-49b9-88d6-74c93c8de22d |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3
d787bba5-2d5e-41aa-8ecf-1a58e47228ff |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D
b2f648de-2b94-5a9f-bd6f-bd69a3054ea2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
4d0a09de-e830-5e18-9a58-84d1aa8dd2f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
5ed47d63-c8bc-54dd-9d3e-6a9bb5516200 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
92935a9d-9741-5284-91c6-92c1080424eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
44ceee34-3863-577d-9b3a-4292a541d3aa |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
e22e41e9-c714-5bce-b7bb-353334d51103 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
df1f8e0b-977a-5141-a39b-9931948ed7e4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
02af7623-321a-53a7-a147-9747648b072b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
d8a7a72f-8692-5d63-9889-e54c5e816241 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
c58dc9ae-adb9-533d-ab47-74e8a3a41c36 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
9cce16be-3dce-5aba-a3f4-ca956ace8837 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
38e4fb92-807a-56a3-989d-5de2db47c4f5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
46700dc1-cc68-5015-8f20-1a9eaeb33645 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
25c5891a-2e78-5db1-880c-1310b746092f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
374852cd-2da3-5072-815b-f9ad4fe01c72 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
3591af88-1018-507f-9eb8-eea149c18509 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
3709d9ec-598d-56ed-9299-2cdbcda94f66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
94cba0cc-87e1-569f-80d3-98256abadca6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
3ce53666-5ae0-5540-b0e4-707a2d8b5e24 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
939b3bc6-c402-5044-bc9a-18f88f083abb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
2c6c64e3-dcfc-56f8-be43-c00b8a3c3612 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
9b303e7c-1f60-587b-a4e4-83a34aed2d8c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
cee19061-f426-5209-8c7c-c366ff5e57ce |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
81393fe8-b73b-5716-a687-3bfd3a2d1623 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
ad4c5e80-28db-5c25-9f4b-c42c3dc7ef9d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
518ddbb7-b378-5848-a27f-a712049a75dc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
d6d77ff9-06ce-5169-8378-3a89ef3b8802 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
06b2b387-1ca1-5808-827d-9acc7156c8c5 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
e4f29e0c-ebbb-509e-b1a1-5f9c60a9bf04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
a2d7d5c6-fec2-5746-baa3-659e3d1b9cc5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
90368b40-ae9e-53ae-a15f-18a51c237f24 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
eb068630-ac47-596e-902b-00f95d31113a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
050f9ce7-d010-5683-8f7f-8f33731e2be4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
dd8ad2ed-133b-571f-8331-bc2b60db3533 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
f37bfa79-e831-5c6c-b124-ee75a5d3b24b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
918e41ee-304c-5c4f-aa72-a14ae64cbe67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
c98c8e6c-ee1e-570a-91f9-18a258018e92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
22c99129-a0f8-55a9-9df7-b34280aa0e0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
02a490e9-de82-55fb-abcc-590c2622d06c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
357e4b1f-52c4-573a-833c-d409d15c58e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
b405f541-fd71-526c-aeda-551a01a3301c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
1f103fca-1600-583c-9e43-d51cd5826c1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
90360b35-eaba-51a0-9c16-2462a960d873 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
86f20aad-df62-5822-b5ac-774be4f8247f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
f8ceac7a-6eac-57b7-96d3-6a713f9b8b70 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
a9c9e544-6ffa-5f08-b59f-bfe3780298e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
73751c3e-25bb-5f44-8867-ca4adc48a3ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
2f2159e3-a88e-5314-8a62-f15936b98a3a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
38baa2cb-eef4-5ab2-afcf-d146afe02579 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
cee339d5-0472-5886-9ae3-9aa757de2305 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
6ac1aa51-8097-5e7b-b0a4-5fc492eb9b9d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
94e55617-7c30-5304-b0cb-f4feba8389ba |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
b3d08b81-2173-5e37-89a2-d36a9af7bfa9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
3aaa9e05-2c09-51b4-8b43-911b5bb280eb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
697dfdba-720b-4ef3-96ec-cf9b2a6edd31 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
0bfc5f1e-27c9-5091-80cd-3460b7dd1112 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C3 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
631aec84-ab90-4a56-b405-0c7736d757f4 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4
7541c04f-e2b5-4957-a8bb-75c2fe97d2e5 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D
3e396588-b4ce-58d6-9311-c007025c3579 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
3bb613a1-8e07-58da-a3a3-ecf9e1980d75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
910f47cd-6375-5b5d-a258-e66111bfb2cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
a0e7495e-1ac4-5132-8c7e-78e9bba69bec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
06059d77-608d-5c56-9e8f-0f760a4cffa1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
7c72079e-0ff6-5957-84ac-6cf964493968 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
e5a2917b-3fa7-5c34-a602-94a323545961 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
ef792c42-2788-563a-9577-61c4464fc2e1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
ef3893c0-714d-5c2c-b00b-262f5a7e4613 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
5ef27fa7-c01a-5e54-9b99-126b10a05236 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
c9545273-db9b-591a-bc03-07f9b11d276f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
f314a5c9-9a91-50b9-928e-6935fba6a9ac |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
4308cb3b-63a7-59ef-a0eb-1468afd47f8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
0585085a-a955-5808-b84c-da3ed5162575 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
b4b57178-8002-5d4c-89e8-257d32411acb |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
7e0e8acc-6a01-5fca-bd13-116ac03f4a27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
9de583f3-7378-5947-8e9b-77f9ded09c84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
e20d44de-508b-5072-959b-ec82731b61f2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
37f34df8-6513-5eac-97ed-fdadb70dc9b2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
7a8ae28f-e80a-5a92-bf85-4724f0deb8a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
d1d110b7-4135-5c6b-80c4-b84dd17524db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
8a13f89f-9028-5775-a027-ce6ab551a293 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
e79b9d3c-9a77-5753-9aad-24bc7c27eb8a |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
842414d1-f032-5562-b9fa-f48800861f0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
d483fe51-67f7-5928-9c13-2d3c3f7b13b0 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
9572c9bb-7b3e-55f9-95c1-3d0614079238 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
9411b0d1-5b97-5179-8b3c-ec7892ed5912 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
6d0bac8b-2c6e-5ff4-94d0-d8f54e7630d2 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
75de3cac-37c7-5d3c-8af0-5da98663ff90 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
394f2632-9b21-5b2d-9924-01fb8e4c9682 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
52f1b541-1db9-582a-bccd-ce26f4cff0ab |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
912ee5f6-c614-5a39-9511-a10fbb7d4dd6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
aa331956-0dd2-54b7-b8d8-493477c69b7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
8e04767b-58fe-5795-9fd5-8164faedd69b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
c727737a-887f-5f7a-b27e-f185fcf8621b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
31294b0d-f5c8-57bf-bc12-cdb182781065 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
b3414460-b6a7-571f-bd01-9fa87a91a7af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
eda2382e-bd19-5ce6-b241-688f898d7ea3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
329990d5-4c6b-5b9a-bd15-d7b5aab16bc1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
d700df09-cfb6-57c1-82c0-43b8ea858cbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
44a94f24-11e8-52c4-bedf-43533343c7f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
98309e3a-3cb6-5a1d-96bb-d9c43a175bf6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
3f96d293-a4bd-5332-a947-92e800abbde2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
9e347267-71ca-5e42-adfe-0c7340a3027d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
1b95e0a8-a048-53fd-9b44-e07bd615c1e3 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
6182e3b7-b417-5c77-a4df-d3b9a4f71f1e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
945d761a-26c2-5e11-9918-1559701c1a39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
5b55cb51-719a-54e7-b64a-4ca8a51e8928 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
920deeb5-d5f4-5041-b51a-d409ea390337 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
46068fce-27e9-529a-b86a-b46b091a42f2 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
091912c3-3d8f-5350-a3e7-bdeb7965f18e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
d7e65324-a44b-5215-a9dd-51c5231ddf49 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
f9d411b7-4f6d-56b9-88f1-181db44ba652 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
6ebaa804-a7bd-5577-932e-bbfea92dc438 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
f9aac3ca-5e00-4275-add6-8db8b2bf01f8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
50647266-0a18-5240-8da8-8ff5486a9be1 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Columns | MGB Pier C | Column C4 | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
4ffa4f03-ace2-4bda-ad7f-12fcc5ada906 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand
5d4cb2c1-f7cb-435f-8098-70e067903598 |  | not-started | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D
71980c9d-ed56-581b-8216-f4d03444b39b |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
3ab849f0-20a6-5493-a92d-6bac616e0244 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
9cedb18d-f1ba-559c-8d42-1ac729974eb2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
ab3126ed-4b0e-55ac-a961-a3a58932846d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
a04abc44-4f06-5a64-b633-3b276e709b62 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
c6a81bc7-36d1-5e8f-8a03-b7f1ed92fc8b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
0f34e82d-185a-50fd-80d4-ec0fbc6a050e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
c18f7a60-d38a-58dd-b450-3fc4a577dd06 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
1cbac32b-170d-5eff-83ef-106a99318a86 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
0425e3a5-900f-5bfd-985c-5719e2977c7a |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
b72d9153-65c4-5c0f-99f9-e38b335f066a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
99f64739-1161-56d3-a55a-24a717e5751d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
b2c4b4c2-1a73-5bd4-9699-55a0e9506f6c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
e19a6c0f-ae27-5843-8675-9f1c9dd05d71 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
c4eaaa20-3c02-55cc-b088-2482158f41a2 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
cca575a9-0d61-5a8d-ba8d-d99be48df7d6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
1758acb3-6e12-5e06-885d-9d87a5d9686f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
425fac54-5a61-575f-abc0-36966ca57538 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
419a0d0b-4c66-5d67-98fa-70802d7e62cb |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
79f60b8e-de8b-590f-a44a-ce96b0aa010f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
7c14f64a-673a-52c3-9a9c-98b604df625c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
fec272d1-24ba-5ced-b9e2-6c3f29929104 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
026922fc-fe87-5987-bc7e-84c951c0ad39 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
9f030940-17d7-579d-867e-05b8636953a1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
a0995706-a733-5cf8-950d-abeae3f0d832 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
35860b3a-1d17-540d-8abc-f9ef99c188ce |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
8d37ab1a-c849-53ed-b8b4-aa15607dda9d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
73ed3463-efdf-56ee-bccf-924e356d96ab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
820b004e-b641-516a-b688-f483cd4451db |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
b58a5996-5ca9-5560-a0e3-856b37e26ed4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
54d180a7-1782-57e6-bf5e-cf40dd5cae10 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
0a3de8b5-7ca0-57f1-9b5c-172f345f17a8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
a32c7bb9-e50a-5bea-b615-648e78c56642 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
89618352-33d0-5bfa-a467-babbdc4c0e7a |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
b8b93029-de94-513a-bab3-3f7fd32046cd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
35fcdc39-fe99-5b47-a0c0-d7ed2f89351c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
7ff2e585-d588-54a7-945f-b00dfb94a70d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
3cdb86ac-4684-56ab-9757-3624b9f0289f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
eb21e060-c3dd-5296-9add-c171b0527e2d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
32ab24ef-38be-56a0-898d-ffa183266b2b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
7c5072b8-3f3a-5b46-b6e0-05be375786fc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
ffad0efd-e09c-5c15-b79c-0d450fa04f0f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
06538548-896e-5c08-a007-dc85b814adb5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
b4f77dc1-4a9f-5da3-8a01-54d9cf9b7fb9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
e9c35ca6-2e0f-5a6a-8186-1029aa2d96ea |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
dc56de82-17af-5cd9-b5b3-bf1cc8d687ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
9a9264a8-7ac0-5388-84b3-921a1277c492 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
ae19ceb6-9143-5892-9eab-de41f2195f23 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
67e46426-fb8c-5b1e-92f9-2264cb3306ad |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
1512e574-bfbc-5cd5-b06b-69ed8141d913 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
75103050-3ef2-5a89-8999-9e4ad0e5fa96 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
a9d07ae1-b4ba-54b9-a7b7-531f85c4597f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
e90b013b-87f7-58a2-a80b-b79fdcbbd9ee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
7866960d-b1a9-5aa4-8428-68ae54e3b8d4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
551beee3-8d0e-4030-b93e-185d8b87d680 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
fd91b735-ad50-5839-8b08-cc5a687eb944 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
e2867fa4-3355-4cfa-8ddc-4ed79c70b7b8 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B
d349e548-e82a-43da-b660-1a53b4b5fcff |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D
709a97ac-317d-56a3-9468-b0bf771ffebc |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
a212fb51-97e4-54f4-82db-384de4577a2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
09748572-a9b9-5b40-a8a1-f5f8477df455 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
ed93e9b1-ef50-50f1-95f2-14be971b4866 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
3a115e6f-6f53-5eb5-9498-3729638ce2c9 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
316417d8-d003-5650-b7ad-4472bf1e3445 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
b79828a4-548c-533b-ad24-27f5d76572c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
6a27a2aa-9bd2-58cd-a201-5b5e5be1013c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
d092f187-6197-5d8b-80a2-e2483d5a0d0b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
2193da62-4d31-53f2-b8d2-7dcc77da851e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
bc7bcd3d-3e3a-549c-8ae9-f46907fed576 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
24e9cf93-54b4-5e5f-adfb-fd7f41285dfe |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
8c0e9750-933d-56e2-8567-fa83cd57ba27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
03d44c0f-c829-514c-8933-9fb2a8c8b584 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
f0f08317-1b02-5b41-a658-de77612ac595 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
15569872-1644-5b4b-af01-e8d74217340d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
3271c898-725c-5c0e-a076-8a6e005a98a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
650d9842-1f05-5f05-914e-579f58f762b4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
09985c73-702f-50ad-a793-8b5f3597e3c9 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
d9557f10-bf52-5f57-b4ff-0f5aba260082 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
543834db-e8cc-5dfa-94cc-35c4dca6b47b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
60e88380-dca1-5476-9d5a-6e20d252132b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
b193d8a0-8585-5a7f-a366-356f85c9f6af |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
fcda207a-c3dc-546f-806e-973b8a9fca23 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
3fc14fb4-20e0-5016-a556-4d875bfe2e8b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
378bb195-404e-5a95-9f5d-a0ec0aa9c745 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
3e0daf9e-3206-5d07-a1c4-34f0a2a96ced |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
f30beab2-2162-58cf-84b4-9cd6d9b8681d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
884448b9-fcb6-53ec-906e-59ec66daac4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
51ffccb7-49e0-5b2c-8181-edf1010217d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
972716ef-de4c-5420-8458-9af02af10a05 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
bb60fc73-90bf-5a4c-8ea4-82d53d1757e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
81917147-ee3a-5f7d-8616-1396c8922ec4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
13a48eba-cfb5-5ce6-aaae-606eb789ef83 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
c5c5bcce-0d31-5d14-945f-7bcea292f893 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
7ed04410-1113-5db6-bd8f-77166014bc0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
154cadd7-70d6-5b6f-a312-0ec005f7c430 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
59a66b89-5a56-5d74-8d1b-aabc9f8157f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
ed196e25-413c-5770-82af-348d7428ffaa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
ab00db1c-0a67-5a7e-b16c-2ca92454bb24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
c6d4b5e9-eebb-5fa9-b1aa-396063230086 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
ad2c82be-3274-568a-9220-e4117ab9c836 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
dff8c3b7-3752-58ec-9888-4094e9ec8c56 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
fa43bac6-aafb-5fa9-9d77-3e317fec8fc8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
c75e7cb5-0a17-53fa-8c5e-a91ff971b3a9 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
0e0189b8-6e4a-5bc5-88fd-ad123c39ce30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
2b3223e3-53fa-541a-8f7f-d40dc5ea6cc8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
0999f7fc-a21b-5c70-b36f-ccb01101f2b4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
86990bf3-68dc-58b5-8fee-b506cf95fc94 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
79efe134-8bb7-5863-b996-bec0507380b5 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
e8dc8ae4-e831-59cf-b58f-9416bbcf543c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
7155f372-cf09-5e71-9ff4-8847adcf8744 |  | work-in-progress |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
18c06946-3c26-5aaf-93a7-526e17ee7491 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
3211d53a-d7a9-5f75-9f44-eea97727b635 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
488bc090-ccb4-4b95-b829-f18e48b37689 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
5af982b7-5bf1-5cab-9065-1a593e24573e |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier B | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
7c018764-1552-4d51-8e4c-0cebe33eaf3e |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C
3c9c909a-65e3-4197-9296-c555839684b1 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D
890bfde0-1d92-5763-9637-7696f69418c5 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
4fddc3e6-2ace-58c2-a2b4-f085600614af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
ace4bfbc-6271-5c89-bbdf-5c83da1e3d83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
7c2b15f0-55a2-59a9-ae84-5378f3812a39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
254278de-a93b-517d-82b8-d5ef991bb47c |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
9e82f4a1-07c6-584e-a06b-0dcfe14e91d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
4a675ac1-4210-57a4-980c-8e9087b01213 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
d189b907-80c4-595f-96d2-b3ec54124119 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
c2c548d4-4a5e-5931-a950-de881caee3af |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
8ec48e21-7eb6-5cc5-a2aa-5cc2abd83952 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
4d3f6f06-1a63-5533-8f38-c1b5c39e592a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
89ad7ee2-883a-53f4-af32-4ecc2f72ce7f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
4f481c71-1ee1-5661-aacb-ab5e1dc841ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
3471a7a7-759e-5edc-ab55-c764279380c6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
096fd09b-f21e-55d8-a1ff-87aceb928fff |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
1f876a43-7ac1-5352-8b43-fbe3fc2f495d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
27da147a-8b81-5fad-8d2d-6c79a4f61ed3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
fcd140fa-c2cc-5c35-8212-c37fb2d06046 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
2affca77-753e-5d12-9a34-44be084fcee4 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
bc0588ab-e7d8-5413-9b69-629134acf95b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
46ee2c9e-b60e-567e-998a-694cb2d7701c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
89332874-8d3a-59d8-bdf9-b291d652891a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
2c90f41c-d18f-5148-a203-ea1d0fd5417a |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
70cd33d2-24de-5fa9-a89c-28422ad7f208 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
a93bf944-5fa9-582c-bbb6-353581a5d538 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
4c3d7d12-472d-510d-8708-4de2c3a571f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
ab22c444-51a5-5437-9dc3-61b916ca22b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
7d30a3b9-9728-5a11-8b80-a4c61d6e1b67 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
3878fe44-8840-5d3b-af2d-dada312bd6e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
9e8f7d10-eeed-52c6-9bfd-a2af822551ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
19e69816-b120-537e-82b4-30bb07dc2605 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
0ae5c45c-1f30-5b33-94f6-d3faeb493487 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
b2078a1c-3c8d-56bf-81e9-ba04a58ce6a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
678234a1-3a7f-594c-8921-370e2ed78a69 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
ab841a3c-f984-53b1-992d-4ddf60f469ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
e22c4de4-4328-5961-a499-80814006c8ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
d2bea17b-c9ca-55f5-9cf7-1458622be332 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
a3add573-d2cb-5d66-b342-f3e6b0b962cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
6b07c9b0-9a13-5813-b0ba-119c3a027fc5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
61f0c583-c0ea-545a-baa5-85e7777c8a49 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
0a245a86-8bed-58a5-bd7b-900437de8ee8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
1acdf8e6-a04c-5594-b27c-148826a0bc0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
78200c8a-104a-53f7-9bcc-8ffeeb89680a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
1e0ae6b6-b119-5501-b347-05031507defd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
4213032e-7554-5f0c-881d-c8b855203697 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
a9613a63-a62c-5967-8e2d-d62ab48fc235 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
0b0ed84a-f513-5a10-b66e-f88f5a9269e7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
e1724937-e9f7-577e-81ef-46511c48fc03 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
a01f54ea-c409-52ab-b7c2-045d5d2ab2af |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
733219ff-1370-538a-b473-bd15fb6eb509 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
c09cbc09-83f7-5be0-8251-d8ecb948ff84 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
186edc8f-ed25-5547-8dff-504e2ff547f2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
09c048fa-9af8-5a48-ab8c-266fa2bb6574 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
97747e04-724d-5ba4-9efa-0e698b1c7a5b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
716fbc28-8ff6-458f-9cbd-1771236498dc |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
4992c869-33ad-5838-8c1d-a6b3d2ab1a91 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Pier Crossheads Downstand | MGB Pier C | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
7f559bf3-9ecb-4209-afd6-420f739f15c3 |  | fail |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams
bc4249c5-6ab4-4c72-b9d7-ab07e2381d76 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection
1ed2af6f-b7fb-4b04-a85a-f29a397b520f |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D
02c8fd5e-2262-4981-88c0-a7778d78b35b |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection
ce5ea53c-7b39-5958-8d4d-7e4932e33afb |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Preliminary
47d0e74a-0c77-5649-8b59-8f00efc1a614 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Preliminary | Engineer notified of pour
785bc066-6ceb-5475-998c-73cc10fd6435 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork
0466455f-d7bc-508e-b8fd-0cb37e608eca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Installed as per formwork design
ce6dc5a5-d023-5f3c-9e11-748ab43a64df |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Permit to load issued
44b72f12-b00c-5f56-836f-72e593a2b2c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Dimensions correct
3f9ab82e-63e7-566a-a57a-de52bce20ab8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Position and orientation correct
1451888a-1e21-5e95-ad88-dbef1161a541 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
77c780ee-7fcf-5d78-940f-dcf3c4b418af |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Forms coated with release agent
127fcbc8-ab76-5245-a9ce-a185d8c4232e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Forms clean and clear of debris
9ea353d3-bfad-5ddd-b54e-4d1fd0f059d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Joints sealed
dbd2fe8d-15fb-56a9-b4c6-4f4db953ad76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Formwork | Pour level marks
6ebd47a4-86eb-5ebd-afb7-67976355ea86 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement
1656325b-69e2-5d4b-a3e0-94fd76c43fdf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
9fe1a742-31d8-53a3-8cb9-9fa4ac35076d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Correct bar size
637a0447-bc23-5cdc-9188-d9b147e465a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Correct number of bars
5a48d2db-6440-54f3-bde8-2c08e956b5e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Correct spacing
6bbd58f4-45d0-55cc-b310-db1f3aa541da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Starters bars included
7cfdd534-2c28-5d9f-963e-8864db73e664 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
502f94fd-33d3-5c3d-9bb8-191cfce78955 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
f33fa1f1-5992-526b-8881-5caa5acaeca5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
cf535684-3c91-5ce5-b11c-50b9959bd488 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
5910f1f3-e872-58d8-bbaf-4e00dc17617d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
0b2abb87-ee06-5c7a-816a-df901a373095 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
f9f8f1f9-2545-56ab-80c7-73f31c975462 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
d3f08dfb-9f0d-5f90-96c6-f99d607e9faa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
89df1657-5aec-5c46-8ede-4be51d0dfcbb |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Embedded items
e46c5be4-6fe4-5055-bf3a-1a93eb82a6d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
88233a8f-9773-5d07-a4af-6c679a6e2539 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Embedded items | Correct position, level & alignment
514e8952-79ae-5aa8-bf29-711750f02802 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Embedded items | Securely fixed in place
53a19723-4230-52ca-ba18-2543d7bb63fd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Construction Joints
9f675915-54f6-59f9-b0f3-36a3e8955c67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Construction Joints | Correct location
aaae2fbc-9b65-57be-ba9a-5384b8dd98e7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Construction Joints | Adequately prepped
b6abb33e-2f8b-580d-beed-7ab2efb7eed0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C1 Pre-pour Inspection | Construction Joints | Joint board installed
a953c696-3b3a-4470-b7cc-c33b8f4208f3 |  | work-in-progress | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection
42371282-5d01-5d3f-8886-f8abb3f491d2 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Preliminary
7df95628-9df6-51b3-974e-8d5233c5d906 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Preliminary | Engineer notified of pour
771b5b00-ba85-53a2-b1f3-365e66f927f8 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork
e930ceb5-53e8-5b77-bf34-8b864ea162a2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Installed as per formwork design
20f1d661-54a1-5b55-8f2f-3c77b8d9f74e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Permit to load issued
f6c6c3ec-cd7c-53c6-9942-0b30ab5ca1f0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Dimensions correct
924adf8f-bebb-599d-bea9-423dd17ff274 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Position and orientation correct
6f29707f-e24e-551e-a75f-894f94986ea2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
5d841924-5050-518d-83c3-62accd0f9fe9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Forms coated with release agent
e44b152f-c833-50b2-bc57-22ad63511794 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Forms clean and clear of debris
35a0ac6d-a3e2-5af9-b1f6-538921814f55 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Joints sealed
c194a34e-a087-5508-a22f-d945ac4e31d9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Formwork | Pour level marks
a05922a5-343e-565f-8dd9-10f890121f39 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement
057692a2-1e64-5183-a39b-2390b5a61380 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
265c625b-9650-50c4-894c-b9c7ac7ca8cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Correct bar size
5000dbff-fb5c-57ca-8f7e-5a6abaca38a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Correct number of bars
e7801cbd-c7ec-5e9e-a446-19904fd56a55 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Correct spacing
0983ed64-186a-5f27-add0-fd852b262748 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Starters bars included
d49af230-3e0e-5189-a9c5-ba99c79d1a24 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
1ba2680a-e69a-5c5c-a5fc-8edc2927ce14 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
488f4389-646d-5dee-a5e2-c8b04e8b8358 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
fa761a67-58d4-5f73-92c3-dfc89989b04a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
efc46faa-2c4e-5943-92f8-deadbf226ed9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
a09e8003-27bc-5350-88ca-6e3972c6c76b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
2b68501a-f6f4-5995-a5af-b00a85a8da73 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
ce29d095-c41b-5cf5-b673-63d52ad32f04 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
296b6627-e7b7-5547-a43d-ea77816a3404 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Embedded items
db4ea6f8-fd4f-5020-a647-8484364535a8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
44d20289-d261-55d7-ad82-5f9a255175aa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Embedded items | Correct position, level & alignment
bc5445a8-efb8-5311-b2ae-55b522ae0cf0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Embedded items | Securely fixed in place
a727cddb-d88c-5bae-886b-612fcfff2325 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Construction Joints
860e780e-2a9b-57bf-92ec-656869a16f34 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Construction Joints | Correct location
8ebc8450-a5c3-53a8-87ac-f591d513639c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Construction Joints | Adequately prepped
fc781c43-0055-541a-8d95-2adbaf3114c7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C2 Pre-pour Inspection | Construction Joints | Joint board installed
736e7130-8c7d-44fb-9983-cc0f5a7440d1 |  | work-in-progress | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection
eca9aa36-0a8a-5557-94ea-611d91301498 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Preliminary
37233f0f-55a1-5a2f-85b5-bee3aa527abf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Preliminary | Engineer notified of pour
b997b6ae-aa12-5f31-afcd-4471113a4058 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork
d49f2ce1-4e56-57c4-a9af-f9e49dbe325f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Installed as per formwork design
bc47febb-fa00-577e-a077-0e8fb91cb0da |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Permit to load issued
bf06bc0a-9187-58d7-bf76-5ea316e9c8aa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Dimensions correct
1c9838ac-85c3-5c74-bb5b-e120f431e3d4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Position and orientation correct
9857d48a-8c28-5c6d-8d35-d0db992dbb4f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
f11cd678-d063-5464-bc7c-cc6844515c87 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Forms coated with release agent
fafb8e1e-610e-542b-bcf9-40c83a427936 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Forms clean and clear of debris
6792daca-98e1-56ee-9e12-c43c714c0233 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Joints sealed
ddb94497-7436-50af-94ee-6d72276c1525 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Formwork | Pour level marks
3024e106-58e2-587f-9ff5-fd087563de61 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement
5396023b-9e24-51ab-ad2b-1bff3a0ced99 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
d6644686-a426-5c08-9729-9e0d96510a9f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Correct bar size
719e04ad-e8c1-588f-89db-515a09431e07 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Correct number of bars
0f5724cf-2d35-5eca-bb21-fbd26832bf4e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Correct spacing
c65b66cd-4570-5080-8367-9391da783ccd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Starters bars included
09dddba0-2d31-59c2-8e9e-27365a508fce |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
bc7c5382-80e3-5404-8cfb-e891e8f9df71 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
a1660b2b-5630-5610-aec5-39bba3f49841 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
66a23828-0090-5501-a6b1-97376ea07e86 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
d0263bef-5b7a-5f75-b255-841901490ddb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
d8a04a12-6ffc-585e-8609-8a1f557855eb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
1b4a2dd6-d904-52fd-bc24-798e69800ba5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
6fdc7932-787e-5c15-ba30-4b3ca04214a2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
f28a456e-3f24-5827-9cee-0605a3d000e7 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Embedded items
e8438a7e-d690-5e48-9d25-4323338e5b8e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
69dca62d-4ab8-51a5-9097-05ecae574e7c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Embedded items | Correct position, level & alignment
cf7c04d2-db64-5739-b598-537e23bb0ba8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Embedded items | Securely fixed in place
64dfe8c8-09ca-517c-841e-9f19a5a3dd57 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Construction Joints
81c0a143-465d-5b0d-8652-def1a7b33bb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Construction Joints | Correct location
750da8a6-18ef-5b4f-acfe-0d6c14b6ad68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Construction Joints | Adequately prepped
5b69b722-33b8-540d-ab4f-6051f1d5b418 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C3 Pre-pour Inspection | Construction Joints | Joint board installed
71610052-346e-40b1-930a-5db339ec3f43 |  | not-started | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection
189bf4c4-a050-51b0-9ebb-2aa4331df549 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Preliminary
c7a91f5d-1569-5c4f-81bc-ca502a8477b1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Preliminary | Engineer notified of pour
d230f282-ae75-53fd-899c-a354c881e163 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork
dcc1407f-f3d2-500d-bba4-de8be5856b68 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Installed as per formwork design
50aef73c-5838-5192-b801-4b1349d170e1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Permit to load issued
b31e9628-804c-5ef2-824e-573cc44221a8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Dimensions correct
898886f9-e331-5315-8738-151a47bff415 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Position and orientation correct
2e19d3a1-695a-5583-92d1-21000ec65db7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
c0d97537-b93e-543e-9db3-a242d8ea264d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Forms coated with release agent
ea97d3a9-6f6f-56f7-8463-ea756adab8a0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Forms clean and clear of debris
b961b20c-edd3-53e8-bc2b-fbe6338c8b3f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Joints sealed
e1cfc1bd-c4bd-5cf2-bf43-3bb4a7b8c77b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Formwork | Pour level marks
7835b2e1-490b-59d5-9988-f78f3f4dbb72 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement
195c077c-4d0b-506d-929e-269efa33695a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
15e2bad0-f723-5c8d-aca0-b06fd5987aea |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Correct bar size
302fde4c-3557-5947-9192-32dfedb5fb5c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Correct number of bars
4e0fd1d2-a0b0-5f29-b2cb-2854ee453d70 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Correct spacing
5c36fa15-b5b6-5971-baf7-9479869518ce |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Starters bars included
5910fc0c-d79e-5bf0-8688-8516b919266c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
ef9e7ff1-9a97-562d-8206-17fd12a1c219 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
377039a1-035c-57b4-a68d-ed49f7334f6d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
67c55b70-1f3c-51f6-a88f-c12232b708bf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
5749b9cc-9131-5161-abb1-f42912495dc4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
3cf9de57-95a3-5316-a68c-6d51c9a8b221 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
c224b997-899a-51cc-b225-87bf6fe8d0eb |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
cc2acb1c-a675-5358-8ca6-b4b4b253fc89 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
567e4a88-1b38-53e0-ba60-c9bdf2c1d8ee |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Embedded items
5edc3d8e-9913-52c5-95ac-41e15ec69555 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
00633dbf-ae67-557a-8ff2-54b05b1ab9f6 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Embedded items | Correct position, level & alignment
dbf8e852-d165-51d8-bc1d-0f21a5127267 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Embedded items | Securely fixed in place
56956588-d5c0-5bb1-84ab-ebb757e75538 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Construction Joints
4b85b069-c34f-587d-9291-d61ea8f67e07 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Construction Joints | Correct location
9e50aa78-0804-5d35-b430-077cbbf5994c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Construction Joints | Adequately prepped
e6258027-7e10-5458-95fb-912e259679ca |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C4 Pre-pour Inspection | Construction Joints | Joint board installed
e7c4e789-7f56-495d-8956-584cf0b12512 |  | work-in-progress | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection
6a28e011-e6e6-5197-a8a4-94ed0b2625d5 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Preliminary
e8cccf4f-fd88-5e02-aea1-e42a43c7af48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Preliminary | Engineer notified of pour
04926e55-4d3c-5212-a451-a776b1f98636 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork
e606af70-83a3-51d7-8437-f31807e3c74f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Installed as per formwork design
adda3376-9967-5d13-89c5-5586d0a7674a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Permit to load issued
e135a841-3f85-5e6c-afee-85f6484fa6e8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Dimensions correct
d7e6a211-c1d6-52b1-92d1-fdae77ccc0de |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Position and orientation correct
ed92a0d6-6c89-5bc9-b82d-5f6f522aa092 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
815a01b9-19d4-56cf-9188-dc306aa88c0a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Forms coated with release agent
62cbb136-95bd-5e44-90fb-fa43c17d2715 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Forms clean and clear of debris
9f6ea93c-12ea-5b1f-8772-907557939fef |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Joints sealed
3b010678-d16a-5a04-9f63-78c4edbc407e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Formwork | Pour level marks
b219ec4f-3cc2-5f46-ac79-cfcf4c7395d8 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement
b7d14bd2-2650-5129-b4c2-28e2c679dfd5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
e787d19e-0040-5a2b-8d79-2e04f0f580d4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Correct bar size
cc2b21fb-5eb3-55e3-9588-28dc827e8754 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Correct number of bars
0cf671eb-d21c-5f85-ae06-8d498366d5f8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Correct spacing
862a66cd-a28a-568c-b885-ab36224903c1 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Starters bars included
46659b27-064e-5ea9-b66e-498b0e890cb7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
a27bad9b-72b2-5e94-8778-cdba0c887af0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
3c06414d-b738-5ae8-a890-11fc77d8395c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
cb0b0321-35d9-51f6-885d-6f45019f58ed |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
7cfc5663-1c1a-5f2b-91c4-ae29b0e67731 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
ef292ff6-70e9-57d0-b6d4-8f4ad940a5db |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
18dcacf5-6124-5ae2-ab89-8f95f23debec |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
11a41da8-cb51-5f6c-9fab-55a61c77dbf0 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
be98fedd-a8ce-515e-a951-b794c73c7692 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Embedded items
6222795e-4672-5589-a931-dbd8968d6448 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
a5aa72ea-7984-53fa-b79d-6c9d8decc6b2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Embedded items | Correct position, level & alignment
f885bc59-b527-5230-941a-57347a9cb559 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Embedded items | Securely fixed in place
83184076-9280-5597-97e4-876fd188639a |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Construction Joints
76a6b03c-156f-5c24-94e3-185106148b6b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Construction Joints | Correct location
67947279-d656-5615-8299-c894e2742b59 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Construction Joints | Adequately prepped
35b56e4a-ed74-5918-bec3-7a3d904d2f5c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C5 Pre-pour Inspection | Construction Joints | Joint board installed
721581e6-768d-48cd-b688-0efcea697a86 |  | not-started | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection
85bd2c61-08dc-596d-8a14-950d829c271b |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Preliminary
db848923-ab2d-56cb-9194-2e8808b6a1ab |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Preliminary | Engineer notified of pour
fc6e9f94-57fa-5f82-ad4b-5cf8cc568102 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork
a9030c3d-14aa-59fb-967f-d51f453a9bee |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Installed as per formwork design
09fbcc31-1961-53fe-9926-4294ed573b9b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Permit to load issued
7dfdd9fb-c54d-5e4f-8a02-5651257dc318 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Dimensions correct
5a609910-a078-5823-b1c1-d2fb56bd61b8 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Position and orientation correct
5ef0ce31-fe83-5c41-b083-0e2924e3ab2b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
26bd4b80-2b7d-5691-a7a6-0d1bd25346be |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Forms coated with release agent
2708b810-bdad-5062-86f2-d722b5833d9f |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Forms clean and clear of debris
98499429-cb9c-5310-bd82-05e26494b417 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Joints sealed
d709ef9d-5b12-5bd8-9ec1-7c7952931b7c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Formwork | Pour level marks
8f9d106e-8379-5064-82de-aaffe30e8a37 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement
1ed3cb5f-8bd3-5bae-8ef5-94e2d2e0445c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
3905f5f4-8bfa-5039-9859-e985bcc1835e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Correct bar size
33459313-bb8d-5148-87a6-86b1533ccb2c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Correct number of bars
5b2fa5ea-f234-5e83-8caf-93913d834f8e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Correct spacing
894dc464-7aee-5c63-96fc-414a2115e965 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Starters bars included
54717358-2dfa-5595-bd22-0a9078366900 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
8960cbac-154b-5621-9bbf-4a8ed1e90c27 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
9a8f7cba-25b4-52b9-80a3-7793dc72a707 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
3fae2be4-32ab-5113-ac7c-66571fd87a62 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
85f1c15c-f0db-58ca-8c32-0ae2f45036a7 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
c0fd8b68-ccc4-54e6-b764-f82fb8fa5d0e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
78bb4e1d-7edb-5dd8-aff0-f915deb0f347 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
284ec94b-788f-5d75-90e2-d21646f76efa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
665925d6-2eb7-593e-ba93-e0e4a818f711 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Embedded items
7d91b97e-d7a2-53e0-8aa3-e059b07b2949 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
5a0c2f4f-f834-50c0-9d75-578d13ae9dcf |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Embedded items | Correct position, level & alignment
90d8aed6-4a7a-5073-b3d7-176dec875ca2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Embedded items | Securely fixed in place
770a5135-e5b7-59cb-926e-aef8293c1622 |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Construction Joints
7fb8da7f-1cbb-5390-9c43-9c9c1e1c9fe9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Construction Joints | Correct location
77593c80-51f1-5279-be08-7c7ad757bdfd |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Construction Joints | Adequately prepped
dc024f7e-763a-5190-a695-6a8c40a7905d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C6 Pre-pour Inspection | Construction Joints | Joint board installed
2e92f09f-d3d1-465a-ac77-e8b1236cef55 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection
4672999a-cee6-5664-aad3-36bc77474c76 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Preliminary
ca847eea-252d-5c7c-806c-7391626fda8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Preliminary | Engineer notified of pour
2feba62e-fed3-54e2-92df-9a13dc9de21c |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork
11eb71b6-0ffd-5a2c-bc4b-ecdd4acad01f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Installed as per formwork design
7acf5808-dcaf-5c24-84ad-55f43d69189e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Permit to load issued
0b9a9bbe-b704-52e4-affe-7a1251b52232 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Dimensions correct
8bde7c64-8590-5036-82de-23ad5dc56252 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Position and orientation correct
08ce27de-a76b-5168-984c-95d43bc0c023 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
0bdd4094-7194-5add-b7bc-2b3582741c84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Forms coated with release agent
680e03cc-fe1b-5bf3-bb8d-47428d25c707 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Forms clean and clear of debris
0ca7b283-ad3b-51e2-8ddb-7a02c33ce32b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Joints sealed
47030822-3e50-5615-b8b6-6f1cb9cb0a8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Formwork | Pour level marks
bb69672d-686f-5723-a8ad-ecbb0f4e7f2c |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement
26ce0f07-ecde-5cb6-bfe2-af7b776f3e33 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
c5c96337-e2e8-58ae-9a87-3176a856b25f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Correct bar size
3556d4b9-0d11-5390-a719-e35969986e78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Correct number of bars
9d3e9c22-817c-590a-824c-d545cace1a8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Correct spacing
ee42673b-2ce1-595c-8f1d-c3d4de64f6b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Starters bars included
bb1a012e-49c6-5b56-96a5-702f9f2c8a00 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
4779b2dc-9a82-582c-bd75-3e3cf330898f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
4d40d048-949a-5b2b-8031-312fd6e2755c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
e02c01ed-51da-509a-a1b1-124af0fb2022 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
9669d3a8-4b89-54e8-91b0-474407c5ac38 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
e9771e7e-c546-5618-90e5-95ad8b556c0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
88c36eda-9943-52bd-9f1f-5bf8d9c5f12a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
d93f2a1e-c7b2-5409-b98a-5b7fa6806750 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
a8ced9dc-cac0-5864-aa14-7c730ea2ba39 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Embedded items
03d345ea-6cc6-5977-8d5d-cac2768dd600 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
cb7c80cc-32a4-5b5d-a9ec-c3a1d2a323fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Embedded items | Correct position, level & alignment
59c9376e-ba51-5f19-86b8-8e1fd1b7aa46 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Embedded items | Securely fixed in place
b1cfd34b-9104-5b68-adac-20668545b608 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Construction Joints
4599ffd1-3f6c-5616-ad8b-0c8c985f5c32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Construction Joints | Correct location
cb89a908-3c73-54ec-a962-1abbb08ff52f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Construction Joints | Adequately prepped
dc937e20-5be3-5aa9-9d31-1ca9ceb4778a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C7 Pre-pour Inspection | Construction Joints | Joint board installed
b07fa6b1-0c5a-4340-b36b-e2945d15fa63 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection
dd065d6e-24e3-58f9-9545-a9d1b92dd084 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Preliminary
539ecbc0-e38d-5d3b-8880-688c9164e688 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Preliminary | Engineer notified of pour
dc5380fd-8d19-5e71-9a0a-bd4979592ce4 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork
87d9cbfe-98c8-567e-8a5b-b753f0842417 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Installed as per formwork design
65dcf10f-2654-5a18-b5d8-b38364bd560d |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Permit to load issued
da9c82be-7bb7-588c-899c-934645b1b0a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Dimensions correct
942ebee8-249d-5875-b323-36e7ec55819b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Position and orientation correct
b602cf7c-b815-5bec-bbf0-84f9452146ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
b404e74d-3e0c-5011-9170-9a484ec5523d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Forms coated with release agent
fc162e87-c7b7-5e94-9b1d-e3789450df62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Forms clean and clear of debris
6fec82b1-aff0-5ef2-9ff7-b928861deed1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Joints sealed
e7f5d944-b0b0-5b10-bfb9-07d5fb3adef3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Formwork | Pour level marks
d2c7eae0-82e4-5ed0-b4b3-d57fff02eabd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement
130fc4e8-78ef-59d4-98c2-7bb9db59120f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
d15fef93-c9f6-52af-befa-026136112b10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Correct bar size
6c2994d8-7e05-5d4f-8005-81635c70d2fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Correct number of bars
9272a0a0-1a42-5f9e-ac9d-7e6eec8ff11f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Correct spacing
a07b8a03-1be3-5f38-be73-cfe3e6c35975 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Starters bars included
09ee3356-ccf3-5133-9c13-7c6796ba3c9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
c46332b6-326c-5d9d-b2a0-0dec7a922113 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
260e90c2-2ea4-5098-8d21-e61786330f8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
dcacbbf6-76e0-58e1-9c5c-062281fb70ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
49618da0-4951-5504-86d8-cef3501f6472 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
c285f2ed-6534-5d97-bb3c-7946822056d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
a0acf489-8d51-53dd-a7cc-c4e1cb5d7834 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
a160c831-9d11-5a40-9fa0-e35a218961c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
11d60514-e7f6-52de-ae03-1cbc1d5a9a93 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Embedded items
0e48472a-785c-57d5-b905-cd3391785032 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
6188fb70-555f-5cde-8b5c-71fb13141768 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Embedded items | Correct position, level & alignment
e3845174-0645-59f5-adcc-c753780bd09a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Embedded items | Securely fixed in place
dc77b573-f62e-556d-aa00-99be74985bd1 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Construction Joints
9076c0fe-b08d-55d2-9a3d-e5a6002c95a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Construction Joints | Correct location
b7d7c3e2-41a9-5e3c-8d94-490454a11468 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Construction Joints | Adequately prepped
f2f9e2ab-9432-5266-a96d-16f20458bdec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C8 Pre-pour Inspection | Construction Joints | Joint board installed
53d98970-c525-41b7-aa1d-d45d071e8462 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection
6586f30c-1a58-5c0b-9ed3-d139a95e6e48 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Preliminary
d49562a9-6aec-51ae-b46d-679865844092 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Preliminary | Engineer notified of pour
23369875-ef83-55b4-bf95-95e4c4fdec39 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork
1a8e02d0-06c7-5a8e-8ded-5e5db60b2c79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Installed as per formwork design
7e79ccc2-5696-5f69-8f47-1a290d6b7fc1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Permit to load issued
7ee518f1-6144-570b-84f9-479351564ccb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Dimensions correct
493b60b2-74a8-5992-abf0-bbbbd9f0fbf5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Position and orientation correct
8c739aa8-1e74-5973-a9f4-876dc0ad91e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
9abef2e5-5c9e-5fd0-8539-7455e5c7a907 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Forms coated with release agent
3c46915b-b127-5723-a5a7-c046e96eb0b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Forms clean and clear of debris
cf93e5aa-1028-5776-a638-1bbe5be0b528 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Joints sealed
9ca256b9-4cde-57c8-966b-63e43cbf55e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Formwork | Pour level marks
81c0da4a-f22d-5110-9e57-c144d746c314 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement
d7ad8b99-4846-5108-bdf9-3f61aa25df3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
d31b2b31-4170-5057-9ee4-cb47ddace176 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Correct bar size
d1e2803c-40b1-5d3d-b4c6-4093235c25b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Correct number of bars
1267b1a8-ba19-5912-b877-a8687a3632c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Correct spacing
cdd6bd1e-59eb-592d-b358-7d2164db6f42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Starters bars included
f9dbe424-86d5-5350-a90b-186ea392b3be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
de758236-fe41-5d0b-a628-8e8a2f702b1c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
e99f97a7-0446-5ae5-ae7d-73016cc3680f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
d32c4bb5-82dd-5096-8ae0-d93d9b25d09a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
4fc01fec-d59a-5edc-97f3-a0e63480249a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
6fadebe4-1476-5c64-b660-2c84c82b1c09 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
f8bf85b6-05aa-591a-8912-a262d0ca4f2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
c3c4e425-e45e-5863-a59d-7c2ddeb79a2f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
981a8489-a5c0-5ac2-aa4a-0685c806e239 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Embedded items
03cf0e77-9f87-59a3-a6a7-9b4e7afb061c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
77f2be72-a0c1-57b0-8182-5ff273931409 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Embedded items | Correct position, level & alignment
6d2e48fc-7cc1-5018-ab70-3561e589fcea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Embedded items | Securely fixed in place
3845a25f-339f-54f7-ad8d-9e3ad379e5d2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Construction Joints
02156c85-4c89-5656-b7c9-46dd0f052ac3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Construction Joints | Correct location
c790f605-c6aa-528b-84c7-990b6a2ab631 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Construction Joints | Adequately prepped
1b4e6709-6eea-50ec-9fa5-2bfaffb2ff78 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span C-D | Beam C9 Pre-pour Inspection | Construction Joints | Joint board installed
3e8e0aff-6e67-4880-8eab-608f85b4de84 |  | pass |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C
ad7a9967-5b09-4b9e-a0cf-563086f323d9 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection
b996f902-05d2-5a79-8794-eb4f564949c8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Preliminary
07571f1f-0560-54f9-9ad6-ce2b2f6a2004 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Preliminary | Engineer notified of pour
3a3ad27f-bc03-5f47-b7c9-740a6763d3b7 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork
51a8e1b9-a028-5410-92e7-d2cc45c213de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Installed as per formwork design
089c65f6-dcd5-5f88-aedf-c26d07690dad |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Permit to load issued
b0cd00cf-6033-5e2e-9c4d-f09b7ee1977d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Dimensions correct
0f374ab6-8b35-5774-8404-9b5e37f9a40b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Position and orientation correct
74fc4f01-ecd1-5e4d-a5f1-0156bde35eee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
c7d1535d-a4ec-51dc-afa9-e7e4a9a2260f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Forms coated with release agent
c70bd0bc-b511-5dd3-bfbc-8c659bbd4d59 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Forms clean and clear of debris
4e80b559-18b7-53ca-b80d-c1087ff933e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Joints sealed
4b65e4da-2dd0-53b1-a6f8-897a9fd4874c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Formwork | Pour level marks
50448e9f-08c9-58b5-af3b-d52c104b1aea |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement
1e61999f-4665-5058-acfd-6cef6389ea7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
079bcd92-799d-5e6f-81f3-dd3b5ef72bfd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Correct bar size
65e4e377-6b71-5b12-8f09-1a0c80c89393 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Correct number of bars
0935adda-7995-5b7b-a298-a843650ddbbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Correct spacing
4b06f69f-43d3-5737-808e-75cad08d56b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Starters bars included
543eadba-3dc7-5502-9365-bab3c61f0aa4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
30e74be0-417e-52c4-bfd5-ae4f507a1feb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
6dd9b657-c90f-5a81-85b4-5f5ebd22b974 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
9523bbb6-ee59-5f4d-bb24-6d84eb9a4744 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
c099fe7e-e2b3-5abb-a2a9-4e3c49100a90 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
fc1e0cb1-9bd3-5992-b668-1ec2c854b359 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
67d93ade-1319-5b4e-a784-a7c5f0f1e4c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
166a06f4-4524-56dd-b819-02751ca68d74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
00d1a0b1-8b49-589d-93ba-53740ef55492 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Embedded items
ded0bd92-1566-594a-8f6a-d7b1ace2f8be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
5c30ebdd-cfcc-5358-b851-b1a16e687bb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Embedded items | Correct position, level & alignment
005c7160-74a3-5415-80a4-6ed0fa645b60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Embedded items | Securely fixed in place
364ee82f-acdc-5f81-82b2-d13a82fe6793 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Construction Joints
0b7257ab-2f34-5ac4-8ff1-132eb67c9344 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Construction Joints | Correct location
aaeb42dd-e8e6-5a22-b85e-37b418fcae87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Construction Joints | Adequately prepped
03d9aa1a-102c-54d9-a843-1ddcd600310d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B1 Pre-pour Inspection | Construction Joints | Joint board installed
3e501319-8cdc-4d57-8120-5d6fb3cfda81 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection
a8705052-a8ca-599a-beff-7d61af85d4e1 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Preliminary
3fc5f944-cff1-5065-bc6c-30f8fbade4e0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Preliminary | Engineer notified of pour
91f4bed5-b47f-5f4d-a091-44c5dd5860dd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork
10ac7442-da13-5a03-895b-41d92dfe1a4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Installed as per formwork design
2cee5867-e3f0-5304-a5d1-8281e6f215fb |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Permit to load issued
766fb318-a1ab-5762-9d01-32502ca34e67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Dimensions correct
6dc757dd-d91c-51a1-940a-267e60696fb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Position and orientation correct
4acbdbb1-c612-5092-b4d0-8bb5ee9606ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
ac68f3e9-0d07-5378-9651-0cccb7a4451e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Forms coated with release agent
99b0990a-7564-5777-a80a-fbd1a88e3f7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Forms clean and clear of debris
64ca5786-acc7-5dc7-9f27-6d3a46f4d217 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Joints sealed
c9452191-c1d2-52e2-b037-588e4a7f5934 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Formwork | Pour level marks
19c2fb59-5bf3-5cc7-9b49-2c83fd9a9fe3 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement
35ecf0b2-5ec3-5706-ad00-88401b623b4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
45038263-e880-5356-8569-c0230cf7c5ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Correct bar size
1053eaf0-b0c6-5c27-8ac9-b22aca1ee63d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Correct number of bars
312962c9-aa4a-5811-afcb-24d94f5db4a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Correct spacing
9c2839c7-ffe6-5be5-8d4e-d852f18c31cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Starters bars included
6e477983-dfd3-5851-8a33-bdaad35c69f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
9192050f-f0c3-5788-99d4-27f884aa7466 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
94640769-e23a-5403-9456-929528677603 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
4102310d-1fef-5c63-ae47-64c89cd5a1c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
63bfebc3-48c5-5d70-a3f1-553a5f457078 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
8b2ef7eb-ed16-519c-8a9c-359200dc9f27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
d20a1a49-09f9-54fe-8c59-ac6ca62f4fb7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
31b20eaa-b78d-5d90-81a8-b5f32f7f58aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
11682d5c-add6-5634-a27d-97acbc269741 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Embedded items
e276179e-8e10-5117-a005-ad6065a0f92e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
99deac2a-2874-576c-95cf-4aa328840f0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Embedded items | Correct position, level & alignment
a54716c4-6bb6-55a7-9f07-72c0bd8b7af3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Embedded items | Securely fixed in place
36971b57-cc6d-562f-b1fd-29332cef4fc8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Construction Joints
216c3093-cc05-5b44-a70f-87b03473d1f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Construction Joints | Correct location
8f055cc8-cae1-5b51-a22a-cd3dd9a5bd0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Construction Joints | Adequately prepped
fb0cb32a-6f67-53b6-b62d-f907dd5c3a64 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B2 Pre-pour Inspection | Construction Joints | Joint board installed
ef92e6ec-aa36-4c65-bf2d-c361af1f0ea9 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection
cf1901b2-e47e-52c6-bf00-4823ae32af4a |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Preliminary
da929560-7a3b-5193-a96f-06c738fb2979 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Preliminary | Engineer notified of pour
9337fb41-a980-5377-8cfb-1940c21bebd0 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork
dac19b8d-ca0d-5ec3-a3db-5b550eb228ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Installed as per formwork design
18c76f5b-16dd-58a2-8cad-31e76a873148 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Permit to load issued
33631ade-2acf-5cdd-802b-4b1b8bc8254e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Dimensions correct
85a8a2dd-de29-5ce2-8802-900df58a5a97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Position and orientation correct
e056478f-73e6-5b75-925c-0c7a681fe253 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
c5ae722c-29a9-5685-b0f2-f8b965e8fbf7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Forms coated with release agent
8edb4fd4-b3da-5413-b43f-712f3aa88c9c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Forms clean and clear of debris
de6088c9-c012-5fa9-8243-e4ab02a5d699 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Joints sealed
85e1b540-3409-534d-b57f-f87a55aee49c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Formwork | Pour level marks
bd8cde1c-fd2a-5682-bcdd-ae1ac5e2bcc3 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement
bc3cb84f-81cd-57c2-a07a-6c74e999869d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
7a40bed4-38e2-55d6-a5e4-a4f8c047c4ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Correct bar size
b4be529b-0bbe-5823-9c0d-e2570f5daa0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Correct number of bars
32901228-cdde-5fa9-a6bb-268a387f3a8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Correct spacing
180105af-13ad-52d7-b848-0827f743238b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Starters bars included
b5e68d0f-1f4e-5f05-9d0a-dacb14d61e84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
61a5e05e-9847-5d8f-861d-d3860206202c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
e334aa2d-c80c-5e44-80f6-0a070acca130 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
e87a55d7-27c6-59e2-afc8-a57aa5bd9d75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
ab264ff0-61d1-57fb-bbbc-cda9fa68fc19 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
bc3cb42a-01f5-5560-93d1-6dc3978b88ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
0f004420-abfc-5109-b32b-562d4a388cc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
64bd95f9-f7e1-5ab1-a1c9-cf5031606eba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
23af45a2-fec0-58b5-8bc3-295d3abddfdc |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Embedded items
f8e26bf6-8d4a-54b9-b003-f9887fae251b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
81499088-9a50-5701-a0aa-b883eaae4283 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Embedded items | Correct position, level & alignment
0a1c50d0-9978-51cf-8e63-cfd554bfe33b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Embedded items | Securely fixed in place
74db440f-2114-5e4c-85ab-6ee3399a7029 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Construction Joints
152449ad-b10e-587c-b7a2-2afb3a5a8aee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Construction Joints | Correct location
2c3a0e29-de6c-5b44-8a3e-66ad45ede8bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Construction Joints | Adequately prepped
80f9231f-aae1-54a3-9e0b-22f45b06ad1c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B3 Pre-pour Inspection | Construction Joints | Joint board installed
405f614e-8cae-4f2e-94c3-5080f64d31fa |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection
746ba8d4-bcee-51a7-86cc-c070897a8926 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Preliminary
5df388d1-40da-5267-b8ad-06dbaf57bedf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Preliminary | Engineer notified of pour
cff91a9f-4b25-588c-a4b9-8fe7b5b78aa2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork
5e79a6d3-3765-527f-8311-22102db1dba7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Installed as per formwork design
36010d5c-d779-5be3-9c54-8e3dad12f115 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Permit to load issued
70573a65-0f76-5534-898b-e51d3dd69d84 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Dimensions correct
e3028575-eca1-5613-8f47-330ae627b5e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Position and orientation correct
9838f9a7-f1fa-591a-b071-d086f3a8cdb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
433a7df4-1305-5c98-bfc5-53d6d918539b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Forms coated with release agent
fe2a4856-d2f8-5903-8268-852902cf779a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Forms clean and clear of debris
82b016b8-396f-52b1-a62e-dddd098974cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Joints sealed
50f9f4ab-fcd0-5659-929a-4b096d1f63e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Formwork | Pour level marks
cd9639b1-0f03-5e06-abfc-f12171af35ad |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement
7ef046c7-58fe-53b4-bd6f-10ff112e522f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
ff7639be-abff-54ed-993a-213279dee8b7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Correct bar size
90fa2236-8fd1-543e-a0ef-bcffa933deb0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Correct number of bars
79dd7934-4208-5469-9afc-dfdab41b706b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Correct spacing
837f4a6b-43a7-59cb-9574-778b710bc0a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Starters bars included
6b89b426-0dae-5f36-b38e-9b43968aafd0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
2d77b6c0-cc46-5627-aedc-dca7ed35cdad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
e241ffe0-e452-52ed-819f-0648034989b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
8f38cb27-fb8c-5c44-adb2-ea4635fd1fec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
448a5228-9764-5b8c-b9b8-5298b68cef74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
2e7c2730-078f-538e-bfc4-f9807866f05a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
19cf22b3-e8bc-5bf6-ba5d-fd8848905117 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
30344643-a131-5fb1-bbb3-cc29d3523af8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
0b33cd45-8cb5-50f1-936f-90ccdfdf796e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Embedded items
15720f7d-8b16-58ca-90f1-f444a4d0e387 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
050aeb8e-71aa-52b4-a931-771e911d107c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Embedded items | Correct position, level & alignment
323c26a1-cc05-5bb6-a0f0-4d8ad66896d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Embedded items | Securely fixed in place
dcf4f625-2ac5-518d-b7be-d6509742533d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Construction Joints
a0c6b90b-5c2c-51a3-946f-17303ce38981 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Construction Joints | Correct location
a9bc952a-66d3-54ae-a912-d306a04f51d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Construction Joints | Adequately prepped
c24a7e3d-0843-5ef3-84ea-a7f2aa93144a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B4 Pre-pour Inspection | Construction Joints | Joint board installed
0d4d6a70-3806-438b-9d44-e248e157382c |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection
38d5b69f-a7f5-506c-bb9f-0e65d8e79e7e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Preliminary
b5890fe8-2c67-5c54-b78c-817ed20ca2fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Preliminary | Engineer notified of pour
e4603a5d-65fc-5f65-b1b4-f8b25f98292b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork
73f1b1c1-db1e-5d64-be22-df9fef3c8844 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Installed as per formwork design
d01d0036-d51d-5e09-81c0-1d2620075d30 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Permit to load issued
3bcdd644-80c4-51af-a48e-77f6469b0e5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Dimensions correct
43e361a6-bced-5419-a15c-6e30d2d3a59b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Position and orientation correct
17fb4953-a9dc-5c92-9cda-7595dac877a1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
206d2e6a-f014-552e-a960-1c629b11b509 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Forms coated with release agent
7c04406c-a634-51d7-a7ea-92b11b70346a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Forms clean and clear of debris
b3bb8a7a-11e6-52c3-b3a1-0af3834c68bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Joints sealed
7cc407c7-cec1-5c4c-a542-ad3df91edd6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Formwork | Pour level marks
48d3cd50-4fac-5437-a18b-70908eabf6c2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement
07884af6-ed0c-5a60-a7ac-0525c17203e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
737b6bb4-6014-5bf0-b7a3-a4afa2519b9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Correct bar size
1706ec91-0ab0-5c16-9429-f300f71d8900 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Correct number of bars
665eaa20-71cf-5f46-b17f-044ba7f70696 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Correct spacing
3c8ac8d8-cf81-52b6-86ed-2d93cc59867d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Starters bars included
ddb7908a-54e2-5948-9585-d7908273d14e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
dce783eb-1815-5729-980f-8935e0ba874a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
819436e1-8cb3-56ee-a218-ab7b7db0a96e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
8b1fa335-85f1-53cc-a209-9652e19dbf2c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
96d8974e-9352-58ef-92bb-f4bcbff84ac3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
e2cf2389-d202-5c36-808d-a275e1b3659a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
3e697781-6f56-51cc-9502-45806475d711 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
b46bffd6-1a20-5fb2-89e4-3a58a6b2305d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
3c9ff891-5bd9-5abb-9b32-f1cce1663f19 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Embedded items
1b7799cc-c395-52c3-a7c9-5a2709a67b89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
60b4847a-bdee-583f-97a7-20b1aec1cbb8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Embedded items | Correct position, level & alignment
11440cb8-1ba7-5a62-b345-6c0570657e34 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Embedded items | Securely fixed in place
c1402322-7c38-5594-9651-dc5452b927bd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Construction Joints
89c87181-f16e-5642-994e-16f61953a38b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Construction Joints | Correct location
68b84fff-b5e9-5388-b2b7-6c4577241fb8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Construction Joints | Adequately prepped
192f7b48-6754-5fd6-bf05-19c5393f08d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B5 Pre-pour Inspection | Construction Joints | Joint board installed
97a7e027-9892-48f4-a7cf-dc0b6cf0adb6 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection
66675aae-cbc7-547f-bcc3-8ea5016e0e41 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Preliminary
9e95f71f-975e-5aee-8ffa-d86ebeaff549 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Preliminary | Engineer notified of pour
383f4e9a-2794-5427-a811-e9ba521e8b8d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork
e9905a63-6927-5a25-9be1-e87836702dde |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Installed as per formwork design
0a79715b-339d-592b-87ef-713004ac4ac1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Permit to load issued
6000da2f-59a3-5cfd-92b1-5017876ebff3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Dimensions correct
cc395285-04bb-58d0-a0ab-60d5f142b930 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Position and orientation correct
eac36901-d91a-52c0-81b3-63920a89f760 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
15dc184a-aed0-59e0-90d8-f3867a37b4cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Forms coated with release agent
85e32163-65f7-5edd-bebb-9efc34a6c827 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Forms clean and clear of debris
afe73575-b9f1-5c18-a2e9-eefb09384956 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Joints sealed
f8d41751-0f39-5432-bdd9-d051d788c6cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Formwork | Pour level marks
2a377d5f-c92c-563b-befb-5d2aa24e0f60 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement
baf37cb7-5478-5a91-a91f-ca9401eff416 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
e5f4c3ab-65e0-5fd1-a554-983177cb7171 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Correct bar size
dae08700-038c-5246-a8d5-d07e00f10ea9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Correct number of bars
af2de6f4-0415-5948-a087-982255077fc9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Correct spacing
67ab73f5-3a6e-53d8-8d35-e649ab96d81d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Starters bars included
39b05aae-85ec-5669-9e99-d8b18f360ac6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
a11a4135-d767-5dc8-b121-c2e7d4e18aad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
1dc5d622-97ec-55a6-b4dc-5b5ea1c07a85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
81f5af24-b150-50c1-b464-cccc2e21f28a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
282c120e-d34b-5893-a33d-71da2446c691 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
3aab1c2c-e9dc-50c6-95de-5c8c10a50d9e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
8b2d6cc9-e380-583b-89ae-11831b18bdb0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
74225f1b-d777-5b3d-8ec0-d8bd5f935dd0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
b26fccd8-491b-5923-b038-c85b03d8b7c6 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Embedded items
1605cf17-7974-5342-89ea-96d5e9373ded |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
d6af3d80-2930-51aa-b3f9-6c49e635e88f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Embedded items | Correct position, level & alignment
0000b5ea-f278-51b5-9165-4e8dcb65541d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Embedded items | Securely fixed in place
f9497a0e-7e30-5698-9cc7-04afeea8421d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Construction Joints
26bcc1c0-b1d4-54af-bf70-917e3ab92b3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Construction Joints | Correct location
834aee05-defe-5a3b-acb5-a3eb37e4a6ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Construction Joints | Adequately prepped
7b889d39-a51a-5041-860b-ba0578803def |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B6 Pre-pour Inspection | Construction Joints | Joint board installed
90bffbec-1631-4b56-acda-242998f108ba |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection
ca84bb21-433c-5be0-a41c-6c8ce401229f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Preliminary
3d5e41b1-a7ae-57ce-9ff7-c6bedf589334 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Preliminary | Engineer notified of pour
86b99966-f695-5702-bcd7-fd51ecaae13e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork
d2e34dbb-9b6e-5288-aca8-61e15c7079b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Installed as per formwork design
25d5c588-636c-5a66-b2cf-705a6b2102c8 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Permit to load issued
ff3f8fda-a547-53b5-8ffe-27ade40e4513 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Dimensions correct
d1873d21-bbbb-513c-a04d-6dc22814fbc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Position and orientation correct
aca0af33-5a1c-5f39-8f05-ce2dc3e76437 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
8a5750b1-7b48-5ef9-81f2-0c52a532d253 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Forms coated with release agent
b69e576e-136b-5796-86c3-63fa66235dcc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Forms clean and clear of debris
359c898d-a7c3-5419-b6d8-bb944f5eb242 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Joints sealed
b37ebc97-07bb-549e-9c92-fdb13308cc10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Formwork | Pour level marks
944ee5df-5b29-5975-bb5f-cadaf6b8d663 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement
8b1c37d4-d8df-5769-814d-a42ca05b95e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
af924a14-eb05-55d5-b0ff-188651d1dc85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Correct bar size
7ffd8f51-bf1d-5182-a789-52b17b600e3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Correct number of bars
ab3d6989-e677-51de-a4c6-7d849899a430 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Correct spacing
10963d3c-b7e8-5a4d-9142-7888d225402d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Starters bars included
25623b6f-e8b8-5a52-8948-4f98624e2272 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
c73bd7db-b457-5009-aa78-cfd4e99f0c3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
0448fdd2-be85-5975-96fa-976708547daa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
98a25695-0914-556b-baa9-3ce647473375 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
f9ed4888-3813-5f9f-918c-3dfdf6ccc856 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
70f072f0-8c1b-594d-8774-6fb35c6d59d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
ba404f91-c456-56d6-876e-6e13ed5588d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
5dc6687c-3cc7-5fd1-a034-1fd46cb5c535 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
5f398e63-eed4-5a37-a08f-52c4bce62218 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Embedded items
b2ac38be-522c-574e-9a06-5e530131c3c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
0acfabac-9d82-54ed-b7e4-fd570a17e7b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Embedded items | Correct position, level & alignment
a88034ca-0823-5ef9-bcd2-adbbc42d5654 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Embedded items | Securely fixed in place
92704226-3d7a-5730-a558-ae86506e0ec0 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Construction Joints
6236e943-4e28-5438-8d70-a062df9a32bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Construction Joints | Correct location
700e75fb-d37d-5ef3-ba11-d88df6d94aef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Construction Joints | Adequately prepped
f314de2b-d6d8-5d76-9ed1-adab7f2d7d14 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B7 Pre-pour Inspection | Construction Joints | Joint board installed
5e7e801c-4895-4f09-9f53-35464a9a9c03 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection
1e6a77b0-1191-5402-807e-6e5233a4de59 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Preliminary
6ef623ed-f6d3-591d-8ef8-ae1167b61091 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Preliminary | Engineer notified of pour
541a8673-a20a-540a-8e7d-b0baa9397da4 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork
3daa1733-4e17-5c94-840c-d8be505c3712 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Installed as per formwork design
bc43406d-8a74-5e2d-9262-52a2be348244 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Permit to load issued
6455ab2c-d65c-525b-b835-85613d600d9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Dimensions correct
725f7ddf-647a-5677-b140-e88574960980 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Position and orientation correct
b925ed67-41f7-5743-869a-46bcbc6dd7ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
169d6f0a-4ce5-5422-ac4c-23278a7850f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Forms coated with release agent
e535d1a1-48f7-5113-abec-315cfbc68456 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Forms clean and clear of debris
5047af60-aeb2-54d5-ad65-d720047e6254 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Joints sealed
3b3b9252-a08c-52a8-9353-9c502cfca083 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Formwork | Pour level marks
aca6bc4e-c553-583a-b2aa-9a1cbf13779b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement
65ca4d62-68f2-5720-a3eb-48e46f2f7f48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
4c6ba826-f56a-590c-b469-1d976869b7ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Correct bar size
f12e5167-4b4e-5018-ab50-f8a20d528bf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Correct number of bars
428b69ea-26cc-59b8-8753-fddb384e4670 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Correct spacing
b69d18f0-653c-59e9-bbde-12e15a11dad7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Starters bars included
68b2c2dc-55c1-5ef6-a650-5700bbdf47cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
ed6f08ff-dd5a-5c9e-839e-fb0b31a2601c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
d7b60d41-0ee2-548e-ac0e-18870b5348d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
4167f73a-bb1e-560e-8fd8-5878c21f1adc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
080616bc-e765-5e6c-b5d7-cc53fb3523c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
6a7c9ae1-33f8-5fe2-9837-33384e66c138 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
6820ebd4-30c4-52f0-b9c7-e87193209bc4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
57eeab0e-62e7-5bb8-86a8-09757936b78e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
1da9af0b-753b-5393-8343-44bff5d91bff |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Embedded items
419ca5e8-64b7-5e4a-94ee-f6b52226dda4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
54c09e21-647c-5d0e-93f0-20adf14a946f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Embedded items | Correct position, level & alignment
155989c3-c2ab-5d94-8483-3fc3528a6028 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Embedded items | Securely fixed in place
62bcf0d5-a14d-581d-8b7c-e814be93e012 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Construction Joints
cad6d75d-ba67-5264-a33c-f93b53faadc6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Construction Joints | Correct location
3083a0e3-2ee1-554f-8470-4dff4a5f1ca1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Construction Joints | Adequately prepped
f6b6dd1f-57b1-5e35-be54-4f1c09ad12eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B8 Pre-pour Inspection | Construction Joints | Joint board installed
1f4f9afe-51f0-4859-b5b8-bb5e056b6fc1 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection
ee9433b4-fe76-5eda-a3df-d37de349c5b4 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Preliminary
9d541fb9-64a9-5a33-bb31-086128b91527 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Preliminary | Engineer notified of pour
bdcc0260-1540-5927-b3b9-ddb42c61dbc5 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork
721ca0aa-c3ca-5ceb-a0fb-2fd84bb89d9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Installed as per formwork design
71fe721f-18d0-5f1b-9866-a45c51a7ece6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Permit to load issued
36095b7e-dbf9-5a16-b3c6-8c910a6db96e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Dimensions correct
1925f940-caf3-5e74-85f8-d857eaa08d93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Position and orientation correct
ab3571fd-4aa9-53e0-9582-ed0535aec242 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
53159304-a244-50ac-ba52-5dd2768ef84b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Forms coated with release agent
7ede32e2-691b-5c4f-b84e-cf3f2b29aa2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Forms clean and clear of debris
d0bed56b-b237-53e9-9479-c48c6b739230 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Joints sealed
43ae18e1-6fad-5762-a239-7574fd940a35 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Formwork | Pour level marks
1c210098-f901-5d2f-b42b-c8716e95952f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement
1e56f00d-7b45-5286-a39b-d5515a6aa799 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
40d151ee-11e8-56c0-a9ff-c45d24acaad9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Correct bar size
de0c9bd4-d39b-5c88-b8c1-ab8199e3fdc8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Correct number of bars
c513bc14-d052-592c-8efb-1aa5f55aa203 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Correct spacing
0a25a234-fc2f-5907-8ef1-d0cedda9933f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Starters bars included
523c04f1-d8a7-5b92-b79f-6fb71404a70c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
209f290a-6a68-5a19-b7b9-f70e7b35b4df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
dd9a34c0-8bd1-54e4-a408-b06ce0b427ed |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
d36711cf-498b-5668-904d-210cdd818e02 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
bd541a12-f801-5541-b341-407c31cb674f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
6a97e350-f583-58d2-8ead-48635ae00f71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
4dad158e-ca3f-56d5-a5aa-f407fb19872d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
819f6826-3ace-5d39-813a-b42e5dfaac68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
c3351c9e-e737-5ec9-b5f3-2a65b9b2a581 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Embedded items
f0cc6441-cb3b-572c-a6ba-009732b19e2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
fc4f6fb9-2940-5f52-94dd-dd4df5cd77c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Embedded items | Correct position, level & alignment
231571b4-beb2-5285-8582-f6a0ae78c776 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Embedded items | Securely fixed in place
b51ec575-f576-5763-9ed5-36fe6950de7d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Construction Joints
a6be328a-2495-5e0f-84f8-9865aea5ed1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Construction Joints | Correct location
e4e5ab32-4720-5fd7-afd1-8f5d2e57adae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Construction Joints | Adequately prepped
052ff038-65df-5ac7-b729-cd5e089cfe42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span B-C | Beam B9 Pre-pour Inspection | Construction Joints | Joint board installed
27762c6d-b509-433e-9abb-b827f95efea5 |  | pass |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B
eb2cb9bc-a25b-48ad-9fc6-ce298528749f |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection
64877038-efc7-58c1-9628-97219490e77d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Preliminary
8ced1e10-6702-5f5c-bbe4-11a498218f01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Preliminary | Engineer notified of pour
0275f084-2177-53de-ad0e-d165318677a5 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork
7c44a011-0e9b-5b68-bfa6-901dfe394e91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Installed as per formwork design
cb750d7f-bc36-5746-ab9d-1259263820c6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Permit to load issued
9eaa72a4-93f8-5e0c-9fea-7379b8ae0d58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Dimensions correct
1dd93494-ceeb-5f88-b351-1b309cbb651e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Position and orientation correct
e9ac1344-e537-5fb1-bae9-ca9f12078908 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
303f33fd-0e89-584d-904b-41b39ab15e8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Forms coated with release agent
40b377d8-114c-53c8-86d7-9365f71c9ff2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Forms clean and clear of debris
98e739af-e6c1-59b0-895a-06f7a96d0681 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Joints sealed
f2502509-6e5a-5a43-b9f4-7a2a456cd813 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Formwork | Pour level marks
93273a99-b6af-5ff8-baf4-16db4fbc6577 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement
097302f9-3669-5a50-98de-b0bda3320082 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
23b69f70-9757-5965-9e02-54fcd994aee1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Correct bar size
ca0aae84-85a2-55d7-b1cb-b32f158e2bc5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Correct number of bars
c59d5086-f7ec-585b-b077-feaed00e4888 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Correct spacing
2eb73a2e-f931-53c3-b516-4c437364c74d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Starters bars included
4e11192b-a3d5-5ee6-9bb5-2f7a49ecf174 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
b98a936b-020d-5c9c-b311-bfdd2bae9fbf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
28ed7338-b47a-54a9-a09f-3180c4c5c768 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
83553b60-103a-5c77-9a2a-7e6aca9aa009 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
f518b1a0-de43-5d7c-b682-0b23fea49f72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
cc4657dd-4192-5cc4-810a-480ce5215ad9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
2c705292-4548-5d77-8d07-b69a3583c44a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
8600bd71-46f5-5a23-ace8-87e98913ffb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
f798d2c8-4b1a-5fa8-94ee-799c46ab6cdd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Embedded items
b02c472d-0ad8-53ff-a35f-88f917cb203d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
f5ae208f-b214-552b-b607-8110befad6f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Embedded items | Correct position, level & alignment
38370c02-813a-5f29-9c01-e200076973a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Embedded items | Securely fixed in place
f4388210-3b30-59f9-80f4-5fa2c873c538 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Construction Joints
4f4f5d33-e29d-5838-bf06-51e05d07a437 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Construction Joints | Correct location
2f6ac6fd-d632-595d-94d8-2535f3e63ffb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Construction Joints | Adequately prepped
4488e74c-e1f4-545f-82b9-24cd76f87b71 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A1 Pre-pour Inspection | Construction Joints | Joint board installed
227a785d-3c7b-47bf-b4f8-829133831fb0 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection
405e1882-02b6-5789-bb29-21b44a4cb2bb |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Preliminary
6d43d437-d281-5c1b-9143-fbe2cdd0d0ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Preliminary | Engineer notified of pour
72ef0f4c-eb57-53b5-b554-728b4cc2a56e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork
86ba6d33-c639-54ab-9368-763396205ff6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Installed as per formwork design
ee8193d8-e33f-5f9b-8212-528c5722dcc7 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Permit to load issued
62804ae1-d98b-51d5-81ab-a40a9a2b0130 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Dimensions correct
fd6323a4-8e31-50b4-b11f-c7ec3844708e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Position and orientation correct
841ca88f-feb7-5112-9c42-c7f869b53ba7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
ddc4ef18-7c64-53f6-b7a1-48e0a1e2a128 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Forms coated with release agent
262a9559-67e4-52e2-bb79-f60fe603337c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Forms clean and clear of debris
6092ddd5-18b6-56bf-ba2b-8c2658da4349 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Joints sealed
5ddb8677-fefb-5316-b838-00a550fce29e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Formwork | Pour level marks
c7e51186-65d8-561f-b31e-7a28a8e9bc9d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement
55721440-1967-5066-94f3-6c577375a295 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
cd01f698-8e26-5043-8e57-d3266a3eda6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Correct bar size
c110ed7e-9f3e-536a-acd3-a5f5f1827627 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Correct number of bars
4196c1c5-4845-5cbe-a188-95ae92553891 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Correct spacing
b8508d00-c8e9-5b84-80e4-f357ae59808c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Starters bars included
afa3151d-ecc1-566d-974b-e82377eb0178 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
07948667-2450-54c4-9909-5fe3149913c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
5a3c1fe3-8aba-59c4-a980-2a2a401ac4bd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
451d8b7d-61b0-5732-b56c-574ef2e51533 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
40dc2592-bda0-5303-b8ec-97e5f0750af1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
9e2d309a-c0b6-5c1e-9744-f7f56811c25f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
7d67885c-ac78-5b7e-81e5-2b0578f53064 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
024c97af-1366-5011-8951-c7a4b4fbcc0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
8e0a3390-e226-56b7-97b1-6ba6ab99dfe3 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Embedded items
f3ec0ed9-1213-5e22-858f-bb600fd147c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
ab60577b-2114-5f91-9a48-83747d2624b4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Embedded items | Correct position, level & alignment
f236d0e1-692f-5658-b122-99fc1680a836 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Embedded items | Securely fixed in place
d7f3130e-5ed5-59c7-a3a1-66465071fbb9 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Construction Joints
278c5d0d-676d-51c1-b0f7-a3d6ceaaea0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Construction Joints | Correct location
4153394d-9df4-5b28-9bb9-6330a0404300 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Construction Joints | Adequately prepped
2859d58c-bea6-5324-b73e-1e02f0022c70 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A2 Pre-pour Inspection | Construction Joints | Joint board installed
f7324336-db6c-4ffd-be7d-f60b21fb9c69 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection
f9eec4b1-97a5-52d9-a023-958f6e8be36f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Preliminary
d4262d13-61b5-522a-8000-77e5a9851b90 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Preliminary | Engineer notified of pour
52a804d7-bb81-5c7e-9eae-354268b66425 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork
e4d824bc-42e8-5736-a594-7c8382ce3525 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Installed as per formwork design
d0434f8f-72c0-5ab8-aabd-cfc901d1e3ab |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Permit to load issued
2ee5ea88-09a2-5630-a8b5-8689af16e440 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Dimensions correct
171bbae5-5b4b-5f63-b731-49642dfbc65f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Position and orientation correct
a237c51c-99dd-58a9-87b1-192f565fb2c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
b2315b26-f542-5bdb-97f0-b7b7d58e0fdd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Forms coated with release agent
4fd68262-a976-5e4f-9943-f283135ce492 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Forms clean and clear of debris
e0c81b1b-26ff-5160-aa75-4f2e409a0f11 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Joints sealed
266378e7-3671-5cb5-bda6-64dbfae3ec27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Formwork | Pour level marks
9c6fb459-175f-5103-9941-1e097e8495f8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement
deab3b7f-2375-56ec-81dd-f2527e46f570 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
d2474a41-f161-5832-9b35-695d4904f1c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Correct bar size
d09ba345-3875-5020-a71d-c16b7fe3c2eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Correct number of bars
ecd45b51-9d3a-58ff-adca-d120435618fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Correct spacing
1aa2e5b7-3184-5620-ad55-a246187447c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Starters bars included
775a645f-4d34-527f-b4b1-7248be5f8460 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
be0181c4-3f95-5348-87a5-128218776829 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
bc0103af-d355-5f84-84d7-9c3ed6f4e3d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
48b282b3-3be7-592c-8e70-ddbd14e89b98 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
65e4cb1d-c9a1-52fd-9126-67f7c387d922 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
16d388d5-578a-56ae-b73f-8f4f35711807 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
fb73317a-ffa5-5183-844b-3d248b35f4b5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
e102123a-5023-535c-956a-95cbc6904ce8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
113279c8-fed1-5a9d-bfe0-10c817af49e9 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Embedded items
5598ab38-18b0-517c-b346-e8ee55d46157 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
9ba19f7e-d139-5c85-ae35-60ed53af0a0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Embedded items | Correct position, level & alignment
9f4e6635-33c9-5b91-b38a-b709eec0484b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Embedded items | Securely fixed in place
bdd560d7-43ea-520d-a604-ba3103c82f46 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Construction Joints
e461d854-dfbe-5168-b9ac-11dfb3a6bcaa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Construction Joints | Correct location
91f4b9b6-dfb4-5a35-9c63-6eb52d652148 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Construction Joints | Adequately prepped
108dbb5e-7a94-525e-bd4f-3f332bd1e0ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A3 Pre-pour Inspection | Construction Joints | Joint board installed
47a5b489-6f4f-488e-852f-c27b77f69022 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection
884727e7-7fe3-5d1e-be9a-91b14863373e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Preliminary
0dcece0b-5ba2-5cd5-bcb6-9b5a88172a80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Preliminary | Engineer notified of pour
128c4856-2102-592e-a04e-b0c178e941e7 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork
5bf616d3-c45b-5f72-a62d-3ed202bc56d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Installed as per formwork design
82dcdb28-6c26-5e9a-ab52-76f223f4a79b |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Permit to load issued
bc7ac82e-01e2-5791-9cb5-4c75210d766e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Dimensions correct
d2f2aecc-d7fc-55d2-81d3-37dc2814043f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Position and orientation correct
55b7d3ab-4db4-5a59-833a-7874eeb9a6f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
d52d496b-df6e-5321-aba7-bf1b0bfe5ef3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Forms coated with release agent
3dfbef52-ce4c-525c-ae7f-c2caa1890954 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Forms clean and clear of debris
2b82e48b-af65-52ed-8d4d-2f97754441be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Joints sealed
b6c04fd9-d307-57c5-932f-c286ba6e8f6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Formwork | Pour level marks
73a5e2a3-6313-52bf-9f6c-aa6cb027a222 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement
e9349679-b917-573b-8ffd-29ede548da9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
e4d7d836-7a0d-59be-b7c7-da0d1d7a2ac2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Correct bar size
92b07e47-855d-550b-b72b-8282a06adddc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Correct number of bars
4369530f-1297-572d-9464-c02ed513091f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Correct spacing
060acacb-47a2-565b-96d3-46d0f2f5a864 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Starters bars included
d47ffc50-36ef-58de-8ddc-715506d73a20 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
e9fc9be6-454d-5d55-8b77-44ecf2d5bbb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
2dedbf8c-219a-5f2a-a538-82776de1053c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
c066696a-9d72-5a5f-8702-a0ada0cdcf05 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
cbf0ec0b-40ed-5fa6-8fec-489e00844fbc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
cd574d4f-ae27-533c-9ef5-dedb1106124a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
65663d7c-07b5-52d3-b312-471b97c65d05 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
027d3384-8274-50e5-9ab0-672c6d1917e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
1411bc08-ebeb-5418-a2d3-1bb7cc3acc5f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Embedded items
2de66428-c74e-5064-ab93-42c09f4bff67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
99dcff01-99a3-5a8d-a240-5ab237d0a404 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Embedded items | Correct position, level & alignment
36cbd7b1-b59d-55c7-bdae-b20269b1c3d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Embedded items | Securely fixed in place
0328c7a4-8852-51ce-9f74-f8c629eb8e08 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Construction Joints
e355e2c3-2267-56b5-8267-c62bcccefbe5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Construction Joints | Correct location
d89689f0-fbe9-5da1-ab16-b8c998340ca5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Construction Joints | Adequately prepped
a711fa94-3b1f-528f-bd94-0f1ba6e17601 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A4 Pre-pour Inspection | Construction Joints | Joint board installed
8425d5e7-ea38-4695-b2ac-dcf14fdc0205 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection
7d8233c0-bb38-57e9-9d7f-5af2fae35033 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Preliminary
b9f0db19-635a-539e-b634-84a01e971386 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Preliminary | Engineer notified of pour
52b43a7d-9121-5943-9f7f-d732095a6c50 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork
2579b66b-5cb3-5ee9-972d-267b82754c4e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Installed as per formwork design
06409b1f-b14b-5127-be19-5b64e6a35a25 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Permit to load issued
2e3c73bf-90bf-5d79-8228-763984046193 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Dimensions correct
b4f4703a-4351-51bd-b931-510c59e0762b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Position and orientation correct
ab981fae-fbd9-565a-a039-c9b6fc16287c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
8e0f4c00-2733-5600-a6a1-09a14f7ebc8b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Forms coated with release agent
fa05ef6f-952a-5ff8-9cfa-625dcc548330 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Forms clean and clear of debris
93cf6531-3221-5ced-ba06-03070f6aed6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Joints sealed
aab9c560-836f-5203-8901-32f0b704b977 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Formwork | Pour level marks
ad28fab5-1685-55ea-aaad-6bee7b608963 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement
0fe1c20c-2e2e-5cb0-92b3-470e0398a6e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
5c5315a4-1aea-5049-8b4a-4c09f883ce4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Correct bar size
47c0fac6-45fb-5413-b06b-27c10b37f2d4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Correct number of bars
5dea1b23-67cd-573d-b3ff-2b7794a063d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Correct spacing
ceaafb74-6bfa-5b3b-b320-fa229cee37b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Starters bars included
0e3c9c5b-3a36-53ad-a0ca-161f412efa04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
d9ea7a31-d9cc-5098-8449-ed35276431ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
35e7b7c2-d9c5-5588-8cc9-3f4fa53ef63d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
55cde4f0-665f-5153-8e96-5f640aa8c609 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
c7c6e2c4-ae2e-5ec1-a55d-51fe94d02e0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
4e6ec9a9-e51d-57ec-9d55-913afff7d241 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
9a561863-5cb4-5143-8fbe-0132f635be13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
9d609334-689b-5d88-b3a7-ac42b028cb13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
f25cd9e9-5ed2-5329-88a5-3b049c2e3b37 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Embedded items
00f4df4d-a255-53ab-b8fb-e9ff6dfb0798 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
ba2a0767-6dd9-58e1-85cf-a24c47a3193b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Embedded items | Correct position, level & alignment
80e6c80d-ab9a-512a-a82c-a07b2ec3519c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Embedded items | Securely fixed in place
9ce1a5a2-325d-5c25-a51b-2627368dd12d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Construction Joints
5f9ab507-b367-58b4-aa87-5af9cefcb5d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Construction Joints | Correct location
3423534c-cd74-5c85-a5fb-3b2d9e18ffe3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Construction Joints | Adequately prepped
97d0d6bf-2119-5d08-b423-b80ffb7084fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A5 Pre-pour Inspection | Construction Joints | Joint board installed
eba30c61-d18c-448a-8f5a-e5233c40dd5e |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection
7d3f4e24-f39d-5d11-b88b-f0b172a5d44a |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Preliminary
80045a73-1e6b-50d6-a9f4-7f886dae16b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Preliminary | Engineer notified of pour
c28d16c7-f70d-5367-9422-4e3281102aac |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork
d42ff794-b0dd-5fe5-a8b7-62feb7325e2e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Installed as per formwork design
f3e403e7-4bfb-5321-9872-5e2f63e605ec |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Permit to load issued
ed9b98f0-6a39-5e20-8a5e-e8302e350e65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Dimensions correct
ee6ac6c4-ef9c-5b52-a882-035dfc11f6ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Position and orientation correct
b63fd931-4840-5da6-8f8f-e33dff9cc90f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
bda677a1-31a0-5a25-a421-52e838695635 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Forms coated with release agent
cb26c830-69cb-565c-958c-87340c0c7bc8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Forms clean and clear of debris
00238669-59fb-549d-95da-50497933bf65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Joints sealed
a1c68ac9-2cd0-5976-bbb5-c4a4d2fcdbc7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Formwork | Pour level marks
1bdf967a-8f5d-500d-b44a-d87f0bd62e0f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement
586eecff-c73a-5b4f-acb1-aa9933ee5512 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
a01e4096-12e8-5e73-b544-e5b01ddc2a9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Correct bar size
fd58b6a5-c4af-5f5c-b25c-a0e66c478d25 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Correct number of bars
4b93b0c5-f4b1-53bf-8ac8-d5a3ae216df1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Correct spacing
9c49a642-9f30-5cbd-abcb-dfab0c1db5e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Starters bars included
c4a2d164-490c-5ced-b4ff-14e6e518d7d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
d858bb41-3553-5c7a-ac51-76448d1ccea0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
35f48f84-b8e9-50a7-9707-2b079595a921 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
ef6e8897-474f-5b39-bf42-0b1b47c37519 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
b6068db6-b6a3-5a85-a506-3dd70bf00d52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
281e4425-7dfd-5e3f-a4e5-8d153070afc6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
ff46aa7a-7081-5f5c-be1a-0585dc0bf37b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
f8c2dddc-58d0-527c-a26e-7d317d02f026 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
78db209e-6300-58c8-9e6f-d990d756cdfd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Embedded items
974faf2f-577f-5c89-adad-4035ec8d13f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
c9e3b5c9-a9f6-5181-83fd-5f26e8ef9621 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Embedded items | Correct position, level & alignment
10f1280c-6408-5471-9afd-74d53b31fe15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Embedded items | Securely fixed in place
6c587d97-e058-5c35-a1ce-f5e99eb52087 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Construction Joints
19279cda-894a-5919-a1f0-6133cd58ec83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Construction Joints | Correct location
4fd30e45-8cc3-5341-a8a1-216db1e1a2a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Construction Joints | Adequately prepped
f736d805-13b3-5719-82b0-d00d99715ef1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A6 Pre-pour Inspection | Construction Joints | Joint board installed
27df0c2f-d1c1-4b9c-bf48-29fe7ce337a7 |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection
2ececf6d-6efb-5b7e-b70d-bddb0cfc0b7e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Preliminary
6c029620-6a59-5853-b1cb-aa9a2c4ff029 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Preliminary | Engineer notified of pour
39a9399b-dc41-5d6a-b980-c065ad2fbc77 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork
856f4273-bfa7-5e0a-a5c9-7dadd8e83feb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Installed as per formwork design
d0c9a4cf-3c6a-5c4a-8749-4a4b6e8af99f |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Permit to load issued
90393ad7-7a71-551c-92ec-295f83382c04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Dimensions correct
7b8ec55e-565f-5020-9f07-3cb7d7e46dca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Position and orientation correct
efc1c488-09eb-50c1-be74-b34476a649d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
7b554927-d023-5c0c-94c9-1fe0afd79912 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Forms coated with release agent
9df63389-0cee-5b9e-9b75-8e6a79b1043c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Forms clean and clear of debris
7e6ddfd7-a434-5100-843c-8bb52878e955 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Joints sealed
af25262e-43c4-52cc-9bc0-dd9256d594e7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Formwork | Pour level marks
af439cd3-1703-5945-83b9-3cc654ec5abc |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement
0494ff06-68a8-58ba-88e1-778598c32971 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
2210b867-6752-5355-906a-26702bfb8633 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Correct bar size
2fd61096-45a0-577c-857e-7109c3f031b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Correct number of bars
174e85c8-213f-535a-b0f4-7fc7bbaedb2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Correct spacing
84b601ec-bd3d-5d73-ac52-56a5a9cb88d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Starters bars included
2fc49077-4baf-563e-a7de-690bd5b0054b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
168d5c40-d6df-55e7-a8b0-bbf06d5c70ea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
7a6aa7c9-3f63-538c-a0a9-0b0ed7ea1b7c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
96f77b77-c6d0-58db-a55c-d2475856459a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
15dfe577-c7e8-52e9-8dea-628976d090fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
b8d717b7-5660-5767-8a2a-7b9fb1eda958 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
db9b4686-3958-55b8-ad10-3c9adcabf4e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
e11a8de0-3992-5b31-be2a-36d7e41d8c12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
d30ab3d0-068a-55cf-b1d0-c12b56924c0e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Embedded items
5571239f-7969-50ae-b1bc-8f6cdcbd71ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
973cce9f-8321-5521-b111-107d17767ed3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Embedded items | Correct position, level & alignment
370b83f2-0d3e-587e-b885-8da302f98179 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Embedded items | Securely fixed in place
6725922b-1752-56c6-964f-939ff43a2c85 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Construction Joints
96a6c4db-cbd9-5b34-88d9-8df2505dc2f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Construction Joints | Correct location
9549a6c2-12a2-5b4f-be58-f7fc6f2c3d21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Construction Joints | Adequately prepped
65bef5f4-dee2-53a8-84f0-cc6fe5eddc51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A7 Pre-pour Inspection | Construction Joints | Joint board installed
b9f16d7f-a60b-4725-bb90-2414bd756dcf |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection
f312f1cd-59dc-5b46-9618-f27007fdeec7 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Preliminary
e52e6f25-7236-5b0a-a7b4-9a253178306e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Preliminary | Engineer notified of pour
ea40aee7-bb56-5d13-976d-e73a002e8dbd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork
23d395ea-a956-5ab8-b259-2f9b1dc2cc65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Installed as per formwork design
5a8831c8-d16d-5bde-85d3-3d25092bdcee |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Permit to load issued
8876ffe6-11ae-53ba-b03f-4441c57a7271 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Dimensions correct
e89c46ef-6a40-51a2-bada-60249651d0a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Position and orientation correct
9d7bb64d-471d-5b0a-bdc8-8386e1d703f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
404544f6-c768-514c-8548-839f80b5bc6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Forms coated with release agent
092f1d05-05d7-5e39-8b0c-cf50240468f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Forms clean and clear of debris
51d5e988-3c8b-5d2c-a2dd-aca54dc5a6e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Joints sealed
563c754c-496c-52c3-854e-f8b70eb53f0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Formwork | Pour level marks
e330272c-0b95-5a92-9de6-1c538f5a4d12 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement
73731cf7-43d0-53b1-be93-ef3f9b22a9c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
cb39e9e8-b324-5528-9bf1-a3ff365e7843 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Correct bar size
8be59807-bfa9-54f9-b582-ffe10a13496b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Correct number of bars
0d5a8b9a-bb6c-541b-a213-ee3e1b0e3d40 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Correct spacing
e7780d86-1dbc-5a50-8488-77ff4834f64b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Starters bars included
874819b9-34e9-56d7-b65a-e6da5e3eedfe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
4139252a-f9c5-5576-a45d-5bf231f6b0ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
d14f79db-3b31-5edb-974b-6bb23653be68 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
1723f5a1-c57b-57ad-b07f-5546bce379ad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
28a8edc4-2aec-5741-bf2b-fc0c46e346b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
ee5dd9b5-63be-5171-8321-621bf0f3e82d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
c2016823-796c-5c8e-81d8-69c4c543b8dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
cedd418d-254e-523b-8293-7d92cab6bf62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
e6bbb2a1-8afc-5fba-8d0e-e07dc97c2c15 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Embedded items
7c34753a-22b7-5f53-8a88-c5d672f99949 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
28a8d5c9-1145-50c4-9da5-dd8b59570135 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Embedded items | Correct position, level & alignment
4cd16923-9ca7-57b0-a686-a74a9e3d5feb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Embedded items | Securely fixed in place
65b1b964-4471-5eb2-8dad-bb80d92ed509 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Construction Joints
00bc7caa-9c09-5d34-afdc-6439553f03fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Construction Joints | Correct location
cb31f394-7f99-5d82-a2d8-eb42ee54d8da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Construction Joints | Adequately prepped
0d88587b-da4c-587d-86b2-70a223ea0255 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A8 Pre-pour Inspection | Construction Joints | Joint board installed
8f294c3e-f896-4af7-a5ec-14b8eda98a5a |  | pass | Concrete Pre-pour Inspection | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection
6145d82d-5fd9-50df-940b-6a7f78eefc3c |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Preliminary
c731dd89-69ed-5577-8c6e-5690e21b312d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Preliminary | Engineer notified of pour
4ab7d252-ea16-5554-ac0c-fcb2146eacbe |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork
3989e470-0343-5604-bd4f-9eb959525c44 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Installed as per formwork design
7d91447c-d634-567f-9c8f-11dab4cfd62a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Permit to load issued
3a7d4182-06a1-5a76-b4e1-9ca9005d5126 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Dimensions correct
d48cd089-43f2-530b-809e-4fff674aaae0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Position and orientation correct
7940ac25-02b2-5c4b-9263-22956d4a3e21 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Forms vertical, plumb and true
b8a7d357-0ca4-5029-8a9d-c80e8897c4e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Forms coated with release agent
7a0c253b-8956-57cb-9442-e5ad2fdaef06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Forms clean and clear of debris
795c481c-d4cc-5569-848f-a97a6d9fa3c8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Joints sealed
3acce404-78d8-5ca1-8e42-6364684ce322 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Formwork | Pour level marks
9a365f4d-4098-5c91-858b-707c3a9ba94c |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement
5336f261-2a03-59eb-b068-f528124a3d2a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Correct grade reinforcement
f5fa8278-f029-5362-8efd-3a61a6a192dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Correct bar size
74009854-4c6c-504e-9026-a05870efcabd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Correct number of bars
63fd1f75-1084-5b29-8b98-3048ca96a58c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Correct spacing
8a838a9a-d05f-5eed-99c2-7831dae318f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Starters bars included
cfc3b251-a9d8-5ee2-9575-dfee2148a5f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
3dbd6b11-34e0-5d2b-984a-a17a0da72158 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Correct weld lengths (min 10 x bar diameter)
7a3b5582-3b8a-5a5f-b368-213e6560f132 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Correct lap length (min 50 x bar diamenter or as per drawing)
62f3f6cb-42de-51e7-bbcd-ca1523b6c8fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Correct lap position (staggered appropriately)
57425423-03cb-591d-a8cf-3dc48c7a19db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Longitudinal bars terminate with 90 or 180 deg hook)
723532ac-0a20-5916-9ea5-16feb3a29d08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
3631e6c8-9903-5a49-b383-029c5a319cd8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Reinforcing adequately tied
60d64ac9-ef7f-5801-990e-97ef7e0722fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Reinforcement | Chairs or spacers fixed in place
d8ff302d-c1eb-53a2-a41e-911bddcf6646 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Embedded items
57a2d070-6fa3-5117-9e03-327e818b2a5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Embedded items | Block-outs, ducts & cast in items installed
356c8bc2-b06f-534f-b9a8-730e43348e66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Embedded items | Correct position, level & alignment
23e92967-1539-5782-9fec-4b657eabdeca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Embedded items | Securely fixed in place
05166c7c-b6e0-523e-922d-37b7ee65ac07 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Construction Joints
2d4489c7-ace2-595c-b73d-e0d67cb86338 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Construction Joints | Correct location
f585b30b-0253-5a92-9cf4-447b73e53102 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Construction Joints | Adequately prepped
f259b9bb-431c-5d10-a974-2eff87cc488a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | Super Tee Beam - Pre Pour Inspection | Span A-B | Beam A9 Pre-pour Inspection | Construction Joints | Joint board installed
1f7d1cd6-b449-4e51-9af3-3948f2995d30 |  | fail |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A
6ca35563-3eb4-402d-b55a-df85ef52d060 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1
6ed57ecc-8f7b-56d9-9480-5f3df5ef125f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction
223b38ca-3c3c-5a84-8caa-249eb0132435 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | 1 - Shop Drawing Approval
ecf1fa03-2258-5526-816a-2fd8d6efc3fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | HOLD POINT
6a6a4e6c-f23f-5fce-b4c9-f21bded3faac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | 2 - Concrete Mix Design Approval
539e307c-bb9c-560f-bdb1-61ae98451853 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | HOLD POINT
5a2e25e4-0d28-50d2-9905-6d866bff4130 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | 3 - Lift Design
1a84adc6-f9ec-5914-9180-d4e3cc0eefc9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | HOLD POINT
d31c1099-6558-53a7-a38f-c3c72fa6c457 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | 4 - Steel Reinforcement compliance
9234128f-485f-59f4-b583-8b1587e7e1b1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | HOLD POINT
52f19728-d724-5faa-a531-66ca2baefa85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
8a022792-d46a-5821-a876-88f64bdec872 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | HOLD POINT
5e4a8072-7c3c-595b-80b1-290f5c2098cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | 6 - Design Stressing calculation
900dd3c6-cc02-5ebd-b14d-fba4b31a1d34 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | A. Pre-Construction | HOLD POINT
38bf35da-7db4-58bd-b011-793afe46a5dc |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting
339d06d5-ba45-5fb4-9513-0a532cd5c5fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 7 - Steel Reinforcement cage assembly
d80cb292-ecbb-5b94-8cdd-d77e5feb011f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 8 - Mould Preparation
2bd407db-3763-5cd8-a913-aabb5fc90e01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 9 - Pre-Stressing
dda0921b-6bb0-523b-bdbb-f541391e860f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 10 - Steel Reinforcement Placement
03a45493-dbf7-518b-9a91-dde0d2f369a4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 11 - Cast-in Items
a4b632d6-db91-5163-adbb-157c91ca0369 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 12 - Pre Pour Inspections
2ee2dbcb-3422-5e3c-b3ea-abf3f92ca7f2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | HOLD POINT
b6b1163c-262e-5d72-9abe-de82fec12f3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 13 - Concrete Mix Conformance
a9a9129a-bf29-565b-a0e0-9916ce085a7f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | HOLD POINT
21df7882-a375-58bc-9efc-17cc241ce45c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 14 - Concrete Mix Workability
083e6e80-920f-5e6e-b0b0-da840aebbb61 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | HOLD POINT
3ac09f54-6459-5ad6-88f7-cc722541a3c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | B. During Casting | 15 - Concrete Finish
1538d439-9f6a-51b2-b1e3-a8a373edc759 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction
c1de634e-407e-5153-8e3c-ad9066004e79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | 16 - Curing and Release Strength
1fe0ecfc-3a95-5704-9579-a406ec024647 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | HOLD POINT
090ce264-1143-5361-af47-5c94bcc72ccd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | 17 - Transfer
86c83bdd-7b15-5ac8-9431-8c84c0980d93 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | 18 - Draw-in
6be8f0f0-a608-5994-8188-f1c9f8037596 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | 19 - Lifting
94934d00-1630-5aa2-bedb-0e2625c6a83b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | 20 - Marking
7b7b37e6-cf45-5930-b9ea-42b41054d18c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | HOLD POINT
3f1d7b5b-eb41-55b5-ab91-4b3b0ebb8f0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | 21 - Concrete Supply Testing
ddb3b9a9-ba5d-5723-b654-ee17471d35c6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | HOLD POINT
ee5be2d4-f454-5c2b-add0-44d5dbf2e90e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | 22 - Post Pour Inspection
468a5e90-09c6-5796-a042-39c3e28a1e5f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | HOLD POINT
3aa8bdbe-c009-53f8-8a4b-333d97c134e2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | 23 - QA Package / Redline Drawings
08bd6b24-609a-5f34-a904-36ce5e31c832 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A1 | C. Post-Construction | HOLD POINT
86ff037f-c43a-4cfb-80de-1ad39cce7627 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2
619f1e42-bffd-53a3-b4ac-07422a27a3ad |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction
b2833bb2-4a1c-55e2-8866-60db2dd23658 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | 1 - Shop Drawing Approval
b7cbdeff-c640-5570-8c78-b1e51518a6f4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | HOLD POINT
bcf3d8fc-3e67-56e5-ba1d-7bc6dcf3e3e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | 2 - Concrete Mix Design Approval
bbcaa235-0612-5bfa-983d-0f8ec432b401 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | HOLD POINT
038067c8-5a91-5ac2-b7ce-74f5471f50cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | 3 - Lift Design
78727b21-0958-5c49-89dd-6b077bbca78a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | HOLD POINT
f3ed1a29-4cce-5eae-8cf1-96e08c01072c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | 4 - Steel Reinforcement compliance
3965e3c9-1f29-58df-9b48-c81564076795 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | HOLD POINT
7daddb2c-f705-5c6e-ae03-446db62bbe12 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
826d30a7-c4e9-5ba6-bdf5-a103e417a208 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | HOLD POINT
cd940938-c6c2-5875-8156-716a3f32e242 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | 6 - Design Stressing calculation
bdb91cfc-3f56-5e7c-8f85-d941b20ac449 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | A. Pre-Construction | HOLD POINT
5d0699fb-cd66-5279-b90f-9000cbc2ae07 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting
70fe3dc8-65e8-581f-a162-440c37ddfeb0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 7 - Steel Reinforcement cage assembly
5fab18c0-4e85-52d9-897c-82a7c541af33 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 8 - Mould Preparation
5978b50a-ef94-5f3a-83e2-568ab85b60ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 9 - Pre-Stressing
174b77c8-a77b-5d81-a2f4-d69d57bfe178 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 10 - Steel Reinforcement Placement
7205ea94-6046-5300-9f58-fd37076be8d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 11 - Cast-in Items
94763178-47c6-50e4-a126-af8863e1a21d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 12 - Pre Pour Inspections
c3a42175-b4bc-5e35-a7ac-953fdafd9a0c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | HOLD POINT
7639bd33-cabb-5caa-b98c-a06894eb40a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 13 - Concrete Mix Conformance
d8c1fb1b-750f-5ffe-80c8-940354ab125f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | HOLD POINT
156898b2-2b54-531e-b860-edb35fc169f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 14 - Concrete Mix Workability
8fa7a7fa-c453-5473-8a6e-3223a2092b50 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | HOLD POINT
06acd942-b3c2-5e30-bb92-b8cc9c9b8234 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | B. During Casting | 15 - Concrete Finish
d172ee66-f93b-5c4a-96f6-5616a6ceeb59 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction
3d36700a-07a1-54e2-9230-2fda4717464b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | 16 - Curing and Release Strength
4fd41ff1-9862-5aaf-98dc-2206de809cf2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | HOLD POINT
d6139510-4682-5946-818f-39c0efbd6e6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | 17 - Transfer
078f585d-8611-5851-80cb-554c54d476cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | 18 - Draw-in
0d6b28dc-3983-5a73-8c0e-fc23efdd56de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | 19 - Lifting
d2ddc93f-abbd-5f54-a9fd-1212af1b6a7a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | 20 - Marking
7d28e04c-c34b-597a-b537-c93536d63ccb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | HOLD POINT
543e4403-bf30-5ce7-abbc-94138de9c491 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | 21 - Concrete Supply Testing
da1de910-9d87-57ac-9a0f-34a087d0735c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | HOLD POINT
fa422569-e258-516b-ac62-3f6b09f71794 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | 22 - Post Pour Inspection
1490cff0-0a01-5885-824b-1c578e438914 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | HOLD POINT
09d685de-cda8-592a-9619-4b4031d6a55d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | 23 - QA Package / Redline Drawings
c12d0066-9cd1-5cee-b098-ac643099287e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A2 | C. Post-Construction | HOLD POINT
7c8211a0-78fc-495d-9112-1d4408a2418e |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3
a8decf07-0ee2-5980-b506-7bac28eb05c9 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction
0b89c05d-065f-5af7-b6dd-82cfca872806 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | 1 - Shop Drawing Approval
fd6cdbd4-782e-5cc4-876a-5b1fef827d39 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | HOLD POINT
dcc6c4fd-e431-53b3-8eeb-93385ea75f3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | 2 - Concrete Mix Design Approval
829b9eae-0774-5064-bdf4-5af9dfa5d63e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | HOLD POINT
86996b3a-2b1f-5db1-b70e-55f0d7009620 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | 3 - Lift Design
1e3188fd-9e36-577b-af59-2f71c1dc8fe6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | HOLD POINT
634b4fa8-efe6-55b1-80c2-8105b11f4e46 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | 4 - Steel Reinforcement compliance
76b0c15d-f910-5da8-97e0-2a3aa62b61a3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | HOLD POINT
65ab14ad-5ed2-5c3b-a789-0c9a94c1ef30 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
7dd33c5e-2da3-5ff0-a4c5-30da2f320bb6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | HOLD POINT
497dedba-30c8-54f5-817f-469df2dd7cd2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | 6 - Design Stressing calculation
0e572a74-d599-5748-b028-d16645ab3de8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | A. Pre-Construction | HOLD POINT
4db63cf0-faad-5eb1-a26e-feb0164dcef1 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting
22e9fc9f-6948-521d-a392-bb7af53d566d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 7 - Steel Reinforcement cage assembly
fc5f37e3-d666-5675-9717-b3cf1c2d12e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 8 - Mould Preparation
5e675c5f-9f39-52a6-b6aa-d3a79e0667d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 9 - Pre-Stressing
771a447f-8de2-529a-a576-9ada73173075 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 10 - Steel Reinforcement Placement
2e59e61a-0739-54fb-bd52-f33afc9e2d9e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 11 - Cast-in Items
4312cb4d-145b-587c-9225-565fb8742417 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 12 - Pre Pour Inspections
63354fa2-b5d3-55ec-8850-7740581a3b6e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | HOLD POINT
9b20d40e-6ce3-5aac-9b6d-4d960383140c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 13 - Concrete Mix Conformance
4e5cc58b-e56e-598c-84bf-2d719879fb24 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | HOLD POINT
c72af1d1-7945-5995-b02b-f754b5c97054 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 14 - Concrete Mix Workability
ea1c1fbc-f578-532d-b4d8-623c8995ae6b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | HOLD POINT
7940deeb-fb3b-53c7-a667-1c869a0f15f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | B. During Casting | 15 - Concrete Finish
15f0275d-cd6b-576b-8c5e-9fb5db9c60cf |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction
c7f23028-9b21-5a50-8c0b-131a0307ef45 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | 16 - Curing and Release Strength
dc7baebe-748d-502f-a3d4-0ad07305d85e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | HOLD POINT
dfbb0cfd-f275-506c-99b2-3d4ec43212a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | 17 - Transfer
68e40959-9b87-5358-bc2b-7ed0aaa0fb10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | 18 - Draw-in
f46acf30-0904-5f06-9841-38ea27ea8977 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | 19 - Lifting
6bcfdaea-3c0f-52da-a475-ca4af3968b06 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | 20 - Marking
165efe0a-39a5-5c17-b94f-f2f9f6977ea8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | HOLD POINT
5e782cdb-b38f-5554-a192-e311eed1d084 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | 21 - Concrete Supply Testing
1ecb7a63-3c6d-5235-87e5-3a449c548c79 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | HOLD POINT
0f265740-01e7-5851-92f2-3fdc06df0eb6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | 22 - Post Pour Inspection
86fba5ef-3c79-581a-a9f2-c1141fe2c1f0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | HOLD POINT
fda3af79-de70-5f00-868b-221c7a121875 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | 23 - QA Package / Redline Drawings
f2ae9b26-32a7-59c0-a702-9b5bca25ae32 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A3 | C. Post-Construction | HOLD POINT
a8b9241d-2194-4e97-a189-cdfedbb79549 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4
ba8dbd43-05a5-5b19-9838-43b894b9ba08 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction
c188f8b5-f463-5f8d-9abf-00508928ce1c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | 1 - Shop Drawing Approval
db5a4059-9d07-5a1a-b4ba-ef842f28d205 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | HOLD POINT
7e00a923-ef71-53c7-a5d6-f635c111d37a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | 2 - Concrete Mix Design Approval
49bdc2b0-d9ba-5b0e-a335-b2d018208d9f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | HOLD POINT
d48302aa-5aee-53be-87a8-c928a9ca145b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | 3 - Lift Design
dc678436-8b2e-554a-bdd8-603298445375 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | HOLD POINT
45454c03-d5a6-5bba-9b22-f95726486821 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | 4 - Steel Reinforcement compliance
019dee33-5394-5f2a-a6ab-b2b763d15a0a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | HOLD POINT
5e98d746-6e9a-56b9-a2f5-1b6b49b31a69 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
64698d34-aa81-54dd-b46d-fce0c0cf4111 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | HOLD POINT
c7626b48-3b73-55e4-8d12-f69b1b5aedae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | 6 - Design Stressing calculation
3de456f9-31c9-5ce9-ac8b-b7725a10df8c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | A. Pre-Construction | HOLD POINT
22bcf749-3907-52b7-986c-95c59aa75932 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting
dd5a0d6a-e55b-56ef-bc74-5e603b263069 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 7 - Steel Reinforcement cage assembly
50b7239f-8705-5e93-aa5a-f8d8de96bfab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 8 - Mould Preparation
9688b76b-d331-5506-a235-d933447fe469 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 9 - Pre-Stressing
f4bc4892-1c8f-571d-96b2-32770a981592 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 10 - Steel Reinforcement Placement
b2c388c5-e922-5da4-88aa-8c0ec5df70ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 11 - Cast-in Items
d90de3f4-264d-5f1f-8d34-c4d7bd2c7ca1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 12 - Pre Pour Inspections
7c059dcf-f481-51ca-8271-89b00c99fd65 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | HOLD POINT
31918b99-97ea-562b-b007-dcbeb4a2d2c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 13 - Concrete Mix Conformance
63582402-d35a-5452-9f34-81b9a956f55d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | HOLD POINT
d944d084-68c7-5829-ae45-5164770d36de |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 14 - Concrete Mix Workability
d39b7616-7d8b-596a-aef6-23fbdd5b67c8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | HOLD POINT
75faa78b-2bd3-5bc9-9303-6ce24af4dacb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | B. During Casting | 15 - Concrete Finish
ef9d9d75-afc1-52d9-9c96-74dcdcdaaf5d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction
be9868f5-e4f2-5dda-8ee4-66f7c11726ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | 16 - Curing and Release Strength
95658411-e62f-5104-9bba-2fa34e174068 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | HOLD POINT
691b3052-828d-55e3-a878-9830e364a1fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | 17 - Transfer
9d3f96af-2142-52eb-9741-a8cdaaa6d2fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | 18 - Draw-in
c2bcea0e-1bb1-5d59-90ba-d20a05586357 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | 19 - Lifting
4c8768ec-5f04-5ea3-98e8-e91ec041a296 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | 20 - Marking
9abcc472-95af-5116-a401-16d4a7f9ba11 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | HOLD POINT
6584f790-172b-58c9-a018-e668ee5cbf5a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | 21 - Concrete Supply Testing
2f4de5f3-b8e0-57ae-9ecb-9a57b48609a5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | HOLD POINT
c7e6fa75-5ff9-5f2b-9d1e-3d689e5cf53d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | 22 - Post Pour Inspection
4cfb4bd2-8268-5336-a3a8-8238c8b396d9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | HOLD POINT
22726ba1-f1d2-5e85-a3ce-76e155236108 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | 23 - QA Package / Redline Drawings
e3f86f74-6d2b-54df-93c0-f10172771213 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A4 | C. Post-Construction | HOLD POINT
580fed22-4ea7-4f6e-aa06-4f2d4b983c54 |  | fail | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5
19107aa9-47a7-5b2e-9751-4177f86dfd71 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction
d603ea53-3d29-561f-911c-65d57998ff9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | 1 - Shop Drawing Approval
50bec2d6-5b8a-5e2a-8a4a-82cada7ac4f8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | HOLD POINT
08095169-8f91-5f4e-b7df-b8be83d5c8f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | 2 - Concrete Mix Design Approval
c694449c-1ffe-561f-bb4f-be36453fc0bb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | HOLD POINT
c10dd671-a1e5-502f-bbfb-fc42ed870191 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | 3 - Lift Design
70573189-3483-5479-8d55-f2b9932df439 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | HOLD POINT
7a68c2f5-43e9-53c9-8c71-6f9ac531fb17 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | 4 - Steel Reinforcement compliance
ef76f4bc-f817-57c5-9f64-1cb6803198cc |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | HOLD POINT
27020b71-dc0c-58ab-8d32-9d93d37b0e42 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
b91c836b-f806-5fc5-b93e-4e85a435fc8e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | HOLD POINT
0107b107-3bf0-5a58-a267-0990b3fddf26 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | 6 - Design Stressing calculation
c39702bd-1bd7-5eb3-9c14-e42ab36ed867 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | A. Pre-Construction | HOLD POINT
4f3ea492-87cb-5693-acfa-99ef36190efd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting
6a7f6481-a7d8-5e1b-b106-3b62375c875c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 7 - Steel Reinforcement cage assembly
a5a397e4-f7d1-5457-8b4b-c3d590e62cc1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 8 - Mould Preparation
f3de1a85-e7a0-5c15-ba09-999d20080ebd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 9 - Pre-Stressing
73e0e005-1a2e-5c90-888c-40da619f873d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 10 - Steel Reinforcement Placement
75446f40-5b0f-5c14-b52a-3aa0e52d2ef0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 11 - Cast-in Items
6b7a231e-9176-50b0-a07f-53d6bab2cfcb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 12 - Pre Pour Inspections
3b384e95-358e-5b2b-ae1a-f83d59791299 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | HOLD POINT
a0d23aef-577f-5270-9b61-1f455c34899e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 13 - Concrete Mix Conformance
f43ff071-018d-536c-8baa-0caf8351ef16 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | HOLD POINT
034b213e-a5e8-5fb4-a9ca-a9825de37116 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 14 - Concrete Mix Workability
50fb8a7e-9522-5e10-9f7e-a78ed12ea0ad |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | HOLD POINT
dc20b251-5653-5d3c-9eb0-756cfc86340d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | B. During Casting | 15 - Concrete Finish
0fc863b1-7d9d-5d6c-b5be-6355e08571fe |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction
24a56fc1-465f-5c71-ae86-8178d8a11d94 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | 16 - Curing and Release Strength
ac23fc76-c0c2-514c-92c1-895b645a5540 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | HOLD POINT
e5dc2d99-d5ab-562d-b41e-a1bf740e8758 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | 17 - Transfer
7a7ca88c-c55c-5a34-ac64-4aac79d61780 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | 18 - Draw-in
5f94beca-bfd8-5c06-a17e-34cbcea35ee9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | 19 - Lifting
dd1426d2-cd73-5107-a236-4459b6e1c15b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | 20 - Marking
9dad95c8-d8cb-57ac-9dfe-edb20c8f321e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | HOLD POINT
ae305bfe-10df-553a-a582-d693fb178c67 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | 21 - Concrete Supply Testing
f695ed5e-09d5-57dc-8527-bca59af88eb2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | HOLD POINT
b651fa5d-768e-56ca-addf-1a7b6f28e9d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | 22 - Post Pour Inspection
58f96a75-6a7a-579b-83a1-6d58af9b8b84 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | HOLD POINT
5a6588fe-48d2-5f52-bd9c-07be998d9e1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | 23 - QA Package / Redline Drawings
99110075-95a8-5f35-a33a-9790ea978a2b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A5 | C. Post-Construction | HOLD POINT
82f81a92-d715-44b5-be2b-6f65f4c61866 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6
cef94ae4-af6e-51bf-bcd7-3a82031946f2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction
b564bb79-c470-524e-81a6-d865fee8ecf8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | 1 - Shop Drawing Approval
023a5a2c-5b8f-5d53-887c-f0f1990d5e5a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | HOLD POINT
a240bcd9-3077-5b8a-a875-c136174503bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | 2 - Concrete Mix Design Approval
fca98e4e-e017-5cec-9305-869de740712a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | HOLD POINT
f79b6782-3181-5c04-8b8c-ef7d4039c24b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | 3 - Lift Design
75c538a3-b28e-513b-a464-f5789c40fef9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | HOLD POINT
d1b4d10f-83b7-5909-9f3c-03a385fcc35b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | 4 - Steel Reinforcement compliance
2bf8f435-0bda-5943-a5cc-cfb612973300 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | HOLD POINT
e0e64511-4c58-5289-9c6a-356e96df43a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
5846bee6-1ea5-55b5-ba24-496c0aa0774b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | HOLD POINT
6a598a07-5ab5-5dba-ba98-5b48c655700f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | 6 - Design Stressing calculation
d9ae0716-21a7-5081-b8e6-26bd61a8d032 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | A. Pre-Construction | HOLD POINT
70d59b79-8804-5a35-bdc9-0222a7c84b85 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting
7f6ac0a2-8e41-5878-8884-c42dcf1d8483 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 7 - Steel Reinforcement cage assembly
9051c2a1-539e-55eb-a3d3-3958292e8e83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 8 - Mould Preparation
87f01f14-e291-5145-acb6-7f3b9c20073a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 9 - Pre-Stressing
c35ac23f-b36d-518e-9820-c908b8a70943 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 10 - Steel Reinforcement Placement
13fddb04-0382-56df-9f7c-733bd374d30d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 11 - Cast-in Items
6391c17b-d7dd-5fc3-bdc0-b603ad361a9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 12 - Pre Pour Inspections
d967266e-9268-5ff0-8990-c9eec66d01ff |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | HOLD POINT
3e8f6d9e-1008-5e97-9da1-d42aa3c8fdec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 13 - Concrete Mix Conformance
37733c12-a4cf-50c9-aa8e-6450a776489a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | HOLD POINT
888d2441-a5c9-5a16-a978-4d21eda10697 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 14 - Concrete Mix Workability
25ab234d-cf2d-5025-b628-913dfb404da4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | HOLD POINT
492a5069-2581-5272-9832-7223c6a976e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | B. During Casting | 15 - Concrete Finish
224446d3-0c87-5389-a6e1-8291522fed0f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction
6686c8a8-ca92-5366-8316-1da088b21d85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | 16 - Curing and Release Strength
076fb0fd-b981-5a29-ac89-affdafbc1361 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | HOLD POINT
7d1f25b2-8074-5494-939b-054153fd9244 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | 17 - Transfer
f7cf191c-2016-57ae-9e30-d5c43b529564 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | 18 - Draw-in
a7e092cb-06b8-563e-a2d0-765d3faf3b57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | 19 - Lifting
e1178ed1-e294-5c46-b141-83cd7c0f86bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | 20 - Marking
8fc3f7b8-468d-5a00-b318-d621b30f4154 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | HOLD POINT
d2ec7cf6-84b4-5737-a153-4b8e1efebecd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | 21 - Concrete Supply Testing
c4033669-6172-51fc-96e4-c443bf03c1cc |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | HOLD POINT
094a116f-cd25-580c-8c7b-8e8597bdf976 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | 22 - Post Pour Inspection
a9a36dab-c2cf-5b18-a0a8-24673bd060e3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | HOLD POINT
f92c1f42-dca1-5cd1-ba29-952fe3960552 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | 23 - QA Package / Redline Drawings
3cc0a141-66c3-502b-90f9-e822de5c1f56 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A6 | C. Post-Construction | HOLD POINT
40c149a8-06c8-4163-a03b-0722ceec2313 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7
4b4e19a4-9f9c-5703-a9e4-c19877bea9cc |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction
b92f2b1b-25cc-5179-bdb4-1be029756935 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | 1 - Shop Drawing Approval
fb6217f3-5eab-5bc3-9c20-a28df80084a4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | HOLD POINT
c73c8c9d-272f-54d9-b1c8-85b182721a91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | 2 - Concrete Mix Design Approval
5b78b06b-f9c4-52ba-9e2c-ed9891ce967f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | HOLD POINT
66e71bcd-54d0-5888-affa-fcfc72b391d9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | 3 - Lift Design
ce2360e3-aa78-5ab0-9b7f-5f727fb4c562 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | HOLD POINT
963c352f-af3e-5090-96bc-9cc70a3cae6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | 4 - Steel Reinforcement compliance
cb2653cd-957f-5d33-9178-9f8ac6e8b021 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | HOLD POINT
6a353ef8-b212-54a6-804b-9ea1bb8ad97a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
44977e4c-b296-5b21-91cd-9011ea24b5ef |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | HOLD POINT
5ad6582f-cb64-5e48-87c9-58be017677df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | 6 - Design Stressing calculation
5c0e2ff5-0682-5662-9831-f44f053424cc |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | A. Pre-Construction | HOLD POINT
68c580ed-1396-51af-9a68-af9bbfd4000d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting
f3eefa70-d94c-5a63-85d0-6383ed2923f2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 7 - Steel Reinforcement cage assembly
1412d997-f052-5a2e-84a6-8382880c3557 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 8 - Mould Preparation
6d13693e-ade6-5487-b4f8-d8cd6651322b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 9 - Pre-Stressing
c645a340-a4f1-5189-ab04-152c11f019f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 10 - Steel Reinforcement Placement
9b2d4890-49b5-54e4-ad18-a6e7ba3387d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 11 - Cast-in Items
c9639ba5-67f1-51bc-86a5-06160e615b5f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 12 - Pre Pour Inspections
f22f7ea9-44f9-5e6e-b73b-ca247bf3090a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | HOLD POINT
75f43c4c-ec9a-52a8-bbfa-aeb2851bf75c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 13 - Concrete Mix Conformance
7a3502a5-8440-5204-a575-f91143f26ae5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | HOLD POINT
b17f377b-b372-5226-a668-fb26a4e44584 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 14 - Concrete Mix Workability
f0543bc2-6a99-556d-a0a8-f45836578134 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | HOLD POINT
44061713-b9d6-5621-9ebb-607893309c72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | B. During Casting | 15 - Concrete Finish
9531f4cb-aa12-5c65-ae48-50f99d697dc7 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction
4374d552-aae6-535c-9c4a-3c78137a4034 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | 16 - Curing and Release Strength
9dc8569e-098e-5671-ac01-1688fed98acd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | HOLD POINT
08767845-5de6-5947-9b68-a744d5500335 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | 17 - Transfer
54ef55bc-ca60-5119-9d17-270b157369f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | 18 - Draw-in
68cca2b0-1182-58f8-ad4d-bf1ada136514 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | 19 - Lifting
400afb33-7e5a-50be-b0bd-749ddb9af0c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | 20 - Marking
7bdb0072-828b-5c5e-82ab-6bbf5d0cb26c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | HOLD POINT
698db154-20d6-5d02-b0bf-a86c433aadf1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | 21 - Concrete Supply Testing
fb1d36c4-a3c2-5367-babf-19b13eac7de9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | HOLD POINT
f97db8ab-7612-585d-a15c-e446221c3aab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | 22 - Post Pour Inspection
81d4e684-9d88-532a-b15c-6dbc1b21e707 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | HOLD POINT
705e1807-7017-5eac-b116-5e8323510517 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | 23 - QA Package / Redline Drawings
4fc68d8f-64d5-52c8-832e-d0ec5092c0db |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A7 | C. Post-Construction | HOLD POINT
7faadb62-eb32-4ab9-94d3-51a4f79743f0 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8
b9176921-23bf-5fda-a4c9-5246e0476643 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction
c485bc9d-4c28-554e-9044-6a0dab160230 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | 1 - Shop Drawing Approval
04465134-d45c-58d2-a520-4e7085832af5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | HOLD POINT
313161c8-d965-549e-9a5b-be696540abba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | 2 - Concrete Mix Design Approval
b4d31671-6ec7-5620-b3c3-66e8b3602546 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | HOLD POINT
ceabd605-b070-5c5a-8780-5fa00ff5ef92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | 3 - Lift Design
67e10057-aa3e-5290-8b64-da0fdf5707fd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | HOLD POINT
29831632-1d9d-5e73-801d-7b30a4fd656e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | 4 - Steel Reinforcement compliance
3a49c186-a27e-5a68-b533-3e4d74f73331 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | HOLD POINT
a5feac1f-dccf-5184-91c1-89975c17b8d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
bf00c680-50d5-5f0a-9aea-9d8f7bdf3f55 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | HOLD POINT
e34a47be-2c41-5ee3-b31c-c1d08b3a5c14 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | 6 - Design Stressing calculation
f19b1ff5-e07a-5c4d-9dd2-a3db7f70191a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | A. Pre-Construction | HOLD POINT
361e43e8-9ffe-5f42-9a5a-249791e8b55b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting
257c7868-c65b-5bb8-9fa4-453a2746f9ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 7 - Steel Reinforcement cage assembly
fc3c1f24-dd63-5bc9-a6f3-88b0820f20c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 8 - Mould Preparation
d25293ba-7787-5c40-a70a-54ee02db0716 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 9 - Pre-Stressing
62c3943c-4673-5335-bd0a-67b7791c5548 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 10 - Steel Reinforcement Placement
1abfc399-6b53-5e8f-9aa9-349c2e77a7e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 11 - Cast-in Items
be4cb9da-4f99-5c09-ace6-bac1f5a22e89 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 12 - Pre Pour Inspections
0545f528-be06-5976-b0b0-700428637755 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | HOLD POINT
6919b3b8-33b1-5c46-8ae5-d0e531ba2d3e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 13 - Concrete Mix Conformance
37d021fe-bf1f-5da1-a1e4-eff3f8834084 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | HOLD POINT
d3590f4d-542e-59d3-952b-11e938b0cf7e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 14 - Concrete Mix Workability
3ab0245e-2c93-5408-a0a6-9bcbd3a00af1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | HOLD POINT
96d517eb-b5af-55c6-b4ba-c7ba874c65a8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | B. During Casting | 15 - Concrete Finish
374bcc9e-7162-53ce-80d5-3c05e837755f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction
3289a77a-56b1-5620-a4fa-bb1b94294f81 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | 16 - Curing and Release Strength
32cc1876-0727-5f39-84c7-07222737eff3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | HOLD POINT
d88ab464-bdf7-531e-86cb-714f731c89a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | 17 - Transfer
127fbc85-67c6-554e-bf7b-3aedf16593f6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | 18 - Draw-in
a84f2404-b27f-5548-ab0e-583cccfbd889 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | 19 - Lifting
0a88699f-72e2-5310-bfbc-fb89da4dc6dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | 20 - Marking
6717453c-9e38-5025-96b8-8c1fac4252e1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | HOLD POINT
fcb6b90b-6e75-59f0-ae86-b3c3fba0d206 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | 21 - Concrete Supply Testing
a65ee865-6c9d-5b30-b262-8ed450bf916d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | HOLD POINT
b8851344-0ce4-55d6-8305-8243912f2abb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | 22 - Post Pour Inspection
6fc1554f-d841-5239-bf53-0881d2001536 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | HOLD POINT
41e8a297-0971-565f-a628-e187bd917a2f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | 23 - QA Package / Redline Drawings
7b9aa379-1222-5d80-a591-a09db1334dc9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A8 | C. Post-Construction | HOLD POINT
7624469c-4b0e-413a-a986-56672d7438a7 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9
6a9d4eb9-f4aa-5f46-8d8f-1df42fa6de48 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction
13799f27-d7a6-585e-b8f7-7d395dc64369 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | 1 - Shop Drawing Approval
1a2e24a4-9142-5e3a-9b24-440a4bd51a41 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | HOLD POINT
4d083655-1229-5b93-9300-d81e14dcac36 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | 2 - Concrete Mix Design Approval
87710c29-f595-5e1a-b87f-23613fe0abd2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | HOLD POINT
fa392ee9-6bd6-5a39-9b63-5a999f090115 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | 3 - Lift Design
627f6c5c-2a85-56c4-971b-3a92321ea0aa |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | HOLD POINT
3e740d17-be26-524f-864b-62c6eca9b483 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | 4 - Steel Reinforcement compliance
8cc16490-6bc5-5ced-b0ab-09f77eb3a8d0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | HOLD POINT
20e9704f-2fb4-5005-9a6d-ba3c8a23011c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
ee3430e1-2763-54a6-9721-1992183ded07 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | HOLD POINT
93c2cc0d-a750-5bab-a88f-bee423ae3d39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | 6 - Design Stressing calculation
b3feca9c-c44e-522c-b520-7d6383bf83dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | A. Pre-Construction | HOLD POINT
d4958090-ead6-5f6a-ac86-4ceec83cc72c |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting
1ce680d8-e4cb-5c1f-b0c5-f05c7ef4484f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 7 - Steel Reinforcement cage assembly
ef199130-9e40-515d-beaf-4f6b86599233 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 8 - Mould Preparation
9e560b07-af16-58e9-8c4a-24d065e18b1f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 9 - Pre-Stressing
1569fb7c-7555-51fb-bef1-059df816d8fc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 10 - Steel Reinforcement Placement
72aaa108-aa9e-51aa-8779-ac0e1775f569 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 11 - Cast-in Items
0b2b19de-2506-545e-ab96-794985eb65b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 12 - Pre Pour Inspections
4d631a79-0343-5caa-b563-013398a9e469 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | HOLD POINT
af656786-d02f-549e-99ae-3b8a22aa6581 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 13 - Concrete Mix Conformance
4b98febd-115e-5eb6-ab7d-327e5f0d1e3c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | HOLD POINT
9b1de686-50f4-5c5b-95b4-4a13f897503a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 14 - Concrete Mix Workability
03ee5055-fcef-5275-9d3c-9a28f5a2bfd2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | HOLD POINT
97a8fe54-dfe7-5e1a-a8a7-63a5fad59e9d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | B. During Casting | 15 - Concrete Finish
6d93dc07-4189-5572-8614-7539e8d8d9e1 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction
dd8fff98-56b7-5f5a-8506-d8e69eda6cf4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | 16 - Curing and Release Strength
64c3b1ac-db7c-5c5e-ae5e-2c2493941191 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | HOLD POINT
e1c1d51c-aff6-5658-9d5e-798295342235 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | 17 - Transfer
a689d318-3a3c-5e0a-b5d1-d20b5ae38243 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | 18 - Draw-in
e94e1f22-a5c8-5ca4-a721-81ce8e4c94be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | 19 - Lifting
b5038b3e-b57c-5668-9877-e400372e2e4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | 20 - Marking
91e992e5-1b89-564f-a4d8-97fe93d40d73 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | HOLD POINT
04b10c6d-7b4d-5a5f-af4f-ee51e2882576 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | 21 - Concrete Supply Testing
d5206023-0cbf-53a5-81de-1852ce42afcb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | HOLD POINT
c043a8a6-b5de-540c-af16-c2b8b311757d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | 22 - Post Pour Inspection
3b771aeb-410f-50b2-82db-29a1ab0892b7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | HOLD POINT
fa2892ba-6f9d-5064-a5e9-e75596d4f21e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | 23 - QA Package / Redline Drawings
f14b935c-f9d7-542d-9eac-d0345d0f232c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span A | Beam A9 | C. Post-Construction | HOLD POINT
23f0c1be-f91f-4111-bac2-745e46ba4c25 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B
64f3dd73-0073-4b61-b236-1f2ec3f04ae3 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1
4aa65661-fe6f-55cd-8077-172af93c831d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction
01e96299-7104-5f1d-905f-fa910863671c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | 1 - Shop Drawing Approval
c73b1f7d-3531-5e99-98c1-4d0983fa09fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | HOLD POINT
923c6faf-696c-50a2-b5e2-3fb0947d6eea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | 2 - Concrete Mix Design Approval
631f3b0e-2392-51df-be9c-79baac229bdb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | HOLD POINT
4efc9890-0ef9-5111-992d-dd792a81aaca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | 3 - Lift Design
6744364d-17f8-534d-b465-893501d43731 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | HOLD POINT
3f41770a-ac59-5476-8582-5790e4a08d0b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | 4 - Steel Reinforcement compliance
f386426d-4c9f-58c2-8631-25ad11274e12 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | HOLD POINT
01889e9b-e2d1-58a7-ae1c-4f906cce798f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
a757e823-2ed0-5a7e-9abc-f6232580ccc9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | HOLD POINT
41af9b69-ff92-5312-bd58-e274ab675a8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | 6 - Design Stressing calculation
cf085163-c596-5fb5-a00c-2384314181d3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | A. Pre-Construction | HOLD POINT
39aea157-623a-5665-aa60-60e3aa2bc8e8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting
23e0d9ee-3d27-5ce1-afa3-5c41e6a103cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 7 - Steel Reinforcement cage assembly
3ea53d97-b562-58bf-b120-043a1a780cbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 8 - Mould Preparation
5a7a65a3-e83b-5dfb-bb2e-7780b79b9e55 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 9 - Pre-Stressing
cb800941-68ba-59a4-8c31-523513fa9c5c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 10 - Steel Reinforcement Placement
17593439-7058-523c-95ab-cbfd21c38775 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 11 - Cast-in Items
2469aa5a-98d3-5e52-97a4-1a5d93c1b672 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 12 - Pre Pour Inspections
65495e2e-d097-52be-a38d-90ca7808d221 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | HOLD POINT
c04a47ea-944f-5f87-9809-f8d1b957b711 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 13 - Concrete Mix Conformance
9efe68d1-5c6b-5255-ab3d-6dacbbae99ae |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | HOLD POINT
7059a22b-9da8-5bee-b510-50941e801fe4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 14 - Concrete Mix Workability
fffc6af2-52a0-506a-8d90-cfbf023bf90e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | HOLD POINT
6c5f0f92-2c4d-53d9-b772-367bb0715e79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | B. During Casting | 15 - Concrete Finish
ee952c0d-7da8-5683-aea7-d380cb7d3134 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction
4e07211c-9a7a-5bef-bae4-d48faa89eb60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | 16 - Curing and Release Strength
9921dbc8-bb5d-52f7-8b82-fa0848b59411 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | HOLD POINT
bcb30a43-e6da-5eea-af56-719737a46837 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | 17 - Transfer
78c4632c-4e57-5a08-ac5b-7a1d0a758f8c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | 18 - Draw-in
6d8e7742-e941-5526-9ad4-34a00424ce54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | 19 - Lifting
035f3741-9c2d-55a3-a8ae-01ae2ccc0ed8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | 20 - Marking
117019a9-8f87-54d2-9e8d-7697680672b3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | HOLD POINT
49cdce23-bde4-5718-aece-58446051913b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | 21 - Concrete Supply Testing
1ab8c8e8-3d55-5327-ab6f-525e1bdbdf7e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | HOLD POINT
7c12a75e-ef42-5edf-8188-b8774920b31a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | 22 - Post Pour Inspection
de2d0478-cc41-5b68-9644-db2ca76f0ae0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | HOLD POINT
b8429180-5e02-5c10-9ce0-04467dd54023 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | 23 - QA Package / Redline Drawings
9f99b536-c287-59ee-8795-dab4b0ab3cf3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B1 | C. Post-Construction | HOLD POINT
39aae016-494b-473a-897f-b7dca87a1c67 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2
28401793-a674-58eb-868d-8b0cb1fde115 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction
02b7374b-3164-5757-bef3-2cb6a0ea8e66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | 1 - Shop Drawing Approval
2f87bf10-b47c-56a4-94fc-532d6b2a281c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | HOLD POINT
50c743d8-7515-522a-88d5-f4b90d7b6284 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | 2 - Concrete Mix Design Approval
462091a8-bae0-5975-9f27-f7a1ce343c22 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | HOLD POINT
466545b8-2eed-5ddb-bc74-55f852d121e7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | 3 - Lift Design
a44fc08a-88da-5393-85bf-d6b046211325 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | HOLD POINT
1e8a39c4-81ae-53f5-bf9a-11b1ba0e4de5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | 4 - Steel Reinforcement compliance
077c0f87-7fb2-52a2-a24e-658dbf0a9882 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | HOLD POINT
71410f22-f2fe-5d47-ad88-282e082a2a8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
ed0ff3dc-38db-5572-a4c4-be2a1a87787a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | HOLD POINT
9121f31b-21bd-5759-857e-b2b68182f01c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | 6 - Design Stressing calculation
0c42cbf8-154e-5f5e-bd28-f5a5c36783b8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | A. Pre-Construction | HOLD POINT
17f83fc6-e016-5e59-9d0a-658dd39bea6b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting
7f76d96f-cced-5240-8405-83431d7bbfe1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 7 - Steel Reinforcement cage assembly
b5b39ed3-74fe-50a5-ace5-bcc01882d14a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 8 - Mould Preparation
9e04444a-5ef5-5a08-9c8a-2f70608d5127 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 9 - Pre-Stressing
c9106515-bec7-5b2c-a7c2-ff583679ce90 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 10 - Steel Reinforcement Placement
b03cb972-0bcd-57d7-bb4a-d5c2bf48d8d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 11 - Cast-in Items
1db9d5b4-9104-5ab1-88f8-1cb50bdc1b99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 12 - Pre Pour Inspections
b32c40e5-d5f2-5a8c-b10b-56d16cb79d4f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | HOLD POINT
4002a3ec-4c9e-5168-9973-08822a0bf950 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 13 - Concrete Mix Conformance
82e6d607-4a30-5d89-bc00-00e61fa93a5c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | HOLD POINT
1fdf52eb-4d31-5452-85cb-40f103d01637 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 14 - Concrete Mix Workability
f1713955-4248-5d7b-9424-d50454313077 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | HOLD POINT
383e67e3-8012-53da-931a-10605bc67b3f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | B. During Casting | 15 - Concrete Finish
62a5ded1-89db-5884-9432-3c6ded858fe7 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction
99254a69-4ad7-58a5-8d37-d95c0772e7e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | 16 - Curing and Release Strength
1a071bca-5204-5f51-ac73-f1bcf3b0475e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | HOLD POINT
dfa4646b-f1b0-510b-8633-59ecb65cdc4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | 17 - Transfer
14aad759-54fe-59af-9ebe-70011f89f506 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | 18 - Draw-in
0db57786-ed62-5997-a211-4dde582029b7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | 19 - Lifting
6838c8d8-42c4-59b7-a35e-66182dbd8243 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | 20 - Marking
5af23237-ce7b-5275-9634-bfc3efcecd5a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | HOLD POINT
20027462-10af-56ae-9fe5-4e57d3725709 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | 21 - Concrete Supply Testing
8e155402-cd0d-51dd-935d-5d3fe4cb5499 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | HOLD POINT
e2a6ccfa-3850-5de3-821d-e66112c73ef0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | 22 - Post Pour Inspection
b1926477-bb60-5965-98c1-6fb59ee99ce6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | HOLD POINT
c463aef2-470c-50cd-bff8-a254791c3438 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | 23 - QA Package / Redline Drawings
0f063eaa-f7a7-5027-9087-ba58d4712202 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B2 | C. Post-Construction | HOLD POINT
20dc0a63-ebc5-4256-8033-7ca85eac891e |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3
bad4bae0-6b6b-53ac-a5b0-232e3bd73dd0 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction
49f4822b-6096-5784-8442-5899ca7aca52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | 1 - Shop Drawing Approval
23964033-5002-52c8-9bec-1cffb6d1895b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | HOLD POINT
247812e4-220e-554e-8725-687c1eb71adc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | 2 - Concrete Mix Design Approval
ba23b7f4-c996-5cd8-8ef6-446726593503 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | HOLD POINT
b8386d4a-cad6-5ffa-b400-d1f582c2f8d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | 3 - Lift Design
38692be7-40d5-5cce-a1d6-8a6016326d62 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | HOLD POINT
76411d39-a1b7-5b01-8eb0-82ba527ac191 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | 4 - Steel Reinforcement compliance
b9d1423b-a3ca-56e1-974b-c91d5959fdf9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | HOLD POINT
cd2bfc89-239f-536b-a3fa-60cfd68fa90a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
7bc8e7ce-1f92-5839-af15-25f23b6eb0dd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | HOLD POINT
7a6f5a11-d12e-5181-9f75-b0cca7b54a04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | 6 - Design Stressing calculation
a9ae0c8e-0fdf-53d0-933c-eca44218f3ec |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | A. Pre-Construction | HOLD POINT
88f16031-dc15-5264-971a-5a7265e39b3b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting
9172d500-0a3f-5155-9864-e3dc20e9cf04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 7 - Steel Reinforcement cage assembly
febc8561-549f-5868-a151-ca7b4e89670b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 8 - Mould Preparation
a7d86e3e-5a9e-54e6-a7ca-2cc396fe5e54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 9 - Pre-Stressing
d8324c76-0d44-5b93-b7e4-52737996dcc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 10 - Steel Reinforcement Placement
1a025b3c-268c-59df-be61-87957292d120 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 11 - Cast-in Items
064f7c6e-fdb4-5947-b90a-98ea21c3b53e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 12 - Pre Pour Inspections
605277d7-e9d6-5227-9ad6-b195be1c3c69 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | HOLD POINT
48464d4c-f596-54d7-aa86-159a30725356 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 13 - Concrete Mix Conformance
86ff9e72-e8c6-5e8a-8600-83ecc3c831bf |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | HOLD POINT
b11f0f22-1d16-5849-a551-948dc7893257 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 14 - Concrete Mix Workability
eab32a83-64d6-5c02-bcd7-412d19a6ee60 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | HOLD POINT
a6320ecd-7880-5664-83b3-021a62d30d33 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | B. During Casting | 15 - Concrete Finish
d04cff38-5883-5b40-ab1d-d3182790f4f6 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction
64d7b25b-eb05-54fc-9316-b2c0bb264d57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | 16 - Curing and Release Strength
e62ec1ea-1ff9-5acb-92c8-d35cfc8da2c8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | HOLD POINT
3a4433dd-031b-516a-81d8-3702b9e7b2f9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | 17 - Transfer
5ab80a0b-37fe-59e6-814b-aa4f6880dbb3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | 18 - Draw-in
f7434d37-7567-53cc-996f-798ac95f6abd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | 19 - Lifting
6a6f9834-123a-5ad7-9afb-234ac4e225ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | 20 - Marking
4e733be0-a745-560f-a160-6bebb958c390 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | HOLD POINT
57e1f180-e6d2-511f-b3b4-cc863599cb24 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | 21 - Concrete Supply Testing
d096534e-8a85-50dd-bcc9-50b9b818b14d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | HOLD POINT
c8dcfb35-9d3a-5f51-aaf6-ef567324bf4d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | 22 - Post Pour Inspection
88b6b97d-07a8-5e75-9615-90aaaf397ec2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | HOLD POINT
94df045c-a6a4-58e0-b93c-b1dab84aacfa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | 23 - QA Package / Redline Drawings
d6de4674-2e3b-5636-8f2a-2e2f3e1d1c7f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B3 | C. Post-Construction | HOLD POINT
8e3b0d3c-d1ed-4345-a35d-273efb481cfe |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4
ce637326-4672-589e-88d4-89ce2bcc56fe |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction
2c7c9312-de56-5031-8441-31b7f630f47b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | 1 - Shop Drawing Approval
e61cf9dd-122d-51fd-b416-e90760ad4e8c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | HOLD POINT
74118e87-daab-5499-93af-efb41d0b22ca |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | 2 - Concrete Mix Design Approval
69f7b4af-afb3-5809-b055-62be7ab3b821 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | HOLD POINT
893d7696-4659-57ff-8e1a-34b0c802afe7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | 3 - Lift Design
91c259b1-c0ad-548e-ad0f-778c41b417f3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | HOLD POINT
200568ed-de61-5b60-9eac-e16ea1cbaa66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | 4 - Steel Reinforcement compliance
b8d65803-6ee1-502c-9387-6753313a6dcb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | HOLD POINT
61faa7a1-980b-5ce7-bd6c-7fe8a793d3b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
2335c9a9-0ab6-5c69-9e45-01edd22f4512 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | HOLD POINT
3472d7ce-de4e-52fc-8de9-da6c659775d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | 6 - Design Stressing calculation
aee34511-05a4-5255-90a2-2761519719a8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | A. Pre-Construction | HOLD POINT
40a59b9b-051f-5864-9580-86f30f52a057 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting
9a40cbc5-954b-5880-a363-7347f3a64e15 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 7 - Steel Reinforcement cage assembly
07c6f186-82ae-5fe9-87db-eb7fd178bce3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 8 - Mould Preparation
6fac4c70-9c73-57fb-ab0b-3d59fd16b248 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 9 - Pre-Stressing
38b1f7b6-c7bc-5f13-a9cc-0e74034186c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 10 - Steel Reinforcement Placement
8c421cf3-6830-539b-81e9-a6a8cb0255e7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 11 - Cast-in Items
7c7ea3b1-b17a-51a7-ac9d-81d88b76b136 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 12 - Pre Pour Inspections
b38761dd-dc89-50aa-886a-d13321c41d09 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | HOLD POINT
bbf21e7e-7bbc-51a2-bf0b-10369cd05369 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 13 - Concrete Mix Conformance
fffaa1e5-80bf-5621-b66d-67881c7fb538 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | HOLD POINT
ea39f237-079e-5534-abf9-644bf94e66ab |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 14 - Concrete Mix Workability
cde8189c-2dc2-5d88-a416-3b69c2709d40 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | HOLD POINT
ec273fdc-73c0-564a-bf57-44df65d9894f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | B. During Casting | 15 - Concrete Finish
4c5b2e3b-17a2-5460-b45e-7d86f459e9cd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction
4970efa2-1464-5810-b2cf-f0b698e540ce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | 16 - Curing and Release Strength
bd4ed4b5-bbdb-5e4b-8742-a9a43007b612 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | HOLD POINT
71a63883-e209-5135-ba13-64a5806fa634 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | 17 - Transfer
30566a1f-b5dd-50e2-859b-35eafbb7e874 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | 18 - Draw-in
7abd7312-1de8-517c-b7c8-038fe5800cc4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | 19 - Lifting
90ed95c0-bd9c-56af-98a2-3adcd9837101 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | 20 - Marking
8381a63c-bc81-51b0-9757-d71a2f70fdff |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | HOLD POINT
09dc47c5-e59d-54e4-a78c-c4e81066e030 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | 21 - Concrete Supply Testing
28ecfc68-af6e-59d3-859f-ff729486e7b1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | HOLD POINT
dce0ef97-5d39-5643-96b5-792b9e2b4ecf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | 22 - Post Pour Inspection
eca07786-83fa-51ac-ad8e-0dde3fb8e252 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | HOLD POINT
e2c81f40-9d1d-55e6-9141-172d8e2542cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | 23 - QA Package / Redline Drawings
c47d569b-3f8f-5e44-b8f0-df4ca3c531cb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B4 | C. Post-Construction | HOLD POINT
d4797f4c-3efd-4c46-a393-2825cd171608 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5
f34c6ef7-a7e3-502a-b1c7-21442271d477 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction
8a34ddf0-c3ae-51c9-a296-50cd9c636769 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | 1 - Shop Drawing Approval
49f1c4d2-a109-58ed-aaae-1e36aba2d2e9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | HOLD POINT
d9ecda3d-5e8b-5979-a071-6967881adc51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | 2 - Concrete Mix Design Approval
fbdebe5e-d0b1-5e63-a034-758620a0a17e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | HOLD POINT
59615ff4-16aa-53ac-b1df-c3378dfada60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | 3 - Lift Design
4b80d791-e3d5-534d-866c-98d33e76582c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | HOLD POINT
5416833f-c611-5940-89b6-384b09113951 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | 4 - Steel Reinforcement compliance
429ad12e-3e1f-5c32-afda-84649fbe779d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | HOLD POINT
7944a240-1e1f-562e-9514-1a085970a489 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
53f14aa4-4b3b-5ccd-bfdb-26453f781c5c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | HOLD POINT
6ee5cd4c-b85c-5d5e-b0b3-72cda5ccf8b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | 6 - Design Stressing calculation
8eeeeaac-c30c-535e-81ea-52db439bd4c0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | A. Pre-Construction | HOLD POINT
3e6b9080-2f37-5c88-965c-3f96970e9ac8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting
22aedf98-17fe-54cb-b5fd-b5137f8dfb74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 7 - Steel Reinforcement cage assembly
3b8ace79-39a4-55a3-98fe-c19ff1850f80 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 8 - Mould Preparation
26ca305e-1bd5-5626-8e6a-89abfb4beb01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 9 - Pre-Stressing
238e3dd1-6df0-5802-b5e7-b4f066816f87 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 10 - Steel Reinforcement Placement
94a3ed5e-c53f-5ab5-be94-e58cd2a8d1e7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 11 - Cast-in Items
63e2b8f9-0c60-5ac5-86ae-09de1d48ec79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 12 - Pre Pour Inspections
3cb7d9f9-6e4d-5e36-8ab9-fb49a0aa8f64 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | HOLD POINT
826cb99b-c878-5f3c-b44b-63317525ecf5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 13 - Concrete Mix Conformance
6e78af10-f549-551a-8d73-6b7c1da819b0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | HOLD POINT
d2ba2dec-ed9d-5029-8152-9b9c942a5e47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 14 - Concrete Mix Workability
35ccef9b-07a6-5598-9fea-254f5c642f3f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | HOLD POINT
8e631ecf-cf55-564c-b8f2-905e51b39844 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | B. During Casting | 15 - Concrete Finish
011024d2-9792-5209-a880-fbf1b6363138 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction
2fae65b1-115f-576c-927d-06c953375388 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | 16 - Curing and Release Strength
6bafb9e0-d62f-5c31-bfbe-ffb0f82e7ffa |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | HOLD POINT
2234a0c4-ce01-518e-9aa2-32554ae31089 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | 17 - Transfer
a0f5819a-1287-5f74-89b7-45e610eebb3b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | 18 - Draw-in
b8c7c140-5caa-57b8-8b13-3437f27ae670 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | 19 - Lifting
2e6c39d3-82cb-5867-8d40-1a3ab1e4b038 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | 20 - Marking
16c83a56-b58f-589c-b93a-fe9716018cba |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | HOLD POINT
6ef283a0-89b1-564d-8cc3-d01f668ee22c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | 21 - Concrete Supply Testing
46977815-e19f-5b0d-9133-f69a44c4174d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | HOLD POINT
9aa7bb2d-9635-5eb5-8399-92197318e072 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | 22 - Post Pour Inspection
acebbd70-dbb5-5fcc-9a9a-31adcde58911 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | HOLD POINT
256928e6-131e-506b-8872-95f1664f6070 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | 23 - QA Package / Redline Drawings
464f4767-9a47-556f-87c0-e47a7b90cdd4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B5 | C. Post-Construction | HOLD POINT
1b6eecfe-3f39-4f97-b183-90ea1d2c3d60 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6
4616b81b-7f52-505c-bff8-d0981a837102 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction
0628a263-f785-577f-a39e-1c0f8ca6b0fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | 1 - Shop Drawing Approval
7acb5d0a-d11e-54d6-aedd-4cfac2597ac4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | HOLD POINT
a04cff24-38da-5c7b-9bc6-8223c5473dd4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | 2 - Concrete Mix Design Approval
c28906dc-7198-5c7a-b35c-3a79fd6e2595 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | HOLD POINT
7f1a7f7a-658c-5673-92b6-fcc42d26759e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | 3 - Lift Design
8df3f942-d711-53b0-94d9-0b8f7ea80110 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | HOLD POINT
d11e7c73-11bd-5999-9858-b6a7d5db242e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | 4 - Steel Reinforcement compliance
f584449c-879e-5e4c-800f-1bf3efaf26b2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | HOLD POINT
b3c61aa3-648b-5ee2-a897-ac1c53143558 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
72187485-c0a9-5c67-a117-c305cd3b274d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | HOLD POINT
d6f07ebc-b372-5fe9-bec9-f7afbe93845a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | 6 - Design Stressing calculation
2ad8443f-a1bc-56d3-9e1b-cfe69b2153d3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | A. Pre-Construction | HOLD POINT
00410e23-8a7d-5341-86f4-85be5311f8af |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting
82232118-fafa-5e32-ba2a-04a009d14efb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 7 - Steel Reinforcement cage assembly
fa40dea8-4a70-518c-8f84-e4e70dde820f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 8 - Mould Preparation
5bf2a634-13e6-577c-b7b1-61f431f97165 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 9 - Pre-Stressing
20d9a4e5-7d7a-5a77-a6f1-b02417b8f32f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 10 - Steel Reinforcement Placement
3397da34-b438-5ff1-a62e-cf010804a2fd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 11 - Cast-in Items
d2b305a9-923b-5f11-a625-a23ffeb4043e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 12 - Pre Pour Inspections
dec8fdd4-4bdb-599a-9b89-e2bbdcd0ddb2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | HOLD POINT
f9c06446-5895-527e-8525-f2bc74dd4f95 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 13 - Concrete Mix Conformance
e532b721-f5d7-5487-a9d4-07506d83a686 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | HOLD POINT
8bd3519c-c77e-5a43-9b80-149175900e6b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 14 - Concrete Mix Workability
ef259a16-d0d4-5c3f-8f8d-4c5fb2fdd4f2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | HOLD POINT
4b74fdc8-05c1-5f48-96dc-d8d8dcb81a16 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | B. During Casting | 15 - Concrete Finish
21d1719d-ab7b-5be9-83f5-2134d979cfae |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction
d74546d4-40a2-5db1-92fa-3523d2887c8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | 16 - Curing and Release Strength
3289d35a-17d4-5c73-89ae-6bf573d443e2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | HOLD POINT
927373df-9416-54cb-b587-ddf8a8ae34fe |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | 17 - Transfer
b57908f5-d611-5c5a-9911-11c70fe31a0f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | 18 - Draw-in
17d8bdc2-a11a-5222-a7cd-76f3ce2c7cb9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | 19 - Lifting
1e687f0f-5e87-50a3-a378-894f1cfe3e57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | 20 - Marking
33503bce-621e-5b3c-b873-ea17c86c5341 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | HOLD POINT
e9371496-144e-5d2c-a5da-38af2b3aebce |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | 21 - Concrete Supply Testing
a25bceb0-2faf-50c2-babd-9a4dcdd18f97 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | HOLD POINT
5033d036-5939-54c2-99b3-7ac4458aa7d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | 22 - Post Pour Inspection
263418e8-f354-5d6c-87f6-2731c0e26ef4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | HOLD POINT
cc885db7-38ed-53be-b0af-280a78d3e995 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | 23 - QA Package / Redline Drawings
7227fa7a-1093-5746-9703-ae60fff49597 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B6 | C. Post-Construction | HOLD POINT
c2f02383-5f46-445a-a4db-4f8cd16fa82a |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7
08ba20be-76a8-5f22-ba73-eae33b99b4c6 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction
1c51bc13-6878-517b-a983-b1d1b8acc6ae |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | 1 - Shop Drawing Approval
5541f111-be12-5a93-b851-65b448873faf |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | HOLD POINT
45f73f07-1dea-5f71-93a9-b99790718116 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | 2 - Concrete Mix Design Approval
f7413bd2-8268-50c7-9e71-30edcfb220c9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | HOLD POINT
44cd1ed7-9726-5795-af4f-eccfa2f1fbdc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | 3 - Lift Design
b70652d4-a5c3-5720-adc9-7a4ebb8c316d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | HOLD POINT
7b0f8da5-495c-5615-afb2-96fa1d2dee49 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | 4 - Steel Reinforcement compliance
fc4f2704-a172-5c16-a472-c8716ed4e551 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | HOLD POINT
cb8a01fb-0ff9-533c-9c4b-29df7c6bf2ee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
28be1853-a71f-529e-bdcc-a14f01dae6f0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | HOLD POINT
a8952a77-972d-5f42-88f7-6cc2c04d4b92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | 6 - Design Stressing calculation
03de58dd-6674-590c-a254-1f096fc16cf0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | A. Pre-Construction | HOLD POINT
3eb6787e-7d34-51fd-a2b3-e9f11cb18118 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting
125454f0-860e-50b0-99b9-716475fd3c13 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 7 - Steel Reinforcement cage assembly
aeacdb50-7f16-56e9-b425-cd1be294d16b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 8 - Mould Preparation
4baa3f63-a534-5184-8d93-c76abd6a7677 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 9 - Pre-Stressing
f6c27340-4468-5e56-b513-73f7e8c958a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 10 - Steel Reinforcement Placement
922d8bd2-e09c-57e4-a3d0-800fd6abc804 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 11 - Cast-in Items
86867087-b7e1-5bbc-bfa6-58079c5e029c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 12 - Pre Pour Inspections
b945a5e4-f153-5df2-9caa-39720e403d5d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | HOLD POINT
9bd46709-8c6d-5aad-b866-02d5facba00c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 13 - Concrete Mix Conformance
2d2678bc-8e93-5205-8e9e-9a5cfdea274c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | HOLD POINT
0bbc43f8-2e72-5c13-872e-88e840fa8c07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 14 - Concrete Mix Workability
13fdd566-8678-5539-988c-56bb95538d86 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | HOLD POINT
d5f146b3-2a26-5f67-9c3e-c1f2066c430a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | B. During Casting | 15 - Concrete Finish
fbad1ae7-40ad-58e9-b7c4-6fbcc9399a2a |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction
1aa04e95-9215-533b-974d-eaa3af76089a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | 16 - Curing and Release Strength
e52cdf79-acba-5b34-adc3-53c48f520f38 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | HOLD POINT
e41e5958-362f-5db8-8394-fc147dd762d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | 17 - Transfer
f12931db-c16b-5c3c-9977-d7dbe88199d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | 18 - Draw-in
47903de8-45b2-55df-a5f5-4c265f089ba5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | 19 - Lifting
b4dbab67-bead-5012-92c5-4f4be4e0277f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | 20 - Marking
fe5212b8-d467-54a1-a236-9eb6c6170454 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | HOLD POINT
622c5aaa-0c80-5ec0-8b0b-c9c4dd71c4cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | 21 - Concrete Supply Testing
78834d4f-9f2b-5d7c-9811-133b28a2a509 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | HOLD POINT
fb2a1f18-da25-58db-934a-6abeef1073aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | 22 - Post Pour Inspection
0b57c8c1-9566-50c4-8735-72e6163aa7b3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | HOLD POINT
ca67f8f8-9d10-5f8f-983e-d40523a21ca9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | 23 - QA Package / Redline Drawings
647de6d0-2265-5932-b27a-e35e6cecf9a3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B7 | C. Post-Construction | HOLD POINT
87034fe5-5942-42bd-9f6b-383f0b9b7af1 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8
1ccb8bdb-ef89-510d-bba7-de7db5afcd5f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction
3b881290-514e-5325-9285-84cf4f75ad59 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | 1 - Shop Drawing Approval
651258da-55e3-5169-aa3c-a18770c84166 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | HOLD POINT
1d28dbc3-9008-545e-bffb-914da99f93ff |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | 2 - Concrete Mix Design Approval
7a03e198-b043-59cd-a3d2-6c9ca0fd17e0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | HOLD POINT
49aa3604-5882-5fb1-81c3-85f8c41fd675 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | 3 - Lift Design
bdda9638-5ec4-5e4d-a4df-d29c2a938a2d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | HOLD POINT
d0b98f3e-93d5-55c7-9fd6-f14961bf9739 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | 4 - Steel Reinforcement compliance
113b98bb-de6e-58c3-88e0-50a519849b3e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | HOLD POINT
e27de28f-92ca-52d6-b4ef-6b7a6ce55d5a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
e2e8091e-afb3-5c72-9ed5-23467b9c16d3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | HOLD POINT
663bc3d1-9824-5370-8f92-667e2f58df1b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | 6 - Design Stressing calculation
ea619ab0-c550-500b-92c6-0dde5dd04af2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | A. Pre-Construction | HOLD POINT
580315e5-6b2c-50ee-9a71-dc82d0ca03b2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting
41dede99-315e-5dd3-9cbc-f40c5987b034 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 7 - Steel Reinforcement cage assembly
e6c73741-d415-55f7-a0d5-31bf0cbec56c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 8 - Mould Preparation
cdd297d3-dfc7-5412-abc8-3f1868cee849 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 9 - Pre-Stressing
ea54f18a-8c32-5814-baf2-ad958859581a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 10 - Steel Reinforcement Placement
f00635c9-254c-5a92-aacd-7c42de536132 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 11 - Cast-in Items
dfe599fa-1d33-517d-baa7-fb060d162155 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 12 - Pre Pour Inspections
ec651afa-5752-584c-bb1a-50b44aa90809 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | HOLD POINT
a4ccd985-983e-553f-9978-f4d086c3883e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 13 - Concrete Mix Conformance
17501a73-8ca3-5aa8-8841-05a97da02c86 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | HOLD POINT
803e6c1e-071f-5a8e-a5e5-11cc12770100 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 14 - Concrete Mix Workability
816f4f1c-37f7-53fd-ac30-4cd1bfe995e2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | HOLD POINT
c13093f6-49c3-5cbc-b7ff-df611895d549 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | B. During Casting | 15 - Concrete Finish
eee70790-beb0-527b-8d2a-32423de20357 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction
6d6faa79-ea14-5647-bd62-0928fc38fdcc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | 16 - Curing and Release Strength
7636629a-e455-54b1-9aba-73f249bd7e9f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | HOLD POINT
f3654198-1831-5eff-9a27-dddeacf90a56 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | 17 - Transfer
191d4fbf-599c-5df7-bbfe-936244ebf3c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | 18 - Draw-in
5f98b2d9-d95e-5288-a79b-1d6fefb93c32 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | 19 - Lifting
346d35b1-5669-5b79-8d02-7eb0522203c4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | 20 - Marking
a6001068-e571-5a3e-8f53-c3e02c6c5ac0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | HOLD POINT
787a19fa-13ca-5580-b354-cd9d93560177 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | 21 - Concrete Supply Testing
cf6de117-ea23-5379-818f-0f743692d34f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | HOLD POINT
38ecc5a4-4055-54b1-8ff5-d199871eafc7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | 22 - Post Pour Inspection
1441524c-4f71-5eac-91a1-a353ff96ffe3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | HOLD POINT
da8eaa7b-1e71-5e10-ad5c-4ed3faf35be2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | 23 - QA Package / Redline Drawings
d83c80ea-eb1a-5805-8685-886772389138 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B8 | C. Post-Construction | HOLD POINT
870a4742-23cb-4126-9200-249f1ffd1eef |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9
6736a06f-bd0f-5591-a51b-a5b2c6c3406a |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction
3c088e31-b62f-5eaa-ae38-2f0aacf457da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | 1 - Shop Drawing Approval
10fe1293-8a4b-5858-9eae-534d2aacdd9b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | HOLD POINT
00a2b679-a407-5e6b-b866-0b7d1e0d481e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | 2 - Concrete Mix Design Approval
ad110f74-3ffe-5ffc-8adf-38af998f9fcd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | HOLD POINT
b2055483-eeb4-5310-a0ea-8782ee29507e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | 3 - Lift Design
75fc9858-6fb2-517f-bd01-18d9951dd8ca |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | HOLD POINT
bc61d505-cdb0-5530-b5d3-1cbec3220195 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | 4 - Steel Reinforcement compliance
dfea0bfe-f309-52d9-9e16-ed19144794b3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | HOLD POINT
8de5de52-a42d-5dc1-825f-9f79c5a7d548 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
676112e1-80bc-5c44-a25b-976ef4ad1258 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | HOLD POINT
1aa1fbc7-3e66-563d-a229-fcecd74b0362 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | 6 - Design Stressing calculation
604fbf6b-e009-5103-a8f6-e049da989ba0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | A. Pre-Construction | HOLD POINT
b663a018-fa83-5885-a9c5-b89dbbacbe84 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting
89f34cf5-7daa-5e26-91da-3988c1b401c7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 7 - Steel Reinforcement cage assembly
2cb19955-2fdb-5c9f-a7fe-af911835a0dd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 8 - Mould Preparation
e7d90127-c453-5ce9-a901-198d33f1740b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 9 - Pre-Stressing
f9352cc2-3c96-5b47-8e73-32fb621619c5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 10 - Steel Reinforcement Placement
62e8f4d3-3564-5d1e-97a3-936d0e4d5734 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 11 - Cast-in Items
4301badb-8748-54bc-bd76-6452fc6575a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 12 - Pre Pour Inspections
89698476-b4d8-55db-a7e6-2de31eebce23 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | HOLD POINT
27c4c27c-3e1c-5643-8cfd-2a5d505cdaf4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 13 - Concrete Mix Conformance
52ceea9e-f58d-5be3-be04-882ed67ddb0a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | HOLD POINT
f156693a-f1aa-5ba0-b409-1169cbd00b09 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 14 - Concrete Mix Workability
4a4ed49b-f97e-5858-83e5-327e3b15f410 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | HOLD POINT
567680a4-87fa-52b2-a080-896717e0c4c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | B. During Casting | 15 - Concrete Finish
169c1e44-6d83-578f-a196-b31f9dc1438a |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction
f372b12b-042c-5cdb-a2f8-2be7d891579c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | 16 - Curing and Release Strength
28bf9f13-52da-5165-b1dd-3cc2d5f8ba76 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | HOLD POINT
e787a311-021e-5766-bce2-e762343936ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | 17 - Transfer
fad778fc-8d35-5585-b615-74068d72f5a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | 18 - Draw-in
d61fa697-dedb-5e4f-8065-a68753a6c081 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | 19 - Lifting
f45c6a46-572e-57ad-aa51-b32a3d678c49 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | 20 - Marking
96d73a29-b6ad-55a5-9e58-9b95b28041ad |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | HOLD POINT
fa473bcf-bde1-59bf-bdd2-62e750dfcc27 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | 21 - Concrete Supply Testing
b8da083f-67e2-530c-aa82-b2093cf93f71 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | HOLD POINT
4ed77aa0-bc9c-5fce-80ae-83d3d8eeff3a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | 22 - Post Pour Inspection
71ee5848-fc91-57e7-93a6-fa7ca63a31ee |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | HOLD POINT
fbaf2e0d-c73f-5c8e-931d-9a3e79709d76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | 23 - QA Package / Redline Drawings
8487212f-2df7-5cdc-81bf-b2f346127807 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span B | Beam B9 | C. Post-Construction | HOLD POINT
3b4ba5ef-aa80-4dae-8e53-855c4ac68049 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C
0fac8c70-94fd-45e8-aed2-178cea1f3bd7 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1
54b0a9da-e5ee-516b-ac2b-ccfa87a09718 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction
5fecd33b-6756-5c40-9672-aba92ddd71cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | 1 - Shop Drawing Approval
3e70d689-1e46-522a-a7bb-8d55f77d54e5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | HOLD POINT
d8281941-0db2-5514-bb5d-5da18da5c77d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | 2 - Concrete Mix Design Approval
24e064dd-0a2a-5be1-8944-d489843966bc |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | HOLD POINT
3bb8996d-a63c-57fc-943b-e0bb85543d9f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | 3 - Lift Design
9130f1b2-6553-5bd3-9b0a-c32dffc6b230 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | HOLD POINT
b2b10698-289c-5b71-a91a-b173ee737805 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | 4 - Steel Reinforcement compliance
9b5c9a66-d57a-5948-ad8d-d0c927af4d61 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | HOLD POINT
4af8e7fd-69ae-54f9-bf9b-3677d9759264 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
03b5e35f-ea00-5cb6-9d5e-b8dff937c387 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | HOLD POINT
824ac754-2e9d-5fae-b768-87446201d579 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | 6 - Design Stressing calculation
283d56a2-e2c2-588c-a601-ffb56ff37fb3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | A. Pre-Construction | HOLD POINT
661c0b56-7f53-58b2-86bb-308b7c0629c8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting
c6760a7f-0786-566a-815e-7cf2dacd7fc9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 7 - Steel Reinforcement cage assembly
532662dd-7c18-5992-9e08-56b063525d38 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 8 - Mould Preparation
5679ec14-963b-5d4e-b80f-d241e0099f18 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 9 - Pre-Stressing
bb395c1d-e3bc-5003-9e3b-9ef357285f66 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 10 - Steel Reinforcement Placement
73e38176-2b7a-53bb-ab92-87518d1fa605 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 11 - Cast-in Items
f4ae5e15-1d9a-5781-a83a-f31759abd6b8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 12 - Pre Pour Inspections
5f6ef7f1-7a9f-53a4-95d2-038fa8aa5f6d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | HOLD POINT
40601b8a-f4c6-5f67-8c1f-64b06df70a60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 13 - Concrete Mix Conformance
5f1e91cb-6c5d-516d-8aeb-ca1464334e97 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | HOLD POINT
7f1ff3c5-aaf7-5093-9180-0dbaf5eb804d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 14 - Concrete Mix Workability
1eca23a1-d4e8-5885-819a-5d4d490ea01f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | HOLD POINT
311b4d10-3011-5863-9c23-f535da40db76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | B. During Casting | 15 - Concrete Finish
7c83774b-3789-569a-90e3-6fe1475c46cc |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction
867902d3-6029-5458-825b-31535aab06c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | 16 - Curing and Release Strength
08a98837-b7a7-5eb4-9d83-f424ba374473 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | HOLD POINT
71afd813-5ef5-577b-b808-a4078a658c11 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | 17 - Transfer
50713206-4fd2-5baf-b12a-d9591189e7aa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | 18 - Draw-in
db391832-43d6-56e6-ba2f-0d6d68cd4fa9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | 19 - Lifting
a35bde53-7d30-5f81-ace2-a3b00a8e9b0c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | 20 - Marking
b2950e92-40cc-5f2a-aca8-cc68dcd6e8cc |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | HOLD POINT
9cb65ca7-32f2-5c8e-8525-e1502d52ff91 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | 21 - Concrete Supply Testing
3828a410-f7e3-5762-85ca-97267ba0b14f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | HOLD POINT
17ad7011-f247-503e-9a9b-e37b78389df3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | 22 - Post Pour Inspection
e3a40d99-f270-5351-8c33-856efc7adf7f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | HOLD POINT
abbc2dec-ef1e-5019-8c40-57d83076588f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | 23 - QA Package / Redline Drawings
0ae434ac-3340-5a01-bbd7-f31949d7813c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C1 | C. Post-Construction | HOLD POINT
7ee43bf1-6f36-41f6-8669-017e03a344d8 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2
74aa3db1-6745-5fd1-a04f-792bbc1e0c4f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction
7131498b-d024-5833-9f83-daef7e364ccc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | 1 - Shop Drawing Approval
2f076a93-8c5d-5e08-9dc8-4d47b0373b2e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | HOLD POINT
cadfeccd-5520-518b-b1e6-de24b2415051 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | 2 - Concrete Mix Design Approval
2cce8c87-8b78-56f1-b291-1d44d56fda8c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | HOLD POINT
ad889fc1-fab7-5a3a-b96a-4e15d79c92f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | 3 - Lift Design
1cbd4ba6-ad5c-5e40-a51c-c55537d51f7b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | HOLD POINT
508fce5b-543d-5779-9f74-74a33ad9f059 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | 4 - Steel Reinforcement compliance
facfe968-05ff-55f5-8756-f8f969ad5ef8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | HOLD POINT
b7de5944-0557-5dba-9009-c437b4eb93e9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
edb973e6-2d0c-561a-915a-cd650b5ebc0d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | HOLD POINT
f3640461-e505-50ea-9834-17cc59263fd1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | 6 - Design Stressing calculation
8af6fd0e-2d9b-5d79-a63a-3afb4621969f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | A. Pre-Construction | HOLD POINT
cff8de22-5331-5fea-bd71-70c27f845cc2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting
111a34ae-aac1-5796-b011-03f3c8cf3c8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 7 - Steel Reinforcement cage assembly
0f5199ac-10c1-5b1b-a6ef-f6ab18df3a8a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 8 - Mould Preparation
622a90f9-58d5-559d-9341-f1795f3585a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 9 - Pre-Stressing
9a50b26e-f0a2-58de-ad11-4b1950c4b292 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 10 - Steel Reinforcement Placement
57809e66-6e37-5069-8920-16c6533f6089 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 11 - Cast-in Items
e8cbb010-adae-54b5-b7fb-b162ca0ecb2f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 12 - Pre Pour Inspections
ecf86da7-ac8e-5f78-b356-39e14adf48d7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | HOLD POINT
cc3cab9b-f26c-5677-b8e0-db4dcc4f5494 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 13 - Concrete Mix Conformance
5ba5ee7e-de67-5d94-b8a5-818baeb3c324 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | HOLD POINT
2b7ddb71-3a2a-5e22-a395-b7bdb53cf419 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 14 - Concrete Mix Workability
8ab8b319-4f65-51a6-aefe-78467f1cde05 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | HOLD POINT
9a734ab6-bab3-5b80-910d-9b082b9c1aad |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | B. During Casting | 15 - Concrete Finish
1f2d8fb8-069d-554d-834b-1eebead22a14 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction
c14fcbb2-f5c9-5a77-85e1-078332dcb999 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | 16 - Curing and Release Strength
8b3a17dd-6577-5f8c-8818-917e67f4a124 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | HOLD POINT
2a172fdd-0802-52b4-bd06-d50e367e11a0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | 17 - Transfer
0d3361f0-18fd-5188-8d95-53da84ab4a83 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | 18 - Draw-in
4d8ab9b7-fb97-5489-b54f-bfd1a8cf1eac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | 19 - Lifting
b2f84f20-3214-5d1e-9086-4e32f28757eb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | 20 - Marking
e88f3367-d0f6-57d7-8ac6-ebf30afa42c3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | HOLD POINT
a3abe711-38bd-5104-8a88-f6f0c2ab6305 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | 21 - Concrete Supply Testing
d802b8e4-fd67-52e7-a61c-3d58da7c9360 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | HOLD POINT
a252b361-e4f8-5871-951a-ceb89c5c0d8e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | 22 - Post Pour Inspection
6668c950-9346-5ac9-a487-87015c0f2023 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | HOLD POINT
4347d8a2-7bb3-5998-b61b-7f4f1c2f1d14 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | 23 - QA Package / Redline Drawings
a5c7aa23-517f-5089-9262-865ec4a32886 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C2 | C. Post-Construction | HOLD POINT
51a5101d-90a3-4d1c-928d-78209246ba36 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3
ea93814c-e78e-5371-9c30-8a609e31cff7 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction
e14a4c1f-73da-5ea0-b960-a4c4986fb00d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | 1 - Shop Drawing Approval
95b0138f-e141-5cba-a627-883b161b3679 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | HOLD POINT
e680b917-8541-5dfa-9f6a-5710d6513e79 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | 2 - Concrete Mix Design Approval
bab786f9-4f9f-5daa-a778-13081cbe555f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | HOLD POINT
e0cd173e-c987-50a9-87fc-7964a22d5802 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | 3 - Lift Design
23bdf53f-f856-55f4-b255-ea3ba7fa381e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | HOLD POINT
0c737957-c293-5529-b980-aa73c84233a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | 4 - Steel Reinforcement compliance
fdc22d3f-6346-5ff8-a3fa-d6cf7a5241fd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | HOLD POINT
36a3a2b8-152b-57fa-97b9-efca0fede3bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
44f3d673-c709-56da-ae4f-a07017d44e32 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | HOLD POINT
3b77d157-a1bf-5f8c-bcb4-ab8242fe40bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | 6 - Design Stressing calculation
c45aedd8-e776-52a9-8b8f-f4532f88dfc8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | A. Pre-Construction | HOLD POINT
7b00b574-a93d-514c-91f1-4fc956dadc33 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting
36a0d1c5-12ca-5349-b8af-849669aecfea |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 7 - Steel Reinforcement cage assembly
c6e74ce3-2181-5dc4-a4a3-5a099cce4795 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 8 - Mould Preparation
c2015b5d-9b80-51b8-b961-b7e74010eb47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 9 - Pre-Stressing
8bc4b402-0286-5199-80ad-faedf08d4c10 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 10 - Steel Reinforcement Placement
257975a4-248c-52e6-92da-2765bd4d4793 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 11 - Cast-in Items
cf23a7ae-2d87-5244-9167-7c44a2fd873d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 12 - Pre Pour Inspections
335d0b44-4f0f-5ca2-92a4-60b1bf099b9f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | HOLD POINT
f8fca99b-0ed5-5a51-8c44-873d50f164d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 13 - Concrete Mix Conformance
e2f34096-73a2-5435-b998-c3814cdb53f6 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | HOLD POINT
e1786518-2e65-5ab3-b097-08e193ba23c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 14 - Concrete Mix Workability
b98f5280-ba8a-55cf-9b1b-fbb193f6fb07 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | HOLD POINT
4265bbd6-478c-5aea-a2e6-72766460746b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | B. During Casting | 15 - Concrete Finish
ec348be6-9f61-5a5c-ada8-1002ac3419b8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction
6fdf8903-aabf-5f3a-ac43-acbe342199ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | 16 - Curing and Release Strength
e8aeb877-9ff1-5e9c-9fb1-608671938bcc |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | HOLD POINT
1ca1ac19-05fd-5661-9dcc-d0697b01dc6d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | 17 - Transfer
9544e431-7af1-5df5-a823-1ab5abcfdb08 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | 18 - Draw-in
6eaf4262-9445-5bb1-9d41-15aeeeb363a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | 19 - Lifting
567a0f99-fba3-5638-b6b6-7cfed11a76fa |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | 20 - Marking
c0612981-9f4c-5c8d-a75c-acdff1b313b7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | HOLD POINT
646a8901-fc4c-58b1-ba45-2eb70dbf9595 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | 21 - Concrete Supply Testing
bbaa9fc7-c45f-5f66-9406-307eed92f5c5 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | HOLD POINT
b3324d48-b8a3-53a8-b45f-713de8676fc0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | 22 - Post Pour Inspection
d7081b96-461e-5e16-aa0f-008c3c8012fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | HOLD POINT
36a68764-ead8-5470-9a91-6cd95f3b6d96 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | 23 - QA Package / Redline Drawings
3ebd166f-a2ec-58a6-8a0a-b7f7a918a911 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C3 | C. Post-Construction | HOLD POINT
d119624d-64b0-434a-b642-5470a7345e6d |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4
ccc80597-3581-5d79-8e8a-783268453473 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction
ca70bac4-4c22-5084-8a85-48a32221d6a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | 1 - Shop Drawing Approval
6e63782a-20d9-5258-a9f6-dec5ed01fe84 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | HOLD POINT
be59b7fd-e2c8-5f0f-a130-8aaf643cbfbb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | 2 - Concrete Mix Design Approval
d5b3acb5-96b5-57fa-91c8-386e17113c34 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | HOLD POINT
1bf1952b-39dd-5267-8bc8-21155500a955 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | 3 - Lift Design
1ed47d34-166c-55c2-8244-170af04a740f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | HOLD POINT
1ecf68e3-946f-50e8-95f0-2504372c25f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | 4 - Steel Reinforcement compliance
6a8c6b34-ff46-59e7-9c5c-6146b8b7d925 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | HOLD POINT
cdf0660c-efad-512f-9351-f22a87a25947 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
08f62432-5119-5512-908f-978863d483ea |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | HOLD POINT
c5224b6a-c675-54a6-bf67-98ce404420b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | 6 - Design Stressing calculation
5f0bd10b-9683-5a50-8e59-3f9e37853c33 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | A. Pre-Construction | HOLD POINT
d396cd04-95c6-5e88-b287-3b38a82224dd |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting
d1a0faf2-6ee2-5d64-9574-9f2298be65a5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 7 - Steel Reinforcement cage assembly
5a5abd15-f280-5618-9cab-2ca501111c76 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 8 - Mould Preparation
733323a2-6970-587e-8081-f2dae774ba40 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 9 - Pre-Stressing
f000c1fa-024e-5976-b0d6-70c74104c13f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 10 - Steel Reinforcement Placement
783af46d-2b46-578f-ac63-f08db0f9063d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 11 - Cast-in Items
97971fae-8e2b-55b3-888f-9e9042368f0d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 12 - Pre Pour Inspections
b1d526a7-f44f-5e17-9112-1ab9465790a3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | HOLD POINT
03955067-83fe-5761-b76d-06e1b61f7cf5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 13 - Concrete Mix Conformance
1f314544-7358-558f-9960-40b88ce1592b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | HOLD POINT
e477c3f0-26c3-5d7a-86fe-30de7c1a4207 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 14 - Concrete Mix Workability
731368c9-f4c6-5f04-8e3d-f941f5f5a977 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | HOLD POINT
c8c22484-259f-5484-99aa-fc64a0e955c6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | B. During Casting | 15 - Concrete Finish
fe281105-e700-5bec-a975-75214ca27f82 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction
9df8291d-05c2-5f54-8c66-3ba3d8028f1c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | 16 - Curing and Release Strength
bd0c09ea-8cf7-5ba1-b765-e88952f43943 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | HOLD POINT
cc7ca880-c747-56b2-bebc-cc56c2aaf4b2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | 17 - Transfer
9be4e11d-5d39-50a6-8ee1-7d9bb9663839 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | 18 - Draw-in
d0b59830-cfd5-5d4a-be7d-9af8a6297949 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | 19 - Lifting
60566aeb-d7a9-551d-adaa-bb699188ed4c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | 20 - Marking
b1ecda96-4762-5702-9bca-f7c72011ef15 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | HOLD POINT
fa84983e-b8b8-54be-9989-a8ee42b3b356 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | 21 - Concrete Supply Testing
b5f0e424-1aa5-5571-9059-7113ee78f0a0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | HOLD POINT
fc698bed-8876-57f9-8101-2f3199f3e5cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | 22 - Post Pour Inspection
0d24d2f1-7a13-50a8-b862-6a791406faf8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | HOLD POINT
8ea26665-7488-5816-b12f-85e440439f1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | 23 - QA Package / Redline Drawings
86b0a168-7651-524c-b794-547975699520 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C4 | C. Post-Construction | HOLD POINT
b3576a7e-e601-4656-8eac-ecfb5dae8322 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5
a095c800-f0de-5f33-8aa6-809d5136e358 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction
b0109fa3-860e-52c4-9cd4-abeaf0367bb0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | 1 - Shop Drawing Approval
fe6b45ab-4b70-582c-975a-d8e482bb5485 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | HOLD POINT
916ece4b-f90c-51b1-aaea-a28b900a57cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | 2 - Concrete Mix Design Approval
42d329bf-4ad2-573c-ba2a-662e646722b1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | HOLD POINT
ab91ab3c-42e1-5c61-8030-3754204e3fbc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | 3 - Lift Design
269ee125-603f-5eca-9ce4-9b115e8923c2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | HOLD POINT
7dbfd163-67fa-5acb-a53e-18e65d2df676 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | 4 - Steel Reinforcement compliance
3d25a3c6-26af-545e-ae2c-7347893dc1c2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | HOLD POINT
f9f87f02-4a73-51d3-bff5-b44badae01a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
6678dea1-25c0-538f-9103-cb592c83ac53 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | HOLD POINT
5c526d1a-8468-5a7a-b48c-1603b6adcd0d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | 6 - Design Stressing calculation
35121823-8bfb-5065-bd44-3189657e3344 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | A. Pre-Construction | HOLD POINT
39ca704e-7b42-50f0-a8dd-ad1b70427fc8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting
c13c56fd-cfd9-53bf-9e11-6f127a8c85bb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 7 - Steel Reinforcement cage assembly
874cb2cb-8fda-591b-b9e0-8a3de4690fb6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 8 - Mould Preparation
ba617dea-73e7-5178-9a55-e83d53c3ef01 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 9 - Pre-Stressing
7c5b40cd-7528-5d63-b5d8-df866220a3a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 10 - Steel Reinforcement Placement
4e57134f-1b0e-59ff-a4dc-7c894274efdb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 11 - Cast-in Items
5e8ef82e-8e7c-52ab-b90c-1ea9575e6aee |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 12 - Pre Pour Inspections
1d3b7faa-b504-55b8-9fbb-ee991c3fdf03 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | HOLD POINT
04f4435f-6271-5049-9717-3252314e18f4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 13 - Concrete Mix Conformance
98357dd4-b0fd-5b25-8a02-95f6e1e5f9a2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | HOLD POINT
03fdcaef-af49-5138-9647-df8ea310c028 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 14 - Concrete Mix Workability
a18fca27-26dd-511f-a08a-c0908ad7a910 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | HOLD POINT
f929dffd-6ff1-5a27-b587-6a90c9e0d127 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | B. During Casting | 15 - Concrete Finish
af1b0256-77bc-5717-bbf0-719b48b5e77c |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction
5ce907c8-1174-5de0-a0ab-f8c9db07df58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | 16 - Curing and Release Strength
2c836801-9456-587d-b282-3c55d9eb18d2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | HOLD POINT
2966b9bb-fcf8-5f2a-b0ce-e907796815ec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | 17 - Transfer
de270bf7-0e39-50d6-9fd7-17fd60130e4f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | 18 - Draw-in
ebbd4f6d-af8f-5a76-a4f5-6a60a80267f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | 19 - Lifting
500bc094-f36b-5ae9-aee8-565400cba6db |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | 20 - Marking
d43619a5-1e12-5b26-9e24-58c6cff69507 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | HOLD POINT
017495ab-dfe3-5e93-b7a7-2873d66b6d92 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | 21 - Concrete Supply Testing
4eddfcd2-62a3-59a2-8d76-e90e75bc3cfb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | HOLD POINT
2b5058bf-fea8-5e5b-9e66-b434a216fb2f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | 22 - Post Pour Inspection
58ffa73c-7b23-5e4a-88af-2f2e2a7176ae |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | HOLD POINT
e93334fd-f55e-5eb8-8518-a24e3ee9b36e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | 23 - QA Package / Redline Drawings
224cda49-6478-5dc2-9f35-06fe45037816 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C5 | C. Post-Construction | HOLD POINT
49c385a9-2b92-4840-8f4c-0edeca1d9700 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6
b4acb848-7aad-506c-8b66-0cdc5c92260b |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction
99c9b1aa-c5eb-5134-9f53-b1d2e039d25d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | 1 - Shop Drawing Approval
5638056e-8c5a-5de5-917d-a22cd7d7d818 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | HOLD POINT
19a55b3e-606d-58b2-9e10-c93b36331abf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | 2 - Concrete Mix Design Approval
b57d4cc2-5ac2-51c7-a102-65b7589e6403 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | HOLD POINT
401854a4-e407-524e-8955-25a2b61f752a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | 3 - Lift Design
4994f2c9-5b97-569c-965d-a20bf7394197 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | HOLD POINT
a2cfde7c-cd81-5e20-aa58-39c8d9be4519 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | 4 - Steel Reinforcement compliance
47439789-4407-5ded-a2b1-f42583786623 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | HOLD POINT
b852c071-2cff-51e8-93d8-5adbc8aaf2c9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
360bb1ac-9119-5d93-860d-64b42bed8458 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | HOLD POINT
e15d292e-d9b0-50f8-ba4a-28e8685e23f8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | 6 - Design Stressing calculation
72fe1041-5c47-535f-afdd-f7e20ec19f11 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | A. Pre-Construction | HOLD POINT
e387d456-043c-56d5-adf6-c648eb691c9a |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting
a2c6a6e5-f9c5-553c-9974-76315a25b259 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 7 - Steel Reinforcement cage assembly
679d53f0-6e50-5d07-9dda-bcc09239f775 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 8 - Mould Preparation
2fe83903-cbd4-5db6-8a62-e518e58324f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 9 - Pre-Stressing
2ff91b67-bc11-5391-986e-4ab7488f1755 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 10 - Steel Reinforcement Placement
2bd054c5-b40e-5d89-a852-aaf6de7b7c6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 11 - Cast-in Items
b5d4a5f0-5986-57d6-bf30-df26f0b60bb5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 12 - Pre Pour Inspections
11436766-7873-56b6-8e7b-31dd5bff5d21 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | HOLD POINT
a332c085-2ecd-5593-95b5-f16ec506d0cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 13 - Concrete Mix Conformance
07e0ce92-2396-5372-8753-fdafe7c7be98 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | HOLD POINT
fd160775-6f62-522a-b080-da6edc7b5e54 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 14 - Concrete Mix Workability
cf9e42c9-37c9-575f-9b86-1f5a926131af |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | HOLD POINT
22e4e98b-be85-5a93-8ddf-779628ff14bf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | B. During Casting | 15 - Concrete Finish
0bbb181a-7857-505f-a9ad-cba228d4cd56 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction
31e2c880-9506-5307-b3a2-2cba7f4750a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | 16 - Curing and Release Strength
0412de19-e40b-52d2-961b-fcbfe2c810db |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | HOLD POINT
5e6fa140-7f43-59f3-b3f2-51c989d8bf00 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | 17 - Transfer
8766305c-6f12-5335-b952-9fc02008c8be |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | 18 - Draw-in
85188017-bf19-5857-8801-b3ca4f397a74 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | 19 - Lifting
a446c3b1-51c2-588d-a2e1-0ad820c4a683 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | 20 - Marking
61f86f6a-0fbb-53f7-9030-facac019a88f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | HOLD POINT
f9261882-1073-5c18-8d68-7940bdc7229e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | 21 - Concrete Supply Testing
18297af1-c383-52a0-b5fa-2d21d1626c3a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | HOLD POINT
f5dec6ab-4835-51df-a73d-212d39c2090f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | 22 - Post Pour Inspection
1a134db6-dfd5-5bd7-8655-16b6bcf55092 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | HOLD POINT
0e0f0044-dba8-5a27-83db-414d2afaf487 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | 23 - QA Package / Redline Drawings
59466c6f-a3f9-512f-8ba5-7bf57bc5cfff |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C6 | C. Post-Construction | HOLD POINT
bde56f0e-5e90-459c-b59f-2e8aaafea6ed |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7
3fe4676b-5a73-5d82-9221-71dbb3d76bef |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction
d3d268cf-646b-56bf-a48e-bbe41bfd8c07 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | 1 - Shop Drawing Approval
a3fda947-ee4c-55ad-a25a-05bc03cd2b95 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | HOLD POINT
bd3be2fe-0776-573d-8cda-1b1d361906ef |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | 2 - Concrete Mix Design Approval
c3beaa3e-4dbb-5259-99dc-a392cf0631f4 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | HOLD POINT
539aec7b-7595-5ae0-b6cc-bfba1cc838d2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | 3 - Lift Design
27c3b022-8b02-55b5-8d84-cb10b75d367d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | HOLD POINT
a6924c28-420e-5945-b642-fe1e7b648250 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | 4 - Steel Reinforcement compliance
3a97ef30-cc21-57d6-ad3e-12723695152a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | HOLD POINT
5b919fae-87f3-518f-8905-cf4ae052ead9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
ece1b1d4-862d-5d5e-9037-ceae898eb75e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | HOLD POINT
ce1e8428-db5f-53dd-9504-7729871161e3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | 6 - Design Stressing calculation
e8822ca2-8044-5ac8-8327-c629e853203b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | A. Pre-Construction | HOLD POINT
f86c0f15-90d4-5114-a557-faff383f6ca2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting
788933c0-63a4-5171-8aa4-958ee28762df |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 7 - Steel Reinforcement cage assembly
ddd4df45-8db5-52e3-ba04-0dd3f29624e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 8 - Mould Preparation
8210dd4b-643d-5bc8-9c2d-a35d7ca933d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 9 - Pre-Stressing
c378e32b-85fa-5b7f-8844-410dd7331682 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 10 - Steel Reinforcement Placement
ae84f318-fd93-56cb-9ab6-65e417977d62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 11 - Cast-in Items
a6ed8889-c1bc-50e9-8976-5d046db26ef7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 12 - Pre Pour Inspections
600f6f11-4c16-543e-ba40-de1d61e8d071 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | HOLD POINT
5e91bd52-9f7b-5fa5-ba60-d1e11a741f1a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 13 - Concrete Mix Conformance
fc45a000-6d43-5730-a7d8-bddec212fa4e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | HOLD POINT
1f38db86-93e4-5f2c-a2f6-1bf1d9dfb913 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 14 - Concrete Mix Workability
edc7f52b-e0a9-5691-a188-f0ca90eb321d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | HOLD POINT
e24cabe6-830b-54c3-a9de-627cf374be47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | B. During Casting | 15 - Concrete Finish
c7b9555f-62ec-53ea-82a9-76a7d0600d7e |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction
749b2e61-c4b7-528f-ad83-0db772c0ed0d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | 16 - Curing and Release Strength
67fa2bbf-8a08-5988-abde-7d440f0856d8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | HOLD POINT
ba26e5b4-35ed-541b-9672-f843bb004dd7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | 17 - Transfer
0558a616-a199-5b5c-8a6e-3968f7990b7f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | 18 - Draw-in
1fa1e0e1-73a5-58a5-b7b1-221a03a9e9cc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | 19 - Lifting
1dab8329-bb08-5011-be07-bee87860c8e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | 20 - Marking
e92c5255-b64f-5de2-b706-6975f704d8a9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | HOLD POINT
5c534715-3a55-57d0-85b1-b130777c6fc7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | 21 - Concrete Supply Testing
c9969228-f6d5-5a9e-a4f7-d2017e4b12f9 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | HOLD POINT
6ab0054a-2194-5d95-9b01-fa60b92940e6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | 22 - Post Pour Inspection
8fc8da36-1d23-54b7-ab84-08f1bf713358 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | HOLD POINT
1f8d3d21-cb0d-5be0-887d-3a2632ca5b5b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | 23 - QA Package / Redline Drawings
822658c5-6a3d-59d1-9ded-256fc5d07244 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C7 | C. Post-Construction | HOLD POINT
5b34b4e2-6c02-4469-8cfd-e2c198a73408 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8
c80bafa0-f0bb-5b61-99af-0de84e993eb9 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction
d1d82416-51dc-52f7-81b1-659acba57f31 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | 1 - Shop Drawing Approval
910a7171-914b-5be6-b5c3-57d2c20990dc |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | HOLD POINT
3529d146-2bb0-5eef-a2ce-6a6868d8231c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | 2 - Concrete Mix Design Approval
bc5e1617-a773-5d67-a8f4-c92087285c93 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | HOLD POINT
5d006768-25cf-5e2d-bc48-7520d5f4a18b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | 3 - Lift Design
09f414ed-e79f-5698-9355-2d4058523165 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | HOLD POINT
b470f047-8780-54c4-a9b0-c5ad16f0422f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | 4 - Steel Reinforcement compliance
de90e32d-ed2e-5c80-a783-566809a9a914 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | HOLD POINT
9becabd7-2b23-559f-8cfe-e9f94074636b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
2b1c96d9-1ad0-584b-96e0-dab90b89e92b |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | HOLD POINT
5f2075aa-5976-5a05-bee5-ea369228eb8d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | 6 - Design Stressing calculation
6e7c957c-7d00-5bcf-92a8-8d7afb1b1471 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | A. Pre-Construction | HOLD POINT
078986ac-7ecf-5fa7-a37a-f891d9c012e9 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting
fcbafc36-1392-5012-b87e-c6af8fffbde2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 7 - Steel Reinforcement cage assembly
45767a96-a568-5ffe-8f36-91a3d1a53ef4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 8 - Mould Preparation
6dfe9499-09ab-5efe-8906-beb7a762dd0a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 9 - Pre-Stressing
a8d5bb5d-e908-5ea6-b9da-2723dd91d5f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 10 - Steel Reinforcement Placement
6b4eba30-afaa-57ed-ac59-5bd58b4b6514 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 11 - Cast-in Items
29692c1e-a666-58db-80da-fae361932b04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 12 - Pre Pour Inspections
b42ec2a7-96ce-53d7-a7d1-9160a089a069 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | HOLD POINT
1e120116-6dc1-5f35-9514-d042e6cd7b53 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 13 - Concrete Mix Conformance
df0709a5-0466-5141-b3d9-da3c7ab84aaa |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | HOLD POINT
74da6d51-d57d-534c-be84-2b8fd757f617 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 14 - Concrete Mix Workability
04c42d30-15da-5d9a-bd8f-33e3d91eb8e0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | HOLD POINT
e83a25e7-5cfc-5a26-85c1-131640e5e1e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | B. During Casting | 15 - Concrete Finish
a423fe90-e696-5bbc-9f22-462d64c85916 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction
f8726940-5283-5927-bc3f-8ded3653ab61 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | 16 - Curing and Release Strength
1d56cdf7-bfeb-5758-a62b-c41308add1e0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | HOLD POINT
5f5856c9-aa49-5f31-ae28-a9620c290c05 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | 17 - Transfer
47a89e09-a295-5d11-951f-6a6b5f3a0b1e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | 18 - Draw-in
1ab563f6-4952-5c64-93fc-7ba02256248b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | 19 - Lifting
028073e8-9f01-537f-816d-dec7682feddd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | 20 - Marking
9cbcd197-b51b-5a4c-accb-ffdf1d940a1a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | HOLD POINT
52766a4e-3ea6-5832-88f6-6f5e3831a295 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | 21 - Concrete Supply Testing
550e4c36-4524-573e-aadf-e141aa4ec95f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | HOLD POINT
2d1f8f7b-d269-5b27-a2f3-8369e3545637 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | 22 - Post Pour Inspection
4890fc78-5452-5644-bf31-519f58bc9955 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | HOLD POINT
de23d266-2343-58bc-8465-e43164f4128e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | 23 - QA Package / Redline Drawings
a8a1dabc-7774-5cba-a7e4-eae537a65916 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C8 | C. Post-Construction | HOLD POINT
534cba60-b361-4552-9363-bfec7d9d83d0 |  | work-in-progress | 0a2c43c5dbf171ab6d354f848397a1088ad6780750eef9688beb5fe821350d02 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9
392abcbd-b099-5231-8b23-52e50890042f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction
8d09fee9-8dec-55e8-9c19-ef7ec90fc956 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | 1 - Shop Drawing Approval
8676c11e-76bb-5f33-bbc4-43ac7a93dfb2 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | HOLD POINT
8be4158b-7fa4-5bdc-809c-4128237c0ee5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | 2 - Concrete Mix Design Approval
03c307a5-2a7e-5c60-bfc2-6aba2ff565bc |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | HOLD POINT
3826278a-53d1-5d7c-bdcf-12a247830f23 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | 3 - Lift Design
ba73b035-c8d8-59c2-91d0-44da7c921f26 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | HOLD POINT
e7606517-d5f4-5897-adf2-1f39e4d0b6f1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | 4 - Steel Reinforcement compliance
ab1dbc29-67fe-516e-a7dd-96c385a33297 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | HOLD POINT
8cda611f-8a29-5b9f-bcdf-0470e2c35e7b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | 5 - Steel pre-stressing material (Strands) compliance
14f4d656-a78f-5112-94a4-d44378bb0327 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | HOLD POINT
93bd2b88-a879-5310-884e-989a4d92bd58 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | 6 - Design Stressing calculation
3a1230a1-d649-5bc2-bc29-92b7b84a9c5c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | A. Pre-Construction | HOLD POINT
9818c897-e59b-51e0-a200-a4cff93ae8c8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting
02d83258-1a95-5a70-b33e-e681c6403564 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 7 - Steel Reinforcement cage assembly
9be6e8b7-199b-5980-957c-7c7bc26498c3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 8 - Mould Preparation
21442944-5584-57f5-97fd-e13a3bc468c0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 9 - Pre-Stressing
b0ac7501-ee29-5172-ae3b-48188bc83fb6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 10 - Steel Reinforcement Placement
e71fbbe8-5fec-5cb3-9c38-e52bcc8a0a72 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 11 - Cast-in Items
39f34c5b-714c-5d96-a77b-7c75d58521d7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 12 - Pre Pour Inspections
f0108675-76e3-59bb-a619-87e01f6bca0c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | HOLD POINT
ee64e727-654e-5eae-ad86-c1b26f26f519 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 13 - Concrete Mix Conformance
16165deb-a7ce-5fda-b5c2-51ff395a79fd |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | HOLD POINT
a7d4ab71-6779-53c1-b7d1-b311cda9b3e5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 14 - Concrete Mix Workability
d6429a6b-3e45-5c1e-b8da-cb40df6563e7 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | HOLD POINT
7b2dace4-819c-5b76-ba14-b476af410a62 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | B. During Casting | 15 - Concrete Finish
b9463a43-cfda-54d7-b3c8-9b2128c7b0a5 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction
44e5cb2d-0322-5b84-8652-52e1f45d4f39 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | 16 - Curing and Release Strength
1711515d-4cf2-514a-87e6-b3fdc614413e |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | HOLD POINT
6d2a2a4b-df31-543e-b7f5-407d80e6eee8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | 17 - Transfer
da61576e-bb4c-506d-aef7-696d9656920b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | 18 - Draw-in
ea2f8704-9524-5f83-a922-fd8098baf8ba |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | 19 - Lifting
048ea4d6-36a8-5617-9fda-0243e21855cf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | 20 - Marking
43745fa9-b5b8-5222-b4f7-7eb8cc319338 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | HOLD POINT
5862b030-04c0-537f-ae0d-df855cc9f67e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | 21 - Concrete Supply Testing
567a2a59-6f33-50d0-bbe1-8b679997c6d0 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | HOLD POINT
0ddb27e0-7fbd-5482-bd6d-09ea130fe997 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | 22 - Post Pour Inspection
5e453696-87b1-54f8-ae04-b926ba612d71 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | HOLD POINT
4187ca5b-1eb1-53af-a917-e2127cb9d4a6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | 23 - QA Package / Redline Drawings
d34dd970-bb86-58ac-9362-0d45a49a590a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Precast Bridge Beams | ST Beam Span C | Beam C9 | C. Post-Construction | HOLD POINT
d1c01185-25b2-41be-a9ea-5553c6a997d1 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs
9e4653c7-5d47-4103-b0f8-6df98f88d53b |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab
c06e5167-9e7e-48f8-9c40-38e1acf6c68f |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D
282af446-eeeb-557c-a151-c12e6225c1bf |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
e965309d-baa8-5911-8b75-f399c37ba6b6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
202cae32-bf34-526c-9506-4683d7d82741 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
3e8fd29e-a45b-5ea4-8f84-fadaff93310f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
8568e8e0-9173-554c-b49c-61e21eea61d4 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
30132199-792d-541c-84a3-216fa534f8b0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
9bdcfb36-86fa-56c7-b567-8ddf79901d03 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
424aac0a-a220-5691-aefe-b089e8586f1f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
27a07312-842c-57fa-8a94-984b9a1d0402 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
85b2c78a-e248-5299-8859-62de138bf365 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
a922f112-3098-551a-b39c-466f73c45085 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
7ef15c95-1c35-591a-bced-5b8dbec71535 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
89919765-543e-5d3e-b907-e72e41f356f7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
1fe64692-3787-5118-96b3-a3482859f825 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
33fe6d16-7610-571d-81bf-ec95c8159a07 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
d739c600-4617-5212-9704-3df77e7ceb48 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
64acccf3-496f-5c29-a217-3f3b3e21960f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
4e6bcd91-c18a-5548-86bc-1e4455a8befb |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
b885bde6-20a4-54d0-83a4-3ac352745cfa |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
c41cbd4e-1a95-570c-af99-0c22e3fed649 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
a73a7ea7-9e82-5e71-8ddf-55fea672721e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
f596ba1f-e565-516a-bd87-194dde56884e |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
2ea13ac0-75db-5bd7-8285-db355e6037cb |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
fbbb5125-3362-52ef-8aa9-396660b61197 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
f0286aa5-a928-581a-b9a9-0b25a22f5fb4 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
38cf9e1b-d95d-5b70-a964-8951923a0785 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
f5c4e674-13bf-5c46-93bc-db0b6b73f5d1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
4274d729-1997-55d6-87d5-90d24af13f10 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
a85fca37-5af7-5e6b-828d-bb2975c85048 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
1cbc86ea-3c22-51ac-a7f9-669b42dfbf7d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
15e71cce-b81a-56db-abf2-9e468b573f0f |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
a356cd47-8b1a-53d9-8902-02cbd88ba351 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
50720143-9e8a-5838-a60e-d3d00620633a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
2c8c748e-bcfe-582c-8af2-fa8b6449f57f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
bff49e54-0842-5fd8-a6b7-8514168fa69b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
1dbd5683-85e6-521d-ba36-d8d671c8374a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
dfa6986c-eedf-55b2-bced-547ee800a0a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
5c617b27-fb0e-5c79-9087-b36042fbbc04 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
f55b2816-b42b-5a10-b52c-5aea03dbe254 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
600f83c0-ee02-50bb-916c-023f559c5c65 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
2154dcab-6c39-523e-9197-145345cc19a2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
c732e86c-03ea-536d-88cc-238876bdb49c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
9b7f7068-0042-5c0e-83fc-692bb98914db |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
3df71945-abed-5e96-ba82-caa9a12f2203 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
b0cd212c-a950-5fbe-af60-232e50e76c43 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
322390c5-3a89-50ab-966d-6218f3e1f63a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
cd403162-8adf-5d30-bbff-aaaf3dd343ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
3f313578-6b97-5966-8a25-f22e7ee0a3a9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
4f3cbdeb-adcd-545c-a43b-51d359b4e653 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
68d31ff2-9531-5349-a3a4-5ba5b95d9e32 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
e752c832-6a82-5cba-bd01-3b0ee083b04a |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
aab820ce-5bf5-5033-b80c-982f552c66c2 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
ca97c7fe-8327-52df-a1b5-b83123ab0c51 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
2aad0785-9073-5ffb-85c8-b38699447671 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
81569c03-4164-47b6-8f0d-85cd845d86a9 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
030ba42f-89f9-50c7-9862-defad84bec93 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment A Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
bc9eebae-c1d6-4721-a153-e0637f9bcba3 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab
dc2a5b03-620d-479e-82b1-ccfd51b4af5c |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D
b390ec16-abd4-5a30-b34a-dd3080c8c341 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
1bdac06b-d936-5326-84ae-5c61bc84c8ac |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
63576843-4f66-514a-875c-2a3795b352f3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
527c8f36-60bf-56d5-b6a3-06f383902f34 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
56b2ee8a-d9b2-5130-9349-20238614a998 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
17127e52-9072-5ff7-82fd-5e4306409987 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
54e2bf97-e6ee-5cdf-b7f0-a4c944f5c4cb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
bba05179-fb42-5433-b307-59ebc8de2f33 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
6d99ff96-a550-55a8-a645-3fefc51d7e74 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
7407a922-ed7c-5ae4-9660-9ac034058af1 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
08bbf630-3fb8-536f-ae6f-4875a94ef264 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
c3d09600-941a-501c-8126-cd64f48684fa |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
3b33c3d7-539a-5cbb-8711-a6632d713db1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
388b8722-9bdd-507d-862a-062acfb8bcd3 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
1d0cdbca-c471-518a-b02d-bc1cb46e50f7 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
dc2be0d2-3bfe-53b0-8c99-a7b40a3c3cf4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
c9e68cb4-dcf2-53c7-90ce-3251f4257cdd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
f96f3e58-e162-57fa-a281-65c729783af1 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
f783b835-fd64-587e-889a-8da7fa7a2193 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
4734f893-a18d-57ed-8181-6b39bd01f07b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
4c037fc5-7bda-5ece-a69c-ddc26276fa3d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
6cfae3c1-27c8-576f-944b-387c20b7864a |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
c97c4c1f-63d5-53c8-8646-b88ec9cc8184 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
80f9741b-c912-53ab-a52c-6c9b43490e73 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
321dfac7-1e69-53d9-8702-9470b36a3f44 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
07b2d95f-547d-5050-bacc-a00ce3f88910 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
a215a768-6915-58bf-9989-4be1fd7189c2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
e87f4c24-2a46-5af2-8fb1-dca891afd324 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
1551e2b5-e86a-5fb7-81ac-5a59302c2adf |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
1ff07c42-44f6-51a0-9986-5770053c8ecd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
c1cc6520-f662-52b6-8540-049d65dcfb07 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
a1c83011-b35c-56ab-8516-2a0ed91e72f5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
2fb3fa91-a0f0-5165-99c4-6c5db2c2138d |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
eefa6877-a4e9-5a92-96a6-7f9970ba3676 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
7933869f-d6cc-510d-9538-68e39c9fc1a7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
96818634-1b04-51f3-a3f3-1a00d47a5f52 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
86dae482-c9bc-5131-9410-f657c2c4c379 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
6df01dcb-52b7-563f-9ef1-b4077f7f8e47 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
77c3e12e-4432-566e-8004-b085878b2f6e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
0bfd89c8-c5c2-571a-97cc-34038e291ce9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
0fd5b65d-c0a9-556a-8b62-b64e4cb4cd4a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
36728a11-b72c-51f3-9bed-2e7cd329be8f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
30bd6c3b-a556-501e-ba9f-ff9701316315 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
5c76ad76-f896-50c2-a9fd-e20d4f42b9d5 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
6bad01c5-a9d2-5276-baab-95aafa8296fb |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
fab7fa1a-b5fa-5bf8-b5b2-b1ce55fee688 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
4828a173-e301-5e7e-87d4-eb4b3d552e41 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
f6c02a7e-c1ac-529f-82a5-4f8104bdc268 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
1174510d-e36a-5d3b-97a1-412a78d04a1d |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
2e330d07-076c-533e-9be9-90abbbbccdd9 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
56b5bd0c-9d0e-5ea2-bd86-aa5f674fef25 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
366b8004-8efd-5e57-909a-f9f0f3fb9c05 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
f1a2f534-d052-5479-9066-cb98dc5f402f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
8bb57e81-459d-5e2f-9b87-4cbcdf23360d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
84f25dde-1e14-4281-95b0-55854ce0a61d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
e8bcc8f0-7ee1-57e6-aeb3-110e117eaed2 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Settlement Slabs | Abutment D Settlement Slab | ITP - Insitu Concrete Construction - Rev D | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
b87637c3-39b4-4af2-ad93-2acb7c385151 |  | work-in-progress |  | folder | TRUE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead
6a1a8f5a-c0ae-4e99-b857-2a5f210c2666 |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B)
1e2f629e-7311-5fa0-8979-6d103799a9f8 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
e567d2c8-bc3d-51ce-aa20-941ff8f1529e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
b69b5d89-be67-5292-be99-ebc3500f1274 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
70b7f469-4323-5925-8112-15d9aa6555d6 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
c3f7ebde-e2a2-57f8-9abf-ac6f438c7628 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
1c93c2f6-e129-5ade-92fd-f3da8134d6b9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
78bfb0de-0beb-5af0-b799-7ee4f6ebeee2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
2692b0e3-9b13-5a14-a262-827857577e1c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
8c2b2bd5-baac-5979-8ff5-313f39a56629 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
2e5c9346-e28c-5b2d-b9fa-f5f9b229a5be |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
1568ceef-bd1e-5d55-8fda-e9e460009ec9 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
a6c22ebd-27a1-54b9-841a-d9c728c1a213 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
812e8c0a-0ae2-573b-bbcb-19fdc5a77900 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
74844a09-5239-58f6-bf6e-a5a741b6a97a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
40c76d7c-868c-5787-819d-1fe520c02d98 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
179a69dd-9732-5e6b-a363-f79582116682 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
c20a5b19-6cc5-5578-898d-23ff0e016057 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
49f11ff0-48e2-561f-8395-52476978c3e8 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
4abe5685-d08a-5a35-848e-83c859df6c95 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
6e5b4195-ecf9-5fb6-94f8-2086b87b70cd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
733e79d6-7030-548b-9183-b8c1d59f6d60 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
9cf358ca-050f-504c-b5e5-cd4eaf422993 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
5a2b5365-57f1-5b40-a087-79896ab154cd |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
b2292b90-4542-5576-ae88-7a23a6a13d82 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
fd0e571a-8610-5183-a4ea-4cfff8a1011d |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
cccf18c1-ab99-536b-9e8b-bb2e570b7507 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
49b1b134-65f9-5d3f-9cdf-1b621a308908 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
1c8f47de-97c9-590b-b67c-b62660667850 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
5b2a6832-497f-543e-a3d1-fa905a9bc317 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
b8c13851-a822-57a5-b808-befbf91752a3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
8f5a1026-47ed-5c29-ac29-af18ca6ebb5a |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
d0531c09-967d-5335-b7b0-1b3a230cd2ba |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
79f4d392-3add-5fcb-925a-1f607a5de03f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
8a8b63f1-92bf-53ec-b238-5d8e22c20626 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
f028c6ad-cb06-5786-951d-541bc16fd3b1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
c059f73b-1060-5a01-a06a-db010f53a8fb |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
ca6be3e7-d1d4-5311-8bb7-d78dc1737a99 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
565e21d2-f8e9-5582-86db-d606666e9e6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
6cafa441-1fbb-5335-9345-9c33e139a353 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
9542dcdb-5746-5639-9407-921c6e8f60e8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
6fbbc215-e40c-5bde-a36b-df67b1801508 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
82e44e80-503f-5f43-9d4d-38e98688571a |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
446db22c-e12b-5ee7-a6e2-64e1f00b32d8 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
c59a1078-82bb-5fbf-9abc-8c66c8bcd0d3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
e310d44a-8c3f-57e8-97b8-a5a8ae9ee541 |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
69f71592-761b-585c-8a32-1a281186d733 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
1c440bff-dc2e-5a5b-a842-69f7ce4b5b94 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
d1e1a783-61be-5173-b083-826287acaaaa |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
4c5b96b2-5c1d-530a-a9b1-3217399977d6 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
4f7bc75e-15c2-5c5d-90e8-5dea8974429c |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
d41e9c2e-45ee-5a0b-839a-e4a24e2c7366 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
e61aba7a-8c92-507e-8475-add3ff71bac4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
a36d28a1-69de-533c-83c6-6b5290b54077 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
52a08a73-1a24-59bd-8dc9-4c4bc2651a4c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
49c00990-1605-40ba-9a14-850b31aa90b5 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
9a14a161-f323-5e91-b607-70cffeaac5a9 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 1st Pour (ABT A & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
34e8fef9-a649-470e-a21c-e508a892ba6d |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B)
4ba7b7ab-17c8-501c-950a-707cd200cd9f |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
a51f4960-b3a9-56fd-8fb8-c8a6daa9f073 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.01 - Construction Pack
5133f1f9-7e75-5b22-b477-4513635977e1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.02 - Survey Setout
295a9aa2-f196-511b-8f02-cd8efe55f982 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.03 - Internal Permits
4356da96-b4db-5dd6-890a-d13717d729c6 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.04 - External Permits
04217f90-d84a-5c2e-9a65-b3db96b3b820 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.05 - Approved Construction Drawings
4540e695-dcac-5d82-b9ec-207b9da94ea7 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.06 - Construction Methodology
94e9690a-fdb4-5bbb-991a-967fa0c8206d |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | AUTHORITY HOLDPOINT
0de6fafd-3cfb-56dc-88c4-bc19d50c97f1 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements | 1.01.07 - Stakeholder
f225ddcd-8d25-56e5-b016-bc981d308182 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
1c2ed47c-f79e-5107-88d6-bff983008f6c |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.01 - Chartered Engineer
e7fc47be-9ab4-52d0-a506-8eac67a38f82 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
5d6cc0b0-810f-5009-a7ba-9c2aa7e00829 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | 2.01.02 - Drawings and calculations
bd36d7e8-3dd5-503b-83d4-3eb69e54987c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works | AUTHORITY HOLDPOINT
5d9e4fc4-c510-5fcf-bcd8-4905c2b845c2 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
3964d524-3b6e-5095-b31a-0a9021991466 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.01 - Concrete Mix Design
f0b948de-9f86-53f8-b8af-541d4bfdbf6f |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | 2.02.02 - Concrete Mix Design Checklist
ba1eb100-cbd5-5ce5-8dc4-8c6b0fc84968 |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete | AUTHORITY HOLDPOINT
23a85243-61c5-5a3b-8549-1111b31dd34c |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
341ff59c-9326-5e4f-bd82-33fa70e46740 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.01 - Reinforcement
1e47e241-fd42-58d6-b6bb-727956893acc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.02 - Reinforcement
a2674217-9f88-5990-859c-e40ba65643fd |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.03 - Welding reinforcing
43e95963-3dfa-5250-9124-3ba518efa6c3 |  | not-applicable |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | AUTHORITY HOLDPOINT
19c46250-feb2-5c46-9ae7-cdc6f6be5d97 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement | 2.03.04 - Steel supply
34ad167f-23cc-5659-9bc5-1cc61a6051fa |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
d20c40ff-8635-5d59-9c14-9b7cb52941da |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.01 - Temporary Works
49b38858-c235-52ee-bbc3-52e84a1dad57 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.02 - Reciept of Reinforcment
63be8de1-9802-5f97-834c-6e6088d36898 |  | not-applicable |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.03 - Reinforcing Welding and NDT Inspections
d628cbb1-bd8d-5517-9f34-319f44aef885 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.04 - Pre pour inspection
b2a8f70f-fafb-5db8-99d5-a5a0bd9f3b9b |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.05 - Engineers Inspection
5de2f4f4-d50e-543b-b42f-dd8a38fab05c |  | pass |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | AUTHORITY HOLDPOINT
c86232be-437e-5bb5-b09f-6ef498a0fea3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.06 - ESCP
6daa30c0-487b-5fe0-8c98-13ca7d8612bc |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour | 3.01.07 - Concrete Cover
4e057100-aaba-5793-b5e1-3a2e82f5dc43 |  | pass |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
c41ecc91-fbbc-50fc-85df-060599e3ebec |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.01 - Unfavourable Conditions - Cold Weather
3b38e4e0-d078-5055-9b2d-985879ecab59 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.02 - Unfavourable Conditions - Hot Weather
67f2d2a2-6e8f-55aa-bf18-92441859acf2 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.03 - Unfavourable Conditions - Rain
79e84d06-7dd6-5dba-862f-8ce783a77bcd |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.04 - Construction Joints
36f0ba76-bc5f-5617-84b2-0bf8143f0c75 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.05 - Delivery dockets
ca5714d4-df8a-5bb4-842a-f3531d799b85 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.06 - Slump tests and spread tests
677fdeef-c80b-5cec-b092-a28482bbe09e |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.07 - Time Limits
32c54dea-e1f7-5a12-98c1-8a099137eea4 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.08 - Compression Testing
f6907c01-8a4c-5d79-bd1d-555975a2a5c1 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.09 - Concrete finishes
aaa95986-730f-5255-b1ca-9d46d93d04f0 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour | 3.02.10 - Curing
7d264d48-cc3e-5370-9099-2d69f4f5e01f |  | not-started |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
233ee679-bdf6-58c3-98e2-c8d178a6b36e |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.01 - Falsework and Formwork Removal
5edd1f52-0134-52c9-a766-2baaf4625b70 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.02 - Post Pour Inspection
d489b00c-0624-5f5a-b875-3c511eb4470d |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | 3.03.03 - Concrete Repair
9ce7978e-8b98-528c-85aa-320dcb7f4312 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour | AUTHORITY HOLDPOINT
ac29db61-7f2e-549d-bc03-9e30c585211f |  | work-in-progress |  | section | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
1a420046-824f-5fd4-9bc1-fe4f4331f99b |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.01 - Construction Record Compilation
98d310ce-b3c7-5945-b9cd-1a49fa3c0b8c |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.02 - Survey Records
616325f3-8b2f-5f0a-aaba-703a38e26de3 |  | pass |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.03 - Redline Drawings
81c39dbf-88ca-54bc-b24e-3f4d3d32dc62 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | 4.01.05 - Delivery dockets
6fed12c7-62db-4104-8eaa-245fa24420d4 |  | not-started |  | checkpoint | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
37ff4ed1-f080-5e80-9209-ddf9f72adc72 |  | not-started |  | signoff | TRUE | TRUE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 2nd Pour (Pier B & Span A-B) | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities | Add Signature
746efef1-8ced-4652-8086-2008b67dde2d |  | work-in-progress | ITP - Insitu Concrete Construction - Rev D | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Deck & Crosshead | Insitu Concrete for 3rd Pour (PIER C & Span B-C)