## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
33600256-a377-4ac1-a7a6-4e67ec9a1cee |  | work-in-progress | 7633da16f5ea4e422f47e6bc1ef93646c8a4a2fb718aa86c7ba4fecb0d5362ab | checklist | FALSE | FALSE | Site QA | Utility Services | Area 1 | RSU00R CH 1550 to CH 1700 | ITP - Utility Trench
6c970634-2962-4637-8e63-98e9510f4996 |  | fail | 2c7f82e493918989315b32fb6e08f2e0c04fb816461613049598363d5700b42c | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1520-1740 BULK EARTHWORKS
b8b49ab7-b52e-4878-b579-feac86fc9545 |  | work-in-progress | c3fd7e996b01855f3d27b4cabfaaf193d7e7cca8b3f4586813e6ebe2296fd785 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (CENTRE & PERIMETER)
5a3dd6d7-98e1-4061-8ec2-da370407d699 |  | work-in-progress | c3fd7e996b01855f3d27b4cabfaaf193d7e7cca8b3f4586813e6ebe2296fd785 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 SUBSOILS (SWALE)
63bbc978-7687-4f04-a315-6eb0d032143f |  | work-in-progress | b64c69fb4abef48fbce438b985333fe7e1c3b427fc12a68194aa5cf437db7b95 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1A (CH1540-1740) | AREA 1A CH1540-CH1740 PAVEMENT DRAINS
32baeb54-805d-4061-a8ae-3636ad6e2b16 |  | fail | 2c7f82e493918989315b32fb6e08f2e0c04fb816461613049598363d5700b42c | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 BULK EARTHWORKS
8c0bd824-2790-4d1c-ae00-cc7475ef6001 |  | work-in-progress | bac6fb00113e4149c0a3115ba5fd7868646f20422b1c36cf5407a24a943e2aa4 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SIL
5cadb1eb-a78c-46cb-bc4d-7041fd14843d |  | work-in-progress | c3fd7e996b01855f3d27b4cabfaaf193d7e7cca8b3f4586813e6ebe2296fd785 | checklist | FALSE | FALSE | Site QA | Earthworks | Area 1 | Area 1B (CH1740-CH1990) | AREA 1B CH1740-CH1990 SUBSOIL DRAINAGE (CENTRE & PERIMETER)
003c6238-9e49-456f-8736-fadc7299b4f6 |  | fail | 1e583f8b70273eabf004fcc38eca8c02710d652e820a3ccc1f9a151f83465210 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1A - CH1600 to CH1730 | ITP - Pavement & Surfacing - Kerb - Rev C
524252ad-4629-45c2-aa16-d5f9e975bb57 |  | work-in-progress | d19eeaa84687926eab71cf54cebaa826ad3d91a2f810c8df2789de9358c46668 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Subbase - Rev E
a5469e71-9c58-43da-b65d-eb3f0d370c2b |  | fail | 1e583f8b70273eabf004fcc38eca8c02710d652e820a3ccc1f9a151f83465210 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 1 | Area 1B - CH1730 to CH1960 | ITP - Pavement & Surfacing - Kerb - Rev C
0463d09a-c7e4-483b-94c3-f66074c3aa75 |  | fail | 63b1e491901cfe89030f9bfcf85c2fe0f9b00560a68517104fc1e1b1037eef12 | checklist | FALSE | FALSE | Site QA | Pavements - Type 1 & Type 2 | Area 3 | Area 3 - CH1020 to CH1200 | ITP - Pavement & Surfacing - Basecourse - Rev 1
5cc286e6-5d5c-4331-b87e-9b669573a0be |  | work-in-progress | a83c92be17ef255d65b7d7d79441fcf3ffebdf903e4e863bc0190c282f1da53a | checklist | FALSE | FALSE | Site QA | Surfacing | Peacockes Road | Peacocke East - CH1500 to CH1270 (HEB Tie-in) | ITP - Pavement & Surfacing - Sealing - Rev 1
aa800302-d167-4d16-9a24-1faae902af12 |  | not-applicable | acc2b89cb863d8d6e6735a13cbb5225bf02fad07656ee7446412807f5fbc421c | checklist | FALSE | FALSE | Site QA | Traffic Signals | Peacockes Road/ RS22 (REMOVED/CANCELLED) | ITP - Traffic Signals - Rev B
46906d33-185a-43d9-8721-c5ddfcafb19c |  | work-in-progress | f2478c84926fe662594ba8557dff929c9396882445c4a69fd6fd36686b397d03 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Piling | ITP - Piling: EASTERN GULLY BRIDGE
ca527faa-59ce-442a-86c5-2ef3115e9fed |  | fail | fec3058051f3508964e0c71c2171b052528e9896e8bc61497ec5db7f73755646 | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier EGB
89b9a109-b1bc-4730-bb10-9abe5e603b21 |  | work-in-progress | 220b8ccdf1bde5ca4538240bfbc232b17b9ed86b1a1d820aba4879bec05217fc | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 3rd Pour on 13/9/2024
9b0e79ba-5568-4e7f-b1da-fafccac0194a |  | work-in-progress | 220b8ccdf1bde5ca4538240bfbc232b17b9ed86b1a1d820aba4879bec05217fc | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 1st Pour on 3/9/2024
44731dc9-2aa8-4bd7-a112-40240aa0132f |  | work-in-progress | 220b8ccdf1bde5ca4538240bfbc232b17b9ed86b1a1d820aba4879bec05217fc | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | 2nd Pour on 9/9/2024
abbf8f5d-5adc-433e-b8c7-357349c1a090 |  | work-in-progress | 220b8ccdf1bde5ca4538240bfbc232b17b9ed86b1a1d820aba4879bec05217fc | checklist | FALSE | FALSE | Site QA | Eastern Gully Bridge | Bridge Barriers | Stitch Pour QA | Last Pour on 20/9/2024
15672725-113e-4129-a16c-f64b642947d7 |  | work-in-progress | fec3058051f3508964e0c71c2171b052528e9896e8bc61497ec5db7f73755646 | checklist | FALSE | FALSE | Site QA | Mangakootukutuku Bridge | Bridge Barriers | Final QA | ITP - Precast Barrier