## ITP Cover Page
[16 empty] | Safety from Falling Barriers | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 141 - Rev B
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 141 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Insitu Concrete Construction |  |  |  |  | Revision: | 1000 |  | B
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 4274, 4275, 4374, 4375
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
A | Draft for Approval |  |  | EK |  | Minor comments |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
B | Draft for Approval | [8 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
[10 empty] | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## In-situ Concrete Construction
Safety from Falling Barriers
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 141 - Rev B
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
1.01 | Site Requirements
1.01.01 | Survey Setout | The Contractor shall verify the setting out position, level and line of the bridge, prior to commencing construction. The Contractor shall advise the Engineer of any apparent anomalies identified. | Downer PS - 11.2 | Survey Records | Prior to Works | H | PE
1.01.02 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
1.01.03 | Approved Shop Drawings | Shop drawings to be approved by Engineer | Downer | Record of Approval Approved Shop Drawings | Prior to manufacturing | HP | ENG
1.01.04 | Approved ITP | Include correspondence of approved ITP. | Downer | Record of Approval Approved ITP | Prior to pouring foundations | H | PE
SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
2.01 | Panels
2.01.01 | Alsteel Defender Fence | All panels to be part of Alsteel Defender Fence system unless instructed otherwise. | Downer | Dockets | Each Order | H | PE
2.01.02 | Hot Dip Galvanised Steel | All steelwork to be hot dip galvanised to achieve HDG600. | AS/NZS 4680 | Test Results | Each Order | H | PE
2.01.03 | Steel Grade | All steelwork to be grade 300 minimum. | AS/NZS 2312 | Dockets | Each Order | H | PE
2.01.04 | Hot Dip Galvanised Bolts | M12 4.6 HDG minimum 150mm embedment. | Downer | Dockets | Each Order | H | PE
2.01.05 | Repairs | All repairs to hot-dipped galvanised materials to be as per manufacturer's specifications or designer's instruction. | Downer | Site Records | All Repairs | H | PE
SECTION 3 – CONSTRUCTION ACTIVITY
3.01 | Installation - Standard Posts (350mm footings)
3.01.01 | Spacings | Maximum centre to centre spacing of posts to be 2445mm. | Drawings | Photos | Each area | H | PE
3.01.02 | Height | Minimum 1100mm height of posts. | Drawings | Photos | Each area | H | PE
3.01.03 | Gaps | Maximum 100mm gap between ground level and first horizontal member. Maximum 100mm gap between vertical members. | Drawings | Photos | Each area | H | PE
3.01.04 | Footings | Standard Alsteel Base Stub footing mounted on foundation with 4/M12 4.6 HDG Bolts @ 90x110 spacing, minimum 150mm embedment. | Drawings | Photos | Each area | H | PE
3.01.05 | Posts | Minimum 65x65x1.6mm SHS posts. | Drawings | Dockets | Each area | H | PE
3.01.06 | Returns on Corner Posts | Returns to be minimum 520mm wide with 90x90 HDG base plate bolted to foundation with 4/M12 4.6 HDG Bolts @ 50x50 spacing, minimum 150mm embedment. | Drawings | Photos | Each area | H | PE
3.02 | Installation - Long Posts (400mm footings)
3.02.01 | Spacings | Maximum centre to centre spacing of posts to be 2445mm. | Drawings | Photos | Each area | H | PE
3.02.02 | Height | Minimum 2020mm height of posts. | Drawings | Photos | Each area | H | PE
3.02.03 | Gaps | Maximum 100mm gap between ground level and first horizontal member. Maximum 100mm gap between vertical members. | Drawings | Photos | Each area | H | PE
3.02.04 | Footings | Standard Alsteel Base Stub footing mounted on foundation with 4/M12 4.6 HDG Bolts @ 90x110 spacing, minimum 150mm embedment. | Drawings | Photos | Each area | H | PE
3.02.05 | Long Posts | Minimum 65x65x2.5mm SHS posts. | Drawings | Photos | Each area | H | PE
3.02.06 | Returns on Corner Posts | Returns to be 520mm wide with 90x90 HDG base plate bolted to foundation with 4/M12 4.6 HDG Bolts @ 50x50 spacing, minimum 150mm embedment. | Drawings | Photos | Each area | H | PE
SECTION 4 – POST CONSTRUCTION
4.01 | Site Post Construction Activities
4.01.01 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV
4.01.02 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. | Downer | Redlines | Post construction | H | SE