## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 141 - Safety from Falling Barriers | itp |  |  |  |  | ITP - 141 - Safety from Falling Barriers Rev B
section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 1.01.01 - Survey Setout
label | Acceptance / Conformance Criteria - The Contractor shall verify the setting out position, level and line of the bridge, prior to commencing construction. The Contractor shall advise the Engineer of any apparent anomalies identified.
label | Standard / Specification - Downer PS - 11.2
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 1.01.02 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 1.01.03 - Approved Shop Drawings
label | Acceptance / Conformance Criteria - Shop drawings to be approved by Engineer
label | Standard / Specification - Downer
label | Verifying Document - Record of Approval, Approved Shop Drawings
label | Frequency - Prior to manufacturing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.01.04 - Approved ITP
label | Acceptance / Conformance Criteria - Include correspondence of approved ITP.
label | Standard / Specification - Downer
label | Verifying Document - Record of Approval, Approved ITP
label | Frequency - Prior to pouring foundations
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 2.01.01 - Alsteel Defender Fence
label | Acceptance / Conformance Criteria - All panels to be part of Alsteel Defender Fence system unless instructed otherwise.
label | Standard / Specification - Downer
label | Verifying Document - Dockets
label | Frequency - Each Order
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.01.02 - Hot Dip Galvanised Steel
label | Acceptance / Conformance Criteria - All steelwork to be hot dip galvanised to achieve HDG600.
label | Standard / Specification - AS/NZS 4680
label | Verifying Document - Test Results
label | Frequency - Each Order
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.01.03 - Steel Grade
label | Acceptance / Conformance Criteria - All steelwork to be grade 300 minimum.
label | Standard / Specification - AS/NZS 2312
label | Verifying Document - Dockets
label | Frequency - Each Order
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.01.04 - Hot Dip Galvanised Bolts
label | Acceptance / Conformance Criteria - M12 4.6 HDG minimum 150mm embedment.
label | Standard / Specification - Downer
label | Verifying Document - Dockets
label | Frequency - Each Order
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 2.01.05 - Repairs
label | Acceptance / Conformance Criteria - All repairs to hot-dipped galvanised materials to be as per manufacturer's specifications or designer's instruction.
label | Standard / Specification - Downer
label | Verifying Document - Site Records
label | Frequency - All Repairs
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint | 3.01.01 - Spacings
label | Acceptance / Conformance Criteria - Maximum centre to centre spacing of posts to be 2445mm.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.02 - Height
label | Acceptance / Conformance Criteria - Minimum 1100mm height of posts.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.03 - Gaps
label | Acceptance / Conformance Criteria - Maximum 100mm gap between ground level and first horizontal member.
label | ○ Maximum 100mm gap between vertical members.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.04 - Footings
label | Acceptance / Conformance Criteria - Standard Alsteel Base Stub footing mounted on foundation with 4/M12 4.6 HDG Bolts @ 90x110 spacing, minimum 150mm embedment.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.05 - Posts
label | Acceptance / Conformance Criteria - Minimum 65x65x1.6mm SHS posts.
label | Standard / Specification - Drawings
label | Verifying Document - Dockets
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.01.06 - Returns on Corner Posts
label | Acceptance / Conformance Criteria - Returns to be minimum 520mm wide with 90x90 HDG base plate bolted to foundation with 4/M12 4.6 HDG Bolts @ 50x50 spacing, minimum 150mm embedment.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.01 - Spacings
label | Acceptance / Conformance Criteria - Maximum centre to centre spacing of posts to be 2445mm.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.02 - Height
label | Acceptance / Conformance Criteria - Minimum 2020mm height of posts.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.03 - Gaps
label | Acceptance / Conformance Criteria - Maximum 100mm gap between ground level and first horizontal member.
label | ○ Maximum 100mm gap between vertical members.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.04 - Footings
label | Acceptance / Conformance Criteria - Standard Alsteel Base Stub footing mounted on foundation with 4/M12 4.6 HDG Bolts @ 90x110 spacing, minimum 150mm embedment.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.05 - Long Posts
label | Acceptance / Conformance Criteria - Minimum 65x65x2.5mm SHS posts.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 3.02.06 - Returns on Corner Posts
label | Acceptance / Conformance Criteria - Returns to be 520mm wide with 90x90 HDG base plate bolted to foundation with 4/M12 4.6 HDG Bolts @ 50x50 spacing, minimum 150mm embedment.
label | Standard / Specification - Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 4 – POST CONSTRUCTION
checkpoint | 4.01.01 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SV
checkpoint | 4.01.02 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Verification Activity: Activity - H
label | Verification Activity: By - SE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature