## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
030af2a0-b63d-4211-af19-e2d7bd88dcfa | checklist | Checkers Checklist - Type B- Bridge Plank |  | Checkers Checklist - Type B- Bridge Plank
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c8cdb1f8-b0fe-4eea-8d32-e8b9ad053142 | checkpoint | Site Safety / Workers Safety
56323356-4589-4c89-b6b3-b45f8f3d4f64 | checkpoint | Availability of updated shop drawing
70a4415a-48f5-41d2-8b11-24afa5b1a1f0 | checkpoint | Double Check the Ferrule placement -Type A (600+1450)
3ad162dd-c6a5-54c4-8e41-aa5fe96873b4 | dropdown |  | 600F1450F, 550F1450F
90290a8a-4562-4bc4-8083-083ce9f84fb9 | checkpoint | Overall Measurements of construction Element
95c8ded7-74ac-458f-a033-908b75de827c | checkpoint | Embedded Item - Ferrules - Position,Size,Orientation -M20 (96mm)
7fe9ecba-00bd-481c-a1d4-d2e875670b1d | checkpoint | Embedded Item - Lifters Correct - Position,Size,Orientation-4 Nos 2.5T or equal
9df92e1a-1578-422b-acc6-247498038637 | checkpoint | Concrete cover check minimum 30mm
e9df32cc-5bf8-4147-95de-bdb9e26414f2 | checkpoint | Panel Thickness check,alignment check (150mm)
7429bc2f-000c-5dfc-bba0-6e184bcd8b29 | dropdown |  | 150mm, 200mm
05af30c5-f49e-494a-8404-56d73b0e5a87 | checkpoint | Panel length check, alignment check (4500mm)
2bd3d9ad-e48d-5789-8686-4915c3bda1f5 | dropdown |  | 5000mm, 4500mm
97930e67-bf5a-4b95-85e8-d26ec9d3510c | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
031cda75-2260-4053-912b-499c05b567f7 | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
5da31b0f-115b-4057-b02b-9ed70c649e0e | checkpoint | Reinforcement (Reo) placed, cleaned, tightened
8a83c279-a538-465a-b049-56f14b70c659 | checkpoint | Curing Procedure arranged
6cf0de48-026d-4a28-a1cb-84bec7981942 | checkpoint | Photo Taken
fce73cb5-a6e1-4095-a6ed-ff6b43d814b3 | checklist | Installers Checklist - Type A - Bridge Plank |  | Installers Checklist - Type A - Bridge Plank
1bb6e8f2-4b8e-482e-8f64-51cecc540565 | section | Job Approval Documents/Construction Documents
188925bd-b050-4ce2-93cb-fa46fdd22905 | checkpoint | Complete Material "Bucket List"
7a5d3fa3-4fe3-4f21-99d9-175f5998774d | checkpoint | Eye Anchor - 2.5T
cde6dbaf-036a-5ff7-b1ba-39f93b69b639 | textbox
352e3cc8-bc12-4a5f-a73f-9798911de1f0 | checkpoint | Ferrules - M20 x 96mm
cf37eee7-90a3-5bde-93f7-0b1a9bed8590 | textbox
14bf7870-8cad-47a0-a930-c3439f88cea4 | checkpoint | ID Plate
789968c6-aaa5-5423-99bc-6a389b87ceb7 | textbox
12535983-b292-4f15-9cc1-277a43df46f8 | section | Pre-Pour Check Approvals
9923e0df-8f4c-473d-b3a8-2b472321790d | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
f04629c4-eec9-4b7c-a9eb-da2a69f9d2bc | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
cb2a1cd8-7b5e-4a9e-8b92-050a3d6a8cd0 | checkpoint | Temporary Fix ID Plate to Formwork
79690ace-0293-4fd7-8bdf-26cf6045fa78 | checkpoint | Double Check the Ferrule placement -Type A
ea8a050e-88e4-49df-bc9f-cc6b3b5ec271 | checkpoint | Reinforcement Check - Reo as-per Shop Drawing
115d88f1-8302-44e6-b033-a5703015a098 | checkpoint | Lifters, Ferrules Fixed Firm & aligned -Check
e09c43a1-c5ea-4fcb-909f-31cf2b28febe | checkpoint | Concrete cover Check - minimum 30mm
71f9e967-4ccb-4424-87a7-608a0203fcd4 | section | Quality Assurance
30ab27bb-8301-4a3c-acc8-e245db460bb9 | checkpoint | QA - Final Check of ALL measurements
63796298-2841-4f7e-8917-697c35c10575 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
6607c965-574e-48c5-982f-22161151a303 | checkpoint | QA - Concrete mix design ,variations%, adjustments%,mix time
36ca3359-1273-4e32-b7fd-c23715e2cbfe | checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
d91e17d5-f907-5565-9339-d160eb73cea4 | date | Pour Date
ab16a28f-3b02-4b6f-a998-dfb41e9af4cc | checkpoint | CONCRETE TEST Procedure
80e348cb-e853-4bd6-8b21-4f8e5598f2b5 | checkpoint | APPROVAL FROM ENGINEER
758a0d0c-5b50-4b3e-8aa1-98f8b3a8a6b6 | section | Other Arrangements
19d67d71-73ec-4d60-a956-e15533ac953e | checkpoint | Concrete surface Finish Requirement arranged
4c32305f-b223-58cf-8491-6adae17977ca | dropdown |  | Fine finish, Broom finish
a938a6c2-d5c2-49e5-996e-7282f744c8be | checkpoint | Curing Procedure arranged