## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Rest Home Room/Hospital 3 - 314/434/458
section | Details
checkpoint | Install surrounding cover on the Ensuite Toilet Call Point (Attach Photos)
checklist | Rest Home Room - 316
section | Details
checkpoint | Check Nurse Presence Call Point - it's not working and causes the virtual Staff Assist alarm to fail as well (Attach Photos)
checklist | Rest Home Room/Independent Apartments - Tenzing - 329/450
section | Details
checkpoint | Check Shower Pull Cord, as it failed (Attach Photos)
checklist | Rest Home Room - 334
section | Details
checkpoint | Check Pendant removal alarm, as it fails intermittently (Attach Photos)
checklist | Rest Home Room - 335/336
section | Details
checkpoint | Replace Ensuite Toilet Call Point - requires very hard pressing to activate (Attach Photos)
checklist | Rest Home Room - 338
section | Details
checkpoint | Check Floor Pressure mat, as it failed (Attach Photos)
checklist | Rest Home/Independent Apartments - Shackleton/Cook/Everest/Ross - Lounge 2/341/G77/374/170/191
section | Details
checkpoint | Check ODL, as it failed (Attach Photos)