## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Serviced Apartments - 110
section | Details
checkpoint | Check reassurance LED on Bedroom and WC Call Points, very dim and hardly visible (Attach Photos)
checklist | Serviced Apartments - 112/205
section | Details
checkpoint | Check Staff Assist alarm, it's not working (Attach Photos)
checklist | Serviced Apartments - 114/308
section | Details
checkpoint | Check Shower Pull Cord reassurance LED, it's not working (Attach Photos)
checklist | Serviced Apartments - 204
section | Details
checkpoint | Check Short-Range wireless pendant, as it failed (Attach Photos)
checklist | Serviced Apartments - 206/210
section | Details
checkpoint | Check Alarm generated by Bedhead Call Point - generating Resident Call when it should be Emergency Alarm (Attach Photos)
checklist | Serviced Apartments - 315
section | Details
checkpoint | Check Shower Pull Cord, it gets stuck during pull test and needs to be manually pushed back to reset the alarm (Attach Photos)
checklist | Serviced Apartments/Independent Apartments Everest - 318/266
section | Details
checkpoint | Check ODL - brightness is very low and hardly visible (Attach Photos)
checklist | Serviced Apartments - 320
section | Details
checkpoint | Check Shower Pull Cord, as it failed (Attach Photos)
checkpoint | Check Short-Range pendant, as it fails intermittently (Attach Photos)