## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Townhouse - 2
section | Details
checkpoint | Change Guest Toilet Call Point Faceplate from Green to Red (Attach Photos)
checklist | Townhouse - 3/4/37/39
section | Details
checkpoint | Change Ensuite Toilet Call Point insert from Green to Red (Attach Photos)
checklist | Townhouse - 6
section | Details
checkpoint | Change Master Bedroom Call Point insert, should be Red (Attach Photos)
checklist | Townhouse - 7
section | Details
checkpoint | Change Guest Bedroom Call Point Faceplate to a Red Emergency Call Faceplate (Attach Photos)
checkpoint | Change Ensuite Toilet Call Point Faceplate to a Red Emergency Call Faceplate (Attach Photos)
checkpoint | Change Guest Toilet Call Point Faceplate to a Red Emergency Call Faceplate (Attach Photos)
checklist | Townhouse - 9
section | Details
checkpoint | Check Master Bedroom Call Point - requires hard pressing to activate (Attach Photos)
checkpoint | Check Shower Pull Cord reassurance LED, as it failed (Attach Photos)
checkpoint | Change Ensuite Toilet Call Point insert from Green to Red (Attach Photos)
checkpoint | Change Guest Toilet Call Point insert from Green to Red (Attach Photos)
checklist | Townhouse - 10
section | Details
checkpoint | Check Guest Toilet Call Point - requires hard pressing to activate (Attach Photos)
checkpoint | Change Ensuite Toilet Call Point insert from Green to Red (Attach Photos)
checkpoint | Change Guest Toilet Call Point insert from Green to Red (Attach Photos)
checklist | Townhouse - 11/15
section | Details
checkpoint | Change Master Bedroom Bedhead Call Point insert from Green to Red (Attach Photos)
checkpoint | Change Ensuite Toilet Call Point insert from Green to Red (Attach Photos)
checkpoint | Change Guest Toilet Call Point insert from Green to Red (Attach Photos)
checklist | Townhouse - 12A/16
section | Details
checkpoint | Change Guest Toilet Call Point insert from Green to Red (Attach Photos)
checklist | Townhouse - 27
section | Details
checkpoint | Replace Call Point in Ensuite Toilet - requires hard press to activate (Attach Photos)
checklist | Townhouse - 33
section | Details
checkpoint | Check Smoke Detector (HM) in the Hallway, as it failed the Smoke Test (Attach Photos)
checkpoint | Check Master Bedroom Bedhead Call Point - requires hard pressing to activate (Attach Photos)
checklist | Townhouse - 35
section | Details
checkpoint | Replace battery on Short Range Wireless Pendant - still working, but activation LED on pendant is dim (Attach Photos)
checklist | Townhouse - 36
section | Details
checkpoint | Check Reassurance Light in Master Bedroom Bedhead Call Point, failed when alarm is active (Attach Photos)
checklist | Townhouse - 43
section | Details
checkpoint | Check Ensuite Shower Pull Cord, it fails intermittently (Attach Photos)
checklist | Townhouse - 56/67
section | Details
checkpoint | Check Ensuite Shower Pull Cord, as it failed (Attach Photos)
checklist | Townhouse/Independent Apartments - Mallory - 61/71/128
section | Details
checkpoint | Check Ensuite Shower Pull Cord reassurance LED, as it's not working when the alarm is active (Attach Photos)
checklist | Townhouse - 63
section | Details
checkpoint | Check Lounge Smoke Detector (System Sensor), as it failed to activate the alarm on Nurse Call Displays and Pagers (Attach Photos)
checklist | Townhouse - 66
section | Details
checkpoint | Change Master Bedroom Bedhead Call Point insert from Green to Red (Attach Photos)
checklist | Townhouse - 79/80
section | Details
checkpoint | Check both Smoke Detectors (System Sensor), as they both failed to activate the alarm on Nurse Call Displays and Pagers (Attach Photos)
checklist | Townhouse - 83/84
section | Details
checkpoint | Check both Smoke Detectors (VST), as they both failed to activate the alarm on Nurse Call Displays and Pagers (Attach Photos)
checklist | Townhouse - 85
section | Details
checkpoint | Check both Smoke Detectors (HM), as they both failed to activate the alarm on Nurse Call Displays and Pagers (Attach Photos)
checklist | Townhouse - 87
section | Details
checkpoint | Check both Smoke Detectors (VST in Hallway and HM in the Lounge), as they both failed to activate the alarm on Nurse Call Displays and Pagers (Attach Photos)
checkpoint | Check Pendant removal alarm, as it failed (Attach Photos)
checklist | Townhouse - 90
section | Details
checkpoint | Check both Smoke Detectors (System Sensors in the Hallway and Lounge), as they both failed to activate the alarm on Nurse Call Displays and Pagers (Attach Photos)