## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Village Centre - SA Main WC Women
section | Details
checkpoint | Check Call Point - Failed to generate any alarm, should be an Emergency Call Alarm (Attach Photos)
checklist | Village Centre - Sales Office
section | Details
checkpoint | Displays as "Doctors Office", this needs to be updated (Attach Photos)
checkpoint | Install surrounding cover on the ODL (Attach Photos)
checklist | Village Centre - Gym
section | Details
checkpoint | Connect Gym Call Point to the ODL at the Gym Entrance - inside the same area, so should work (Attach Photos)
checklist | Village Centre - Gym F WC
section | Details
checkpoint | Check ODL, as it failed (Attach Photos)
checkpoint | Install ODL above Female Toilet Door (Attach Photos)
checkpoint | Change Call Point insert from green to red (Attach Photos)
checklist | Village Centre - Pool
section | Details
checkpoint | Check Call Point - requires hard pressing to activate (Attach Photos)
checklist | Village Centre - Lounge, by Bar area
section | Details
checkpoint | Check Call Point by the Bar, as it failed (Attach Photos)