## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | QA - Flooring
section | PRIOR TO COMMENCEMENT
checkpoint | 1.01 Manufacturer's specifications on hand and consulted for substrate acceptance and installation instructions.
checkpoint | 1.02 Climate conditions and positioning of climate-altering services checked for compatibility as per manufacturer's specifications and NZS 2455.2.
checkpoint | 1.03 Substrate is suitably clean and stable
checkpoint | 1.04 Curing/seasoning of substrate checked for compatibility as per manufacturer's specifications.
checkpoint | 1.05 Substrate is flat within a deviation of 6.0mm under a 3000mm straight edge laid in any direction.
checkpoint | 1.06 Substrate is smooth within a deviation of 1.0mm under a 150mm straight edge laid in any direction
checkpoint | 1.07 Relative humidity of subfloor measured as 75% or lower by hygrometer test.
checkpoint | 1.08 Setout planned prior to laying; per NZS 2455.2, with uniform and disguised pile direction; continuous lengths without cross joins in the body of the area
checkpoint | 1.09 Floor and walls form a right angle to each other to allow correct fitting of carpet gripper.
checkpoint | 1.10 Carpet prepared to be laid in a single floor, and of a single specified type, quality, colour and design, is from one manufacturing batch and dye lot.
checkpoint | 1.11 Confirm that permanent partitions have been installed before starting carpet laying. Seek approval from the Main Contractor
section | DURING WORKS
checkpoint | 2.01 Lay the carpet in continuous lengths without cross joins in the body of the area
checkpoint | 2.02 Primer shall be used where recommended by the adhesive manufacturer and shall be allowed to dry thoroughly before applying adhesive.
checkpoint | 2.03 Adhesive: Spread evenly, pressing down firmly and rolling (if recommended) to ensure full contact and a good bond overall. Remove surplus from exposed faces
checkpoint | 2.04 Adhesive systems protected from traffic for 24 hours after installation.
checkpoint | 2.05 Joints in underlay: Joints in underlay do not coincide with carpet joints. Do not carry underlay over carpet grippers or edge strips
checkpoint | 2.06 Where different floor covering abut at doorways where there is a fitted door, the junction is within the thickness of the closed door.
checkpoint | 2.07 Seams and cross-joins strong enough to permit stretching without gaping or breaking.
checkpoint | 2.08 Fixing method as per manufacturer's specifications.
checkpoint | 2.09 Area examined for lumps, tightness and air pockets.
checkpoint | 2.10 Terminations and junctions protect carpet edge and provide smooth transition to adjacent floor surfaces.
checkpoint | 2.11 Area cleaned and protection established to allow construction traffic.